## Reference
Track No. | Column Side | Activities | Bracket Type | Station | Track Stationing | Tunnel | Description | Track Stationing | Notes
B1 | W | Steel Messenger Supports | 1 | Church Avenue | 556+96 to 563+56 | CHU-FOR | Church Ave to Fort Hamilton | 563+56 to 584+88
B2 | E | Messenger Clamps | 2 | Fort Hamilton Parkway | 584+88 to 591+90 | FOR-15S | Fort Hamilton to 15th Street | 591+90 to 625+70
B3 | W | Messenger Wire Pull | 3 | 15th Street Prospect Park | 625+70 to 632+30 | 15S-7AV | 15th Street to 7th Avenue | 632+30 to 653+96
B4 | E | Messenger Wire Tension | 4 | 7th Avenue | 653+96 to 660+56 | 7AV-4TH | 7th Avenue to 4th & 9th Street | 660+56-683+83
E1 | W | Cable Pull | 4A | 4th & 9th Street | 683+83 to 690+91 | 4TH-SMI | 4th & 9th Street to Smith & 9th Street | 690+91 to 705+11
E2 | E | Messenger Straps | 5 | Smith & 9th Street | 705+11 to 712+32 | SMI-CAR | Smith & 9th Street to Carroll Street | 712+32 to 732+89
E3 |  | 15inch CMRS |  | Carroll Street | 732+39 to 738+99 | CAR-BER | Carroll Street to Bergen Street | 738+99 to 756+82
E4 |  | 24inch CMRS |  | Bergen Street | 756+82 to 763+42 | BER-HOY | Bergen Street to Hoyt Schermerhorn | 763+42 to 761+84 | track goes from 768+XX to 693+95
E5 |  | Column mount CMRS |  | Hoyt Schermerhorn | 761+84 to 768+87 | HOY-FUL | Hoyt Schermerhorn to Fulton | 768+87 to 740+30
|  | Station Brackets |  | Fulton Street | 740+30 to 733+70 | FUL-CLI | Fulton to Clinton Washington | 733+70 to 951+82 | track goes from 733+15 to 934+96
Location |  | Grounding |  | Clinton Washington Avenue | 951+82 to 958+42 | CLI-CLA | Clinton Washington to Classon | 958+42 to 970+82
Church Avenue |  | Obstruction Brackets |  | Classon Avenue | 970+82 to 977+42 | CLA-BED | Classon to Bedford Nostand | 977+42 to 989+22
CHU-FOR |  | Cable Pull |  | Bedford Nostrand Avenue | 989+22 to 995+82 | BED-MYR | Bedford Nostrand to Myrtle Willoughby | 995+82 to 1017+47
Fort Hamilton Parkway |  | Cable Tray Brackets |  | Myrtle Willoughby Ave | 1017+47 to 1024+52 | MYR-FLU | Myrtle Willoughby to Flushing Avenue | 1024+52 to 1039+42
FOR-15S |  | Installing Tray |  | Flushing Avenue Station | 1039+42 to 1046+20 | FLU-BRO | Flushing Avenue to Broadway | 1046+20 to 1060+52
15th Street Prospect Park |  | Core Drilling |  | Broadway | 1060+52 to 1067+12 | BRO-MET | Broadway to Metropolitan | 1067+12 to 1132+45
15S-7AV |  | Cable Pull |  | Metropolitan Avenue | 1132+45 to 1139+50 | MET-NAS | Metropolitan to Nassau | 1139+50 to 1131+52
7th Avenue |  | Arch Bar Installation |  | Nassau Avenue | 1131+52 to 1138+32 | NAS-GRE | Nassau to Greenpoint | 1138+32 to 1157+00
7AV-4TH |  |  |  | Greenpoint Avenue | 1157+00 to 1164+32 | GRE-21S | Greenpoint to 21 St | 1164+32 to 1211+33
4th & 9th Street |  |  |  | 21 St Station | 1211+33 to 1217+92 | 21S-COU | 21 St to Court Square | 1217+92 to 1229+23
4TH-SMI |  |  |  | Court Square | 1229+23 to 1236+66 | COU-QUE | Court Square to Queens Plaza | 1236+66 to 1250+65
Smith & 9th Street |  |  |  | Queens Plaza | 1250+65 to 1257+27
SMI-CAR
Carroll Street |  |  |  | Signal Types
CAR-BER |  |  |  | HOME
Bergen Street* |  |  |  | APPROACH
BER-HOY |  |  |  | BUMPER
Hoyt Schermerhorn |  |  |  | REV. HOME
HOY-FUL |  |  |  | REV. APPROACH
Fulton Street
FUL-CLI
Clinton Washington Avenue
CLI-CLA
Classon Avenue
CLA-BED
Bedford Nostrand Avenue
BED-MYR
Myrtle Willoughby Ave
MYR-FLU
Flushing Avenue Station
FLU-BRO
Broadway
BRO-MET
Metropolitan Avenue
MET-NAS
Nassau Avenue
NAS-GRE
Greenpoint Avenue
GRE-21S
21 St Station
21S-COU
Court Square
COU-QUE
Queens Plaza

## Work Sheet (hidden)
OVERALL INSTALLATION PER AREA
Status | Count
Not Started | #REF!
In Progress | #REF!
Completed | #REF!
Remaining | #REF!
Total Tasks | #REF!
Completed Sections | #REF!
Remaining Sections | #REF!

## Ref Activity Bar (hidden)
RADIO INSTALLATION DASHBOARD
TRACK | C3/C4
TASK | COMPLETION PROGRESS
Removals | 12.5%
Grand Total | 12.5%

## Ref Progress per Activity (hidden)
TASK | Acceptance Test
|  | Not Started | 0 | Completed Sections | 13.04%
TRACK | Average of PROGRESS | In Progress | 0 | Remaining Sections | 86.96%
C1 | 16.67% | Completed | 0
C2 | 16.67%
C3 | 0%
C3/C4 | 14.29%
C4 | 0%
C5 | 0%
C6 | 0%
Grand Total | 13.04%

## CMRS
Start | Finish | Track No | Location | Activity | Total Quantity | QTY Installed | Date | Progress | General Progress | Notes | Notes
124510 | 124500 | D1 | COU-QUE | Steel Mess Supports | 61 | 14 |  | 0.22951 | 0.4053
|  |  |  | Messenger Clamps | 499 | 136 |  | 0.27255
|  |  |  | Messenger Wire Pull | 971 | 207 |  | 0.21318
|  |  |  | Messenger Wire Tension | 558 | 473 |  | 0.84767
|  |  |  | # Cables Pulled | 862 | 749 |  | 0.86891
|  |  |  | Messenger Straps | 27 | 0 |  | 0
124500 | 124320 | D1 | COU-QUE | Steel Mess Supports | 373 | 150 |  | 0.40214 | 0.47758
|  |  |  | Messenger Clamps | 184 | 38 |  | 0.20652
|  |  |  | Messenger Wire Pull | 42 | 10 |  | 0.2381
|  |  |  | Messenger Wire Tension | 971 | 928 |  | 0.95572
|  |  |  | # Cables Pulled | 621 | 68 |  | 0.1095
|  |  |  | Messenger Straps | 817 | 779 |  | 0.95349
124320 | 124100 | D1 | COU-QUE | Steel Mess Supports | 716 | 415 |  | 0.57961 | 0.41166
|  |  |  | Messenger Clamps | 336 | 38 |  | 0.1131
|  |  |  | Messenger Wire Pull | 702 | 275 |  | 0.39174
|  |  |  | Messenger Wire Tension | 380 | 126 |  | 0.33158
|  |  |  | # Cables Pulled | 625 | 378 |  | 0.6048
|  |  |  | Messenger Straps | 118 | 53 |  | 0.44915
124100 | 123970 | D1 | COU-QUE | Steel Mess Supports | 765 | 360 |  | 0.47059 | 0.66804
|  |  |  | Messenger Clamps | 596 | 383 |  | 0.64262
|  |  |  | Messenger Wire Pull | 325 | 195 |  | 0.6
|  |  |  | Messenger Wire Tension | 389 | 366 |  | 0.94087
|  |  |  | # Cables Pulled | 614 | 459 |  | 0.74756
|  |  |  | Messenger Straps | 999 | 606 |  | 0.60661
123970 | 123930 | D1 | COU-QUE | 15" CMRS Install | 33 | 6 |  | 0.18182 | 0.42477
|  |  |  | Column Clamp | 756 | 571 |  | 0.75529
|  |  |  | Station Brackets | 206 | 115 |  | 0.55825
|  |  |  | Grounding | 578 | 258 |  | 0.44637
|  |  |  | Obstruction Brackets | 139 | 40 |  | 0.28777
|  |  |  | # Cables Pulled | 47 | 15 |  | 0.31915
123930 | 123715 | D1 | COU-QUE | 15" CMRS Install | 657 | 217 |  | 0.33029 | 0.6209
|  |  |  | Column Clamp | 632 | 524 |  | 0.82911
|  |  |  | Station Brackets | 811 | 661 |  | 0.81504
|  |  |  | Grounding | 229 | 33 |  | 0.1441
|  |  |  | Obstruction Brackets | 698 | 605 |  | 0.86676
|  |  |  | # Cables Pulled | 277 | 205 |  | 0.74007
|  | D1 | COU-QUE | Crossover (Arch Bar Installation) | 401 | 400 |  | 0.99751
122975 | 122827 | E1 | 21S-COU | Steel Mess Supports | 165 | 79 |  | 0.47879 | 0.37943
|  |  |  | Messenger Clamps | 114 | 19 |  | 0.16667
|  |  |  | Messenger Wire Pull | 168 | 54 |  | 0.32143
|  |  |  | Messenger Wire Tension | 294 | 198 |  | 0.67347
|  |  |  | # Cables Pulled | 575 | 277 |  | 0.48174
|  |  |  | Messenger Straps | 466 | 72 |  | 0.15451
122827 | 122250 | E1 | 21S-COU | 24" CMRS Install | 828 | 155 |  | 0.1872 | 0.42336
|  |  |  | Column Clamp | 577 | 457 |  | 0.79203
|  |  |  | Station Brackets | 367 | 256 |  | 0.69755
|  |  |  | Grounding | 934 | 350 |  | 0.37473
|  |  |  | Obstruction Brackets | 282 | 59 |  | 0.20922
|  |  |  | # Cables Pulled | 816 | 228 |  | 0.27941
122250 | 121833 | E1 | 21S-COU | Steel Mess Supports | 580 | 379 |  | 0.65345 | 0.51885
|  |  |  | Messenger Clamps | 475 | 464 |  | 0.97684
|  |  |  | Messenger Wire Pull | 417 | 84 |  | 0.20144
|  |  |  | Messenger Wire Tension | 230 | 0 |  | 0
|  |  |  | # Cables Pulled | 342 | 207 |  | 0.60526
|  |  |  | Messenger Straps | 636 | 430 |  | 0.6761
121833 | 121030 | E1 | 21 STREET | Steel Mess Supports | 815 | 233 |  | 0.28589 | 0.57707
|  |  |  | Messenger Clamps | 563 | 365 |  | 0.64831
|  |  |  | Messenger Wire Pull | 344 | 270 |  | 0.78488
|  |  |  | Messenger Wire Tension | 35 | 28 |  | 0.8
|  |  |  | # Cables Pulled | 465 | 198 |  | 0.42581
|  |  |  | Messenger Straps | 713 | 369 |  | 0.51753
121030 | 117010 | E1 | GRE-21S | 15" CMRS Install | 71 | 52 |  | 0.73239 | 0.37778
|  |  |  | Column Clamp | 112 | 32 |  | 0.28571
|  |  |  | Station Brackets | 280 | 66 |  | 0.23571
|  |  |  | Grounding | 564 | 8 |  | 0.014184
|  |  |  | Obstruction Brackets | 81 | 71 |  | 0.87654
|  |  |  | # Cables Pulled | 131 | 16 |  | 0.12214
117010 | 116810 | E1 | GRE-21S | 15" CMRS Install | 255 | 138 |  | 0.54118 | 0.40825
|  |  |  | Column Clamp | 206 | 83 |  | 0.40291
|  |  |  | Station Brackets | 533 | 324 |  | 0.60788
|  |  |  | Grounding | 430 | 141 |  | 0.32791
|  |  |  | Obstruction Brackets | 831 | 244 |  | 0.29362
|  |  |  | # Cables Pulled | 750 | 207 |  | 0.276
116810 | 116471 | E1 | GRE-21S | 15" CMRS Install | 190 | 40 |  | 0.21053 | 0.50916
|  |  |  | Column Clamp | 115 | 3 |  | 0.026087
|  |  |  | Station Brackets | 474 | 316 |  | 0.66667
|  |  |  | Grounding | 492 | 348 |  | 0.70732
|  |  |  | Obstruction Brackets | 233 | 136 |  | 0.58369
|  |  |  | # Cables Pulled | 366 | 315 |  | 0.86066
116471 | 115694 | E1 | GREENPOINT | 24" CMRS Install | 709 | 589 |  | 0.83075 | 0.52681
|  |  |  | Column Clamp | 830 | 747 |  | 0.9
|  |  |  | Station Brackets | 119 | 42 |  | 0.35294
|  |  |  | Grounding | 735 | 122 |  | 0.16599
|  |  |  | Obstruction Brackets | 905 | 655 |  | 0.72376
|  |  |  | # Cables Pulled | 875 | 164 |  | 0.18743
115694 | 115628 | E1 | NAS-GRE | 24" CMRS Install | 930 | 388 |  | 0.4172 | 0.47963
|  |  |  | Column Clamp | 913 | 297 |  | 0.3253
|  |  |  | Station Brackets | 835 | 795 |  | 0.9521
|  |  |  | Grounding | 384 | 43 |  | 0.11198
|  |  |  | Obstruction Brackets | 753 | 184 |  | 0.24436
|  |  |  | # Cables Pulled | 537 | 444 |  | 0.82682
115628 | 114897 | E1 | NAS-GRE | 24" CMRS Install | 422 | 130 |  | 0.30806 | 0.40231
|  |  |  | Column Clamp | 207 | 35 |  | 0.16908
|  |  |  | Station Brackets | 71 | 51 |  | 0.71831
|  |  |  | Grounding | 54 | 29 |  | 0.53704
|  |  |  | Obstruction Brackets | 135 | 24 |  | 0.17778
|  |  |  | # Cables Pulled | 840 | 423 |  | 0.50357
114897 | 114719 | E1 | NAS-GRE | Steel Mess Supports | 744 | 229 |  | 0.3078 | 0.43789
|  |  |  | Messenger Clamps | 155 | 145 |  | 0.93548
|  |  |  | Messenger Wire Pull | 294 | 79 |  | 0.26871
|  |  |  | Messenger Wire Tension | 928 | 247 |  | 0.26616
|  |  |  | # Cables Pulled | 274 | 114 |  | 0.41606
|  |  |  | Messenger Straps | 374 | 162 |  | 0.43316
114719 | 114040 | E1 | NAS-GRE | 24" CMRS Install | 823 | 781 |  | 0.94897 | 0.55582
|  |  |  | Column Clamp | 190 | 9 |  | 0.047368
|  |  |  | Station Brackets | 661 | 404 |  | 0.6112
|  |  |  | Grounding | 225 | 129 |  | 0.57333
|  |  |  | Obstruction Brackets | 150 | 118 |  | 0.78667
|  |  |  | # Cables Pulled | 313 | 115 |  | 0.36741
114040 | 113815 | E1 | NAS-GRE | Steel Mess Supports | 837 | 576 |  | 0.68817 | 0.3887
|  |  |  | Messenger Clamps | 566 | 50 |  | 0.088339
|  |  |  | Messenger Wire Pull | 407 | 117 |  | 0.28747
|  |  |  | Messenger Wire Tension | 572 | 8 |  | 0.013986
|  |  |  | # Cables Pulled | 426 | 337 |  | 0.79108
|  |  |  | Messenger Straps | 991 | 459 |  | 0.46317
113815 | 113019 | E1 | NASSAU | 24" CMRS Install | 471 | 294 |  | 0.6242 | 0.58622 |  | weight: 6.7 lb/ft
|  |  |  | Column Clamp | 930 | 191 |  | 0.20538
|  |  |  | Station Brackets | 918 | 673 |  | 0.73312
|  |  |  | Grounding | 646 | 479 |  | 0.74149
|  |  |  | Obstruction Brackets | 738 | 409 |  | 0.5542
|  |  |  | # Cables Pulled | 173 | 114 |  | 0.65896
|  | E1 | NASSAU | 24" CMRS Install | 545 | 508 |  | 0.93211 | 0.58117
|  |  |  | Column Clamp | 109 | 36 |  | 0.33028
|  |  |  | Station Brackets | 994 | 724 |  | 0.72837
|  |  |  | Grounding | 235 | 123 |  | 0.5234
|  |  |  | Obstruction Brackets | 343 | 288 |  | 0.83965
|  |  |  | # Cables Pulled | 991 | 132 |  | 0.1332
113019 | 112700 | E1 | MET-NAS | 24" CMRS Install | 109 | 2 |  | 0.018349 | 0.47853
|  |  |  | Column Clamp | 322 | 129 |  | 0.40062
|  |  |  | Station Brackets | 941 | 642 |  | 0.68225
|  |  |  | Grounding | 200 | 13 |  | 0.065
|  |  |  | Obstruction Brackets | 81 | 60 |  | 0.74074
|  |  |  | # Cables Pulled | 391 | 377 |  | 0.96419
112700 | 110878 | E1 | MET-NAS | 15" CMRS Install | 890 | 499 |  | 0.56067 | 0.52498
|  |  |  | Column Clamp | 609 | 581 |  | 0.95402
|  |  |  | Station Brackets | 850 | 109 |  | 0.12824
|  |  |  | Grounding | 228 | 159 |  | 0.69737
|  |  |  | Obstruction Brackets | 236 | 111 |  | 0.47034
|  |  |  | # Cables Pulled | 675 | 229 |  | 0.33926
110878 | 110793 | E1 | MET-NAS | 15" CMRS Install | 212 | 13 |  | 0.061321 | 0.54851
|  |  |  | Column Clamp | 537 | 220 |  | 0.40968
|  |  |  | Station Brackets | 95 | 50 |  | 0.52632
|  |  |  | Grounding | 875 | 799 |  | 0.91314
|  |  |  | Obstruction Brackets | 754 | 455 |  | 0.60345
|  |  |  | # Cables Pulled | 691 | 537 |  | 0.77713
110793 | 109251 | E1 | MET-NAS | 15" CMRS Install | 391 | 150 |  | 0.38363 | 0.38057
|  |  |  | Column Clamp | 534 | 27 |  | 0.050562
|  |  |  | Station Brackets | 424 | 354 |  | 0.83491
|  |  |  | Grounding | 975 | 217 |  | 0.22256
|  |  |  | Obstruction Brackets | 796 | 562 |  | 0.70603
|  |  |  | # Cables Pulled | 560 | 48 |  | 0.085714
109251 | 109133 | E1 | MET-NAS | 15" CMRS Install | 447 | 153 |  | 0.34228 | 0.52151
|  |  |  | Column Clamp | 290 | 38 |  | 0.13103
|  |  |  | Station Brackets | 991 | 963 |  | 0.97175
|  |  |  | Grounding | 275 | 244 |  | 0.88727
|  |  |  | Obstruction Brackets | 626 | 169 |  | 0.26997
|  |  |  | # Cables Pulled | 972 | 512 |  | 0.52675
109133 | 108356 | E1 | METROPOLITAN | 15" CMRS Install | 54 | 24 |  | 0.44444 | 0.40859
|  |  |  | Column Clamp | 145 | 62 |  | 0.42759
|  |  |  | Station Brackets | 174 | 63 |  | 0.36207
|  |  |  | Grounding | 905 | 297 |  | 0.32818
|  |  |  | Obstruction Brackets | 304 | 147 |  | 0.48355
|  |  |  | # Cables Pulled | 456 | 185 |  | 0.4057
108356 | 107651 | E1 | BRO-MET | 15" CMRS Install | 369 | 234 |  | 0.63415 | 0.44607
|  |  |  | Column Clamp | 685 | 143 |  | 0.20876
|  |  |  | Station Brackets | 246 | 85 |  | 0.34553
|  |  |  | Grounding | 878 | 203 |  | 0.23121
|  |  |  | Obstruction Brackets | 294 | 147 |  | 0.5
|  |  |  | # Cables Pulled | 74 | 56 |  | 0.75676
107651 | 107611 | E1 | BRO-MET | 15" CMRS Install | 201 | 48 |  | 0.23881 | 0.3898 |  | Check endings for specific stationings (DWG 48012-17N-006.0) where cable switches from 1 to 2
|  |  |  | Column Clamp | 346 | 25 |  | 0.072254
|  |  |  | Station Brackets | 770 | 458 |  | 0.59481
|  |  |  | Grounding | 731 | 654 |  | 0.89466
|  |  |  | Obstruction Brackets | 850 | 225 |  | 0.26471
|  |  |  | # Cables Pulled | 424 | 116 |  | 0.27358
107611 | 106768 | E1 | BRO-MET | 15" CMRS Install | 606 | 226 |  | 0.37294 | 0.39495
|  |  |  | Column Clamp | 382 | 339 |  | 0.88743
|  |  |  | Station Brackets | 578 | 189 |  | 0.32699
|  |  |  | Grounding | 638 | 177 |  | 0.27743
|  |  |  | Obstruction Brackets | 663 | 169 |  | 0.2549
|  |  |  | # Cables Pulled | 72 | 18 |  | 0.25
106768 | 106702 | E1 | BRO-MET | 15" CMRS Install | 369 | 295 |  | 0.79946 | 0.71853
|  |  |  | Column Clamp | 812 | 490 |  | 0.60345
|  |  |  | Station Brackets | 961 | 924 |  | 0.9615
|  |  |  | Grounding | 792 | 362 |  | 0.45707
|  |  |  | Obstruction Brackets | 441 | 392 |  | 0.88889
|  |  |  | # Cables Pulled | 977 | 587 |  | 0.60082
106702 | 106011 | E1 | BROADWAY | 15" CMRS Install | 913 | 281 |  | 0.30778 | 0.31388
|  |  |  | Column Clamp | 376 | 163 |  | 0.43351
|  |  |  | Station Brackets | 771 | 186 |  | 0.24125
|  |  |  | Grounding | 985 | 204 |  | 0.20711
|  |  |  | Obstruction Brackets | 500 | 242 |  | 0.484
|  |  |  | # Cables Pulled | 415 | 87 |  | 0.20964
|  | E1 | BROADWAY | 15" CMRS Install | 543 | 118 |  | 0.21731 | 0.67945
|  |  |  | Column Clamp | 139 | 128 |  | 0.92086
|  |  |  | Station Brackets | 585 | 444 |  | 0.75897
|  |  |  | Grounding | 334 | 142 |  | 0.42515
|  |  |  | Obstruction Brackets | 367 | 356 |  | 0.97003
|  |  |  | # Cables Pulled | 691 | 542 |  | 0.78437
|  | E1 | BROADWAY | 15" CMRS Install | 142 | 46 |  | 0.32394 | 0.36432
|  |  |  | Column Clamp | 282 | 94 |  | 0.33333
|  |  |  | Station Brackets | 795 | 69 |  | 0.086792
|  |  |  | Grounding | 347 | 90 |  | 0.25937
|  |  |  | Obstruction Brackets | 403 | 156 |  | 0.3871
|  |  |  | # Cables Pulled | 865 | 688 |  | 0.79538
106011 | 105293 | E1 | FLU-BRO | 15" CMRS Install | 788 | 732 |  | 0.92893 | 0.43788
|  |  |  | Column Clamp | 844 | 664 |  | 0.78673
|  |  |  | Station Brackets | 641 | 289 |  | 0.45086
|  |  |  | Grounding | 511 | 1 |  | 0.0019569
|  |  |  | Obstruction Brackets | 945 | 327 |  | 0.34603
|  |  |  | # Cables Pulled | 736 | 83 |  | 0.11277
105293 | 104667 | E1 | FLU-BRO | 15" CMRS Install | 865 | 667 |  | 0.7711 | 0.61324
|  |  |  | Column Clamp | 501 | 143 |  | 0.28543
|  |  |  | Station Brackets | 241 | 56 |  | 0.23237
|  |  |  | Grounding | 638 | 425 |  | 0.66614
|  |  |  | Obstruction Brackets | 381 | 276 |  | 0.72441
|  |  |  | # Cables Pulled | 39 | 39 |  | 1
104667 | 103784 | E1 | FLUSHING | 15" CMRS Install | 28 | 13 |  | 0.46429 | 0.55866
|  |  |  | Column Clamp | 944 | 249 |  | 0.26377
|  |  |  | Station Brackets | 813 | 311 |  | 0.38253
|  |  |  | Grounding | 427 | 348 |  | 0.81499
|  |  |  | Obstruction Brackets | 161 | 89 |  | 0.5528
|  |  |  | # Cables Pulled | 356 | 311 |  | 0.8736
103784 | 103231 | E1 | MYR-FLU | 15" CMRS Install | 150 | 12 |  | 0.08 | 0.55322
|  |  |  | Column Clamp | 708 | 399 |  | 0.56356
|  |  |  | Station Brackets | 589 | 581 |  | 0.98642
|  |  |  | Grounding | 940 | 221 |  | 0.23511
|  |  |  | Obstruction Brackets | 356 | 210 |  | 0.58989
|  |  |  | # Cables Pulled | 494 | 427 |  | 0.86437
103231 | 103165 | E1 | MYR-FLU | 15" CMRS Install | 526 | 488 |  | 0.92776 | 0.28732
|  |  |  | Column Clamp | 351 | 183 |  | 0.52137
|  |  |  | Station Brackets | 457 | 25 |  | 0.054705
|  |  |  | Grounding | 661 | 59 |  | 0.089259
|  |  |  | Obstruction Brackets | 355 | 7 |  | 0.019718
|  |  |  | # Cables Pulled | 414 | 46 |  | 0.11111
103165 | 102533 | E1 | MYR-FLU | 15" CMRS Install | 890 | 580 |  | 0.65169 | 0.42874
|  |  |  | Column Clamp | 152 | 63 |  | 0.41447
|  |  |  | Station Brackets | 960 | 393 |  | 0.40937
|  |  |  | Grounding | 520 | 195 |  | 0.375
|  |  |  | Obstruction Brackets | 852 | 590 |  | 0.69249
|  |  |  | # Cables Pulled | 408 | 12 |  | 0.029412
102533 | 101595 | E1 | MYRTLE AVE | 24" CMRS Install | 433 | 397 |  | 0.91686 | 0.72294
|  |  |  | Column Clamp | 162 | 152 |  | 0.93827
|  |  |  | Station Brackets | 301 | 248 |  | 0.82392
|  |  |  | Grounding | 396 | 148 |  | 0.37374
|  |  |  | Obstruction Brackets | 611 | 561 |  | 0.91817
|  |  |  | # Cables Pulled | 30 | 11 |  | 0.36667
101595 | 101558 | E1 | BED-MYR | 24" CMRS Install | 633 | 227 |  | 0.35861 | 0.32433
|  |  |  | Column Clamp | 691 | 107 |  | 0.15485
|  |  |  | Station Brackets | 860 | 854 |  | 0.99302
|  |  |  | Grounding | 754 | 98 |  | 0.12997
|  |  |  | Obstruction Brackets | 897 | 129 |  | 0.14381
|  |  |  | # Cables Pulled | 175 | 29 |  | 0.16571
101558 | 101050 | E1 | BED-MYR | 24" CMRS Install | 620 | 377 |  | 0.60806 | 0.45522
|  |  |  | Column Clamp | 32 | 20 |  | 0.625
|  |  |  | Station Brackets | 724 | 254 |  | 0.35083
|  |  |  | Grounding | 330 | 102 |  | 0.30909
|  |  |  | Obstruction Brackets | 549 | 357 |  | 0.65027
|  |  |  | # Cables Pulled | 585 | 110 |  | 0.18803
101050 | 101015 | E1 | BED-MYR | 24" CMRS Install | 552 | 101 |  | 0.18297 | 0.40021
|  |  |  | Column Clamp | 319 | 49 |  | 0.15361
|  |  |  | Station Brackets | 812 | 489 |  | 0.60222
|  |  |  | Grounding | 52 | 16 |  | 0.30769
|  |  |  | Obstruction Brackets | 254 | 46 |  | 0.1811
|  |  |  | # Cables Pulled | 228 | 222 |  | 0.97368
101015 | 100530 | E1 | BED-MYR | 24" CMRS Install | 421 | 278 |  | 0.66033 | 0.5714
|  |  |  | Column Clamp | 459 | 389 |  | 0.84749
|  |  |  | Station Brackets | 417 | 60 |  | 0.14388
|  |  |  | Grounding | 76 | 52 |  | 0.68421
|  |  |  | Obstruction Brackets | 982 | 337 |  | 0.34318
|  |  |  | # Cables Pulled | 702 | 526 |  | 0.74929
100530 | 100383 | E1 | BED-MYR | Steel Mess Supports | 743 | 71 |  | 0.095559 | 0.45329
|  |  |  | Messenger Clamps | 480 | 140 |  | 0.29167
|  |  |  | Messenger Wire Pull | 396 | 278 |  | 0.70202
|  |  |  | Messenger Wire Tension | 719 | 312 |  | 0.43394
|  |  |  | # Cables Pulled | 103 | 45 |  | 0.43689
|  |  |  | Messenger Straps | 258 | 196 |  | 0.75969
|  | E1 | BED-MYR | Crossover (Arch Bar Installation) | 950 | 712 |  | 0.74947
100383 | 100282 | E1 | BED-MYR | Steel Mess Supports | 933 | 501 |  | 0.53698 | 0.48054
|  |  |  | Messenger Clamps | 157 | 28 |  | 0.17834
|  |  |  | Messenger Wire Pull | 919 | 786 |  | 0.85528
|  |  |  | Messenger Wire Tension | 921 | 503 |  | 0.54615
|  |  |  | # Cables Pulled | 172 | 69 |  | 0.40116
|  |  |  | Messenger Straps | 958 | 350 |  | 0.36534
100282 | 100036 | E1 | BED-MYR | Steel Mess Supports | 12 | 11 |  | 0.91667 | 0.62394
|  |  |  | Messenger Clamps | 368 | 210 |  | 0.57065
|  |  |  | Messenger Wire Pull | 777 | 705 |  | 0.90734
|  |  |  | Messenger Wire Tension | 369 | 81 |  | 0.21951
|  |  |  | # Cables Pulled | 565 | 512 |  | 0.90619
|  |  |  | Messenger Straps | 524 | 117 |  | 0.22328
100036 | 99560 | E1 | BED-MYR | Steel Mess Supports | 164 | 117 |  | 0.71341 | 0.58573
|  |  |  | Messenger Clamps | 596 | 485 |  | 0.81376
|  |  |  | Messenger Wire Pull | 893 | 21 |  | 0.023516
|  |  |  | Messenger Wire Tension | 16 | 5 |  | 0.3125
|  |  |  | # Cables Pulled | 883 | 575 |  | 0.65119
|  |  |  | Messenger Straps | 22 | 22 |  | 1
98845 | 98555 | E1 | CLA-BED | 24" CMRS Install | 228 | 179 |  | 0.78509 | 0.51361
|  |  |  | Column Clamp | 899 | 481 |  | 0.53504
|  |  |  | Station Brackets | 736 | 383 |  | 0.52038
|  |  |  | Grounding | 281 | 254 |  | 0.90391
|  |  |  | Obstruction Brackets | 511 | 159 |  | 0.31115
|  |  |  | # Cables Pulled | 613 | 16 |  | 0.026101
|  | E1 | CLA-BED | Crossover (Arch Bar Installation) | 721 | 546 |  | 0.75728
98555 | 98220 | E1 | CLA-BED | 24" CMRS Install | 939 | 495 |  | 0.52716 | 0.40907
|  |  |  | Column Clamp | 500 | 77 |  | 0.154
|  |  |  | Station Brackets | 140 | 77 |  | 0.55
|  |  |  | Grounding | 864 | 263 |  | 0.3044
|  |  |  | Obstruction Brackets | 65 | 28 |  | 0.43077
|  |  |  | # Cables Pulled | 545 | 266 |  | 0.48807
98220 | 98140 | E1 | CLA-BED | 24" CMRS Install | 886 | 52 |  | 0.058691 | 0.40479
|  |  |  | Column Clamp | 313 | 0 |  | 0
|  |  |  | Station Brackets | 358 | 218 |  | 0.60894
|  |  |  | Grounding | 789 | 297 |  | 0.37643
|  |  |  | Obstruction Brackets | 952 | 560 |  | 0.58824
|  |  |  | # Cables Pulled | 624 | 497 |  | 0.79647
98140 | 97920 | E1 | CLA-BED | 24" CMRS Install | 686 | 325 |  | 0.47376 | 0.52502
|  |  |  | Column Clamp | 620 | 596 |  | 0.96129
|  |  |  | Station Brackets | 910 | 78 |  | 0.085714
|  |  |  | Grounding | 322 | 158 |  | 0.49068
|  |  |  | Obstruction Brackets | 340 | 290 |  | 0.85294
|  |  |  | # Cables Pulled | 497 | 142 |  | 0.28571
97920 | 97670 | E1 | CLA-BED | Steel Mess Supports | 295 | 162 |  | 0.54915 | 0.5157
|  |  |  | Messenger Clamps | 276 | 177 |  | 0.6413
|  |  |  | Messenger Wire Pull | 180 | 136 |  | 0.75556
|  |  |  | Messenger Wire Tension | 949 | 20 |  | 0.021075
|  |  |  | # Cables Pulled | 406 | 353 |  | 0.86946
|  |  |  | Messenger Straps | 423 | 109 |  | 0.25768
97670 | 97580 | E1 | CLASSON | 24" CMRS Install | 300 | 206 |  | 0.68667 | 0.44257
|  |  |  | Column Clamp | 713 | 51 |  | 0.071529
|  |  |  | Station Brackets | 892 | 430 |  | 0.48206
|  |  |  | Grounding | 361 | 181 |  | 0.50139
|  |  |  | Obstruction Brackets | 819 | 588 |  | 0.71795
|  |  |  | # Cables Pulled | 240 | 47 |  | 0.19583
97580 | 97230 | E1 | CLASSON | 24" CMRS Install | 23 | 18 |  | 0.78261 | 0.50108
|  |  |  | Column Clamp | 171 | 66 |  | 0.38596
|  |  |  | Station Brackets | 366 | 52 |  | 0.14208
|  |  |  | Grounding | 140 | 13 |  | 0.092857
|  |  |  | Obstruction Brackets | 108 | 86 |  | 0.7963
|  |  |  | # Cables Pulled | 812 | 655 |  | 0.80665
97230 | 96920 | E1 | CLASSON | 24" CMRS Install | 667 | 426 |  | 0.63868 | 0.6351
|  |  |  | Column Clamp | 214 | 210 |  | 0.98131
|  |  |  | Station Brackets | 340 | 263 |  | 0.77353
|  |  |  | Grounding | 810 | 662 |  | 0.81728
|  |  |  | Obstruction Brackets | 361 | 9 |  | 0.024931
|  |  |  | # Cables Pulled | 995 | 572 |  | 0.57487
96920 | 96685 | E1 | CLI-CLA | Steel Mess Supports | 590 | 387 |  | 0.65593 | 0.6297
|  |  |  | Messenger Clamps | 233 | 219 |  | 0.93991
|  |  |  | Messenger Wire Pull | 465 | 328 |  | 0.70538
|  |  |  | Messenger Wire Tension | 304 | 93 |  | 0.30592
|  |  |  | # Cables Pulled | 227 | 209 |  | 0.9207
|  |  |  | Messenger Straps | 775 | 194 |  | 0.25032
96685 | 96460 | E1 | CLI-CLA | 24" CMRS Install | 127 | 5 |  | 0.03937 | 0.34925
|  |  |  | Column Clamp | 810 | 742 |  | 0.91605
|  |  |  | Station Brackets | 889 | 401 |  | 0.45107
|  |  |  | Grounding | 286 | 39 |  | 0.13636
|  |  |  | Obstruction Brackets | 401 | 181 |  | 0.45137
|  |  |  | # Cables Pulled | 474 | 48 |  | 0.10127
96460 | 96387 | E1 | CLI-CLA | 24" CMRS Install | 662 | 267 |  | 0.40332 | 0.42929
|  |  |  | Column Clamp | 724 | 337 |  | 0.46547
|  |  |  | Station Brackets | 503 | 98 |  | 0.19483
|  |  |  | Grounding | 653 | 206 |  | 0.31547
|  |  |  | Obstruction Brackets | 584 | 170 |  | 0.2911
|  |  |  | # Cables Pulled | 180 | 163 |  | 0.90556
96387 | 96051 | E1 | CLI-CLA | 24" CMRS Install | 614 | 139 |  | 0.22638 | 0.378
|  |  |  | Column Clamp | 744 | 216 |  | 0.29032
|  |  |  | Station Brackets | 387 | 361 |  | 0.93282
|  |  |  | Grounding | 478 | 163 |  | 0.341
|  |  |  | Obstruction Brackets | 547 | 32 |  | 0.058501
|  |  |  | # Cables Pulled | 864 | 362 |  | 0.41898
96038 | 95998 | E1 | CLI-CLA | 24" CMRS Install | 142 | 4 |  | 0.028169 | 0.35979
|  |  |  | Column Clamp | 878 | 485 |  | 0.55239
|  |  |  | Station Brackets | 718 | 229 |  | 0.31894
|  |  |  | Grounding | 226 | 50 |  | 0.22124
|  |  |  | Obstruction Brackets | 798 | 662 |  | 0.82957
|  |  |  | # Cables Pulled | 854 | 178 |  | 0.20843
95998 | 95873 | E1 | CLI-CLA | 24" CMRS Install | 373 | 138 |  | 0.36997 | 0.44136
|  |  |  | Column Clamp | 689 | 426 |  | 0.61829
|  |  |  | Station Brackets | 588 | 565 |  | 0.96088
|  |  |  | Grounding | 977 | 592 |  | 0.60594
|  |  |  | Obstruction Brackets | 807 | 70 |  | 0.086741
|  |  |  | # Cables Pulled | 789 | 5 |  | 0.0063371
95873 | 95781 | E1 | CLINTON-WASHINGTON | 24" CMRS Install | 497 | 349 |  | 0.70221 | 0.64846
|  |  |  | Column Clamp | 371 | 170 |  | 0.45822
|  |  |  | Station Brackets | 155 | 123 |  | 0.79355
|  |  |  | Grounding | 34 | 17 |  | 0.5
|  |  |  | Obstruction Brackets | 400 | 184 |  | 0.46
|  |  |  | # Cables Pulled | 517 | 505 |  | 0.97679
95781 | 95695 | E1 | CLINTON-WASHINGTON | 24" CMRS Install | 211 | 152 |  | 0.72038 | 0.57967
|  |  |  | Column Clamp | 183 | 83 |  | 0.45355
|  |  |  | Station Brackets | 791 | 475 |  | 0.60051
|  |  |  | Grounding | 30 | 4 |  | 0.13333
|  |  |  | Obstruction Brackets | 930 | 781 |  | 0.83978
|  |  |  | # Cables Pulled | 653 | 477 |  | 0.73047
95695 | 95544 | E1 | CLINTON-WASHINGTON | 24" CMRS Install | 989 | 630 |  | 0.63701 | 0.45512
|  |  |  | Column Clamp | 251 | 90 |  | 0.35857
|  |  |  | Station Brackets | 116 | 43 |  | 0.37069
|  |  |  | Grounding | 255 | 28 |  | 0.1098
|  |  |  | Obstruction Brackets | 374 | 295 |  | 0.78877
|  |  |  | # Cables Pulled | 938 | 437 |  | 0.46588
95544 | 95155 | E1 | CLINTON-WASHINGTON | 24" CMRS Install | 361 | 81 |  | 0.22438 | 0.58597
|  |  |  | Column Clamp | 14 | 4 |  | 0.28571
|  |  |  | Station Brackets | 777 | 663 |  | 0.85328
|  |  |  | Grounding | 529 | 311 |  | 0.5879
|  |  |  | Obstruction Brackets | 683 | 558 |  | 0.81698
|  |  |  | # Cables Pulled | 915 | 684 |  | 0.74754
95155 | 95004 | E1 | CLINTON-WASHINGTON | 24" CMRS Install | 521 | 150 |  | 0.28791 | 0.40099
|  |  |  | Column Clamp | 246 | 236 |  | 0.95935
|  |  |  | Station Brackets | 965 | 45 |  | 0.046632
|  |  |  | Grounding | 376 | 338 |  | 0.89894
|  |  |  | Obstruction Brackets | 29 | 0 |  | 0
|  |  |  | # Cables Pulled | 61 | 13 |  | 0.21311
95004 | 94266 | E1 | FUL-CLI | 24" CMRS Install | 18 | 17 |  | 0.94444 | 0.40099
|  |  |  | Column Clamp | 858 | 43 |  | 0.050117
|  |  |  | Station Brackets | 26 | 8 |  | 0.30769
|  |  |  | Grounding | 112 | 60 |  | 0.53571
|  |  |  | Obstruction Brackets | 270 | 1 |  | 0.0037037
|  |  |  | # Cables Pulled | 856 | 483 |  | 0.56425
94266 | 94207 | E1 | FUL-CLI | 24" CMRS Install | 67 | 8 |  | 0.1194 | 0.37128
|  |  |  | Column Clamp | 496 | 91 |  | 0.18347
|  |  |  | Station Brackets | 810 | 386 |  | 0.47654
|  |  |  | Grounding | 376 | 218 |  | 0.57979
|  |  |  | Obstruction Brackets | 936 | 666 |  | 0.71154
|  |  |  | # Cables Pulled | 325 | 51 |  | 0.15692
94207 | 93350 | E1 | FUL-CLI | 24" CMRS Install | 354 | 7 |  | 0.019774 | 0.58487
|  |  |  | Column Clamp | 387 | 219 |  | 0.56589
|  |  |  | Station Brackets | 602 | 486 |  | 0.80731
|  |  |  | Grounding | 822 | 642 |  | 0.78102
|  |  |  | Obstruction Brackets | 81 | 51 |  | 0.62963
|  |  |  | # Cables Pulled | 394 | 278 |  | 0.70558
73350 | 73690 | E1 | FULTON | 15" CMRS Install | 996 | 594 |  | 0.59639 | 0.5062
|  |  |  | Column Clamp | 654 | 165 |  | 0.25229
|  |  |  | Station Brackets | 774 | 636 |  | 0.82171
|  |  |  | Grounding | 673 | 576 |  | 0.85587
|  |  |  | Obstruction Brackets | 822 | 9 |  | 0.010949
|  |  |  | # Cables Pulled | 16 | 8 |  | 0.5
73690 | 74030 | E1 | FULTON | 15" CMRS Install | 826 | 41 |  | 0.049637 | 0.4748
|  |  |  | Column Clamp | 931 | 368 |  | 0.39527
|  |  |  | Station Brackets | 946 | 735 |  | 0.77696
|  |  |  | Grounding | 437 | 246 |  | 0.56293
|  |  |  | Obstruction Brackets | 255 | 50 |  | 0.19608
|  |  |  | # Cables Pulled | 742 | 644 |  | 0.86792
|  | E1 | FULTON | 15" CMRS Install | 616 | 303 |  | 0.49188 | 0.66833
|  |  |  | Column Clamp | 772 | 12 |  | 0.015544
|  |  |  | Station Brackets | 79 | 64 |  | 0.81013
|  |  |  | Grounding | 595 | 562 |  | 0.94454
|  |  |  | Obstruction Brackets | 124 | 96 |  | 0.77419
|  |  |  | # Cables Pulled | 76 | 74 |  | 0.97368
74030 | 76085 | E1 | HOY-FUL | 24" CMRS Install | 51 | 3 |  | 0.058824 | 0.28893
|  |  |  | Column Clamp | 300 | 206 |  | 0.68667
|  |  |  | Station Brackets | 95 | 39 |  | 0.41053
|  |  |  | Grounding | 691 | 51 |  | 0.073806
|  |  |  | Obstruction Brackets | 481 | 14 |  | 0.029106
|  |  |  | # Cables Pulled | 769 | 365 |  | 0.47464
76085 | 76110 | E1 | HOY-FUL | 15" CMRS Install | 780 | 44 |  | 0.05641 | 0.35214
|  |  |  | Column Clamp | 775 | 308 |  | 0.39742
|  |  |  | Station Brackets | 187 | 41 |  | 0.21925
|  |  |  | Grounding | 252 | 100 |  | 0.39683
|  |  |  | Obstruction Brackets | 250 | 198 |  | 0.792
|  |  |  | # Cables Pulled | 542 | 136 |  | 0.25092
76110 | 76165 | E1 | HOY-FUL | 15" CMRS Install | 742 | 455 |  | 0.61321 | 0.42839
|  |  |  | Column Clamp | 632 | 625 |  | 0.98892
|  |  |  | Station Brackets | 640 | 213 |  | 0.33281
|  |  |  | Grounding | 882 | 83 |  | 0.094104
|  |  |  | Obstruction Brackets | 177 | 61 |  | 0.34463
|  |  |  | # Cables Pulled | 844 | 166 |  | 0.19668
76165 | 77470 | E1 | HOYT SCHERMERHORN | 15" CMRS Install | 883 | 184 |  | 0.20838 | 0.59657
|  |  |  | Column Clamp | 453 | 421 |  | 0.92936
|  |  |  | Station Brackets | 224 | 16 |  | 0.071429
|  |  |  | Grounding | 513 | 449 |  | 0.87524
|  |  |  | Obstruction Brackets | 403 | 303 |  | 0.75186
|  |  |  | # Cables Pulled | 401 | 298 |  | 0.74314
77470 | 77595 | E1 | BER-HOY | 15" CMRS Install | 703 | 252 |  | 0.35846 | 0.3804
|  |  |  | Column Clamp | 736 | 254 |  | 0.34511
|  |  |  | Station Brackets | 213 | 187 |  | 0.87793
|  |  |  | Grounding | 760 | 179 |  | 0.23553
|  |  |  | Obstruction Brackets | 315 | 42 |  | 0.13333
|  |  |  | # Cables Pulled | 524 | 174 |  | 0.33206
77595 | 78230 | E1 | BER-HOY | 24" CMRS Install | 602 | 122 |  | 0.20266 | 0.53272
|  |  |  | Column Clamp | 16 | 15 |  | 0.9375
|  |  |  | Station Brackets | 419 | 54 |  | 0.12888
|  |  |  | Grounding | 99 | 47 |  | 0.47475
|  |  |  | Obstruction Brackets | 215 | 214 |  | 0.99535
|  |  |  | # Cables Pulled | 409 | 187 |  | 0.45721
78230 | 78515 | E1 | BER-HOY | 24" CMRS Install | 429 | 256 |  | 0.59674 | 0.45067
|  |  |  | Column Clamp | 732 | 328 |  | 0.44809
|  |  |  | Station Brackets | 583 | 229 |  | 0.3928
|  |  |  | Grounding | 835 | 213 |  | 0.25509
|  |  |  | Obstruction Brackets | 665 | 596 |  | 0.89624
|  |  |  | # Cables Pulled | 782 | 90 |  | 0.11509
|  | E2 | BERGEN | Cable Tray Brackets | 494 | 413 |  | 0.83603 | 0.41573
|  |  |  | Installing Tray | 462 | 240 |  | 0.51948
|  |  |  | Core Drilling | 114 | 16 |  | 0.14035
|  |  |  | Cable Pull | 449 | 75 |  | 0.16704
78515 | 78315 | E2 | BER-HOY | Steel Mess Supports | 269 | 90 |  | 0.33457 | 0.35976
|  |  |  | Messenger Clamps | 600 | 133 |  | 0.22167
|  |  |  | Messenger Wire Pull | 911 | 580 |  | 0.63666
|  |  |  | Messenger Wire Tension | 914 | 272 |  | 0.29759
|  |  |  | # Cables Pulled | 756 | 3 |  | 0.0039683
|  |  |  | Messenger Straps | 259 | 172 |  | 0.66409
78315 | 77655 | E2 | BER-HOY | 24" CMRS Install | 419 | 344 |  | 0.821 | 0.59795
|  |  |  | Column Clamp | 834 | 534 |  | 0.64029
|  |  |  | Station Brackets | 834 | 364 |  | 0.43645
|  |  |  | Grounding | 407 | 260 |  | 0.63882
|  |  |  | Obstruction Brackets | 597 | 146 |  | 0.24456
|  |  |  | # Cables Pulled | 305 | 246 |  | 0.80656
77655 | 77585 | E2 | BER-HOY | 24" CMRS Install | 325 | 112 |  | 0.34462 | 0.36668
|  |  |  | Column Clamp | 503 | 171 |  | 0.33996
|  |  |  | Station Brackets | 657 | 75 |  | 0.11416
|  |  |  | Grounding | 724 | 151 |  | 0.20856
|  |  |  | Obstruction Brackets | 615 | 367 |  | 0.59675
|  |  |  | # Cables Pulled | 906 | 540 |  | 0.59603
77585 | 76845 | E2 | BER-HOY | 24" CMRS Install | 626 | 505 |  | 0.80671 | 0.75601
|  |  |  | Column Clamp | 377 | 355 |  | 0.94164
|  |  |  | Station Brackets | 321 | 262 |  | 0.8162
|  |  |  | Grounding | 792 | 607 |  | 0.76641
|  |  |  | Obstruction Brackets | 512 | 210 |  | 0.41016
|  |  |  | # Cables Pulled | 556 | 442 |  | 0.79496
76845 | 76150 | E2 | HOYT SCHERMERHORN | 24" CMRS Install | 708 | 18 |  | 0.025424 | 0.28289
|  |  |  | Column Clamp | 472 | 436 |  | 0.92373
|  |  |  | Station Brackets | 142 | 25 |  | 0.17606
|  |  |  | Grounding | 674 | 43 |  | 0.063798
|  |  |  | Obstruction Brackets | 811 | 32 |  | 0.039457
|  |  |  | # Cables Pulled | 787 | 369 |  | 0.46887
76150 | 76090 | E2 | HOY-FUL | 24" CMRS Install | 927 | 415 |  | 0.44768 | 0.56982
|  |  |  | Column Clamp | 984 | 289 |  | 0.2937
|  |  |  | Station Brackets | 711 | 535 |  | 0.75246
|  |  |  | Grounding | 626 | 545 |  | 0.87061
|  |  |  | Obstruction Brackets | 57 | 11 |  | 0.19298
|  |  |  | # Cables Pulled | 953 | 821 |  | 0.86149
76090 | 75950 | E2 | HOY-FUL | 24" CMRS Install | 881 | 581 |  | 0.65948 | 0.70682
|  |  |  | Column Clamp | 554 | 136 |  | 0.24549
|  |  |  | Station Brackets | 29 | 29 |  | 1
|  |  |  | Grounding | 237 | 97 |  | 0.40928
|  |  |  | Obstruction Brackets | 269 | 262 |  | 0.97398
|  |  |  | # Cables Pulled | 740 | 705 |  | 0.9527
75950 | 75900 | E2 | HOY-FUL | Steel Mess Supports | 473 | 294 |  | 0.62156 | 0.51264
|  |  |  | Messenger Clamps | 667 | 396 |  | 0.5937
|  |  |  | Messenger Wire Pull | 383 | 99 |  | 0.25849
|  |  |  | Messenger Wire Tension | 230 | 35 |  | 0.15217
|  |  |  | # Cables Pulled | 443 | 349 |  | 0.78781
|  |  |  | Messenger Straps | 367 | 243 |  | 0.66213
75900 | 74590 | E2 | HOY-FUL | 24" CMRS Install | 278 | 62 |  | 0.22302 | 0.41098
|  |  |  | Column Clamp | 955 | 700 |  | 0.73298
|  |  |  | Station Brackets | 374 | 72 |  | 0.19251
|  |  |  | Grounding | 70 | 16 |  | 0.22857
|  |  |  | Obstruction Brackets | 475 | 382 |  | 0.80421
|  |  |  | # Cables Pulled | 123 | 35 |  | 0.28455
74590 | 74450 | E2 | HOY-FUL | Steel Mess Supports | 917 | 780 |  | 0.8506 | 0.64213
|  |  |  | Messenger Clamps | 942 | 684 |  | 0.72611
|  |  |  | Messenger Wire Pull | 44 | 32 |  | 0.72727
|  |  |  | Messenger Wire Tension | 403 | 73 |  | 0.18114
|  |  |  | # Cables Pulled | 218 | 209 |  | 0.95872
|  |  |  | Messenger Straps | 648 | 265 |  | 0.40895
74450 | 74070 | E2 | HOY-FUL | 24" CMRS Install | 971 | 808 |  | 0.83213 | 0.52116
|  |  |  | Column Clamp | 392 | 128 |  | 0.32653
|  |  |  | Station Brackets | 626 | 462 |  | 0.73802
|  |  |  | Grounding | 610 | 174 |  | 0.28525
|  |  |  | Obstruction Brackets | 728 | 184 |  | 0.25275
|  |  |  | # Cables Pulled | 416 | 288 |  | 0.69231
74070 | 74030 | E2 | HOY-FUL | 24" CMRS Install | 433 | 339 |  | 0.78291 | 0.54943
|  |  |  | Column Clamp | 832 | 322 |  | 0.38702
|  |  |  | Station Brackets | 213 | 110 |  | 0.51643
|  |  |  | Grounding | 592 | 474 |  | 0.80068
|  |  |  | Obstruction Brackets | 824 | 62 |  | 0.075243
|  |  |  | # Cables Pulled | 764 | 561 |  | 0.73429
74030 | 73690 | E2 | FULTON | 15" CMRS Install | 541 | 353 |  | 0.6525 | 0.71754
|  |  |  | Column Clamp | 846 | 721 |  | 0.85225
|  |  |  | Station Brackets | 248 | 90 |  | 0.3629
|  |  |  | Grounding | 649 | 543 |  | 0.83667
|  |  |  | Obstruction Brackets | 632 | 573 |  | 0.90665
|  |  |  | # Cables Pulled | 471 | 327 |  | 0.69427
73690 | 73250 | E2 | FULTON | 15" CMRS Install | 554 | 187 |  | 0.33755 | 0.62506 | Cable Management Takeoffs Cell F110* - 147LF instead of 440LF | Cable Management Takeoffs Cell F110* - 147LF instead of 440LF
|  |  |  | Column Clamp | 163 | 139 |  | 0.85276
|  |  |  | Station Brackets | 492 | 221 |  | 0.44919
|  |  |  | Grounding | 646 | 626 |  | 0.96904
|  |  |  | Obstruction Brackets | 562 | 139 |  | 0.24733
|  |  |  | # Cables Pulled | 398 | 356 |  | 0.89447
|  | E2 | FULTON | 15" CMRS Install | 691 | 607 |  | 0.87844 | 0.42508
|  |  |  | Column Clamp | 887 | 604 |  | 0.68095
|  |  |  | Station Brackets | 12 | 4 |  | 0.33333
|  |  |  | Grounding | 671 | 151 |  | 0.22504
|  |  |  | Obstruction Brackets | 974 | 322 |  | 0.3306
|  |  |  | # Cables Pulled | 284 | 29 |  | 0.10211
73250 | 72315 | E2 | FUL-CLI | 24" CMRS Install | 649 | 317 |  | 0.48844 | 0.46199
|  |  |  | Column Clamp | 55 | 48 |  | 0.87273
|  |  |  | Station Brackets | 699 | 66 |  | 0.094421
|  |  |  | Grounding | 166 | 6 |  | 0.036145
|  |  |  | Obstruction Brackets | 447 | 238 |  | 0.53244
|  |  |  | # Cables Pulled | 888 | 664 |  | 0.74775
94400 | 94989 | E2 | FUL-CLI | 24" CMRS Install | 978 | 455 |  | 0.46524 | 0.42682
|  |  |  | Column Clamp | 853 | 492 |  | 0.57679
|  |  |  | Station Brackets | 933 | 49 |  | 0.052519
|  |  |  | Grounding | 324 | 239 |  | 0.73765
|  |  |  | Obstruction Brackets | 633 | 91 |  | 0.14376
|  |  |  | # Cables Pulled | 571 | 334 |  | 0.58494
94989 | 95114 | E2 | FUL-CLI | 24" CMRS Install | 849 | 758 |  | 0.89282 | 0.61612
|  |  |  | Column Clamp | 473 | 129 |  | 0.27273
|  |  |  | Station Brackets | 722 | 610 |  | 0.84488
|  |  |  | Grounding | 999 | 279 |  | 0.27928
|  |  |  | Obstruction Brackets | 817 | 627 |  | 0.76744
|  |  |  | # Cables Pulled | 394 | 252 |  | 0.63959
94989 | 95114 | E2 | CLINTON-WASHINGTON | 24" CMRS Install | 925 | 911 |  | 0.98486 | 0.55727
|  |  |  | Column Clamp | 598 | 542 |  | 0.90635
|  |  |  | Station Brackets | 897 | 178 |  | 0.19844
|  |  |  | Grounding | 97 | 74 |  | 0.76289
|  |  |  | Obstruction Brackets | 607 | 130 |  | 0.21417
|  |  |  | # Cables Pulled | 372 | 103 |  | 0.27688
95503 | 95701 | E2 | CLINTON-WASHINGTON | 24" CMRS Install | 749 | 163 |  | 0.21762 | 0.64549
|  |  |  | Column Clamp | 287 | 211 |  | 0.73519
|  |  |  | Station Brackets | 995 | 451 |  | 0.45327
|  |  |  | Grounding | 79 | 49 |  | 0.62025
|  |  |  | Obstruction Brackets | 92 | 90 |  | 0.97826
|  |  |  | # Cables Pulled | 319 | 277 |  | 0.86834
95767 | 95852 | E2 | CLINTON-WASHINGTON | 24" CMRS Install | 816 | 490 |  | 0.60049 | 0.5248
|  |  |  | Column Clamp | 912 | 827 |  | 0.9068
|  |  |  | Station Brackets | 441 | 292 |  | 0.66213
|  |  |  | Grounding | 718 | 29 |  | 0.04039
|  |  |  | Obstruction Brackets | 863 | 244 |  | 0.28273
|  |  |  | # Cables Pulled | 32 | 21 |  | 0.65625
95852 | 96366 | E2 | CLINTON-WASHINGTON | 24" CMRS Install | 878 | 758 |  | 0.86333 | 0.80297
|  |  |  | Column Clamp | 814 | 765 |  | 0.9398
|  |  |  | Station Brackets | 459 | 366 |  | 0.79739
|  |  |  | Grounding | 315 | 271 |  | 0.86032
|  |  |  | Obstruction Brackets | 847 | 305 |  | 0.36009
|  |  |  | # Cables Pulled | 650 | 648 |  | 0.99692
96366 | 96432 | E2 | CLINTON-WASHINGTON | 24" CMRS Install | 268 | 178 |  | 0.66418 | 0.59032
|  |  |  | Column Clamp | 121 | 21 |  | 0.17355
|  |  |  | Station Brackets | 937 | 466 |  | 0.49733
|  |  |  | Grounding | 364 | 333 |  | 0.91484
|  |  |  | Obstruction Brackets | 864 | 751 |  | 0.86921
|  |  |  | # Cables Pulled | 473 | 200 |  | 0.42283
96432 | 96649 | E2 | CLINTON-WASHINGTON | 24" CMRS Install | 705 | 305 |  | 0.43262 | 0.31667
|  |  |  | Column Clamp | 624 | 170 |  | 0.27244
|  |  |  | Station Brackets | 809 | 438 |  | 0.54141
|  |  |  | Grounding | 387 | 43 |  | 0.11111
|  |  |  | Obstruction Brackets | 733 | 291 |  | 0.397
|  |  |  | # Cables Pulled | 275 | 40 |  | 0.14545
95767 | 95852 | E2 | CLINTON-WASHINGTON | 24" CMRS Install | 349 | 268 |  | 0.76791 | 0.62732
|  |  |  | Column Clamp | 217 | 45 |  | 0.20737
|  |  |  | Station Brackets | 500 | 107 |  | 0.214
|  |  |  | Grounding | 535 | 373 |  | 0.6972
|  |  |  | Obstruction Brackets | 339 | 332 |  | 0.97935
|  |  |  | # Cables Pulled | 981 | 881 |  | 0.89806
95852 | 96366 | E2 | CLI-CLA | 24" CMRS Install | 480 | 175 |  | 0.36458 | 0.26621
|  |  |  | Column Clamp | 799 | 144 |  | 0.18023
|  |  |  | Station Brackets | 591 | 171 |  | 0.28934
|  |  |  | Grounding | 878 | 88 |  | 0.10023
|  |  |  | Obstruction Brackets | 996 | 574 |  | 0.57631
|  |  |  | # Cables Pulled | 993 | 86 |  | 0.086606
96366 | 96432 | E2 | CLI-CLA | 24" CMRS Install | 933 | 907 |  | 0.97213 | 0.75939
|  |  |  | Column Clamp | 498 | 385 |  | 0.77309
|  |  |  | Station Brackets | 576 | 543 |  | 0.94271
|  |  |  | Grounding | 227 | 139 |  | 0.61233
|  |  |  | Obstruction Brackets | 969 | 732 |  | 0.75542
|  |  |  | # Cables Pulled | 737 | 369 |  | 0.50068
96432 | 96649 | E2 | CLI-CLA | 24" CMRS Install | 333 | 299 |  | 0.8979 | 0.60546
|  |  |  | Column Clamp | 192 | 63 |  | 0.32812
|  |  |  | Station Brackets | 780 | 502 |  | 0.64359
|  |  |  | Grounding | 486 | 260 |  | 0.53498
|  |  |  | Obstruction Brackets | 435 | 430 |  | 0.98851
|  |  |  | # Cables Pulled | 797 | 191 |  | 0.23965
96649 | 96770 | E2 | CLI-CLA | 24" CMRS Install | 273 | 265 |  | 0.9707 | 0.34702
|  |  |  | Column Clamp | 531 | 134 |  | 0.25235
|  |  |  | Station Brackets | 915 | 131 |  | 0.14317
|  |  |  | Grounding | 808 | 212 |  | 0.26238
|  |  |  | Obstruction Brackets | 32 | 2 |  | 0.0625
|  |  |  | # Cables Pulled | 312 | 122 |  | 0.39103
96770 | 96990 | E2 | CLI-CLA | Steel Mess Supports | 516 | 296 |  | 0.57364 | 0.43653
|  |  |  | Messenger Clamps | 171 | 81 |  | 0.47368
|  |  |  | Messenger Wire Pull | 928 | 642 |  | 0.69181
|  |  |  | Messenger Wire Tension | 165 | 21 |  | 0.12727
|  |  |  | # Cables Pulled | 522 | 33 |  | 0.063218
|  |  |  | Messenger Straps | 306 | 211 |  | 0.68954
96990 | 97230 | E2 | CLASSON | 24" CMRS Install | 837 | 172 |  | 0.2055 | 0.46279
|  |  |  | Column Clamp | 701 | 322 |  | 0.45934
|  |  |  | Station Brackets | 118 | 102 |  | 0.86441
|  |  |  | Grounding | 46 | 19 |  | 0.41304
|  |  |  | Obstruction Brackets | 79 | 45 |  | 0.56962
|  |  |  | # Cables Pulled | 438 | 116 |  | 0.26484
97230 | 97538 | E2 | CLASSON | 24" CMRS Install | 629 | 163 |  | 0.25914 | 0.41514
|  |  |  | Column Clamp | 941 | 818 |  | 0.86929
|  |  |  | Station Brackets | 918 | 231 |  | 0.25163
|  |  |  | Grounding | 632 | 429 |  | 0.6788
|  |  |  | Obstruction Brackets | 204 | 82 |  | 0.40196
|  |  |  | # Cables Pulled | 100 | 3 |  | 0.03
97538 | 97670 | E2 | CLASSON | 24" CMRS Install | 718 | 667 |  | 0.92897 | 0.66118
|  |  |  | Column Clamp | 458 | 443 |  | 0.96725
|  |  |  | Station Brackets | 345 | 257 |  | 0.74493
|  |  |  | Grounding | 229 | 95 |  | 0.41485
|  |  |  | Obstruction Brackets | 165 | 11 |  | 0.066667
|  |  |  | # Cables Pulled | 90 | 76 |  | 0.84444
97670 | 98015 | E2 | CLA-BED | Steel Mess Supports | 961 | 923 |  | 0.96046 | 0.71734
|  |  |  | Messenger Clamps | 131 | 81 |  | 0.61832
|  |  |  | Messenger Wire Pull | 352 | 200 |  | 0.56818
|  |  |  | Messenger Wire Tension | 18 | 15 |  | 0.83333
|  |  |  | # Cables Pulled | 759 | 375 |  | 0.49407
|  |  |  | Messenger Straps | 229 | 190 |  | 0.82969
98015 | 98125 | E2 | CLA-BED | 24" CMRS Install | 251 | 26 |  | 0.10359 | 0.6237
|  |  |  | Column Clamp | 802 | 676 |  | 0.84289
|  |  |  | Station Brackets | 152 | 118 |  | 0.77632
|  |  |  | Grounding | 918 | 637 |  | 0.6939
|  |  |  | Obstruction Brackets | 772 | 330 |  | 0.42746
|  |  |  | # Cables Pulled | 412 | 370 |  | 0.89806
98125 | 98185 | E2 | CLA-BED | 24" CMRS Install | 840 | 623 |  | 0.74167 | 0.72691
|  |  |  | Column Clamp | 992 | 467 |  | 0.47077
|  |  |  | Station Brackets | 796 | 398 |  | 0.5
|  |  |  | Grounding | 184 | 165 |  | 0.89674
|  |  |  | Obstruction Brackets | 675 | 618 |  | 0.91556
|  |  |  | # Cables Pulled | 392 | 328 |  | 0.83673
98185 | 98440 | E2 | CLA-BED | 24" CMRS Install | 327 | 127 |  | 0.38838 | 0.53633
|  |  |  | Column Clamp | 359 | 14 |  | 0.038997
|  |  |  | Station Brackets | 922 | 830 |  | 0.90022
|  |  |  | Grounding | 391 | 258 |  | 0.65985
|  |  |  | Obstruction Brackets | 554 | 272 |  | 0.49097
|  |  |  | # Cables Pulled | 96 | 71 |  | 0.73958
|  | E2 | CLA-BED | Crossover (Arch Bar Installation) | 730 | 460 |  | 0.63014
98440 | 98586 | E2 | CLA-BED | 24" CMRS Install | 475 | 249 |  | 0.52421 | 0.74213
|  |  |  | Column Clamp | 741 | 692 |  | 0.93387
|  |  |  | Station Brackets | 535 | 471 |  | 0.88037
|  |  |  | Grounding | 610 | 398 |  | 0.65246
|  |  |  | Obstruction Brackets | 197 | 186 |  | 0.94416
|  |  |  | # Cables Pulled | 141 | 73 |  | 0.51773
98586 | 98836 | E2 | CLA-BED | Steel Mess Supports | 46 | 1 |  | 0.021739 | 0.29532
|  |  |  | Messenger Clamps | 637 | 210 |  | 0.32967
|  |  |  | Messenger Wire Pull | 625 | 190 |  | 0.304
|  |  |  | Messenger Wire Tension | 28 | 19 |  | 0.67857
|  |  |  | # Cables Pulled | 406 | 66 |  | 0.16256
|  |  |  | Messenger Straps | 552 | 152 |  | 0.27536
98836 | 99505 | E2 | BEDFORD NOSTRAND | Cable Tray Brackets | 123 | 17 |  | 0.13821 | 0.28438
|  |  |  | Installing Tray | 737 | 4 |  | 0.0054274
|  |  |  | Core Drilling | 431 | 322 |  | 0.7471
|  |  |  | Cable Pull | 543 | 134 |  | 0.24678
99505 | 99950 | E2 | BED-MYR | Steel Mess Supports | 835 | 417 |  | 0.4994 | 0.42363
|  |  |  | Messenger Clamps | 811 | 339 |  | 0.418
|  |  |  | Messenger Wire Pull | 805 | 113 |  | 0.14037
|  |  |  | Messenger Wire Tension | 551 | 237 |  | 0.43013
|  |  |  | # Cables Pulled | 861 | 292 |  | 0.33914
|  |  |  | Messenger Straps | 666 | 476 |  | 0.71471
|  | E2 | CLA-BED | Crossover (Arch Bar Installation) | 862 | 266 |  | 0.30858
99950 | 100290 | E2 | BED-MYR | 24" CMRS Install | 705 | 437 |  | 0.61986 | 0.51202
|  |  |  | Column Clamp | 212 | 132 |  | 0.62264
|  |  |  | Station Brackets | 756 | 269 |  | 0.35582
|  |  |  | Grounding | 807 | 320 |  | 0.39653
|  |  |  | Obstruction Brackets | 359 | 94 |  | 0.26184
|  |  |  | # Cables Pulled | 959 | 782 |  | 0.81543
100290 | 100740 | E2 | BED-MYR | 24" CMRS Install | 58 | 48 |  | 0.82759 | 0.60257
|  |  |  | Column Clamp | 709 | 424 |  | 0.59803
|  |  |  | Station Brackets | 285 | 22 |  | 0.077193
|  |  |  | Grounding | 42 | 36 |  | 0.85714
|  |  |  | Obstruction Brackets | 704 | 195 |  | 0.27699
|  |  |  | # Cables Pulled | 93 | 91 |  | 0.97849
100740 | 100792 | E2 | BED-MYR | 24" CMRS Install | 671 | 671 |  | 1 | 0.58238
|  |  |  | Column Clamp | 964 | 359 |  | 0.37241
|  |  |  | Station Brackets | 800 | 182 |  | 0.2275
|  |  |  | Grounding | 557 | 433 |  | 0.77738
|  |  |  | Obstruction Brackets | 220 | 202 |  | 0.91818
|  |  |  | # Cables Pulled | 171 | 34 |  | 0.19883
100792 | 101595 | E2 | BED-MYR | 24" CMRS Install | 90 | 11 |  | 0.12222 | 0.33726
|  |  |  | Column Clamp | 649 | 159 |  | 0.24499
|  |  |  | Station Brackets | 432 | 295 |  | 0.68287
|  |  |  | Grounding | 21 | 4 |  | 0.19048
|  |  |  | Obstruction Brackets | 278 | 112 |  | 0.40288
|  |  |  | # Cables Pulled | 684 | 260 |  | 0.38012
101595 | 101688 | E2 | BED-MYR | 24" CMRS Install | 711 | 582 |  | 0.81857 | 0.56119
|  |  |  | Column Clamp | 65 | 58 |  | 0.89231
|  |  |  | Station Brackets | 168 | 53 |  | 0.31548
|  |  |  | Grounding | 100 | 78 |  | 0.78
|  |  |  | Obstruction Brackets | 847 | 304 |  | 0.35891
|  |  |  | # Cables Pulled | 525 | 106 |  | 0.2019
101688 | 102400 | E2 | MYRTLE AVE | 15" CMRS Install | 281 | 264 |  | 0.9395 | 0.49159
|  |  |  | Column Clamp | 700 | 159 |  | 0.22714
|  |  |  | Station Brackets | 699 | 261 |  | 0.37339
|  |  |  | Grounding | 774 | 93 |  | 0.12016
|  |  |  | Obstruction Brackets | 543 | 505 |  | 0.93002
|  |  |  | # Cables Pulled | 423 | 152 |  | 0.35934
102400 | 102550 | E2 | MYR-FLU | Steel Mess Supports | 445 | 215 |  | 0.48315 | 0.34286
|  |  |  | Messenger Clamps | 683 | 353 |  | 0.51684
|  |  |  | Messenger Wire Pull | 930 | 370 |  | 0.39785
|  |  |  | Messenger Wire Tension | 499 | 67 |  | 0.13427
|  |  |  | # Cables Pulled | 509 | 117 |  | 0.22986
|  |  |  | Messenger Straps | 935 | 276 |  | 0.29519
102550 | 103165 | E2 | MYR-FLU | 15" CMRS Install | 649 | 569 |  | 0.87673 | 0.65946
|  |  |  | Column Clamp | 747 | 305 |  | 0.4083
|  |  |  | Station Brackets | 674 | 667 |  | 0.98961
|  |  |  | Grounding | 767 | 548 |  | 0.71447
|  |  |  | Obstruction Brackets | 65 | 12 |  | 0.18462
|  |  |  | # Cables Pulled | 295 | 231 |  | 0.78305
103165 | 103230 | E2 | MYR-FLU | 15" CMRS Install | 821 | 343 |  | 0.41778 | 0.4417
|  |  |  | Column Clamp | 137 | 25 |  | 0.18248
|  |  |  | Station Brackets | 506 | 235 |  | 0.46443
|  |  |  | Grounding | 771 | 416 |  | 0.53956
|  |  |  | Obstruction Brackets | 938 | 860 |  | 0.91684
|  |  |  | # Cables Pulled | 457 | 59 |  | 0.1291
103230 | 103809 | E2 | MYR-FLU | 15" CMRS Install | 35 | 29 |  | 0.82857 | 0.44236
|  |  |  | Column Clamp | 259 | 124 |  | 0.47876
|  |  |  | Station Brackets | 930 | 5 |  | 0.0053763
|  |  |  | Grounding | 596 | 229 |  | 0.38423
|  |  |  | Obstruction Brackets | 683 | 447 |  | 0.65447
|  |  |  | # Cables Pulled | 109 | 33 |  | 0.30275
103809 | 103902 | E2 | MYR-FLU | 15" CMRS Install | 615 | 460 |  | 0.74797 | 0.36656
|  |  |  | Column Clamp | 981 | 573 |  | 0.5841
|  |  |  | Station Brackets | 837 | 234 |  | 0.27957
|  |  |  | Grounding | 154 | 23 |  | 0.14935
|  |  |  | Obstruction Brackets | 993 | 426 |  | 0.429
|  |  |  | # Cables Pulled | 214 | 2 |  | 0.0093458
103902 | 104595 | E2 | FLUSHING | 15" CMRS Install | 715 | 706 |  | 0.98741 | 0.87754
|  |  |  | Column Clamp | 292 | 289 |  | 0.98973
|  |  |  | Station Brackets | 380 | 217 |  | 0.57105
|  |  |  | Grounding | 833 | 820 |  | 0.98439
|  |  |  | Obstruction Brackets | 80 | 69 |  | 0.8625
|  |  |  | # Cables Pulled | 154 | 134 |  | 0.87013
104595 | 104750 | E2 | FLU-BRO | Steel Mess Supports | 898 | 322 |  | 0.35857 | 0.54139
|  |  |  | Messenger Clamps | 345 | 315 |  | 0.91304
|  |  |  | Messenger Wire Pull | 104 | 61 |  | 0.58654
|  |  |  | Messenger Wire Tension | 568 | 499 |  | 0.87852
|  |  |  | # Cables Pulled | 502 | 131 |  | 0.26096
|  |  |  | Messenger Straps | 682 | 171 |  | 0.25073
104750 | 105270 | E2 | FLU-BRO | 15" CMRS Install | 511 | 510 |  | 0.99804 | 0.61822
|  |  |  | Column Clamp | 677 | 267 |  | 0.39439
|  |  |  | Station Brackets | 162 | 110 |  | 0.67901
|  |  |  | Grounding | 135 | 84 |  | 0.62222
|  |  |  | Obstruction Brackets | 211 | 47 |  | 0.22275
|  |  |  | # Cables Pulled | 787 | 624 |  | 0.79288
105270 | 105930 | E2 | FLU-BRO | 15" CMRS Install | 82 | 64 |  | 0.78049 | 0.62615
|  |  |  | Column Clamp | 367 | 132 |  | 0.35967
|  |  |  | Station Brackets | 390 | 362 |  | 0.92821
|  |  |  | Grounding | 314 | 140 |  | 0.44586
|  |  |  | Obstruction Brackets | 815 | 368 |  | 0.45153
|  |  |  | # Cables Pulled | 747 | 591 |  | 0.79116
105930 | 106003 | E2 | FLU-BRO | 15" CMRS Install | 502 | 112 |  | 0.22311 | 0.56613
|  |  |  | Column Clamp | 116 | 79 |  | 0.68103
|  |  |  | Station Brackets | 33 | 15 |  | 0.45455
|  |  |  | Grounding | 913 | 859 |  | 0.94085
|  |  |  | Obstruction Brackets | 414 | 355 |  | 0.85749
|  |  |  | # Cables Pulled | 805 | 193 |  | 0.23975
106003 | 106648 | E2 | BROADWAY | 15" CMRS Install | 989 | 243 |  | 0.2457 | 0.53781
|  |  |  | Column Clamp | 875 | 589 |  | 0.67314
|  |  |  | Station Brackets | 606 | 540 |  | 0.89109
|  |  |  | Grounding | 931 | 612 |  | 0.65736
|  |  |  | Obstruction Brackets | 578 | 417 |  | 0.72145
|  |  |  | # Cables Pulled | 315 | 12 |  | 0.038095
|  | E2 | BROADWAY | 15" CMRS Install | 813 | 365 |  | 0.44895 | 0.29761
|  |  |  | Column Clamp | 824 | 156 |  | 0.18932
|  |  |  | Station Brackets | 339 | 25 |  | 0.073746
|  |  |  | Grounding | 997 | 807 |  | 0.80943
|  |  |  | Obstruction Brackets | 292 | 45 |  | 0.15411
|  |  |  | # Cables Pulled | 445 | 49 |  | 0.11011
|  | E2 | BROADWAY | 15" CMRS Install | 996 | 355 |  | 0.35643 | 0.40012
|  |  |  | Column Clamp | 165 | 16 |  | 0.09697
|  |  |  | Station Brackets | 955 | 147 |  | 0.15393
|  |  |  | Grounding | 336 | 257 |  | 0.76488
|  |  |  | Obstruction Brackets | 480 | 31 |  | 0.064583
|  |  |  | # Cables Pulled | 749 | 722 |  | 0.96395
106650 | 106920 | E2 | BRO-MET | Steel Mess Supports | 867 | 199 |  | 0.22953 | 0.52398
|  |  |  | Messenger Clamps | 436 | 302 |  | 0.69266
|  |  |  | Messenger Wire Pull | 789 | 566 |  | 0.71736
|  |  |  | Messenger Wire Tension | 71 | 71 |  | 1
|  |  |  | # Cables Pulled | 490 | 105 |  | 0.21429
|  |  |  | Messenger Straps | 331 | 96 |  | 0.29003
106918 | 107620 | E2 | BRO-MET | 15" CMRS Install | 850 | 610 |  | 0.71765 | 0.47201
|  |  |  | Column Clamp | 573 | 249 |  | 0.43455
|  |  |  | Station Brackets | 482 | 180 |  | 0.37344
|  |  |  | Grounding | 943 | 101 |  | 0.1071
|  |  |  | Obstruction Brackets | 383 | 233 |  | 0.60836
|  |  |  | # Cables Pulled | 819 | 484 |  | 0.59096
107620 | 107683 | E2 | BRO-MET | 15" CMRS Install | 288 | 185 |  | 0.64236 | 0.50668
|  |  |  | Column Clamp | 345 | 284 |  | 0.82319
|  |  |  | Station Brackets | 107 | 52 |  | 0.48598
|  |  |  | Grounding | 904 | 33 |  | 0.036504
|  |  |  | Obstruction Brackets | 877 | 858 |  | 0.97834
|  |  |  | # Cables Pulled | 95 | 7 |  | 0.073684
107683 | 108360 | E2 | BRO-MET | 15" CMRS Install | 211 | 146 |  | 0.69194 | 0.54203
|  |  |  | Column Clamp | 561 | 496 |  | 0.88414
|  |  |  | Station Brackets | 714 | 99 |  | 0.13866
|  |  |  | Grounding | 465 | 305 |  | 0.65591
|  |  |  | Obstruction Brackets | 850 | 473 |  | 0.55647
|  |  |  | # Cables Pulled | 643 | 209 |  | 0.32504
108360 | 109235 | E2 | METROPOLITAN | 15" CMRS Install | 245 | 119 |  | 0.48571 | 0.45849
|  |  |  | Column Clamp | 160 | 146 |  | 0.9125
|  |  |  | Station Brackets | 583 | 83 |  | 0.14237
|  |  |  | Grounding | 616 | 524 |  | 0.85065
|  |  |  | Obstruction Brackets | 622 | 115 |  | 0.18489
|  |  |  | # Cables Pulled | 675 | 118 |  | 0.17481
109235 | 110795 | E2 | MET-NAS | 24" CMRS Install | 375 | 228 |  | 0.608 | 0.30295
|  |  |  | Column Clamp | 564 | 106 |  | 0.18794
|  |  |  | Station Brackets | 119 | 38 |  | 0.31933
|  |  |  | Grounding | 716 | 233 |  | 0.32542
|  |  |  | Obstruction Brackets | 487 | 72 |  | 0.14784
|  |  |  | # Cables Pulled | 48 | 11 |  | 0.22917
110795 | 110865 | E2 | MET-NAS | 24" CMRS Install | 793 | 531 |  | 0.66961 | 0.5849
|  |  |  | Column Clamp | 707 | 506 |  | 0.7157
|  |  |  | Station Brackets | 164 | 8 |  | 0.04878
|  |  |  | Grounding | 765 | 580 |  | 0.75817
|  |  |  | Obstruction Brackets | 149 | 79 |  | 0.5302
|  |  |  | # Cables Pulled | 291 | 229 |  | 0.78694
110865 | 113020 | E2 | MET-NAS | 24" CMRS Install | 568 | 394 |  | 0.69366 | 0.43542
|  |  |  | Column Clamp | 203 | 29 |  | 0.14286
|  |  |  | Station Brackets | 286 | 114 |  | 0.3986
|  |  |  | Grounding | 702 | 194 |  | 0.27635
|  |  |  | Obstruction Brackets | 588 | 528 |  | 0.89796
|  |  |  | # Cables Pulled | 650 | 132 |  | 0.20308
113020 | 113155 | E2 | MET-NAS | 24" CMRS Install | 974 | 595 |  | 0.61088 | 0.59836
|  |  |  | Column Clamp | 242 | 226 |  | 0.93388
|  |  |  | Station Brackets | 473 | 407 |  | 0.86047
|  |  |  | Grounding | 571 | 194 |  | 0.33975
|  |  |  | Obstruction Brackets | 793 | 44 |  | 0.055485
|  |  |  | # Cables Pulled | 851 | 672 |  | 0.78966
113155 | 113815 | E2 | NASSAU | 24" CMRS Install | 843 | 486 |  | 0.57651 | 0.51646
|  |  |  | Column Clamp | 179 | 111 |  | 0.62011
|  |  |  | Station Brackets | 289 | 115 |  | 0.39792
|  |  |  | Grounding | 639 | 254 |  | 0.3975
|  |  |  | Obstruction Brackets | 875 | 475 |  | 0.54286
|  |  |  | # Cables Pulled | 603 | 340 |  | 0.56385
113815 | 114105 | E2 | NAS-GRE | Steel Mess Supports | 43 | 38 |  | 0.88372 | 0.62533
|  |  |  | Messenger Clamps | 411 | 57 |  | 0.13869
|  |  |  | Messenger Wire Pull | 524 | 392 |  | 0.74809
|  |  |  | Messenger Wire Tension | 225 | 210 |  | 0.93333
|  |  |  | # Cables Pulled | 795 | 459 |  | 0.57736
|  |  |  | Messenger Straps | 342 | 161 |  | 0.47076
114105 | 114730 | E2 | NAS-GRE | 24" CMRS Install | 514 | 56 |  | 0.10895 | 0.47215
|  |  |  | Column Clamp | 260 | 199 |  | 0.76538
|  |  |  | Station Brackets | 768 | 304 |  | 0.39583
|  |  |  | Grounding | 346 | 125 |  | 0.36127
|  |  |  | Obstruction Brackets | 952 | 437 |  | 0.45903
|  |  |  | # Cables Pulled | 330 | 245 |  | 0.74242
114730 | 114910 | E2 | NAS-GRE | Steel Mess Supports | 665 | 32 |  | 0.04812 | 0.32247
|  |  |  | Messenger Clamps | 249 | 126 |  | 0.50602
|  |  |  | Messenger Wire Pull | 117 | 70 |  | 0.59829
|  |  |  | Messenger Wire Tension | 957 | 402 |  | 0.42006
|  |  |  | # Cables Pulled | 745 | 231 |  | 0.31007
|  |  |  | Messenger Straps | 785 | 41 |  | 0.052229
114910 | 115625 | E2 | NAS-GRE | 24" CMRS Install | 232 | 117 |  | 0.50431 | 0.49417
|  |  |  | Column Clamp | 420 | 284 |  | 0.67619
|  |  |  | Station Brackets | 912 | 185 |  | 0.20285
|  |  |  | Grounding | 708 | 607 |  | 0.85734
|  |  |  | Obstruction Brackets | 482 | 179 |  | 0.37137
|  |  |  | # Cables Pulled | 119 | 42 |  | 0.35294
115625 | 116435 | E2 | GREENPOINT | 24" CMRS Install | 137 | 134 |  | 0.9781 | 0.46938
|  |  |  | Column Clamp | 675 | 527 |  | 0.78074
|  |  |  | Station Brackets | 876 | 82 |  | 0.093607
|  |  |  | Grounding | 339 | 1 |  | 0.0029499
|  |  |  | Obstruction Brackets | 486 | 215 |  | 0.44239
|  |  |  | # Cables Pulled | 162 | 84 |  | 0.51852
116435 | 117130 | E2 | GRE-21S | 24" CMRS Install | 802 | 458 |  | 0.57107 | 0.51895
|  |  |  | Column Clamp | 235 | 168 |  | 0.71489
|  |  |  | Station Brackets | 211 | 191 |  | 0.90521
|  |  |  | Grounding | 459 | 42 |  | 0.091503
|  |  |  | Obstruction Brackets | 511 | 39 |  | 0.076321
|  |  |  | # Cables Pulled | 53 | 40 |  | 0.75472
|  | E2 | GRE-21S | Crossover (Arch Bar Installation) | 394 | 16 |  | 0.040609
117130 | 121035 | E2 | GRE-21S | 24" CMRS Install | 615 | 365 |  | 0.5935 | 0.57867
|  |  |  | Column Clamp | 231 | 91 |  | 0.39394
|  |  |  | Station Brackets | 673 | 376 |  | 0.55869
|  |  |  | Grounding | 929 | 717 |  | 0.7718
|  |  |  | Obstruction Brackets | 658 | 233 |  | 0.3541
|  |  |  | # Cables Pulled | 300 | 240 |  | 0.8
121035 | 122030 | E2 | 21ST STATION | Steel Mess Supports | 968 | 737 |  | 0.76136 | 0.60616
|  |  |  | Messenger Clamps | 666 | 437 |  | 0.65616
|  |  |  | Messenger Wire Pull | 620 | 148 |  | 0.23871
|  |  |  | Messenger Wire Tension | 608 | 571 |  | 0.93914
|  |  |  | # Cables Pulled | 412 | 167 |  | 0.40534
|  |  |  | Messenger Straps | 657 | 418 |  | 0.63623
122030 | 122430 | E2 | 21S-COU | 24" CMRS Install | 511 | 172 |  | 0.33659 | 0.68684
|  |  |  | Column Clamp | 400 | 376 |  | 0.94
|  |  |  | Station Brackets | 125 | 79 |  | 0.632
|  |  |  | Grounding | 146 | 121 |  | 0.82877
|  |  |  | Obstruction Brackets | 300 | 225 |  | 0.75
|  |  |  | # Cables Pulled | 202 | 128 |  | 0.63366
122430 | 122660 | E2 | 21S-COU | Steel Mess Supports | 938 | 840 |  | 0.89552 | 0.72847
|  |  |  | Messenger Clamps | 109 | 44 |  | 0.40367
|  |  |  | Messenger Wire Pull | 652 | 285 |  | 0.43712
|  |  |  | Messenger Wire Tension | 591 | 456 |  | 0.77157
|  |  |  | # Cables Pulled | 237 | 207 |  | 0.87342
|  |  |  | Messenger Straps | 574 | 568 |  | 0.98955
122660 | 122827 | E2 | 21S-COU | 24" CMRS Install | 613 | 112 |  | 0.18271 | 0.39373
|  |  |  | Column Clamp | 286 | 204 |  | 0.71329
|  |  |  | Station Brackets | 47 | 15 |  | 0.31915
|  |  |  | Grounding | 829 | 217 |  | 0.26176
|  |  |  | Obstruction Brackets | 436 | 108 |  | 0.24771
|  |  |  | # Cables Pulled | 196 | 125 |  | 0.63776
122827 | 123085 | E2 | 21S-COU | Steel Mess Supports | 209 | 174 |  | 0.83254 | 0.38315
|  |  |  | Messenger Clamps | 725 | 113 |  | 0.15586
|  |  |  | Messenger Wire Pull | 638 | 63 |  | 0.098746
|  |  |  | Messenger Wire Tension | 553 | 150 |  | 0.27125
|  |  |  | # Cables Pulled | 60 | 33 |  | 0.55
|  |  |  | Messenger Straps | 507 | 198 |  | 0.39053
123085 | 123690 | E2 | COURT SQ | Cable Tray Brackets | 303 | 134 |  | 0.44224 | 0.50624
|  |  |  | Installing Tray | 493 | 161 |  | 0.32657
|  |  |  | Core Drilling | 424 | 235 |  | 0.55425
|  |  |  | Cable Pull | 473 | 332 |  | 0.7019
123690 | 123750 | E2 | COU-QUE | Steel Mess Supports | 450 | 325 |  | 0.72222 | 0.41413
|  |  |  | Messenger Clamps | 489 | 185 |  | 0.37832
|  |  |  | Messenger Wire Pull | 656 | 394 |  | 0.60061
|  |  |  | Messenger Wire Tension | 512 | 61 |  | 0.11914
|  |  |  | # Cables Pulled | 378 | 186 |  | 0.49206
|  |  |  | Messenger Straps | 609 | 105 |  | 0.17241
123750 | 123950 | E2 | COU-QUE | Steel Mess Supports | 990 | 703 |  | 0.7101 | 0.50556
|  |  |  | Messenger Clamps | 337 | 312 |  | 0.92582
|  |  |  | Messenger Wire Pull | 11 | 1 |  | 0.090909
|  |  |  | Messenger Wire Tension | 608 | 116 |  | 0.19079
|  |  |  | # Cables Pulled | 348 | 264 |  | 0.75862
|  |  |  | Messenger Straps | 434 | 155 |  | 0.35714
123950 | 124050 | E2 | COU-QUE | Steel Mess Supports | 259 | 123 |  | 0.4749 | 0.52057
|  |  |  | Messenger Clamps | 919 | 262 |  | 0.28509
|  |  |  | Messenger Wire Pull | 193 | 133 |  | 0.68912
|  |  |  | Messenger Wire Tension | 771 | 248 |  | 0.32166
|  |  |  | # Cables Pulled | 524 | 202 |  | 0.3855
|  |  |  | Messenger Straps | 396 | 383 |  | 0.96717
124050 | 124190 | E2 | COU-QUE | Steel Mess Supports | 193 | 77 |  | 0.39896 | 0.46392
|  |  |  | Messenger Clamps | 358 | 15 |  | 0.041899
|  |  |  | Messenger Wire Pull | 700 | 69 |  | 0.098571
|  |  |  | Messenger Wire Tension | 147 | 58 |  | 0.39456
|  |  |  | # Cables Pulled | 368 | 337 |  | 0.91576
|  |  |  | Messenger Straps | 815 | 761 |  | 0.93374
124190 | 124490 | E2 | COU-QUE | Steel Mess Supports | 818 | 354 |  | 0.43276 | 0.42783
|  |  |  | Messenger Clamps | 990 | 205 |  | 0.20707
|  |  |  | Messenger Wire Pull | 39 | 13 |  | 0.33333
|  |  |  | Messenger Wire Tension | 698 | 360 |  | 0.51576
|  |  |  | # Cables Pulled | 998 | 501 |  | 0.502
|  |  |  | Messenger Straps | 835 | 481 |  | 0.57605
124490 | 124700 | E2 | COU-QUE | Steel Mess Supports | 94 | 4 |  | 0.042553 | 0.32878
|  |  |  | Messenger Clamps | 515 | 13 |  | 0.025243
|  |  |  | Messenger Wire Pull | 682 | 47 |  | 0.068915
|  |  |  | Messenger Wire Tension | 394 | 272 |  | 0.69036
|  |  |  | # Cables Pulled | 287 | 278 |  | 0.96864
|  |  |  | Messenger Straps | 113 | 20 |  | 0.17699
124700 | 125010 | E2 | COU-QUE | Steel Mess Supports | 730 | 669 |  | 0.91644 | 0.44128
|  |  |  | Messenger Clamps | 23 | 5 |  | 0.21739
|  |  |  | Messenger Wire Pull | 517 | 248 |  | 0.47969
|  |  |  | Messenger Wire Tension | 967 | 660 |  | 0.68252
|  |  |  | # Cables Pulled | 716 | 187 |  | 0.26117
|  |  |  | Messenger Straps | 630 | 57 |  | 0.090476
|  | E2 | COU-QUE | Crossover (Arch Bar Installation) | 667 | 659 |  | 0.98801
75650 | 78244 | B3 | BERGEN ST | Steel Mess Supports | 668 | 160 |  | 0.23952 | 0.45297
|  |  |  | Messenger Clamps | 297 | 220 |  | 0.74074
|  |  |  | Messenger Wire Pull | 101 | 37 |  | 0.36634
|  |  |  | Messenger Wire Tension | 814 | 250 |  | 0.30713
|  |  |  | # Cables Pulled | 301 | 38 |  | 0.12625
|  |  |  | Messenger Straps | 386 | 362 |  | 0.93782
|  | B3 | BER-JAY | Steel Mess Supports | 815 | 275 |  | 0.33742 | 0.43424
|  |  |  | Messenger Clamps | 694 | 584 |  | 0.8415
|  |  |  | Messenger Wire Pull | 126 | 24 |  | 0.19048
|  |  |  | Messenger Wire Tension | 676 | 110 |  | 0.16272
|  |  |  | # Cables Pulled | 328 | 209 |  | 0.6372
|  |  |  | Messenger Straps | 493 | 215 |  | 0.43611
|  | B4 | BER-JAY | Steel Mess Supports | 357 | 10 |  | 0.028011 | 0.35595
|  |  |  | Messenger Clamps | 520 | 141 |  | 0.27115
|  |  |  | Messenger Wire Pull | 967 | 145 |  | 0.14995
|  |  |  | Messenger Wire Tension | 395 | 327 |  | 0.82785
|  |  |  | # Cables Pulled | 92 | 52 |  | 0.56522
|  |  |  | Messenger Straps | 879 | 258 |  | 0.29352
|  | E3/E4 | COURT SQ | Steel Mess Supports | 740 | 549 |  | 0.74189 | 0.55802
|  |  |  | Messenger Clamps | 694 | 575 |  | 0.82853
|  |  |  | Messenger Wire Pull | 76 | 31 |  | 0.40789
|  |  |  | Messenger Wire Tension | 501 | 163 |  | 0.32535
|  |  |  | # Cables Pulled | 322 | 170 |  | 0.52795
|  |  |  | Messenger Straps | 910 | 470 |  | 0.51648
75640 | 75300 | B1 | CAR-BER | Steel Mess Supports | 190 | 107 |  | 0.56316 | 0.36022
|  |  |  | Messenger Clamps | 307 | 35 |  | 0.11401
|  |  |  | Messenger Wire Pull | 670 | 107 |  | 0.1597
|  |  |  | Messenger Wire Tension | 809 | 141 |  | 0.17429
|  |  |  | # Cables Pulled | 976 | 220 |  | 0.22541
|  |  |  | Messenger Straps | 598 | 553 |  | 0.92475
68570 | 68330 | B3 | 4TH AVE | Steel Mess Supports | 739 | 253 |  | 0.34235 | 0.40251
|  |  |  | Messenger Clamps | 612 | 256 |  | 0.4183
|  |  |  | Messenger Wire Pull | 583 | 429 |  | 0.73585
|  |  |  | Messenger Wire Tension | 967 | 343 |  | 0.35471
|  |  |  | # Cables Pulled | 205 | 34 |  | 0.16585
|  |  |  | Messenger Straps | 985 | 392 |  | 0.39797
68330 | 68030 | B3 | 4AV-7AV | Steel Mess Supports | 766 | 36 |  | 0.046997 | 0.41762
|  |  |  | Messenger Clamps | 126 | 62 |  | 0.49206
|  |  |  | Messenger Wire Pull | 949 | 138 |  | 0.14542
|  |  |  | Messenger Wire Tension | 523 | 357 |  | 0.6826
|  |  |  | # Cables Pulled | 527 | 423 |  | 0.80266
|  |  |  | Messenger Straps | 628 | 211 |  | 0.33599
66070 | 66000 | B3 | 4AV-7AV | Steel Mess Supports | 619 | 39 |  | 0.063005 | 0.33329
|  |  |  | Messenger Clamps | 716 | 516 |  | 0.72067
|  |  |  | Messenger Wire Pull | 744 | 250 |  | 0.33602
|  |  |  | Messenger Wire Tension | 109 | 26 |  | 0.23853
|  |  |  | # Cables Pulled | 387 | 80 |  | 0.20672
|  |  |  | Messenger Straps | 46 | 20 |  | 0.43478
60350 | 60000 | B1 | FOR-15S | Steel Mess Supports | 359 | 140 |  | 0.38997 | 0.28875
|  |  |  | Messenger Clamps | 242 | 62 |  | 0.2562
|  |  |  | Messenger Wire Pull | 377 | 214 |  | 0.56764
|  |  |  | Messenger Wire Tension | 518 | 191 |  | 0.36873
|  |  |  | # Cables Pulled | 877 | 84 |  | 0.095781
|  |  |  | Messenger Straps | 517 | 28 |  | 0.054159
56440 | 56350 | B1 | CHU-FOR | Steel Mess Supports | 47 | 25 |  | 0.53191 | 0.49218
|  |  |  | Messenger Clamps | 412 | 31 |  | 0.075243
|  |  |  | Messenger Wire Pull | 654 | 581 |  | 0.88838
|  |  |  | Messenger Wire Tension | 427 | 4 |  | 0.0093677
|  |  |  | # Cables Pulled | 689 | 330 |  | 0.47896
|  |  |  | Messenger Straps | 325 | 315 |  | 0.96923
55580 | 54500 | B2 | CHU-DIT | Steel Mess Supports | 779 | 158 |  | 0.20282 | 0.49212
|  |  |  | Messenger Clamps | 991 | 163 |  | 0.16448
|  |  |  | Messenger Wire Pull | 283 | 128 |  | 0.4523
|  |  |  | Messenger Wire Tension | 92 | 83 |  | 0.90217
|  |  |  | # Cables Pulled | 946 | 455 |  | 0.48097
|  |  |  | Messenger Straps | 344 | 258 |  | 0.75
54730 | 55000 | B2 | CHU-DIT | Steel Mess Supports | 891 | 462 |  | 0.51852 | 0.30228
|  |  |  | Messenger Clamps | 352 | 1 |  | 0.0028409
|  |  |  | Messenger Wire Pull | 516 | 231 |  | 0.44767
|  |  |  | Messenger Wire Tension | 952 | 175 |  | 0.18382
|  |  |  | # Cables Pulled | 26 | 16 |  | 0.61538
|  |  |  | Messenger Straps | 44 | 2 |  | 0.045455
55485 | 55725 | B2 | CHU-DIT | Steel Mess Supports | 941 | 271 |  | 0.28799 | 0.53247
|  |  |  | Messenger Clamps | 827 | 150 |  | 0.18138
|  |  |  | Messenger Wire Pull | 498 | 291 |  | 0.58434
|  |  |  | Messenger Wire Tension | 105 | 57 |  | 0.54286
|  |  |  | # Cables Pulled | 837 | 796 |  | 0.95102
|  |  |  | Messenger Straps | 635 | 411 |  | 0.64724
55725 | 56635 | B2 | CHURCH AVE | Steel Mess Supports | 39 | 4 |  | 0.10256 | 0.65169
|  |  |  | Messenger Clamps | 445 | 347 |  | 0.77978
|  |  |  | Messenger Wire Pull | 981 | 178 |  | 0.18145
|  |  |  | Messenger Wire Tension | 509 | 496 |  | 0.97446
|  |  |  | # Cables Pulled | 801 | 775 |  | 0.96754
|  |  |  | Messenger Straps | 732 | 662 |  | 0.90437
57320 | 57445 | B2 | CHU-FOR | Steel Mess Supports | 45 | 34 |  | 0.75556 | 0.60465
|  |  |  | Messenger Clamps | 118 | 31 |  | 0.26271
|  |  |  | Messenger Wire Pull | 177 | 176 |  | 0.99435
|  |  |  | Messenger Wire Tension | 701 | 523 |  | 0.74608
|  |  |  | # Cables Pulled | 980 | 111 |  | 0.11327
|  |  |  | Messenger Straps | 504 | 381 |  | 0.75595
60165 | 60620 | B2 | FOR-15S | Steel Mess Supports | 208 | 76 |  | 0.36538 | 0.48937
|  |  |  | Messenger Clamps | 154 | 45 |  | 0.29221
|  |  |  | Messenger Wire Pull | 248 | 239 |  | 0.96371
|  |  |  | Messenger Wire Tension | 645 | 117 |  | 0.1814
|  |  |  | # Cables Pulled | 540 | 209 |  | 0.38704
|  |  |  | Messenger Straps | 71 | 53 |  | 0.74648
62560 | 63425 | B2 | 15TH STREET PROSPECT PARK | Steel Mess Supports | 551 | 493 |  | 0.89474 | 0.53705
|  |  |  | Messenger Clamps | 238 | 78 |  | 0.32773
|  |  |  | Messenger Wire Pull | 238 | 149 |  | 0.62605
|  |  |  | Messenger Wire Tension | 265 | 77 |  | 0.29057
|  |  |  | # Cables Pulled | 92 | 70 |  | 0.76087
|  |  |  | Messenger Straps | 546 | 176 |  | 0.32234
67950 | 68330 | B4/B2 | 4AV-7AV | Steel Mess Supports | 685 | 653 |  | 0.95328 | 0.47305
|  |  |  | Messenger Clamps | 608 | 34 |  | 0.055921
|  |  |  | Messenger Wire Pull | 873 | 202 |  | 0.23139
|  |  |  | Messenger Wire Tension | 161 | 110 |  | 0.68323
|  |  |  | # Cables Pulled | 506 | 29 |  | 0.057312
|  |  |  | Messenger Straps | 28 | 24 |  | 0.85714
74740 | 74840 | B2 | CAR-BER | Steel Mess Supports | 243 | 84 |  | 0.34568 | 0.43516
|  |  |  | Messenger Clamps | 82 | 42 |  | 0.5122
|  |  |  | Messenger Wire Pull | 415 | 56 |  | 0.13494
|  |  |  | Messenger Wire Tension | 795 | 604 |  | 0.75975
|  |  |  | # Cables Pulled | 69 | 38 |  | 0.55072
|  |  |  | Messenger Straps | 247 | 76 |  | 0.30769
75395 | 75650 | B2 | CAR-BER | Steel Mess Supports | 493 | 442 |  | 0.89655 | 0.6114
|  |  |  | Messenger Clamps | 943 | 362 |  | 0.38388
|  |  |  | Messenger Wire Pull | 638 | 246 |  | 0.38558
|  |  |  | Messenger Wire Tension | 91 | 81 |  | 0.89011
|  |  |  | # Cables Pulled | 761 | 757 |  | 0.99474
|  |  |  | Messenger Straps | 434 | 51 |  | 0.11751
78905 | 75950 | B3 | JAY-BER | Steel Mess Supports | 298 | 23 |  | 0.077181 | 0.35171
|  |  |  | Messenger Clamps | 663 | 396 |  | 0.59729
|  |  |  | Messenger Wire Pull | 622 | 59 |  | 0.094855
|  |  |  | Messenger Wire Tension | 93 | 24 |  | 0.25806
|  |  |  | # Cables Pulled | 399 | 141 |  | 0.35338
|  |  |  | Messenger Straps | 695 | 507 |  | 0.7295
75950 | 75650 | B3 | BERGEN ST | Steel Mess Supports | 862 | 195 |  | 0.22622 | 0.49678
|  |  |  | Messenger Clamps | 116 | 63 |  | 0.5431
|  |  |  | Messenger Wire Pull | 97 | 45 |  | 0.46392
|  |  |  | Messenger Wire Tension | 677 | 0 |  | 0
|  |  |  | # Cables Pulled | 50 | 49 |  | 0.98
|  |  |  | Messenger Straps | 43 | 33 |  | 0.76744
75650 | 75420 | B3 | CAR-BER | Steel Mess Supports | 916 | 37 |  | 0.040393 | 0.51177
|  |  |  | Messenger Clamps | 129 | 14 |  | 0.10853
|  |  |  | Messenger Wire Pull | 621 | 410 |  | 0.66023
|  |  |  | Messenger Wire Tension | 530 | 383 |  | 0.72264
|  |  |  | # Cables Pulled | 899 | 738 |  | 0.82091
|  |  |  | Messenger Straps | 748 | 537 |  | 0.71791
73285 | 72960 | B3 | CAR-BER | Steel Mess Supports | 534 | 19 |  | 0.035581 | 0.3538
|  |  |  | Messenger Clamps | 262 | 203 |  | 0.77481
|  |  |  | Messenger Wire Pull | 221 | 168 |  | 0.76018
|  |  |  | Messenger Wire Tension | 261 | 89 |  | 0.341
|  |  |  | # Cables Pulled | 926 | 146 |  | 0.15767
|  |  |  | Messenger Straps | 672 | 36 |  | 0.053571
72960 | 72035 | B3/B4 | CAR-4TH | Steel Mess Supports | 813 | 445 |  | 0.54736 | 0.66169
|  |  |  | Messenger Clamps | 896 | 765 |  | 0.85379
|  |  |  | Messenger Wire Pull | 137 | 90 |  | 0.65693
|  |  |  | Messenger Wire Tension | 895 | 296 |  | 0.33073
|  |  |  | # Cables Pulled | 368 | 259 |  | 0.7038
|  |  |  | Messenger Straps | 49 | 43 |  | 0.87755
71150 | 70965 | B3/B4 | CAR-4TH | Steel Mess Supports | 804 | 360 |  | 0.44776 | 0.70108
|  |  |  | Messenger Clamps | 396 | 338 |  | 0.85354
|  |  |  | Messenger Wire Pull | 778 | 431 |  | 0.55398
|  |  |  | Messenger Wire Tension | 353 | 331 |  | 0.93768
|  |  |  | # Cables Pulled | 680 | 622 |  | 0.91471
|  |  |  | Messenger Straps | 429 | 214 |  | 0.49883
70965 | 70445 | B3/B6 | CAR-4TH | Steel Mess Supports | 969 | 351 |  | 0.36223 | 0.41856
|  |  |  | Messenger Clamps | 68 | 54 |  | 0.79412
|  |  |  | Messenger Wire Pull | 204 | 97 |  | 0.47549
|  |  |  | Messenger Wire Tension | 394 | 282 |  | 0.71574
|  |  |  | # Cables Pulled | 270 | 34 |  | 0.12593
|  |  |  | Messenger Straps | 871 | 33 |  | 0.037887
70445 | 70045 | B3/B7 | CAR-4TH | Steel Mess Supports | 17 | 15 |  | 0.88235 | 0.51004
|  |  |  | Messenger Clamps | 206 | 116 |  | 0.56311
|  |  |  | Messenger Wire Pull | 728 | 328 |  | 0.45055
|  |  |  | Messenger Wire Tension | 804 | 68 |  | 0.084577
|  |  |  | # Cables Pulled | 388 | 254 |  | 0.65464
|  |  |  | Messenger Straps | 440 | 187 |  | 0.425
68625 | 68400 | B3/B8 | CAR-4TH | Steel Mess Supports | 102 | 36 |  | 0.35294 | 0.55862
|  |  |  | Messenger Clamps | 270 | 213 |  | 0.78889
|  |  |  | Messenger Wire Pull | 506 | 47 |  | 0.092885
|  |  |  | Messenger Wire Tension | 594 | 248 |  | 0.41751
|  |  |  | # Cables Pulled | 616 | 533 |  | 0.86526
|  |  |  | Messenger Straps | 362 | 302 |  | 0.83425
68400 | 68330 | B3/B9 | CAR-4TH | Steel Mess Supports | 298 | 6 |  | 0.020134 | 0.47884
|  |  |  | Messenger Clamps | 350 | 314 |  | 0.89714
|  |  |  | Messenger Wire Pull | 103 | 71 |  | 0.68932
|  |  |  | Messenger Wire Tension | 127 | 2 |  | 0.015748
|  |  |  | # Cables Pulled | 495 | 422 |  | 0.85253
|  |  |  | Messenger Straps | 874 | 348 |  | 0.39817

## AXLE COUNTER
Stationing | Track No | Location | Activity | Date | Progress | General Progress | Notes | DWG REF.
54600 | B1 | DIT-CHU | Axle Counter Installation |  | 80.34% | 52.7% | STATIONING SHOWN IS THAT OF THE NEAREST IJ, AXC STATIONING DOES NOT EXIST | B1-546
|  |  | JB Installation |  | 30.49%
|  |  | Line Cable Installation |  | 17.87%
|  |  | Express Cable Installation |  | 68.51%
|  |  | Pre-Operation Testing |  | 66.28%
| B1 |  | Axle Counter Installation |  | 25.91% | 32.75% | NO INFO | B1-547
|  |  | JB Installation |  | 33.91%
|  |  | Line Cable Installation |  | 0.8982%
|  |  | Express Cable Installation |  | 16.27%
|  |  | Pre-Operation Testing |  | 86.76%
59297 | B1 | FOR-15S | Axle Counter Installation |  | 33.14% | 53.72% |  | B1-553
|  |  | JB Installation |  | 63.81%
|  |  | Line Cable Installation |  | 59.21%
|  |  | Express Cable Installation |  | 38.23%
|  |  | Pre-Operation Testing |  | 74.23%
| B1 |  | Axle Counter Installation |  | 20.6% | 18.64% | NO INFO | B1-554
|  |  | JB Installation |  | 8.17%
|  |  | Line Cable Installation |  | 20.9%
|  |  | Express Cable Installation |  | 23.29%
|  |  | Pre-Operation Testing |  | 20.23%
55687 | B1 | DIT-CHU | Axle Counter Installation |  | 28.65% | 64.13% |  | B1-557
|  |  | JB Installation |  | 91.91%
|  |  | Line Cable Installation |  | 46.37%
|  |  | Express Cable Installation |  | 95.72%
|  |  | Pre-Operation Testing |  | 58.01%
56367 | B1 | CHU-FOR | Axle Counter Installation |  | 92.64% | 88.15% |  | B1-564
|  |  | JB Installation |  | 91.24%
|  |  | Line Cable Installation |  | 83.6%
|  |  | Express Cable Installation |  | 85.37%
|  |  | Pre-Operation Testing |  | 87.89%
58524.6 | B1 | FORT HAMILTON PARKWAY | Axle Counter Installation |  | 25.64% | 45.1% |  | B1-585
|  |  | JB Installation |  | 25.31%
|  |  | Line Cable Installation |  | 86.85%
|  |  | Express Cable Installation |  | 71.86%
|  |  | Pre-Operation Testing |  | 15.82%
59210.25 | B1 | FOR-15S | Axle Counter Installation |  | 15.51% | 41.34% |  | B1-592
|  |  | JB Installation |  | 89.14%
|  |  | Line Cable Installation |  | 73.81%
|  |  | Express Cable Installation |  | 25.8%
|  |  | Pre-Operation Testing |  | 2.447%
62572.5 | B1 | FOR-15S | Axle Counter Installation |  | 28.09% | 72.41% |  | B1-626
|  |  | JB Installation |  | 98.96%
|  |  | Line Cable Installation |  | 51.74%
|  |  | Express Cable Installation |  | 93.01%
|  |  | Pre-Operation Testing |  | 90.24%
63251.4 | B1 | 15S-7AV | Axle Counter Installation |  | 70.91% | 54.01% |  | B1-632
|  |  | JB Installation |  | 5.073%
|  |  | Line Cable Installation |  | 80.01%
|  |  | Express Cable Installation |  | 84.38%
|  |  | Pre-Operation Testing |  | 29.67%
65387.3 | B1 | 15S-7AV | Axle Counter Installation |  | 69.96% | 53.49% |  | B1-654
|  |  | JB Installation |  | 40.6%
|  |  | Line Cable Installation |  | 15.83%
|  |  | Express Cable Installation |  | 64.13%
|  |  | Pre-Operation Testing |  | 76.93%
66076 | B1 | 7AV-4TH | Axle Counter Installation |  | 86.12% | 76.28% |  | B1-661
|  |  | JB Installation |  | 87.76%
|  |  | Line Cable Installation |  | 58.49%
|  |  | Express Cable Installation |  | 64.2%
|  |  | Pre-Operation Testing |  | 84.86%
73206.7 | B1 | SMI-CAR | Axle Counter Installation |  | 8.606% | 13.11% |  | B1-732
|  |  | JB Installation |  | 26.39%
|  |  | Line Cable Installation |  | 10.69%
|  |  | Express Cable Installation |  | 6.631%
|  |  | Pre-Operation Testing |  | 13.24%
73932 | B1 | CAR-BER | Axle Counter Installation |  | 71.32% | 48.02% |  | B1-739
|  |  | JB Installation |  | 26.1%
|  |  | Line Cable Installation |  | 37.2%
|  |  | Express Cable Installation |  | 96.34%
|  |  | Pre-Operation Testing |  | 9.14%
75408 | B1 | CAR-BER | Axle Counter Installation |  | 64.65% | 68.12% |  | B1-755
|  |  | JB Installation |  | 33.1%
|  |  | Line Cable Installation |  | 98.32%
|  |  | Express Cable Installation |  | 63.34%
|  |  | Pre-Operation Testing |  | 81.17%
75669 | B1 | CAR-BER | Axle Counter Installation |  | 67.48% | 44.74% |  | B1-756
|  |  | JB Installation |  | 62.43%
|  |  | Line Cable Installation |  | 11.1%
|  |  | Express Cable Installation |  | 53.79%
|  |  | Pre-Operation Testing |  | 28.87%
76352 | B1 | BER-HOY | Axle Counter Installation |  | 81.53% | 64.48% |  | B1-763, B1-764
|  |  | JB Installation |  | 40.55%
|  |  | Line Cable Installation |  | 52.76%
|  |  | Express Cable Installation |  | 88.08%
|  |  | Pre-Operation Testing |  | 59.49%
76589 | B1 | HOYT-SCHERMERHORN | Axle Counter Installation |  | 30.36% | 41.48% |  | B1-766
|  |  | JB Installation |  | 74.67%
|  |  | Line Cable Installation |  | 56.66%
|  |  | Express Cable Installation |  | 44.48%
|  |  | Pre-Operation Testing |  | 1.229%
76901.5 | B1 | HOY-FUL | Axle Counter Installation |  | 76.12% | 67.26% |  | B1-770
|  |  | JB Installation |  | 45.26%
|  |  | Line Cable Installation |  | 43.19%
|  |  | Express Cable Installation |  | 84.46%
|  |  | Pre-Operation Testing |  | 87.29%
77088 | B1 | FUL-CLI | Axle Counter Installation |  | 75.64% | 44.27% |  | B1-771
|  |  | JB Installation |  | 49.73%
|  |  | Line Cable Installation |  | 46.23%
|  |  | Express Cable Installation |  | 10.74%
|  |  | Pre-Operation Testing |  | 39.02%
54737 | B2 | DIT-CHU | Axle Counter Installation |  | 17.04% | 27.48% |  | B2-546
|  |  | JB Installation |  | 51.5%
|  |  | Line Cable Installation |  | 9.618%
|  |  | Express Cable Installation |  | 30.23%
|  |  | Pre-Operation Testing |  | 29.02%
54731 | B2 |  | Axle Counter Installation |  | 63.54% | 58.06% |  | B2-547
|  |  | JB Installation |  | 93.25%
|  |  | Line Cable Installation |  | 49.46%
|  |  | Express Cable Installation |  | 3.755%
|  |  | Pre-Operation Testing |  | 80.29%
55000 | B2 | DIT-CHU | Axle Counter Installation |  | 48.39% | 39.61% |  | B2-549
|  |  | JB Installation |  | 47.62%
|  |  | Line Cable Installation |  | 49.81%
|  |  | Express Cable Installation |  | 20.8%
|  |  | Pre-Operation Testing |  | 31.45%
55498 | B2 | DIT-CHU | Axle Counter Installation |  | 45.32% | 70.1% |  | B2-554
|  |  | JB Installation |  | 74.28%
|  |  | Line Cable Installation |  | 76.45%
|  |  | Express Cable Installation |  | 65.85%
|  |  | Pre-Operation Testing |  | 88.61%
| B2 |  | Axle Counter Installation |  | 57.03% | 35.94% | NO REF DWG EXISTS | B2-555
|  |  | JB Installation |  | 94.44%
|  |  | Line Cable Installation |  | 5.837%
|  |  | Express Cable Installation |  | 16.23%
|  |  | Pre-Operation Testing |  | 6.18%
| B2 |  | Axle Counter Installation |  | 26.15% | 51.51% | NO REF DWG EXISTS | B2-556
|  |  | JB Installation |  | 88.39%
|  |  | Line Cable Installation |  | 44.14%
|  |  | Express Cable Installation |  | 69.76%
|  |  | Pre-Operation Testing |  | 29.13%
55857 | B2 | CHURCH AVE | Axle Counter Installation |  | 90.63% | 61.31% |  | B2-558
|  |  | JB Installation |  | 56.7%
|  |  | Line Cable Installation |  | 75.98%
|  |  | Express Cable Installation |  | 21.85%
|  |  | Pre-Operation Testing |  | 61.38%
58500 | B2 | FORT HAMILTON PARKWAY | Axle Counter Installation |  | 43.35% | 47.22% |  | B2-585
|  |  | JB Installation |  | 53.27%
|  |  | Line Cable Installation |  | 42.94%
|  |  | Express Cable Installation |  | 82.5%
|  |  | Pre-Operation Testing |  | 14.04%
59203.8 | B2 | FOR-15S | Axle Counter Installation |  | 85.46% | 60.17% |  | B2-592
|  |  | JB Installation |  | 61.82%
|  |  | Line Cable Installation |  | 80.83%
|  |  | Express Cable Installation |  | 46.15%
|  |  | Pre-Operation Testing |  | 26.58%
62550.6 | B2 |  | Axle Counter Installation |  | 69.49% | 42.52% |  | B2-625
|  |  | JB Installation |  | 55.67%
|  |  | Line Cable Installation |  | 5.688%
|  |  | Express Cable Installation |  | 68.25%
|  |  | Pre-Operation Testing |  | 13.48%
65375.3 | B2 | 15S-7AV | Axle Counter Installation |  | 58.09% | 49.27% |  | B2-654
|  |  | JB Installation |  | 72.89%
|  |  | Line Cable Installation |  | 29.05%
|  |  | Express Cable Installation |  | 10.27%
|  |  | Pre-Operation Testing |  | 76.06%
66062.3 | B2 | 7AV-4TH | Axle Counter Installation |  | 64.14% | 65.93% |  | B2-661
|  |  | JB Installation |  | 63.04%
|  |  | Line Cable Installation |  | 71.23%
|  |  | Express Cable Installation |  | 78.78%
|  |  | Pre-Operation Testing |  | 52.44%
| B2 |  | Axle Counter Installation |  | 47.1% | 42.05% | NO REF DWG EXISTS | B2-665
|  |  | JB Installation |  | 26.84%
|  |  | Line Cable Installation |  | 5.558%
|  |  | Express Cable Installation |  | 78.87%
|  |  | Pre-Operation Testing |  | 51.87%
| B2 |  | Axle Counter Installation |  | 47.45% | 51.95% | NO REF DWG EXISTS | B2-684
|  |  | JB Installation |  | 88.07%
|  |  | Line Cable Installation |  | 39.43%
|  |  | Express Cable Installation |  | 79.63%
|  |  | Pre-Operation Testing |  | 5.144%
| B2 |  | Axle Counter Installation |  | 55.03% | 55.71% | NO REF DWG EXISTS | B2-691
|  |  | JB Installation |  | 50.43%
|  |  | Line Cable Installation |  | 58.78%
|  |  | Express Cable Installation |  | 93.78%
|  |  | Pre-Operation Testing |  | 20.54%
| B2 |  | Axle Counter Installation |  | 63.88% | 32.19% | NO REF DWG EXISTS | B2-692
|  |  | JB Installation |  | 49.78%
|  |  | Line Cable Installation |  | 36.09%
|  |  | Express Cable Installation |  | 6.24%
|  |  | Pre-Operation Testing |  | 4.975%
| B2 |  | Axle Counter Installation |  | 21.79% | 48.48% | NO REF DWG EXISTS | B2-692A
|  |  | JB Installation |  | 3.217%
|  |  | Line Cable Installation |  | 72.31%
|  |  | Express Cable Installation |  | 77.49%
|  |  | Pre-Operation Testing |  | 67.57%
| B2 |  | Axle Counter Installation |  | 86.14% | 68.44% | NO REF DWG EXISTS | B2-693
|  |  | JB Installation |  | 61.11%
|  |  | Line Cable Installation |  | 77.73%
|  |  | Express Cable Installation |  | 24%
|  |  | Pre-Operation Testing |  | 93.21%
| B2 |  | Axle Counter Installation |  | 0.1284% | 63.65% | NO REF DWG EXISTS | B2-705
|  |  | JB Installation |  | 68.74%
|  |  | Line Cable Installation |  | 81.66%
|  |  | Express Cable Installation |  | 99.11%
|  |  | Pre-Operation Testing |  | 68.61%
| B2 |  | Axle Counter Installation |  | 60.69% | 56.86% | NO REF DWG EXISTS | B2-712
|  |  | JB Installation |  | 0.1255%
|  |  | Line Cable Installation |  | 63.81%
|  |  | Express Cable Installation |  | 63.35%
|  |  | Pre-Operation Testing |  | 96.33%
| B2 |  | Axle Counter Installation |  | 12.63% | 22.32% | DWG EXISTS, BUT EMPTY | B2-732
|  |  | JB Installation |  | 19.12%
|  |  | Line Cable Installation |  | 8.537%
|  |  | Express Cable Installation |  | 5.433%
|  |  | Pre-Operation Testing |  | 65.89%
73926.3 | B2 | CARROLL STREET | Axle Counter Installation |  | 70.97% | 58% |  | B2-739
|  |  | JB Installation |  | 63.64%
|  |  | Line Cable Installation |  | 73.02%
|  |  | Express Cable Installation |  | 11.99%
|  |  | Pre-Operation Testing |  | 70.4%
75267 | B2 | CAR-BER | Axle Counter Installation |  | 70.17% | 62.04% |  | B2-753
|  |  | JB Installation |  | 38.22%
|  |  | Line Cable Installation |  | 62.96%
|  |  | Express Cable Installation |  | 84.51%
|  |  | Pre-Operation Testing |  | 54.32%
| B2 |  | Axle Counter Installation |  | 74.54% | 67.36% | NO REF DWG EXISTS | B2-755
|  |  | JB Installation |  | 78.75%
|  |  | Line Cable Installation |  | 61.34%
|  |  | Express Cable Installation |  | 41.4%
|  |  | Pre-Operation Testing |  | 80.79%
75646 | B2 | CAR-BER | Axle Counter Installation |  | 35.66% | 54.46% |  | B2-756
|  |  | JB Installation |  | 29.97%
|  |  | Line Cable Installation |  | 61.16%
|  |  | Express Cable Installation |  | 46.76%
|  |  | Pre-Operation Testing |  | 98.74%
76352 | B2 |  | Axle Counter Installation |  | 9.826% | 45.2% |  | B2-763, B2-764
|  |  | JB Installation |  | 93.49%
|  |  | Line Cable Installation |  | 59.8%
|  |  | Express Cable Installation |  | 41.74%
|  |  | Pre-Operation Testing |  | 21.14%
76536 | B2 |  | Axle Counter Installation |  | 17.79% | 42.45% |  | B2-765
|  |  | JB Installation |  | 6.451%
|  |  | Line Cable Installation |  | 97.6%
|  |  | Express Cable Installation |  | 18.74%
|  |  | Pre-Operation Testing |  | 71.68%
76797 | B2 |  | Axle Counter Installation |  | 14.14% | 50.87% |  | B2-768
|  |  | JB Installation |  | 53.08%
|  |  | Line Cable Installation |  | 96.45%
|  |  | Express Cable Installation |  | 58.69%
|  |  | Pre-Operation Testing |  | 31.98%
77116 | B2 |  | Axle Counter Installation |  | 34.81% | 68.22% |  | B2-770
|  |  | JB Installation |  | 97.92%
|  |  | Line Cable Installation |  | 72.04%
|  |  | Express Cable Installation |  | 42.91%
|  |  | Pre-Operation Testing |  | 93.43%
| B3 |  | Axle Counter Installation |  | 94.53% | 45.66% | REF DWG EXISTS, NO STATIONINGS SHOWN | B3-546
|  |  | JB Installation |  | 80.87%
|  |  | Line Cable Installation |  | 20.27%
|  |  | Express Cable Installation |  | 8.441%
|  |  | Pre-Operation Testing |  | 24.19%
| B3 |  | Axle Counter Installation |  | 79.3% | 55.86% | REF DWG EXISTS, NO STATIONINGS SHOWN | B3-548
|  |  | JB Installation |  | 10.29%
|  |  | Line Cable Installation |  | 86.44%
|  |  | Express Cable Installation |  | 72.52%
|  |  | Pre-Operation Testing |  | 30.77%
53361 | B3 |  | Axle Counter Installation |  | 80.52% | 49% |  | B3-554
|  |  | JB Installation |  | 92.02%
|  |  | Line Cable Installation |  | 16.65%
|  |  | Express Cable Installation |  | 6.364%
|  |  | Pre-Operation Testing |  | 49.44%
55626 | B3 |  | Axle Counter Installation |  | 10.52% | 43.86% |  | B3-555
|  |  | JB Installation |  | 17.07%
|  |  | Line Cable Installation |  | 72%
|  |  | Express Cable Installation |  | 53.01%
|  |  | Pre-Operation Testing |  | 66.72%
| B3 |  | Axle Counter Installation |  | 51.61% | 59.73% | REF DWG EXISTS, NO STATIONINGS SHOWN | B3-556
|  |  | JB Installation |  | 75.75%
|  |  | Line Cable Installation |  | 58.48%
|  |  | Express Cable Installation |  | 55.36%
|  |  | Pre-Operation Testing |  | 57.45%
| B3 |  | Axle Counter Installation |  | 72.46% | 56.89% | REF DWG EXISTS, NO STATIONINGS SHOWN | B3-557
|  |  | JB Installation |  | 26.22%
|  |  | Line Cable Installation |  | 37.07%
|  |  | Express Cable Installation |  | 95.8%
|  |  | Pre-Operation Testing |  | 52.9%
| B3 |  | Axle Counter Installation |  | 28.73% | 31.89% | NO REF DWG EXISTS | B3-565
|  |  | JB Installation |  | 1.17%
|  |  | Line Cable Installation |  | 29.23%
|  |  | Express Cable Installation |  | 82.64%
|  |  | Pre-Operation Testing |  | 17.68%
65384.6 | B3 |  | Axle Counter Installation |  | 67.36% | 28.83% |  | B3-654
|  |  | JB Installation |  | 4.719%
|  |  | Line Cable Installation |  | 3.503%
|  |  | Express Cable Installation |  | 12.39%
|  |  | Pre-Operation Testing |  | 56.18%
66073.4 | B3 |  | Axle Counter Installation |  | 3.085% | 51.74% |  | B3-661
|  |  | JB Installation |  | 8.488%
|  |  | Line Cable Installation |  | 92.29%
|  |  | Express Cable Installation |  | 82.3%
|  |  | Pre-Operation Testing |  | 72.52%
| B3 |  | Axle Counter Installation |  | 4.233% | 12.09% | NO REF DWG EXISTS | B3-689
|  |  | JB Installation |  | 24.82%
|  |  | Line Cable Installation |  | 3.781%
|  |  | Express Cable Installation |  | 0.3888%
|  |  | Pre-Operation Testing |  | 27.22%
| B3 |  | Axle Counter Installation |  | 3.38% | 60.76% | NO REF DWG EXISTS | B3-690
|  |  | JB Installation |  | 79.14%
|  |  | Line Cable Installation |  | 87.03%
|  |  | Express Cable Installation |  | 77.73%
|  |  | Pre-Operation Testing |  | 56.52%
| B3 |  | Axle Counter Installation |  | 11.46% | 46.88% | NO REF DWG EXISTS | B3-691
|  |  | JB Installation |  | 42.81%
|  |  | Line Cable Installation |  | 74.05%
|  |  | Express Cable Installation |  | 45.77%
|  |  | Pre-Operation Testing |  | 60.33%
| B3 |  | Axle Counter Installation |  | 75.8% | 49.55% | NO REF DWG EXISTS | B3-692
|  |  | JB Installation |  | 58.71%
|  |  | Line Cable Installation |  | 26.56%
|  |  | Express Cable Installation |  | 49.76%
|  |  | Pre-Operation Testing |  | 36.89%
| B3 |  | Axle Counter Installation |  | 9.722% | 55.36% | NO REF DWG EXISTS | B3-693
|  |  | JB Installation |  | 53.22%
|  |  | Line Cable Installation |  | 70.44%
|  |  | Express Cable Installation |  | 89.18%
|  |  | Pre-Operation Testing |  | 54.23%
| B3 |  | Axle Counter Installation |  | 29.43% | 67.43% | NO REF DWG EXISTS | B3-694
|  |  | JB Installation |  | 60.04%
|  |  | Line Cable Installation |  | 99.13%
|  |  | Express Cable Installation |  | 54.13%
|  |  | Pre-Operation Testing |  | 94.44%
| B3 |  | Axle Counter Installation |  | 73.13% | 52.2% | NO REF DWG EXISTS | B3-695
|  |  | JB Installation |  | 55.47%
|  |  | Line Cable Installation |  | 2.595%
|  |  | Express Cable Installation |  | 98.15%
|  |  | Pre-Operation Testing |  | 31.66%
| B3 |  | Axle Counter Installation |  | 93.7% | 63.44% | NO REF DWG EXISTS | B3-696
|  |  | JB Installation |  | 64.08%
|  |  | Line Cable Installation |  | 74.48%
|  |  | Express Cable Installation |  | 1.171%
|  |  | Pre-Operation Testing |  | 83.8%
75405 | B3 |  | Axle Counter Installation |  | 93.72% | 82.91% |  | B3-754
|  |  | JB Installation |  | 76.14%
|  |  | Line Cable Installation |  | 91.38%
|  |  | Express Cable Installation |  | 61.24%
|  |  | Pre-Operation Testing |  | 92.06%
| B3 |  | Axle Counter Installation |  | 43.04% | 72.03% | NO REF DWG EXISTS | B3-755
|  |  | JB Installation |  | 83.82%
|  |  | Line Cable Installation |  | 36.17%
|  |  | Express Cable Installation |  | 98.84%
|  |  | Pre-Operation Testing |  | 98.29%
75405 | B3 |  | Axle Counter Installation |  | 26.51% | 49.34% |  | B3-756
|  |  | JB Installation |  | 79.23%
|  |  | Line Cable Installation |  | 42.42%
|  |  | Express Cable Installation |  | 88.16%
|  |  | Pre-Operation Testing |  | 10.36%
76383 | B3 |  | Axle Counter Installation |  | 71.99% | 58.17% |  | B3-764
|  |  | JB Installation |  | 57.87%
|  |  | Line Cable Installation |  | 79.27%
|  |  | Express Cable Installation |  | 75.32%
|  |  | Pre-Operation Testing |  | 6.414%
76920 | B3 |  | Axle Counter Installation |  | 15.04% | 44.83% |  | B3-769
|  |  | JB Installation |  | 12.64%
|  |  | Line Cable Installation |  | 71.48%
|  |  | Express Cable Installation |  | 95.4%
|  |  | Pre-Operation Testing |  | 29.57%
| B4 |  | Axle Counter Installation |  | 16.4% | 47.44% | REF DWG EXISTS, NO STATIONINGS SHOWN | B4-547
|  |  | JB Installation |  | 86.32%
|  |  | Line Cable Installation |  | 4.371%
|  |  | Express Cable Installation |  | 80.24%
|  |  | Pre-Operation Testing |  | 49.88%
| B4 |  | Axle Counter Installation |  | 82.62% | 52.07% | REF DWG EXISTS, NO STATIONINGS SHOWN | B4-551
|  |  | JB Installation |  | 29.77%
|  |  | Line Cable Installation |  | 55.29%
|  |  | Express Cable Installation |  | 82.52%
|  |  | Pre-Operation Testing |  | 10.17%
| B4 |  | Axle Counter Installation |  | 84.36% | 63.63% | NO REF DWG EXISTS, AWAITING RESPONSE FROM THALES ON WHETHER THIS AXC WILL BE INSTALLED | B4-554A, B4-554B
|  |  | JB Installation |  | 67.83%
|  |  | Line Cable Installation |  | 7.461%
|  |  | Express Cable Installation |  | 95.13%
|  |  | Pre-Operation Testing |  | 63.36%
55533 | B4 |  | Axle Counter Installation |  | 23.2% | 63.54% |  | B4-555
|  |  | JB Installation |  | 90.9%
|  |  | Line Cable Installation |  | 63.75%
|  |  | Express Cable Installation |  | 93.63%
|  |  | Pre-Operation Testing |  | 46.23%
55685 | B4 |  | Axle Counter Installation |  | 7.667% | 52.9% |  | B4-556
|  |  | JB Installation |  | 14.27%
|  |  | Line Cable Installation |  | 96.88%
|  |  | Express Cable Installation |  | 49.55%
|  |  | Pre-Operation Testing |  | 96.13%
56396.5 | B4 |  | Axle Counter Installation |  | 16.33% | 41.57% |  | B4-564
|  |  | JB Installation |  | 5.142%
|  |  | Line Cable Installation |  | 62.27%
|  |  | Express Cable Installation |  | 81.61%
|  |  | Pre-Operation Testing |  | 42.49%

## SIGNALS
Stationing | Track No | Signal Type | Location | Activity | Date | Progress | General Progress | Notes
74076 | E1 | APPROACH |  | Signal Installation |  | 89.89% | 80.86% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 70.23%
|  |  |  | Stop Machine Installation |  | 49.97%
|  |  |  | Line Cable Installation |  | 99.44%
|  |  |  | Breakdown Testing |  | 67.92%
|  |  |  | Pre-Operation Testing |  | 97.1%
98643 | E1 | HOME |  | Signal Installation |  | 25.64% | 40.22% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 19.47%
|  |  |  | Stop Machine Installation |  | 68.52%
|  |  |  | Line Cable Installation |  | 15.68%
|  |  |  | Breakdown Testing |  | 25.85%
|  |  |  | Pre-Operation Testing |  | 65.41%
98903 | E1 | HOME |  | Signal Installation |  | 84.01% | 52.95% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 87.08%
|  |  |  | Stop Machine Installation |  | 36.45%
|  |  |  | Line Cable Installation |  | 78.98%
|  |  |  | Breakdown Testing |  | 26.96%
|  |  |  | Pre-Operation Testing |  | 38.37%
100068 | E1 | HOME |  | Signal Installation |  | 86.22% | 59.9% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 54.35%
|  |  |  | Stop Machine Installation |  | 46.18%
|  |  |  | Line Cable Installation |  | 65.47%
|  |  |  | Breakdown Testing |  | 7.59%
|  |  |  | Pre-Operation Testing |  | 94.05%
106031 | E1 | APPROACH |  | Signal Installation |  | 85.42% | 56.66% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 63.41%
|  |  |  | Stop Machine Installation |  | 27.3%
|  |  |  | Line Cable Installation |  | 33.75%
|  |  |  | Breakdown Testing |  | 36.99%
|  |  |  | Pre-Operation Testing |  | 99.82%
113852 | E1 | HOME |  | Signal Installation |  | 12.09% | 49.37% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 99.12%
|  |  |  | Stop Machine Installation |  | 47.2%
|  |  |  | Line Cable Installation |  | 77.64%
|  |  |  | Breakdown Testing |  | 14.3%
|  |  |  | Pre-Operation Testing |  | 95.62%
114110 | E1 | HOME |  | Signal Installation |  | 84.62% | 68.42% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 17.55%
|  |  |  | Stop Machine Installation |  | 82.14%
|  |  |  | Line Cable Installation |  | 45.48%
|  |  |  | Breakdown Testing |  | 33.79%
|  |  |  | Pre-Operation Testing |  | 96.08%
114869 | E1 | HOME |  | Signal Installation |  | 48.93% | 38.41% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 72.8%
|  |  |  | Stop Machine Installation |  | 10.09%
|  |  |  | Line Cable Installation |  | 27.22%
|  |  |  | Breakdown Testing |  | 17.22%
|  |  |  | Pre-Operation Testing |  | 88.61%
119024 | E1 | APPROACH |  | Signal Installation |  | 13.88% | 32.03% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 91%
|  |  |  | Stop Machine Installation |  | 62.39%
|  |  |  | Line Cable Installation |  | 74.17%
|  |  |  | Breakdown Testing |  | 3.924%
|  |  |  | Pre-Operation Testing |  | 5.803%
119485 | E1 | APPROACH |  | Signal Installation |  | 48.95% | 69.26% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 40.24%
|  |  |  | Stop Machine Installation |  | 81.03%
|  |  |  | Line Cable Installation |  | 93.26%
|  |  |  | Breakdown Testing |  | 26.28%
|  |  |  | Pre-Operation Testing |  | 96.76%
| E1 | APPROACH |  | Signal Installation |  | 39.97% | 39.3% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 6.968%
|  |  |  | Stop Machine Installation |  | 23.58%
|  |  |  | Line Cable Installation |  | 86.08%
|  |  |  | Breakdown Testing |  | 2.891%
|  |  |  | Pre-Operation Testing |  | 43.99%
121810 | E1 | HOME |  | Signal Installation |  | 45.48% | 66.53% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 62.2%
|  |  |  | Stop Machine Installation |  | 91.74%
|  |  |  | Line Cable Installation |  | 74.37%
|  |  |  | Breakdown Testing |  | 22.13%
|  |  |  | Pre-Operation Testing |  | 98.92%
122198 | E1 | HOME |  | Signal Installation |  | 32.43% | 43.38% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 17.54%
|  |  |  | Stop Machine Installation |  | 56.76%
|  |  |  | Line Cable Installation |  | 14.01%
|  |  |  | Breakdown Testing |  | 94.68%
|  |  |  | Pre-Operation Testing |  | 19%
122570 | E1 | HOME |  | Signal Installation |  | 22.37% | 46.28% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 6.913%
|  |  |  | Stop Machine Installation |  | 43.57%
|  |  |  | Line Cable Installation |  | 92.25%
|  |  |  | Breakdown Testing |  | 10.77%
|  |  |  | Pre-Operation Testing |  | 62.47%
122987 | E1 | HOME |  | Signal Installation |  | 84.85% | 54.54% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 76.15%
|  |  |  | Stop Machine Installation |  | 33.35%
|  |  |  | Line Cable Installation |  | 60.09%
|  |  |  | Breakdown Testing |  | 53.74%
|  |  |  | Pre-Operation Testing |  | 40.68%
123669 | D1 | HOME |  | Signal Installation |  | 60.55% | 37.84% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 75.88%
|  |  |  | Stop Machine Installation |  | 2.799%
|  |  |  | Line Cable Installation |  | 5.298%
|  |  |  | Breakdown Testing |  | 30.97%
|  |  |  | Pre-Operation Testing |  | 89.61%
73318 | E2 | APPROACH |  | Signal Installation |  | 82.89% | 43.01% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0.7974%
|  |  |  | Stop Machine Installation |  | 33.28%
|  |  |  | Line Cable Installation |  | 83.23%
|  |  |  | Breakdown Testing |  | 8.967%
|  |  |  | Pre-Operation Testing |  | 6.688%
98565 | E2 | HOME |  | Signal Installation |  | 26.93% | 47.11% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 45.99%
|  |  |  | Stop Machine Installation |  | 33.2%
|  |  |  | Line Cable Installation |  | 68.43%
|  |  |  | Breakdown Testing |  | 89.51%
|  |  |  | Pre-Operation Testing |  | 17.47%
99593 | E2 | HOME |  | Signal Installation |  | 31.34% | 55.2% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 63.75%
|  |  |  | Stop Machine Installation |  | 2.484%
|  |  |  | Line Cable Installation |  | 83.22%
|  |  |  | Breakdown Testing |  | 79.39%
|  |  |  | Pre-Operation Testing |  | 79.55%
99970 | E2 | HOME |  | Signal Installation |  | 51.35% | 45.63% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 81.76%
|  |  |  | Stop Machine Installation |  | 64.82%
|  |  |  | Line Cable Installation |  | 3.98%
|  |  |  | Breakdown Testing |  | 15.9%
|  |  |  | Pre-Operation Testing |  | 92.11%
106749 | E2 | APPROACH |  | Signal Installation |  | 41.19% | 46.38% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 2.472%
|  |  |  | Stop Machine Installation |  | 85.36%
|  |  |  | Line Cable Installation |  | 70.83%
|  |  |  | Breakdown Testing |  | 10.64%
|  |  |  | Pre-Operation Testing |  | 23.85%
112529 | E2 | HOME |  | Signal Installation |  | 88.42% | 42.29% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 39.48%
|  |  |  | Stop Machine Installation |  | 49.23%
|  |  |  | Line Cable Installation |  | 7.442%
|  |  |  | Breakdown Testing |  | 46.84%
|  |  |  | Pre-Operation Testing |  | 19.49%
113850 | E2 | HOME |  | Signal Installation |  | 36.15% | 39.16% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 49.63%
|  |  |  | Stop Machine Installation |  | 46.19%
|  |  |  | Line Cable Installation |  | 86.43%
|  |  |  | Breakdown Testing |  | 17.13%
|  |  |  | Pre-Operation Testing |  | 9.892%
118065 | E2 | APPROACH |  | Signal Installation |  | 31.75% | 41.95% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 72.83%
|  |  |  | Stop Machine Installation |  | 15.88%
|  |  |  | Line Cable Installation |  | 13.95%
|  |  |  | Breakdown Testing |  | 50.27%
|  |  |  | Pre-Operation Testing |  | 97.92%
119215 | E2 | APPROACH |  | Signal Installation |  | 72.24% | 59.79% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 33.76%
|  |  |  | Stop Machine Installation |  | 30.97%
|  |  |  | Line Cable Installation |  | 85.41%
|  |  |  | Breakdown Testing |  | 77.17%
|  |  |  | Pre-Operation Testing |  | 33.18%
123687 | D2 | HOME |  | Signal Installation |  | 78.53% | 65.51% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 58.4%
|  |  |  | Stop Machine Installation |  | 74.06%
|  |  |  | Line Cable Installation |  | 55.74%
|  |  |  | Breakdown Testing |  | 72.92%
|  |  |  | Pre-Operation Testing |  | 46.31%
124043 | D2 | HOME |  | Signal Installation |  | 59.01% | 35.88% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 59.07%
|  |  |  | Stop Machine Installation |  | 40.68%
|  |  |  | Line Cable Installation |  | 23.67%
|  |  |  | Breakdown Testing |  | 17.65%
|  |  |  | Pre-Operation Testing |  | 38.36%
99806 | E3 | HOME |  | Signal Installation |  | 40.85% | 32.34% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 68.58%
|  |  |  | Stop Machine Installation |  | 2.365%
|  |  |  | Line Cable Installation |  | 47.99%
|  |  |  | Breakdown Testing |  | 4.527%
|  |  |  | Pre-Operation Testing |  | 65.97%
100019 | E3 | HOME |  | Signal Installation |  | 43.63% | 65.66% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 57.55%
|  |  |  | Stop Machine Installation |  | 97.57%
|  |  |  | Line Cable Installation |  | 75.06%
|  |  |  | Breakdown Testing |  | 49.25%
|  |  |  | Pre-Operation Testing |  | 62.78%
99592 | E4 | HOME |  | Signal Installation |  | 71.22% | 53.55% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 41.64%
|  |  |  | Stop Machine Installation |  | 69.77%
|  |  |  | Line Cable Installation |  | 68.73%
|  |  |  | Breakdown Testing |  | 3.229%
|  |  |  | Pre-Operation Testing |  | 54.82%
122071 | E5 | HOME |  | Signal Installation |  | 48.32% | 32.22% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 67.01%
|  |  |  | Stop Machine Installation |  | 18.34%
|  |  |  | Line Cable Installation |  | 57.53%
|  |  |  | Breakdown Testing |  | 12.51%
|  |  |  | Pre-Operation Testing |  | 24.41%
122687 | E5 | HOME |  | Signal Installation |  | 66.37% | 71.43% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 8.83%
|  |  |  | Stop Machine Installation |  | 85.63%
|  |  |  | Line Cable Installation |  | 51.58%
|  |  |  | Breakdown Testing |  | 76.26%
|  |  |  | Pre-Operation Testing |  | 77.32%

## SWITCH
Name | Stationing | Track No | Location | Activity | Date | Progress | General Progress | Notes
B331 | 76395 | B1 |  | Switch Machine Installation |  | 74.84% | 32.05%
|  |  |  | Switch JB Installation |  | 25.3%
|  |  |  | Switch Cable Installation |  | 32.37%
|  |  |  | Line Cable Installation |  | 37.47%
|  |  |  | Breakdown Testing |  | 5.743%
|  |  |  | Pre-Operation Testing |  | 9.818%
B325 | 76395 | E2 |  | Switch Machine Installation |  | 87.2% | 37.58%
|  |  |  | Switch JB Installation |  | 13.59%
|  |  |  | Switch Cable Installation |  | 21.6%
|  |  |  | Line Cable Installation |  | 14.42%
|  |  |  | Breakdown Testing |  | 49.47%
|  |  |  | Pre-Operation Testing |  | 15.21%
633A | 99999 | E1 |  | Switch Machine Installation |  | 64.09% | 40.31%
|  |  |  | Switch JB Installation |  | 84.89%
|  |  |  | Switch Cable Installation |  | 66.54%
|  |  |  | Line Cable Installation |  | 28.77%
|  |  |  | Breakdown Testing |  | 29.74%
|  |  |  | Pre-Operation Testing |  | 12.43%
633B | 98900 | E3-4 |  | Switch Machine Installation |  | 59.88% | 51.05%
|  |  |  | Switch JB Installation |  | 50.26%
|  |  |  | Switch Cable Installation |  | 52.59%
|  |  |  | Line Cable Installation |  | 8.673%
|  |  |  | Breakdown Testing |  | 79.37%
|  |  |  | Pre-Operation Testing |  | 54.74%
625A | 98808 | E3-4 |  | Switch Machine Installation |  | 87.31% | 44.6%
|  |  |  | Switch JB Installation |  | 84.93%
|  |  |  | Switch Cable Installation |  | 6.479%
|  |  |  | Line Cable Installation |  | 1.785%
|  |  |  | Breakdown Testing |  | 60.85%
|  |  |  | Pre-Operation Testing |  | 66.6%
625B | 99949 | E2 |  | Switch Machine Installation |  | 53.99% | 65.21%
|  |  |  | Switch JB Installation |  | 44.41%
|  |  |  | Switch Cable Installation |  | 88.15%
|  |  |  | Line Cable Installation |  | 36.23%
|  |  |  | Breakdown Testing |  | 75.24%
|  |  |  | Pre-Operation Testing |  | 72.45%
663 | 99628 | E3-4 |  | Switch Machine Installation |  | 39.17% | 57.25%
|  |  |  | Switch JB Installation |  | 37.27%
|  |  |  | Switch Cable Installation |  | 33.3%
|  |  |  | Line Cable Installation |  | 55.19%
|  |  |  | Breakdown Testing |  | 77.94%
|  |  |  | Pre-Operation Testing |  | 80.67%
673A | 99999 | E1 |  | Switch Machine Installation |  | 13.96% | 39.25%
|  |  |  | Switch JB Installation |  | 8.034%
|  |  |  | Switch Cable Installation |  | 15.54%
|  |  |  | Line Cable Installation |  | 76.64%
|  |  |  | Breakdown Testing |  | 15.65%
|  |  |  | Pre-Operation Testing |  | 74.47%
673B | 99826 | E3 |  | Switch Machine Installation |  | 47.63% | 46.39%
|  |  |  | Switch JB Installation |  | 12.33%
|  |  |  | Switch Cable Installation |  | 50.61%
|  |  |  | Line Cable Installation |  | 15.94%
|  |  |  | Breakdown Testing |  | 75.9%
|  |  |  | Pre-Operation Testing |  | 41.88%
651A | 99761 | E4 |  | Switch Machine Installation |  | 63.65% | 30.11%
|  |  |  | Switch JB Installation |  | 91.21%
|  |  |  | Switch Cable Installation |  | 26.27%
|  |  |  | Line Cable Installation |  | 2.418%
|  |  |  | Breakdown Testing |  | 41.58%
|  |  |  | Pre-Operation Testing |  | 16.61%
651B | 99949 | E2 |  | Switch Machine Installation |  | 9.209% | 53.86%
|  |  |  | Switch JB Installation |  | 54.17%
|  |  |  | Switch Cable Installation |  | 65.93%
|  |  |  | Line Cable Installation |  | 73.51%
|  |  |  | Breakdown Testing |  | 95.58%
|  |  |  | Pre-Operation Testing |  | 25.05%
757A | 113880 | E1 |  | Switch Machine Installation |  | 89.31% | 73.9%
|  |  |  | Switch JB Installation |  | 47.91%
|  |  |  | Switch Cable Installation |  | 73.54%
|  |  |  | Line Cable Installation |  | 71.01%
|  |  |  | Breakdown Testing |  | 48.36%
|  |  |  | Pre-Operation Testing |  | 87.27%
757B | 114010 | E2 |  | Switch Machine Installation |  | 43.61% | 63.25%
|  |  |  | Switch JB Installation |  | 54.97%
|  |  |  | Switch Cable Installation |  | 75.12%
|  |  |  | Line Cable Installation |  | 82.84%
|  |  |  | Breakdown Testing |  | 81.23%
|  |  |  | Pre-Operation Testing |  | 33.45%
753A | 114010 | E1 |  | Switch Machine Installation |  | 30.12% | 26.27%
|  |  |  | Switch JB Installation |  | 82.64%
|  |  |  | Switch Cable Installation |  | 29.65%
|  |  |  | Line Cable Installation |  | 0.271%
|  |  |  | Breakdown Testing |  | 27.08%
|  |  |  | Pre-Operation Testing |  | 44.26%
753B | 113880 | E2 |  | Switch Machine Installation |  | 60.75% | 47.03%
|  |  |  | Switch JB Installation |  | 63.8%
|  |  |  | Switch Cable Installation |  | 7.424%
|  |  |  | Line Cable Installation |  | 20.16%
|  |  |  | Breakdown Testing |  | 56.64%
|  |  |  | Pre-Operation Testing |  | 90.18%
825 |  | E1 |  | Switch Machine Installation |  | 44.84% | 54.95% | Stationing missing
|  |  |  | Switch JB Installation |  | 97.56%
|  |  |  | Switch Cable Installation |  | 49.13%
|  |  |  | Line Cable Installation |  | 26.46%
|  |  |  | Breakdown Testing |  | 99.5%
|  |  |  | Pre-Operation Testing |  | 54.82%
815A | 121995 | E5 |  | Switch Machine Installation |  | 4.879% | 55.15%
|  |  |  | Switch JB Installation |  | 38.45%
|  |  |  | Switch Cable Installation |  | 74.07%
|  |  |  | Line Cable Installation |  | 78.74%
|  |  |  | Breakdown Testing |  | 52.2%
|  |  |  | Pre-Operation Testing |  | 65.83%
815B | 121831 | E2 |  | Switch Machine Installation |  | 36.42% | 36.68%
|  |  |  | Switch JB Installation |  | 96.28%
|  |  |  | Switch Cable Installation |  | 67.41%
|  |  |  | Line Cable Installation |  | 31.38%
|  |  |  | Breakdown Testing |  | 2.974%
|  |  |  | Pre-Operation Testing |  | 45.23%
851B | 122757 | E5 |  | Switch Machine Installation |  | 0.3887% | 40.89%
|  |  |  | Switch JB Installation |  | 22.29%
|  |  |  | Switch Cable Installation |  | 58.26%
|  |  |  | Line Cable Installation |  | 24.11%
|  |  |  | Breakdown Testing |  | 71.77%
|  |  |  | Pre-Operation Testing |  | 49.93%
851A | 122923 | E1 |  | Switch Machine Installation |  | 32.38% | 54.95%
|  |  |  | Switch JB Installation |  | 94.3%
|  |  |  | Switch Cable Installation |  | 69.33%
|  |  |  | Line Cable Installation |  | 31.12%
|  |  |  | Breakdown Testing |  | 79.15%
|  |  |  | Pre-Operation Testing |  | 62.78%
841 | 122923 | E2 |  | Switch Machine Installation |  | 2.253% | 41.78%
|  |  |  | Switch JB Installation |  | 95.98%
|  |  |  | Switch Cable Installation |  | 18.66%
|  |  |  | Line Cable Installation |  | 94.31%
|  |  |  | Breakdown Testing |  | 17.61%
|  |  |  | Pre-Operation Testing |  | 76.05%
753B | 113880 | E2 |  | Switch Machine Installation |  | 66.14% | 43.11%
|  |  |  | Switch JB Installation |  | 25.07%
|  |  |  | Switch Cable Installation |  | 25.43%
|  |  |  | Line Cable Installation |  | 12.18%
|  |  |  | Breakdown Testing |  | 43.24%
|  |  |  | Pre-Operation Testing |  | 68.55%

## WRU
Stationing | Track No | Location | Activity | Date | Progress | General Progress | Notes
54000 | B1 |  | Radio Unit Installation |  | 44.68% | 50.96% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 67.91%
|  |  | Fiber Box Installation |  | 87.91%
|  |  | Antenna Installation |  | 17.78%
|  |  | Antenna Cable Installation |  | 1.517%
|  |  | Splitter Installation |  | 86.34%
|  |  | Fiber Cable Splicing |  | 14.01%
|  |  | Fiber Testing |  | 48.31%
|  |  | Power Testing |  | 90.14%
54000 | B3 |  | Radio Unit Installation |  | 17.21% | 31.83% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 64.03%
|  |  | Fiber Box Installation |  | 18.42%
|  |  | Antenna Installation |  | 30.81%
|  |  | Antenna Cable Installation |  | 95.76%
|  |  | Splitter Installation |  | 13.77%
|  |  | Fiber Cable Splicing |  | 4.226%
|  |  | Fiber Testing |  | 24.69%
|  |  | Power Testing |  | 17.51%
54000 | B4 |  | Radio Unit Installation |  | 28.14% | 51.2% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 9.105%
|  |  | Fiber Box Installation |  | 21.27%
|  |  | Antenna Installation |  | 26.97%
|  |  | Antenna Cable Installation |  | 94.39%
|  |  | Splitter Installation |  | 92.71%
|  |  | Fiber Cable Splicing |  | 94.5%
|  |  | Fiber Testing |  | 16.75%
|  |  | Power Testing |  | 76.99%
54000 | B2 |  | Radio Unit Installation |  | 11.67% | 49.57% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 80.1%
|  |  | Fiber Box Installation |  | 38.18%
|  |  | Antenna Installation |  | 66.75%
|  |  | Antenna Cable Installation |  | 22.4%
|  |  | Splitter Installation |  | 97.05%
|  |  | Fiber Cable Splicing |  | 6.671%
|  |  | Fiber Testing |  | 70.49%
|  |  | Power Testing |  | 52.82%
54000 | B5 |  | Radio Unit Installation |  | 45.19% | 65.02% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 58.75%
|  |  | Fiber Box Installation |  | 52.72%
|  |  | Antenna Installation |  | 76.98%
|  |  | Antenna Cable Installation |  | 97.09%
|  |  | Splitter Installation |  | 62.5%
|  |  | Fiber Cable Splicing |  | 37.76%
|  |  | Fiber Testing |  | 84.79%
|  |  | Power Testing |  | 69.43%
55500 | B2 |  | Radio Unit Installation |  | 44.48% | 57.48% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 86.7%
|  |  | Fiber Box Installation |  | 61.15%
|  |  | Antenna Installation |  | 25.84%
|  |  | Antenna Cable Installation |  | 89.43%
|  |  | Splitter Installation |  | 61.83%
|  |  | Fiber Cable Splicing |  | 40.83%
|  |  | Fiber Testing |  | 94.56%
|  |  | Power Testing |  | 12.53%
55500 | B1 |  | Radio Unit Installation |  | 59.73% | 55.39% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 29.32%
|  |  | Fiber Box Installation |  | 61.72%
|  |  | Antenna Installation |  | 94.63%
|  |  | Antenna Cable Installation |  | 34.16%
|  |  | Splitter Installation |  | 38.8%
|  |  | Fiber Cable Splicing |  | 51.28%
|  |  | Fiber Testing |  | 51.81%
|  |  | Power Testing |  | 77.03%
56300 | B1 |  | Radio Unit Installation |  | 46.77% | 51.93% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 82.56%
|  |  | Fiber Box Installation |  | 31.52%
|  |  | Antenna Installation |  | 84.11%
|  |  | Antenna Cable Installation |  | 1.849%
|  |  | Splitter Installation |  | 43.14%
|  |  | Fiber Cable Splicing |  | 62.11%
|  |  | Fiber Testing |  | 84.08%
|  |  | Power Testing |  | 31.23%
56500 | B1 |  | Radio Unit Installation |  | 90.68% | 56% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 3.658%
|  |  | Fiber Box Installation |  | 11.64%
|  |  | Antenna Installation |  | 60.23%
|  |  | Antenna Cable Installation |  | 79.3%
|  |  | Splitter Installation |  | 90%
|  |  | Fiber Cable Splicing |  | 33.19%
|  |  | Fiber Testing |  | 78.22%
|  |  | Power Testing |  | 57.06%
57200 | B1 |  | Radio Unit Installation |  | 49.95% | 41.76% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 58.73%
|  |  | Fiber Box Installation |  | 44.17%
|  |  | Antenna Installation |  | 53.39%
|  |  | Antenna Cable Installation |  | 21.44%
|  |  | Splitter Installation |  | 42.26%
|  |  | Fiber Cable Splicing |  | 57.84%
|  |  | Fiber Testing |  | 27.9%
|  |  | Power Testing |  | 20.18%
57400 | B1 |  | Radio Unit Installation |  | 23.03% | 47.13% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 20.09%
|  |  | Fiber Box Installation |  | 68.55%
|  |  | Antenna Installation |  | 34.29%
|  |  | Antenna Cable Installation |  | 44.11%
|  |  | Splitter Installation |  | 44.86%
|  |  | Fiber Cable Splicing |  | 24.52%
|  |  | Fiber Testing |  | 98.87%
|  |  | Power Testing |  | 65.84%
58300 | B1 |  | Radio Unit Installation |  | 26.62% | 36.61% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 11.65%
|  |  | Fiber Box Installation |  | 6.276%
|  |  | Antenna Installation |  | 8.202%
|  |  | Antenna Cable Installation |  | 74.78%
|  |  | Splitter Installation |  | 41.69%
|  |  | Fiber Cable Splicing |  | 62.61%
|  |  | Fiber Testing |  | 1.808%
|  |  | Power Testing |  | 95.89%
58400 | B1 |  | Radio Unit Installation |  | 98.17% | 56.83% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 35.95%
|  |  | Fiber Box Installation |  | 3.595%
|  |  | Antenna Installation |  | 77.79%
|  |  | Antenna Cable Installation |  | 46.98%
|  |  | Splitter Installation |  | 31.14%
|  |  | Fiber Cable Splicing |  | 62.49%
|  |  | Fiber Testing |  | 79.76%
|  |  | Power Testing |  | 75.63%
59400 | B1 |  | Radio Unit Installation |  | 0.5247% | 42.78% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 22.26%
|  |  | Fiber Box Installation |  | 34.97%
|  |  | Antenna Installation |  | 91.25%
|  |  | Antenna Cable Installation |  | 20.71%
|  |  | Splitter Installation |  | 85.91%
|  |  | Fiber Cable Splicing |  | 4.214%
|  |  | Fiber Testing |  | 75.79%
|  |  | Power Testing |  | 49.37%
59700 | B1 |  | Radio Unit Installation |  | 6.409% | 48.18% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 56.56%
|  |  | Fiber Box Installation |  | 33.58%
|  |  | Antenna Installation |  | 89.23%
|  |  | Antenna Cable Installation |  | 25.4%
|  |  | Splitter Installation |  | 64.11%
|  |  | Fiber Cable Splicing |  | 88.28%
|  |  | Fiber Testing |  | 3.296%
|  |  | Power Testing |  | 66.78%
60500 | B1 |  | Radio Unit Installation |  | 81.12% | 59.43% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 42.95%
|  |  | Fiber Box Installation |  | 0.9789%
|  |  | Antenna Installation |  | 86.57%
|  |  | Antenna Cable Installation |  | 56.08%
|  |  | Splitter Installation |  | 88.16%
|  |  | Fiber Cable Splicing |  | 19.6%
|  |  | Fiber Testing |  | 89.9%
|  |  | Power Testing |  | 69.51%
60800 | B2 |  | Radio Unit Installation |  | 17.57% | 64.82% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 82.99%
|  |  | Fiber Box Installation |  | 46.46%
|  |  | Antenna Installation |  | 76.57%
|  |  | Antenna Cable Installation |  | 61.48%
|  |  | Splitter Installation |  | 91.8%
|  |  | Fiber Cable Splicing |  | 39.45%
|  |  | Fiber Testing |  | 82.57%
|  |  | Power Testing |  | 84.49%
60800 | B1 |  | Radio Unit Installation |  | 7.151% | 40.94% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 66.39%
|  |  | Fiber Box Installation |  | 38.83%
|  |  | Antenna Installation |  | 22.94%
|  |  | Antenna Cable Installation |  | 90.19%
|  |  | Splitter Installation |  | 32.08%
|  |  | Fiber Cable Splicing |  | 81.26%
|  |  | Fiber Testing |  | 16.13%
|  |  | Power Testing |  | 13.47%
61900 | B2 |  | Radio Unit Installation |  | 70.63% | 66.32% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 72.77%
|  |  | Fiber Box Installation |  | 49.17%
|  |  | Antenna Installation |  | 94.65%
|  |  | Antenna Cable Installation |  | 47.73%
|  |  | Splitter Installation |  | 65.19%
|  |  | Fiber Cable Splicing |  | 63.52%
|  |  | Fiber Testing |  | 50.64%
|  |  | Power Testing |  | 82.6%
61900 | B1 |  | Radio Unit Installation |  | 74.31% | 48.77% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 48.03%
|  |  | Fiber Box Installation |  | 76.22%
|  |  | Antenna Installation |  | 90.88%
|  |  | Antenna Cable Installation |  | 37.38%
|  |  | Splitter Installation |  | 25.84%
|  |  | Fiber Cable Splicing |  | 45.65%
|  |  | Fiber Testing |  | 24.9%
|  |  | Power Testing |  | 15.76%
62300 | B1 |  | Radio Unit Installation |  | 85.7% | 37.95% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 14.02%
|  |  | Fiber Box Installation |  | 43.02%
|  |  | Antenna Installation |  | 35.95%
|  |  | Antenna Cable Installation |  | 61.11%
|  |  | Splitter Installation |  | 21.26%
|  |  | Fiber Cable Splicing |  | 33.85%
|  |  | Fiber Testing |  | 28.05%
|  |  | Power Testing |  | 18.56%
63200 | B1 |  | Radio Unit Installation |  | 5.433% | 48.65% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 64.67%
|  |  | Fiber Box Installation |  | 32.75%
|  |  | Antenna Installation |  | 22.51%
|  |  | Antenna Cable Installation |  | 6.686%
|  |  | Splitter Installation |  | 84.66%
|  |  | Fiber Cable Splicing |  | 70.83%
|  |  | Fiber Testing |  | 58.95%
|  |  | Power Testing |  | 91.38%
63300 | B1 |  | Radio Unit Installation |  | 48.22% | 55.7% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 23.44%
|  |  | Fiber Box Installation |  | 80.19%
|  |  | Antenna Installation |  | 30.81%
|  |  | Antenna Cable Installation |  | 72.62%
|  |  | Splitter Installation |  | 55.57%
|  |  | Fiber Cable Splicing |  | 58.69%
|  |  | Fiber Testing |  | 68.31%
|  |  | Power Testing |  | 63.42%
64200 | B1 |  | Radio Unit Installation |  | 68.13% | 57.54% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 47.28%
|  |  | Fiber Box Installation |  | 65.5%
|  |  | Antenna Installation |  | 19.74%
|  |  | Antenna Cable Installation |  | 92.69%
|  |  | Splitter Installation |  | 62.27%
|  |  | Fiber Cable Splicing |  | 62.59%
|  |  | Fiber Testing |  | 53.48%
|  |  | Power Testing |  | 46.14%
64300 | B1 |  | Radio Unit Installation |  | 95.03% | 41.64% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 46.23%
|  |  | Fiber Box Installation |  | 44.75%
|  |  | Antenna Installation |  | 20.61%
|  |  | Antenna Cable Installation |  | 0.09079%
|  |  | Splitter Installation |  | 2.213%
|  |  | Fiber Cable Splicing |  | 82.16%
|  |  | Fiber Testing |  | 35.41%
|  |  | Power Testing |  | 48.3%
65200 | B1 |  | Radio Unit Installation |  | 84.88% | 36% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 12.01%
|  |  | Fiber Box Installation |  | 9.131%
|  |  | Antenna Installation |  | 89.98%
|  |  | Antenna Cable Installation |  | 10.63%
|  |  | Splitter Installation |  | 21.99%
|  |  | Fiber Cable Splicing |  | 29.19%
|  |  | Fiber Testing |  | 9.015%
|  |  | Power Testing |  | 57.16%
65200 | B2 |  | Radio Unit Installation |  | 35.28% | 41.02% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 36.02%
|  |  | Fiber Box Installation |  | 73.16%
|  |  | Antenna Installation |  | 3.26%
|  |  | Antenna Cable Installation |  | 84.72%
|  |  | Splitter Installation |  | 20.75%
|  |  | Fiber Cable Splicing |  | 32.69%
|  |  | Fiber Testing |  | 19.56%
|  |  | Power Testing |  | 63.78%
66300 | B1 |  | Radio Unit Installation |  | 92.52% | 59.03% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 48.27%
|  |  | Fiber Box Installation |  | 17.87%
|  |  | Antenna Installation |  | 78.99%
|  |  | Antenna Cable Installation |  | 34.68%
|  |  | Splitter Installation |  | 40.22%
|  |  | Fiber Cable Splicing |  | 90.07%
|  |  | Fiber Testing |  | 34.19%
|  |  | Power Testing |  | 94.46%
66300 | B2 |  | Radio Unit Installation |  | 19.42% | 59.17% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 72.81%
|  |  | Fiber Box Installation |  | 71.27%
|  |  | Antenna Installation |  | 4.41%
|  |  | Antenna Cable Installation |  | 96.46%
|  |  | Splitter Installation |  | 98.17%
|  |  | Fiber Cable Splicing |  | 81.52%
|  |  | Fiber Testing |  | 11.32%
|  |  | Power Testing |  | 77.12%
67500 | B1 |  | Radio Unit Installation |  | 6.366% | 34.68% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 42.05%
|  |  | Fiber Box Installation |  | 50.33%
|  |  | Antenna Installation |  | 83.61%
|  |  | Antenna Cable Installation |  | 11.59%
|  |  | Splitter Installation |  | 96.32%
|  |  | Fiber Cable Splicing |  | 4.231%
|  |  | Fiber Testing |  | 9.848%
|  |  | Power Testing |  | 7.755%
67500 | B2 |  | Radio Unit Installation |  | 86.99% | 37.05% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 74.17%
|  |  | Fiber Box Installation |  | 9.821%
|  |  | Antenna Installation |  | 35.26%
|  |  | Antenna Cable Installation |  | 42.74%
|  |  | Splitter Installation |  | 43.19%
|  |  | Fiber Cable Splicing |  | 1.556%
|  |  | Fiber Testing |  | 2.399%
|  |  | Power Testing |  | 37.31%
68300 | B1 |  | Radio Unit Installation |  | 89.92% | 56.32% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 83.07%
|  |  | Fiber Box Installation |  | 27.56%
|  |  | Antenna Installation |  | 3.987%
|  |  | Antenna Cable Installation |  | 21.66%
|  |  | Splitter Installation |  | 66.38%
|  |  | Fiber Cable Splicing |  | 76%
|  |  | Fiber Testing |  | 52.79%
|  |  | Power Testing |  | 85.56%
68300 | B2 |  | Radio Unit Installation |  | 99.07% | 54.87% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 2.714%
|  |  | Fiber Box Installation |  | 71.13%
|  |  | Antenna Installation |  | 10.4%
|  |  | Antenna Cable Installation |  | 27.13%
|  |  | Splitter Installation |  | 97.98%
|  |  | Fiber Cable Splicing |  | 90.04%
|  |  | Fiber Testing |  | 66.4%
|  |  | Power Testing |  | 28.92%
69900 | B1 |  | Radio Unit Installation |  | 49.81% | 47.61% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 91%
|  |  | Fiber Box Installation |  | 12.51%
|  |  | Antenna Installation |  | 57.66%
|  |  | Antenna Cable Installation |  | 47.34%
|  |  | Splitter Installation |  | 2.969%
|  |  | Fiber Cable Splicing |  | 0.8943%
|  |  | Fiber Testing |  | 87.49%
|  |  | Power Testing |  | 78.78%
71400 | B1 |  | Radio Unit Installation |  | 8.411% | 34.38% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 2.451%
|  |  | Fiber Box Installation |  | 82.69%
|  |  | Antenna Installation |  | 60.8%
|  |  | Antenna Cable Installation |  | 74.16%
|  |  | Splitter Installation |  | 74.96%
|  |  | Fiber Cable Splicing |  | 0.5941%
|  |  | Fiber Testing |  | 3.625%
|  |  | Power Testing |  | 1.703%
73000 | B1 |  | Radio Unit Installation |  | 96.31% | 52.11% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 86.9%
|  |  | Fiber Box Installation |  | 82.32%
|  |  | Antenna Installation |  | 14.72%
|  |  | Antenna Cable Installation |  | 8.03%
|  |  | Splitter Installation |  | 85.93%
|  |  | Fiber Cable Splicing |  | 41.4%
|  |  | Fiber Testing |  | 13.14%
|  |  | Power Testing |  | 40.21%
73000 | B2 |  | Radio Unit Installation |  | 88.78% | 45.84% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 18.69%
|  |  | Fiber Box Installation |  | 6.726%
|  |  | Antenna Installation |  | 95.25%
|  |  | Antenna Cable Installation |  | 46.49%
|  |  | Splitter Installation |  | 17.53%
|  |  | Fiber Cable Splicing |  | 12.53%
|  |  | Fiber Testing |  | 42.04%
|  |  | Power Testing |  | 84.5%
74100 | B1 |  | Radio Unit Installation |  | 13.24% | 47.25% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 78.01%
|  |  | Fiber Box Installation |  | 72.3%
|  |  | Antenna Installation |  | 17.07%
|  |  | Antenna Cable Installation |  | 99.45%
|  |  | Splitter Installation |  | 42.19%
|  |  | Fiber Cable Splicing |  | 17.37%
|  |  | Fiber Testing |  | 35.7%
|  |  | Power Testing |  | 49.93%
75300 | B1 |  | Radio Unit Installation |  | 33.16% | 44.51% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 84.62%
|  |  | Fiber Box Installation |  | 48.2%
|  |  | Antenna Installation |  | 66.77%
|  |  | Antenna Cable Installation |  | 26.1%
|  |  | Splitter Installation |  | 37.14%
|  |  | Fiber Cable Splicing |  | 69.64%
|  |  | Fiber Testing |  | 7.18%
|  |  | Power Testing |  | 27.75%
75300 | B2 |  | Radio Unit Installation |  | 44.75% | 56.57% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 57.93%
|  |  | Fiber Box Installation |  | 93.63%
|  |  | Antenna Installation |  | 4.61%
|  |  | Antenna Cable Installation |  | 90.11%
|  |  | Splitter Installation |  | 10.96%
|  |  | Fiber Cable Splicing |  | 88.84%
|  |  | Fiber Testing |  | 66.42%
|  |  | Power Testing |  | 51.86%
88300 | E1 |  | Radio Unit Installation |  | 58.95% | 43.92% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 3.947%
|  |  | Fiber Box Installation |  | 65.21%
|  |  | Antenna Installation |  | 26.86%
|  |  | Antenna Cable Installation |  | 7.652%
|  |  | Splitter Installation |  | 10.75%
|  |  | Fiber Cable Splicing |  | 81.24%
|  |  | Fiber Testing |  | 57.82%
|  |  | Power Testing |  | 82.86%
88600 | E1 |  | Radio Unit Installation |  | 75.79% | 51.63% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 82.13%
|  |  | Fiber Box Installation |  | 12.09%
|  |  | Antenna Installation |  | 29.31%
|  |  | Antenna Cable Installation |  | 39.14%
|  |  | Splitter Installation |  | 22.37%
|  |  | Fiber Cable Splicing |  | 44.71%
|  |  | Fiber Testing |  | 65.46%
|  |  | Power Testing |  | 93.68%
90800 | E1 |  | Radio Unit Installation |  | 99.84% | 74.91% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 97.61%
|  |  | Fiber Box Installation |  | 34.88%
|  |  | Antenna Installation |  | 85.63%
|  |  | Antenna Cable Installation |  | 83.69%
|  |  | Splitter Installation |  | 88.67%
|  |  | Fiber Cable Splicing |  | 13.14%
|  |  | Fiber Testing |  | 80%
|  |  | Power Testing |  | 90.77%
92400 | E1 |  | Radio Unit Installation |  | 87.18% | 72.01% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 97.73%
|  |  | Fiber Box Installation |  | 92.69%
|  |  | Antenna Installation |  | 80.92%
|  |  | Antenna Cable Installation |  | 34.38%
|  |  | Splitter Installation |  | 76.49%
|  |  | Fiber Cable Splicing |  | 64.38%
|  |  | Fiber Testing |  | 47.53%
|  |  | Power Testing |  | 66.75%
93600 | E1 |  | Radio Unit Installation |  | 16.05% | 43.39% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 29.1%
|  |  | Fiber Box Installation |  | 30.8%
|  |  | Antenna Installation |  | 63.94%
|  |  | Antenna Cable Installation |  | 70.85%
|  |  | Splitter Installation |  | 43.33%
|  |  | Fiber Cable Splicing |  | 41.81%
|  |  | Fiber Testing |  | 87.95%
|  |  | Power Testing |  | 6.683%
95000 | E1 |  | Radio Unit Installation |  | 10.3% | 43.21% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 92.44%
|  |  | Fiber Box Installation |  | 20.25%
|  |  | Antenna Installation |  | 10.72%
|  |  | Antenna Cable Installation |  | 26.3%
|  |  | Splitter Installation |  | 85.78%
|  |  | Fiber Cable Splicing |  | 68.08%
|  |  | Fiber Testing |  | 66.04%
|  |  | Power Testing |  | 9.028%
96500 | E1 |  | Radio Unit Installation |  | 68.51% | 56.58% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 37.37%
|  |  | Fiber Box Installation |  | 30.98%
|  |  | Antenna Installation |  | 25.58%
|  |  | Antenna Cable Installation |  | 11.56%
|  |  | Splitter Installation |  | 78.43%
|  |  | Fiber Cable Splicing |  | 75.78%
|  |  | Fiber Testing |  | 83.38%
|  |  | Power Testing |  | 97.59%
98200 | E1 |  | Radio Unit Installation |  | 18.73% | 51.79% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 99.91%
|  |  | Fiber Box Installation |  | 54.47%
|  |  | Antenna Installation |  | 19.29%
|  |  | Antenna Cable Installation |  | 23.78%
|  |  | Splitter Installation |  | 72.14%
|  |  | Fiber Cable Splicing |  | 26.72%
|  |  | Fiber Testing |  | 56.52%
|  |  | Power Testing |  | 94.55%
99700 | E1 |  | Radio Unit Installation |  | 43.73% | 48.18% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 11.88%
|  |  | Fiber Box Installation |  | 71.57%
|  |  | Antenna Installation |  | 68.72%
|  |  | Antenna Cable Installation |  | 31.78%
|  |  | Splitter Installation |  | 22.69%
|  |  | Fiber Cable Splicing |  | 64.28%
|  |  | Fiber Testing |  | 59.33%
|  |  | Power Testing |  | 59.67%
99700 | E2 |  | Radio Unit Installation |  | 20.77% | 66.71% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 93.09%
|  |  | Fiber Box Installation |  | 63.17%
|  |  | Antenna Installation |  | 46.78%
|  |  | Antenna Cable Installation |  | 83.44%
|  |  | Splitter Installation |  | 87.88%
|  |  | Fiber Cable Splicing |  | 68.85%
|  |  | Fiber Testing |  | 75.21%
|  |  | Power Testing |  | 61.21%
100400 | E1 |  | Radio Unit Installation |  | 18.73% | 37.22% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 4.491%
|  |  | Fiber Box Installation |  | 70.73%
|  |  | Antenna Installation |  | 17.37%
|  |  | Antenna Cable Installation |  | 1.455%
|  |  | Splitter Installation |  | 19.45%
|  |  | Fiber Cable Splicing |  | 96.66%
|  |  | Fiber Testing |  | 58.56%
|  |  | Power Testing |  | 47.52%
100600 | E1 |  | Radio Unit Installation |  | 19.03% | 55.2% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 54.72%
|  |  | Fiber Box Installation |  | 68.38%
|  |  | Antenna Installation |  | 89.35%
|  |  | Antenna Cable Installation |  | 96.23%
|  |  | Splitter Installation |  | 54.42%
|  |  | Fiber Cable Splicing |  | 54.23%
|  |  | Fiber Testing |  | 15.63%
|  |  | Power Testing |  | 44.85%
101500 | E1 |  | Radio Unit Installation |  | 81.99% | 50.97% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 27.47%
|  |  | Fiber Box Installation |  | 33.98%
|  |  | Antenna Installation |  | 50.1%
|  |  | Antenna Cable Installation |  | 22.33%
|  |  | Splitter Installation |  | 91.26%
|  |  | Fiber Cable Splicing |  | 68.75%
|  |  | Fiber Testing |  | 44.83%
|  |  | Power Testing |  | 38.04%
102600 | E1 |  | Radio Unit Installation |  | 48.68% | 46.86% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 81.11%
|  |  | Fiber Box Installation |  | 37.52%
|  |  | Antenna Installation |  | 25.51%
|  |  | Antenna Cable Installation |  | 0.1032%
|  |  | Splitter Installation |  | 4.273%
|  |  | Fiber Cable Splicing |  | 78.53%
|  |  | Fiber Testing |  | 91.77%
|  |  | Power Testing |  | 54.27%
103800 | E1 |  | Radio Unit Installation |  | 48.53% | 36.69% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 86.44%
|  |  | Fiber Box Installation |  | 17.78%
|  |  | Antenna Installation |  | 42.1%
|  |  | Antenna Cable Installation |  | 18.88%
|  |  | Splitter Installation |  | 8.222%
|  |  | Fiber Cable Splicing |  | 37.82%
|  |  | Fiber Testing |  | 9.544%
|  |  | Power Testing |  | 60.86%
104700 | E1 |  | Radio Unit Installation |  | 79.55% | 57.82% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 35.1%
|  |  | Fiber Box Installation |  | 80.35%
|  |  | Antenna Installation |  | 74.45%
|  |  | Antenna Cable Installation |  | 20.51%
|  |  | Splitter Installation |  | 98.98%
|  |  | Fiber Cable Splicing |  | 39.62%
|  |  | Fiber Testing |  | 73.86%
|  |  | Power Testing |  | 17.98%
105900 | E1 |  | Radio Unit Installation |  | 29.88% | 54.08% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 69.27%
|  |  | Fiber Box Installation |  | 83.95%
|  |  | Antenna Installation |  | 54.58%
|  |  | Antenna Cable Installation |  | 51.85%
|  |  | Splitter Installation |  | 43.74%
|  |  | Fiber Cable Splicing |  | 26.94%
|  |  | Fiber Testing |  | 69.29%
|  |  | Power Testing |  | 57.24%
106900 | E1 |  | Radio Unit Installation |  | 80.62% | 52.25% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 60.33%
|  |  | Fiber Box Installation |  | 62.43%
|  |  | Antenna Installation |  | 92.79%
|  |  | Antenna Cable Installation |  | 52.86%
|  |  | Splitter Installation |  | 65.87%
|  |  | Fiber Cable Splicing |  | 4.192%
|  |  | Fiber Testing |  | 21.83%
|  |  | Power Testing |  | 29.37%
108300 | E1 |  | Radio Unit Installation |  | 23.66% | 39.61% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 45.5%
|  |  | Fiber Box Installation |  | 86.12%
|  |  | Antenna Installation |  | 36.21%
|  |  | Antenna Cable Installation |  | 40.32%
|  |  | Splitter Installation |  | 61.24%
|  |  | Fiber Cable Splicing |  | 35.14%
|  |  | Fiber Testing |  | 9.809%
|  |  | Power Testing |  | 18.51%
109900 | E1 |  | Radio Unit Installation |  | 97.1% | 33.2% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 39.13%
|  |  | Fiber Box Installation |  | 49.94%
|  |  | Antenna Installation |  | 5.765%
|  |  | Antenna Cable Installation |  | 34.79%
|  |  | Splitter Installation |  | 23.84%
|  |  | Fiber Cable Splicing |  | 4.772%
|  |  | Fiber Testing |  | 28.05%
|  |  | Power Testing |  | 15.37%
111100 | E1 |  | Radio Unit Installation |  | 45.15% | 46.26% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 56.18%
|  |  | Fiber Box Installation |  | 75.21%
|  |  | Antenna Installation |  | 23.28%
|  |  | Antenna Cable Installation |  | 88.32%
|  |  | Splitter Installation |  | 30.84%
|  |  | Fiber Cable Splicing |  | 3.871%
|  |  | Fiber Testing |  | 23.5%
|  |  | Power Testing |  | 69.98%
112200 | E1 |  | Radio Unit Installation |  | 28.28% | 52.96% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 60.89%
|  |  | Fiber Box Installation |  | 75.05%
|  |  | Antenna Installation |  | 77.16%
|  |  | Antenna Cable Installation |  | 37.65%
|  |  | Splitter Installation |  | 6.932%
|  |  | Fiber Cable Splicing |  | 76.59%
|  |  | Fiber Testing |  | 91.81%
|  |  | Power Testing |  | 22.23%
113000 | E1 |  | Radio Unit Installation |  | 17.07% | 59.59% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 68.68%
|  |  | Fiber Box Installation |  | 83.16%
|  |  | Antenna Installation |  | 87.82%
|  |  | Antenna Cable Installation |  | 83.35%
|  |  | Splitter Installation |  | 25.45%
|  |  | Fiber Cable Splicing |  | 82.81%
|  |  | Fiber Testing |  | 85.4%
|  |  | Power Testing |  | 2.526%
114300 | E1 |  | Radio Unit Installation |  | 3.265% | 56.09% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 79%
|  |  | Fiber Box Installation |  | 13.53%
|  |  | Antenna Installation |  | 48.29%
|  |  | Antenna Cable Installation |  | 73.33%
|  |  | Splitter Installation |  | 19.01%
|  |  | Fiber Cable Splicing |  | 77.59%
|  |  | Fiber Testing |  | 92.93%
|  |  | Power Testing |  | 97.87%
115500 | E1 |  | Radio Unit Installation |  | 17.28% | 54.59% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 72.04%
|  |  | Fiber Box Installation |  | 48.74%
|  |  | Antenna Installation |  | 93.58%
|  |  | Antenna Cable Installation |  | 40.44%
|  |  | Splitter Installation |  | 34.13%
|  |  | Fiber Cable Splicing |  | 41.24%
|  |  | Fiber Testing |  | 67.24%
|  |  | Power Testing |  | 76.63%
116900 | E1 |  | Radio Unit Installation |  | 71.39% | 52.04% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 49.88%
|  |  | Fiber Box Installation |  | 61.93%
|  |  | Antenna Installation |  | 72.22%
|  |  | Antenna Cable Installation |  | 54.25%
|  |  | Splitter Installation |  | 49.5%
|  |  | Fiber Cable Splicing |  | 77.7%
|  |  | Fiber Testing |  | 22.24%
|  |  | Power Testing |  | 9.254%
118300 | E1 |  | Radio Unit Installation |  | 25.23% | 53.21% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 32.46%
|  |  | Fiber Box Installation |  | 74.12%
|  |  | Antenna Installation |  | 98.86%
|  |  | Antenna Cable Installation |  | 17.59%
|  |  | Splitter Installation |  | 30.19%
|  |  | Fiber Cable Splicing |  | 7.171%
|  |  | Fiber Testing |  | 98.83%
|  |  | Power Testing |  | 94.43%
118300 | E2 |  | Radio Unit Installation |  | 10.59% | 43.64% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 67.18%
|  |  | Fiber Box Installation |  | 3.457%
|  |  | Antenna Installation |  | 37.83%
|  |  | Antenna Cable Installation |  | 3.981%
|  |  | Splitter Installation |  | 98.62%
|  |  | Fiber Cable Splicing |  | 55.75%
|  |  | Fiber Testing |  | 20.02%
|  |  | Power Testing |  | 95.33%
119500 | E1 |  | Radio Unit Installation |  | 19.07% | 45.97% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 28.16%
|  |  | Fiber Box Installation |  | 80.88%
|  |  | Antenna Installation |  | 69.27%
|  |  | Antenna Cable Installation |  | 27.82%
|  |  | Splitter Installation |  | 59.96%
|  |  | Fiber Cable Splicing |  | 77.16%
|  |  | Fiber Testing |  | 7.146%
|  |  | Power Testing |  | 44.26%
119500 | E2 |  | Radio Unit Installation |  | 79.56% | 49.03% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 52.97%
|  |  | Fiber Box Installation |  | 25.1%
|  |  | Antenna Installation |  | 9.769%
|  |  | Antenna Cable Installation |  | 25%
|  |  | Splitter Installation |  | 66.5%
|  |  | Fiber Cable Splicing |  | 27.11%
|  |  | Fiber Testing |  | 96.64%
|  |  | Power Testing |  | 58.64%
120800 | E1 |  | Radio Unit Installation |  | 6.91% | 40.9% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 55.98%
|  |  | Fiber Box Installation |  | 49.43%
|  |  | Antenna Installation |  | 5.109%
|  |  | Antenna Cable Installation |  | 39.32%
|  |  | Splitter Installation |  | 22.54%
|  |  | Fiber Cable Splicing |  | 79%
|  |  | Fiber Testing |  | 55.48%
|  |  | Power Testing |  | 54.28%
120800 | E2 |  | Radio Unit Installation |  | 43.35% | 33.6% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 69.16%
|  |  | Fiber Box Installation |  | 25.8%
|  |  | Antenna Installation |  | 8.781%
|  |  | Antenna Cable Installation |  | 63.72%
|  |  | Splitter Installation |  | 25.43%
|  |  | Fiber Cable Splicing |  | 21.76%
|  |  | Fiber Testing |  | 39.56%
|  |  | Power Testing |  | 4.878%
121900 | E1 |  | Radio Unit Installation |  | 33.19% | 51% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 1.266%
|  |  | Fiber Box Installation |  | 57.1%
|  |  | Antenna Installation |  | 41.66%
|  |  | Antenna Cable Installation |  | 56.98%
|  |  | Splitter Installation |  | 97.64%
|  |  | Fiber Cable Splicing |  | 84.17%
|  |  | Fiber Testing |  | 86.87%
|  |  | Power Testing |  | 0.1014%
122800 | E1 |  | Radio Unit Installation |  | 6.495% | 29.73% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 6.847%
|  |  | Fiber Box Installation |  | 97.09%
|  |  | Antenna Installation |  | 47.77%
|  |  | Antenna Cable Installation |  | 1.599%
|  |  | Splitter Installation |  | 30.24%
|  |  | Fiber Cable Splicing |  | 19.03%
|  |  | Fiber Testing |  | 6.056%
|  |  | Power Testing |  | 52.41%
123900 | D1 |  | Radio Unit Installation |  | 81.74% | 30.64% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 14.42%
|  |  | Fiber Box Installation |  | 34.29%
|  |  | Antenna Installation |  | 12.69%
|  |  | Antenna Cable Installation |  | 84.23%
|  |  | Splitter Installation |  | 12.19%
|  |  | Fiber Cable Splicing |  | 12.97%
|  |  | Fiber Testing |  | 13.16%
|  |  | Power Testing |  | 10.08%
124900 | D1 |  | Radio Unit Installation |  | 4.017% | 56.49% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 45.02%
|  |  | Fiber Box Installation |  | 83.09%
|  |  | Antenna Installation |  | 68.79%
|  |  | Antenna Cable Installation |  | 93%
|  |  | Splitter Installation |  | 45.19%
|  |  | Fiber Cable Splicing |  | 21.6%
|  |  | Fiber Testing |  | 74.46%
|  |  | Power Testing |  | 73.19%
125900 | D1 |  | Radio Unit Installation |  | 46.43% | 26.02% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 45.24%
|  |  | Fiber Box Installation |  | 9.416%
|  |  | Antenna Installation |  | 10.17%
|  |  | Antenna Cable Installation |  | 13.18%
|  |  | Splitter Installation |  | 50.93%
|  |  | Fiber Cable Splicing |  | 37.78%
|  |  | Fiber Testing |  | 1.21%
|  |  | Power Testing |  | 19.87%
123900 | D2 |  | Radio Unit Installation |  | 75.82% | 57.63% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 72.58%
|  |  | Fiber Box Installation |  | 5.226%
|  |  | Antenna Installation |  | 38.91%
|  |  | Antenna Cable Installation |  | 56.14%
|  |  | Splitter Installation |  | 85.82%
|  |  | Fiber Cable Splicing |  | 28.71%
|  |  | Fiber Testing |  | 62.61%
|  |  | Power Testing |  | 92.83%
124900 | D2 |  | Radio Unit Installation |  | 20.54% | 53.45% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 13.48%
|  |  | Fiber Box Installation |  | 98.78%
|  |  | Antenna Installation |  | 71.6%
|  |  | Antenna Cable Installation |  | 47.82%
|  |  | Splitter Installation |  | 65.57%
|  |  | Fiber Cable Splicing |  | 55.65%
|  |  | Fiber Testing |  | 57.26%
|  |  | Power Testing |  | 50.36%
125900 | D2 |  | Radio Unit Installation |  | 20.89% | 30.8% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 15.44%
|  |  | Fiber Box Installation |  | 55.13%
|  |  | Antenna Installation |  | 55.55%
|  |  | Antenna Cable Installation |  | 76.87%
|  |  | Splitter Installation |  | 14.01%
|  |  | Fiber Cable Splicing |  | 25.68%
|  |  | Fiber Testing |  | 4.16%
|  |  | Power Testing |  | 9.473%

## Z-CASE
Stationing | Track No | Location | Activity | Date | Progress | General Progress | Notes
|  |  | CASE Install |  | 78.89% |  | Z-CASE IS BY E1-986 (Z)
|  |  | Cable Connection/Termination |  | 4.253%
|  |  | Pre-Op testing |  | 69.3%
|  |  | CASE Install |  | 25.03% |  | Z-CASE IS BY E1-1006 (Z)
|  |  | Cable Connection/Termination |  | 16.55%
|  |  | Pre-Op testing |  | 89.07%
|  |  | CASE Install |  | 18.36% |  | Z-CASE IS BY E1-1030 (Z)
|  |  | Cable Connection/Termination |  | 46.47%
|  |  | Pre-Op testing |  | 97.81%
|  |  | CASE Install |  | 41.64% |  | Z-CASE IS BY E1-1068 (Z)
|  |  | Cable Connection/Termination |  | 66.95%
|  |  | Pre-Op testing |  | 51.88%
115725 | E1 |  | CASE Install |  | 54.29% |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
|  |  | Cable Connection/Termination |  | 66.41%
|  |  | Pre-Op testing |  | 41.88%
121810 | E1 | 21S-COU | CASE Install |  | 75.3% |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
|  |  | Cable Connection/Termination |  | 20.86%
|  |  | Pre-Op testing |  | 10.91%
| E1 |  | CASE Install |  | 12.82% |  | Z-CASE IS BY E1-1229 (Z)
|  |  | Cable Connection/Termination |  | 4.902%
|  |  | Pre-Op testing |  | 56.15%
| E1 |  | CASE Install |  | 82.4% |  | Z-CASE IS BY E1-1230 (Z)
|  |  | Cable Connection/Termination |  | 79.6%
|  |  | Pre-Op testing |  | 16.96%
98565 | E2 |  | CASE Install |  | 36.16% |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
|  |  | Cable Connection/Termination |  | 5.137%
|  |  | Pre-Op testing |  | 96.76%
114869 | E2 |  | CASE Install |  | 68.57% |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
|  |  | Cable Connection/Termination |  | 21.52%
|  |  | Pre-Op testing |  | 82.85%
| E2 |  | CASE Install |  | 58.63% |  | Z-CASE IS BY E2-1230(Z)
|  |  | Cable Connection/Termination |  | 49.1%
|  |  | Pre-Op testing |  | 52.83%
122071 | E5 |  | CASE Install |  | 18.36% |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
|  |  | Cable Connection/Termination |  | 54.79%
|  |  | Pre-Op testing |  | 66.3%
122687 | E5 |  | CASE Install |  | 39.21% |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
|  |  | Cable Connection/Termination |  | 57.13%
|  |  | Pre-Op testing |  | 83.08%

## TOPB
Stationing | Track No | Location | Activity | Date | Progress | General Progress | Notes
121810 | E1 |  | TOPB Install |  | 64.51% |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
|  |  | Cable Connection/Termination |  | 48.88%
|  |  | Pre-Op testing |  | 20.98%
122987 | E1 |  | TOPB Install |  | 43.29% |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
|  |  | Cable Connection/Termination |  | 55.32%
|  |  | Pre-Op testing |  | 3.55%
|  |  | TOPB Install |  | 76.01% |  | TOPB @ ~D1-1239
|  |  | Cable Connection/Termination |  | 26.21%
|  |  | Pre-Op testing |  | 56.23%
121809 | E2 |  | TOPB Install |  | 11.28% |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
|  |  | Cable Connection/Termination |  | 27.14%
|  |  | Pre-Op testing |  | 63.14%
122970 | E2 |  | TOPB Install |  | 41.9% |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
|  |  | Cable Connection/Termination |  | 96.56%
|  |  | Pre-Op testing |  | 73.12%
124043 | D2 |  | TOPB Install |  | 61.83% |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
|  |  | Cable Connection/Termination |  | 6.899%
|  |  | Pre-Op testing |  | 69.67%

## Report Screenshot
Tasks | Total Quantity | Installed/Tested Quantity
Acceptance Test (Ea) | 29 | 3
Antenna Cable (ft) | 61885 | 58432
Brackets (Ea) | 12147 | 11856
Coax Cable (Ea) | 59 | 59
Insertion Loss (Segment) (ft) | 47445 | 43615
Removals (ft) | 30946 | 2380
Coupler Plates | 27 | 27
DC Resistance (Segment) | 47410 | 43580
Megger (Segment) | 47445 | 43615
VSWR (Segment) | 47445 | 43615
End-To-End | 47445 | 33565
Heat Map Test | 47445 | 29175
Coverage Test/Survey | 47445 | 3160
Megger Coax Cable (Reel) | 4000 | 4000
Megger Antenna Cable (Reel) | 80000 | 80000
Megger 1/2in Cable (Reel) | 100 | 100
DC Resistance Coax Cable (Reel) | 4000 | 4000
DC Resistance Antenna Cable (Reel) | 80000 | 80000
DC Resistance 1/2in Cable (Reel) | 100 | 100

## Dashboard
RADIO INSTALLATION DASHBOARD
OVERALL TASK COMPLETION (ALL TRACKS)
TASK PERCENT COMPLETION (PER TRACK)
OVERALL INSTALLATION PROGRESS PER TRACK SECTION
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.