## Reference
Track No. | Column Side | Activities | Bracket Type | Station | Track Stationing | Tunnel | Description | Track Stationing | Notes
B1 | W | Steel Messenger Supports | 1 | Church Avenue | 556+96 to 563+56 | CHU-FOR | Church Ave to Fort Hamilton | 563+56 to 584+88
B2 | E | Messenger Clamps | 2 | Fort Hamilton Parkway | 584+88 to 591+90 | FOR-15S | Fort Hamilton to 15th Street | 591+90 to 625+70
B3 | W | Messenger Wire Pull | 3 | 15th Street Prospect Park | 625+70 to 632+30 | 15S-7AV | 15th Street to 7th Avenue | 632+30 to 653+96
B4 | E | Messenger Wire Tension | 4 | 7th Avenue | 653+96 to 660+56 | 7AV-4TH | 7th Avenue to 4th & 9th Street | 660+56-683+83
E1 | W | Cable Pull | 4A | 4th & 9th Street | 683+83 to 690+91 | 4TH-SMI | 4th & 9th Street to Smith & 9th Street | 690+91 to 705+11
E2 | E | Messenger Straps | 5 | Smith & 9th Street | 705+11 to 712+32 | SMI-CAR | Smith & 9th Street to Carroll Street | 712+32 to 732+89
E3 |  | 15inch CMRS |  | Carroll Street | 732+39 to 738+99 | CAR-BER | Carroll Street to Bergen Street | 738+99 to 756+82
E4 |  | 24inch CMRS |  | Bergen Street | 756+82 to 763+42 | BER-HOY | Bergen Street to Hoyt Schermerhorn | 763+42 to 761+84 | track goes from 768+XX to 693+95
E5 |  | Column mount CMRS |  | Hoyt Schermerhorn | 761+84 to 768+87 | HOY-FUL | Hoyt Schermerhorn to Fulton | 768+87 to 740+30
|  | Station Brackets |  | Fulton Street | 740+30 to 733+70 | FUL-CLI | Fulton to Clinton Washington | 733+70 to 951+82 | track goes from 733+15 to 934+96
Location |  | Grounding |  | Clinton Washington Avenue | 951+82 to 958+42 | CLI-CLA | Clinton Washington to Classon | 958+42 to 970+82
Church Avenue |  | Obstruction Brackets |  | Classon Avenue | 970+82 to 977+42 | CLA-BED | Classon to Bedford Nostand | 977+42 to 989+22
CHU-FOR |  | Cable Pull |  | Bedford Nostrand Avenue | 989+22 to 995+82 | BED-MYR | Bedford Nostrand to Myrtle Willoughby | 995+82 to 1017+47
Fort Hamilton Parkway |  | Cable Tray Brackets |  | Myrtle Willoughby Ave | 1017+47 to 1024+52 | MYR-FLU | Myrtle Willoughby to Flushing Avenue | 1024+52 to 1039+42
FOR-15S |  | Installing Tray |  | Flushing Avenue Station | 1039+42 to 1046+20 | FLU-BRO | Flushing Avenue to Broadway | 1046+20 to 1060+52
15th Street Prospect Park |  | Core Drilling |  | Broadway | 1060+52 to 1067+12 | BRO-MET | Broadway to Metropolitan | 1067+12 to 1132+45
15S-7AV |  | Cable Pull |  | Metropolitan Avenue | 1132+45 to 1139+50 | MET-NAS | Metropolitan to Nassau | 1139+50 to 1131+52
7th Avenue |  | Arch Bar Installation |  | Nassau Avenue | 1131+52 to 1138+32 | NAS-GRE | Nassau to Greenpoint | 1138+32 to 1157+00
7AV-4TH |  |  |  | Greenpoint Avenue | 1157+00 to 1164+32 | GRE-21S | Greenpoint to 21 St | 1164+32 to 1211+33
4th & 9th Street |  |  |  | 21 St Station | 1211+33 to 1217+92 | 21S-COU | 21 St to Court Square | 1217+92 to 1229+23
4TH-SMI |  |  |  | Court Square | 1229+23 to 1236+66 | COU-QUE | Court Square to Queens Plaza | 1236+66 to 1250+65
Smith & 9th Street |  |  |  | Queens Plaza | 1250+65 to 1257+27
SMI-CAR
Carroll Street |  |  |  | Signal Types
CAR-BER |  |  |  | HOME
Bergen Street* |  |  |  | APPROACH
BER-HOY |  |  |  | BUMPER
Hoyt Schermerhorn |  |  |  | REV. HOME
HOY-FUL |  |  |  | REV. APPROACH
Fulton Street
FUL-CLI
Clinton Washington Avenue
CLI-CLA
Classon Avenue
CLA-BED
Bedford Nostrand Avenue
BED-MYR
Myrtle Willoughby Ave
MYR-FLU
Flushing Avenue Station
FLU-BRO
Broadway
BRO-MET
Metropolitan Avenue
MET-NAS
Nassau Avenue
NAS-GRE
Greenpoint Avenue
GRE-21S
21 St Station
21S-COU
Court Square
COU-QUE
Queens Plaza

## Work Sheet (hidden)
OVERALL INSTALLATION PER AREA
Status | Count
Not Started | #REF!
In Progress | #REF!
Completed | #REF!
Remaining | #REF!
Total Tasks | #REF!
Completed Sections | #REF!
Remaining Sections | #REF!

## Ref Activity Bar (hidden)
RADIO INSTALLATION DASHBOARD
TRACK | C3/C4
TASK | COMPLETION PROGRESS
Removals | 12.5%
Grand Total | 12.5%

## Ref Progress per Activity (hidden)
TASK | Acceptance Test
|  | Not Started | 0 | Completed Sections | 13.04%
TRACK | Average of PROGRESS | In Progress | 0 | Remaining Sections | 86.96%
C1 | 16.67% | Completed | 0
C2 | 16.67%
C3 | 0%
C3/C4 | 14.29%
C4 | 0%
C5 | 0%
C6 | 0%
Grand Total | 13.04%

## CMRS
Start | Finish | Track No | Location | Activity | Total Quantity | QTY Installed | Date | Progress | General Progress | Notes | Notes
124510 | 124500 | D1 | COU-QUE | Steel Mess Supports | 689 | 540 |  | 0.78374 | 0.42854
|  |  |  | Messenger Clamps | 515 | 2 |  | 0.0038835
|  |  |  | Messenger Wire Pull | 457 | 113 |  | 0.24726
|  |  |  | Messenger Wire Tension | 788 | 360 |  | 0.45685
|  |  |  | # Cables Pulled | 283 | 263 |  | 0.92933
|  |  |  | Messenger Straps | 526 | 79 |  | 0.15019
124500 | 124320 | D1 | COU-QUE | Steel Mess Supports | 259 | 28 |  | 0.10811 | 0.134
|  |  |  | Messenger Clamps | 862 | 159 |  | 0.18445
|  |  |  | Messenger Wire Pull | 691 | 18 |  | 0.026049
|  |  |  | Messenger Wire Tension | 478 | 22 |  | 0.046025
|  |  |  | # Cables Pulled | 218 | 38 |  | 0.17431
|  |  |  | Messenger Straps | 996 | 264 |  | 0.26506
124320 | 124100 | D1 | COU-QUE | Steel Mess Supports | 261 | 29 |  | 0.11111 | 0.45274
|  |  |  | Messenger Clamps | 305 | 287 |  | 0.94098
|  |  |  | Messenger Wire Pull | 887 | 612 |  | 0.68997
|  |  |  | Messenger Wire Tension | 573 | 42 |  | 0.073298
|  |  |  | # Cables Pulled | 394 | 94 |  | 0.23858
|  |  |  | Messenger Straps | 960 | 636 |  | 0.6625
124100 | 123970 | D1 | COU-QUE | Steel Mess Supports | 551 | 407 |  | 0.73866 | 0.65569
|  |  |  | Messenger Clamps | 685 | 651 |  | 0.95036
|  |  |  | Messenger Wire Pull | 35 | 10 |  | 0.28571
|  |  |  | Messenger Wire Tension | 125 | 24 |  | 0.192
|  |  |  | # Cables Pulled | 789 | 662 |  | 0.83904
|  |  |  | Messenger Straps | 349 | 324 |  | 0.92837
123970 | 123930 | D1 | COU-QUE | 15" CMRS Install | 906 | 906 |  | 1 | 0.52284
|  |  |  | Column Clamp | 329 | 63 |  | 0.19149
|  |  |  | Station Brackets | 505 | 296 |  | 0.58614
|  |  |  | Grounding | 20 | 5 |  | 0.25
|  |  |  | Obstruction Brackets | 962 | 373 |  | 0.38773
|  |  |  | # Cables Pulled | 97 | 70 |  | 0.72165
123930 | 123715 | D1 | COU-QUE | 15" CMRS Install | 951 | 600 |  | 0.63091 | 0.52039
|  |  |  | Column Clamp | 722 | 104 |  | 0.14404
|  |  |  | Station Brackets | 400 | 337 |  | 0.8425
|  |  |  | Grounding | 905 | 646 |  | 0.71381
|  |  |  | Obstruction Brackets | 15 | 3 |  | 0.2
|  |  |  | # Cables Pulled | 966 | 571 |  | 0.5911
|  | D1 | COU-QUE | Crossover (Arch Bar Installation) | 64 | 30 |  | 0.46875
122975 | 122827 | E1 | 21S-COU | Steel Mess Supports | 47 | 15 |  | 0.31915 | 0.54416
|  |  |  | Messenger Clamps | 78 | 54 |  | 0.69231
|  |  |  | Messenger Wire Pull | 989 | 917 |  | 0.9272
|  |  |  | Messenger Wire Tension | 304 | 292 |  | 0.96053
|  |  |  | # Cables Pulled | 330 | 105 |  | 0.31818
|  |  |  | Messenger Straps | 672 | 32 |  | 0.047619
122827 | 122250 | E1 | 21S-COU | 24" CMRS Install | 547 | 195 |  | 0.35649 | 0.54315
|  |  |  | Column Clamp | 483 | 403 |  | 0.83437
|  |  |  | Station Brackets | 517 | 304 |  | 0.58801
|  |  |  | Grounding | 680 | 416 |  | 0.61176
|  |  |  | Obstruction Brackets | 106 | 42 |  | 0.39623
|  |  |  | # Cables Pulled | 841 | 397 |  | 0.47206
122250 | 121833 | E1 | 21S-COU | Steel Mess Supports | 670 | 109 |  | 0.16269 | 0.43424
|  |  |  | Messenger Clamps | 959 | 150 |  | 0.15641
|  |  |  | Messenger Wire Pull | 863 | 858 |  | 0.99421
|  |  |  | Messenger Wire Tension | 648 | 532 |  | 0.82099
|  |  |  | # Cables Pulled | 484 | 24 |  | 0.049587
|  |  |  | Messenger Straps | 102 | 43 |  | 0.42157
121833 | 121030 | E1 | 21 STREET | Steel Mess Supports | 480 | 202 |  | 0.42083 | 0.33241
|  |  |  | Messenger Clamps | 200 | 15 |  | 0.075
|  |  |  | Messenger Wire Pull | 994 | 87 |  | 0.087525
|  |  |  | Messenger Wire Tension | 118 | 52 |  | 0.44068
|  |  |  | # Cables Pulled | 979 | 856 |  | 0.87436
|  |  |  | Messenger Straps | 229 | 22 |  | 0.09607
121030 | 117010 | E1 | GRE-21S | 15" CMRS Install | 651 | 225 |  | 0.34562 | 0.66858
|  |  |  | Column Clamp | 889 | 680 |  | 0.7649
|  |  |  | Station Brackets | 20 | 16 |  | 0.8
|  |  |  | Grounding | 326 | 263 |  | 0.80675
|  |  |  | Obstruction Brackets | 818 | 481 |  | 0.58802
|  |  |  | # Cables Pulled | 827 | 584 |  | 0.70617
117010 | 116810 | E1 | GRE-21S | 15" CMRS Install | 422 | 225 |  | 0.53318 | 0.36425
|  |  |  | Column Clamp | 447 | 388 |  | 0.86801
|  |  |  | Station Brackets | 894 | 297 |  | 0.33221
|  |  |  | Grounding | 269 | 24 |  | 0.089219
|  |  |  | Obstruction Brackets | 700 | 142 |  | 0.20286
|  |  |  | # Cables Pulled | 800 | 128 |  | 0.16
116810 | 116471 | E1 | GRE-21S | 15" CMRS Install | 739 | 569 |  | 0.76996 | 0.56463
|  |  |  | Column Clamp | 996 | 705 |  | 0.70783
|  |  |  | Station Brackets | 681 | 138 |  | 0.20264
|  |  |  | Grounding | 970 | 195 |  | 0.20103
|  |  |  | Obstruction Brackets | 577 | 539 |  | 0.93414
|  |  |  | # Cables Pulled | 783 | 448 |  | 0.57216
116471 | 115694 | E1 | GREENPOINT | 24" CMRS Install | 207 | 72 |  | 0.34783 | 0.48736
|  |  |  | Column Clamp | 63 | 43 |  | 0.68254
|  |  |  | Station Brackets | 90 | 43 |  | 0.47778
|  |  |  | Grounding | 333 | 178 |  | 0.53453
|  |  |  | Obstruction Brackets | 183 | 118 |  | 0.64481
|  |  |  | # Cables Pulled | 338 | 80 |  | 0.23669
115694 | 115628 | E1 | NAS-GRE | 24" CMRS Install | 688 | 282 |  | 0.40988 | 0.54207
|  |  |  | Column Clamp | 879 | 858 |  | 0.97611
|  |  |  | Station Brackets | 972 | 34 |  | 0.034979
|  |  |  | Grounding | 419 | 348 |  | 0.83055
|  |  |  | Obstruction Brackets | 988 | 570 |  | 0.57692
|  |  |  | # Cables Pulled | 842 | 357 |  | 0.42399
115628 | 114897 | E1 | NAS-GRE | 24" CMRS Install | 134 | 31 |  | 0.23134 | 0.62361
|  |  |  | Column Clamp | 710 | 673 |  | 0.94789
|  |  |  | Station Brackets | 437 | 410 |  | 0.93822
|  |  |  | Grounding | 14 | 6 |  | 0.42857
|  |  |  | Obstruction Brackets | 348 | 284 |  | 0.81609
|  |  |  | # Cables Pulled | 411 | 156 |  | 0.37956
114897 | 114719 | E1 | NAS-GRE | Steel Mess Supports | 630 | 335 |  | 0.53175 | 0.33339
|  |  |  | Messenger Clamps | 222 | 52 |  | 0.23423
|  |  |  | Messenger Wire Pull | 735 | 318 |  | 0.43265
|  |  |  | Messenger Wire Tension | 877 | 570 |  | 0.64994
|  |  |  | # Cables Pulled | 524 | 5 |  | 0.009542
|  |  |  | Messenger Straps | 218 | 31 |  | 0.1422
114719 | 114040 | E1 | NAS-GRE | 24" CMRS Install | 198 | 81 |  | 0.40909 | 0.51809
|  |  |  | Column Clamp | 716 | 275 |  | 0.38408
|  |  |  | Station Brackets | 992 | 793 |  | 0.7994
|  |  |  | Grounding | 577 | 312 |  | 0.54073
|  |  |  | Obstruction Brackets | 64 | 61 |  | 0.95312
|  |  |  | # Cables Pulled | 271 | 6 |  | 0.02214
114040 | 113815 | E1 | NAS-GRE | Steel Mess Supports | 870 | 763 |  | 0.87701 | 0.66727
|  |  |  | Messenger Clamps | 883 | 438 |  | 0.49604
|  |  |  | Messenger Wire Pull | 324 | 267 |  | 0.82407
|  |  |  | Messenger Wire Tension | 891 | 688 |  | 0.77217
|  |  |  | # Cables Pulled | 231 | 52 |  | 0.22511
|  |  |  | Messenger Straps | 152 | 123 |  | 0.80921
113815 | 113019 | E1 | NASSAU | 24" CMRS Install | 51 | 32 |  | 0.62745 | 0.54619 |  | weight: 6.7 lb/ft
|  |  |  | Column Clamp | 706 | 309 |  | 0.43768
|  |  |  | Station Brackets | 813 | 64 |  | 0.078721
|  |  |  | Grounding | 981 | 566 |  | 0.57696
|  |  |  | Obstruction Brackets | 652 | 446 |  | 0.68405
|  |  |  | # Cables Pulled | 924 | 806 |  | 0.87229
|  | E1 | NASSAU | 24" CMRS Install | 460 | 209 |  | 0.45435 | 0.32007
|  |  |  | Column Clamp | 601 | 381 |  | 0.63394
|  |  |  | Station Brackets | 408 | 37 |  | 0.090686
|  |  |  | Grounding | 706 | 279 |  | 0.39518
|  |  |  | Obstruction Brackets | 949 | 87 |  | 0.091675
|  |  |  | # Cables Pulled | 813 | 207 |  | 0.25461
113019 | 112700 | E1 | MET-NAS | 24" CMRS Install | 584 | 308 |  | 0.5274 | 0.40366
|  |  |  | Column Clamp | 178 | 4 |  | 0.022472
|  |  |  | Station Brackets | 970 | 58 |  | 0.059794
|  |  |  | Grounding | 181 | 102 |  | 0.56354
|  |  |  | Obstruction Brackets | 667 | 565 |  | 0.84708
|  |  |  | # Cables Pulled | 239 | 96 |  | 0.40167
112700 | 110878 | E1 | MET-NAS | 15" CMRS Install | 690 | 188 |  | 0.27246 | 0.43804
|  |  |  | Column Clamp | 415 | 43 |  | 0.10361
|  |  |  | Station Brackets | 182 | 177 |  | 0.97253
|  |  |  | Grounding | 908 | 425 |  | 0.46806
|  |  |  | Obstruction Brackets | 82 | 55 |  | 0.67073
|  |  |  | # Cables Pulled | 845 | 119 |  | 0.14083
110878 | 110793 | E1 | MET-NAS | 15" CMRS Install | 619 | 152 |  | 0.24556 | 0.51733
|  |  |  | Column Clamp | 520 | 203 |  | 0.39038
|  |  |  | Station Brackets | 759 | 310 |  | 0.40843
|  |  |  | Grounding | 83 | 54 |  | 0.6506
|  |  |  | Obstruction Brackets | 1000 | 948 |  | 0.948
|  |  |  | # Cables Pulled | 551 | 254 |  | 0.46098
110793 | 109251 | E1 | MET-NAS | 15" CMRS Install | 891 | 70 |  | 0.078563 | 0.48612
|  |  |  | Column Clamp | 627 | 496 |  | 0.79107
|  |  |  | Station Brackets | 342 | 280 |  | 0.81871
|  |  |  | Grounding | 559 | 298 |  | 0.53309
|  |  |  | Obstruction Brackets | 771 | 364 |  | 0.47211
|  |  |  | # Cables Pulled | 717 | 160 |  | 0.22315
109251 | 109133 | E1 | MET-NAS | 15" CMRS Install | 520 | 362 |  | 0.69615 | 0.43432
|  |  |  | Column Clamp | 765 | 626 |  | 0.8183
|  |  |  | Station Brackets | 944 | 53 |  | 0.056144
|  |  |  | Grounding | 934 | 146 |  | 0.15632
|  |  |  | Obstruction Brackets | 133 | 47 |  | 0.35338
|  |  |  | # Cables Pulled | 527 | 277 |  | 0.52562
109133 | 108356 | E1 | METROPOLITAN | 15" CMRS Install | 586 | 207 |  | 0.35324 | 0.47596
|  |  |  | Column Clamp | 943 | 133 |  | 0.14104
|  |  |  | Station Brackets | 563 | 482 |  | 0.85613
|  |  |  | Grounding | 492 | 347 |  | 0.70528
|  |  |  | Obstruction Brackets | 792 | 615 |  | 0.77652
|  |  |  | # Cables Pulled | 552 | 13 |  | 0.023551
108356 | 107651 | E1 | BRO-MET | 15" CMRS Install | 492 | 461 |  | 0.93699 | 0.3771
|  |  |  | Column Clamp | 292 | 51 |  | 0.17466
|  |  |  | Station Brackets | 184 | 22 |  | 0.11957
|  |  |  | Grounding | 285 | 101 |  | 0.35439
|  |  |  | Obstruction Brackets | 505 | 69 |  | 0.13663
|  |  |  | # Cables Pulled | 161 | 87 |  | 0.54037
107651 | 107611 | E1 | BRO-MET | 15" CMRS Install | 675 | 462 |  | 0.68444 | 0.49661 |  | Check endings for specific stationings (DWG 48012-17N-006.0) where cable switches from 1 to 2
|  |  |  | Column Clamp | 87 | 36 |  | 0.41379
|  |  |  | Station Brackets | 385 | 9 |  | 0.023377
|  |  |  | Grounding | 457 | 139 |  | 0.30416
|  |  |  | Obstruction Brackets | 984 | 906 |  | 0.92073
|  |  |  | # Cables Pulled | 856 | 542 |  | 0.63318
107611 | 106768 | E1 | BRO-MET | 15" CMRS Install | 877 | 641 |  | 0.7309 | 0.70522
|  |  |  | Column Clamp | 544 | 465 |  | 0.85478
|  |  |  | Station Brackets | 291 | 63 |  | 0.21649
|  |  |  | Grounding | 446 | 356 |  | 0.79821
|  |  |  | Obstruction Brackets | 838 | 719 |  | 0.858
|  |  |  | # Cables Pulled | 960 | 742 |  | 0.77292
106768 | 106702 | E1 | BRO-MET | 15" CMRS Install | 158 | 102 |  | 0.64557 | 0.31536
|  |  |  | Column Clamp | 722 | 56 |  | 0.077562
|  |  |  | Station Brackets | 488 | 147 |  | 0.30123
|  |  |  | Grounding | 321 | 232 |  | 0.72274
|  |  |  | Obstruction Brackets | 207 | 18 |  | 0.086957
|  |  |  | # Cables Pulled | 396 | 23 |  | 0.058081
106702 | 106011 | E1 | BROADWAY | 15" CMRS Install | 986 | 14 |  | 0.014199 | 0.42099
|  |  |  | Column Clamp | 611 | 399 |  | 0.65303
|  |  |  | Station Brackets | 490 | 39 |  | 0.079592
|  |  |  | Grounding | 298 | 78 |  | 0.26174
|  |  |  | Obstruction Brackets | 816 | 620 |  | 0.7598
|  |  |  | # Cables Pulled | 693 | 525 |  | 0.75758
|  | E1 | BROADWAY | 15" CMRS Install | 618 | 176 |  | 0.28479 | 0.51239
|  |  |  | Column Clamp | 737 | 510 |  | 0.69199
|  |  |  | Station Brackets | 743 | 535 |  | 0.72005
|  |  |  | Grounding | 467 | 63 |  | 0.1349
|  |  |  | Obstruction Brackets | 358 | 138 |  | 0.38547
|  |  |  | # Cables Pulled | 427 | 366 |  | 0.85714
|  | E1 | BROADWAY | 15" CMRS Install | 264 | 198 |  | 0.75 | 0.6378
|  |  |  | Column Clamp | 350 | 262 |  | 0.74857
|  |  |  | Station Brackets | 65 | 33 |  | 0.50769
|  |  |  | Grounding | 611 | 524 |  | 0.85761
|  |  |  | Obstruction Brackets | 436 | 169 |  | 0.38761
|  |  |  | # Cables Pulled | 518 | 298 |  | 0.57529
106011 | 105293 | E1 | FLU-BRO | 15" CMRS Install | 362 | 32 |  | 0.088398 | 0.2804
|  |  |  | Column Clamp | 888 | 20 |  | 0.022523
|  |  |  | Station Brackets | 292 | 241 |  | 0.82534
|  |  |  | Grounding | 701 | 368 |  | 0.52496
|  |  |  | Obstruction Brackets | 393 | 78 |  | 0.19847
|  |  |  | # Cables Pulled | 264 | 6 |  | 0.022727
105293 | 104667 | E1 | FLU-BRO | 15" CMRS Install | 480 | 89 |  | 0.18542 | 0.42942
|  |  |  | Column Clamp | 471 | 299 |  | 0.63482
|  |  |  | Station Brackets | 840 | 76 |  | 0.090476
|  |  |  | Grounding | 629 | 572 |  | 0.90938
|  |  |  | Obstruction Brackets | 837 | 88 |  | 0.10514
|  |  |  | # Cables Pulled | 152 | 99 |  | 0.65132
104667 | 103784 | E1 | FLUSHING | 15" CMRS Install | 960 | 892 |  | 0.92917 | 0.66627
|  |  |  | Column Clamp | 701 | 541 |  | 0.77175
|  |  |  | Station Brackets | 828 | 287 |  | 0.34662
|  |  |  | Grounding | 227 | 226 |  | 0.99559
|  |  |  | Obstruction Brackets | 672 | 88 |  | 0.13095
|  |  |  | # Cables Pulled | 170 | 140 |  | 0.82353
103784 | 103231 | E1 | MYR-FLU | 15" CMRS Install | 489 | 53 |  | 0.10838 | 0.39958
|  |  |  | Column Clamp | 529 | 271 |  | 0.51229
|  |  |  | Station Brackets | 629 | 505 |  | 0.80286
|  |  |  | Grounding | 88 | 30 |  | 0.34091
|  |  |  | Obstruction Brackets | 944 | 391 |  | 0.41419
|  |  |  | # Cables Pulled | 786 | 172 |  | 0.21883
103231 | 103165 | E1 | MYR-FLU | 15" CMRS Install | 658 | 174 |  | 0.26444 | 0.45233
|  |  |  | Column Clamp | 381 | 202 |  | 0.53018
|  |  |  | Station Brackets | 584 | 154 |  | 0.2637
|  |  |  | Grounding | 857 | 395 |  | 0.46091
|  |  |  | Obstruction Brackets | 27 | 10 |  | 0.37037
|  |  |  | # Cables Pulled | 205 | 169 |  | 0.82439
103165 | 102533 | E1 | MYR-FLU | 15" CMRS Install | 985 | 829 |  | 0.84162 | 0.59841
|  |  |  | Column Clamp | 432 | 294 |  | 0.68056
|  |  |  | Station Brackets | 345 | 164 |  | 0.47536
|  |  |  | Grounding | 124 | 83 |  | 0.66935
|  |  |  | Obstruction Brackets | 174 | 61 |  | 0.35057
|  |  |  | # Cables Pulled | 185 | 106 |  | 0.57297
102533 | 101595 | E1 | MYRTLE | 24" CMRS Install | 60 | 40 |  | 0.66667 | 0.48855
|  |  |  | Column Clamp | 731 | 389 |  | 0.53215
|  |  |  | Station Brackets | 983 | 613 |  | 0.6236
|  |  |  | Grounding | 187 | 134 |  | 0.71658
|  |  |  | Obstruction Brackets | 226 | 86 |  | 0.38053
|  |  |  | # Cables Pulled | 681 | 8 |  | 0.011747
101595 | 101558 | E1 | BED-MYR | 24" CMRS Install | 969 | 244 |  | 0.25181 | 0.39566
|  |  |  | Column Clamp | 856 | 248 |  | 0.28972
|  |  |  | Station Brackets | 646 | 391 |  | 0.60526
|  |  |  | Grounding | 986 | 570 |  | 0.57809
|  |  |  | Obstruction Brackets | 625 | 187 |  | 0.2992
|  |  |  | # Cables Pulled | 503 | 176 |  | 0.3499
101558 | 101050 | E1 | BED-MYR | 24" CMRS Install | 893 | 510 |  | 0.57111 | 0.77877
|  |  |  | Column Clamp | 177 | 159 |  | 0.89831
|  |  |  | Station Brackets | 988 | 925 |  | 0.93623
|  |  |  | Grounding | 56 | 55 |  | 0.98214
|  |  |  | Obstruction Brackets | 206 | 60 |  | 0.29126
|  |  |  | # Cables Pulled | 935 | 929 |  | 0.99358
101050 | 101015 | E1 | BED-MYR | 24" CMRS Install | 275 | 62 |  | 0.22545 | 0.53975
|  |  |  | Column Clamp | 870 | 366 |  | 0.42069
|  |  |  | Station Brackets | 946 | 724 |  | 0.76533
|  |  |  | Grounding | 269 | 205 |  | 0.76208
|  |  |  | Obstruction Brackets | 500 | 330 |  | 0.66
|  |  |  | # Cables Pulled | 121 | 49 |  | 0.40496
101015 | 100530 | E1 | BED-MYR | 24" CMRS Install | 567 | 423 |  | 0.74603 | 0.47106
|  |  |  | Column Clamp | 165 | 76 |  | 0.46061
|  |  |  | Station Brackets | 771 | 296 |  | 0.38392
|  |  |  | Grounding | 769 | 440 |  | 0.57217
|  |  |  | Obstruction Brackets | 981 | 212 |  | 0.21611
|  |  |  | # Cables Pulled | 467 | 209 |  | 0.44754
100530 | 100383 | E1 | BED-MYR | Steel Mess Supports | 567 | 273 |  | 0.48148 | 0.41126
|  |  |  | Messenger Clamps | 484 | 110 |  | 0.22727
|  |  |  | Messenger Wire Pull | 670 | 9 |  | 0.013433
|  |  |  | Messenger Wire Tension | 416 | 398 |  | 0.95673
|  |  |  | # Cables Pulled | 444 | 113 |  | 0.2545
|  |  |  | Messenger Straps | 586 | 313 |  | 0.53413
|  | E1 | BED-MYR | Crossover (Arch Bar Installation) | 731 | 499 |  | 0.68263
100383 | 100282 | E1 | BED-MYR | Steel Mess Supports | 448 | 232 |  | 0.51786 | 0.67088
|  |  |  | Messenger Clamps | 183 | 158 |  | 0.86339
|  |  |  | Messenger Wire Pull | 301 | 265 |  | 0.8804
|  |  |  | Messenger Wire Tension | 412 | 72 |  | 0.17476
|  |  |  | # Cables Pulled | 666 | 494 |  | 0.74174
|  |  |  | Messenger Straps | 314 | 266 |  | 0.84713
100282 | 100036 | E1 | BED-MYR | Steel Mess Supports | 392 | 167 |  | 0.42602 | 0.55995
|  |  |  | Messenger Clamps | 192 | 134 |  | 0.69792
|  |  |  | Messenger Wire Pull | 65 | 37 |  | 0.56923
|  |  |  | Messenger Wire Tension | 446 | 255 |  | 0.57175
|  |  |  | # Cables Pulled | 250 | 75 |  | 0.3
|  |  |  | Messenger Straps | 497 | 395 |  | 0.79477
100036 | 99560 | E1 | BED-MYR | Steel Mess Supports | 832 | 828 |  | 0.99519 | 0.52419
|  |  |  | Messenger Clamps | 704 | 162 |  | 0.23011
|  |  |  | Messenger Wire Pull | 328 | 191 |  | 0.58232
|  |  |  | Messenger Wire Tension | 49 | 11 |  | 0.22449
|  |  |  | # Cables Pulled | 410 | 124 |  | 0.30244
|  |  |  | Messenger Straps | 961 | 779 |  | 0.81061
98845 | 98555 | E1 | CLA-BED | 24" CMRS Install | 77 | 56 |  | 0.72727 | 0.40651
|  |  |  | Column Clamp | 209 | 10 |  | 0.047847
|  |  |  | Station Brackets | 299 | 95 |  | 0.31773
|  |  |  | Grounding | 121 | 5 |  | 0.041322
|  |  |  | Obstruction Brackets | 331 | 326 |  | 0.98489
|  |  |  | # Cables Pulled | 525 | 168 |  | 0.32
|  | E1 | CLA-BED | Crossover (Arch Bar Installation) | 990 | 459 |  | 0.46364
98555 | 98220 | E1 | CLA-BED | 24" CMRS Install | 563 | 340 |  | 0.60391 | 0.67692
|  |  |  | Column Clamp | 436 | 345 |  | 0.79128
|  |  |  | Station Brackets | 923 | 511 |  | 0.55363
|  |  |  | Grounding | 742 | 626 |  | 0.84367
|  |  |  | Obstruction Brackets | 321 | 302 |  | 0.94081
|  |  |  | # Cables Pulled | 984 | 323 |  | 0.32825
98220 | 98140 | E1 | CLA-BED | 24" CMRS Install | 494 | 352 |  | 0.71255 | 0.56105
|  |  |  | Column Clamp | 997 | 235 |  | 0.23571
|  |  |  | Station Brackets | 764 | 337 |  | 0.4411
|  |  |  | Grounding | 833 | 762 |  | 0.91477
|  |  |  | Obstruction Brackets | 512 | 400 |  | 0.78125
|  |  |  | # Cables Pulled | 89 | 25 |  | 0.2809
98140 | 97920 | E1 | CLA-BED | 24" CMRS Install | 638 | 578 |  | 0.90596 | 0.55165
|  |  |  | Column Clamp | 118 | 28 |  | 0.23729
|  |  |  | Station Brackets | 938 | 649 |  | 0.6919
|  |  |  | Grounding | 696 | 319 |  | 0.45833
|  |  |  | Obstruction Brackets | 730 | 363 |  | 0.49726
|  |  |  | # Cables Pulled | 888 | 461 |  | 0.51914
97920 | 97670 | E1 | CLA-BED | Steel Mess Supports | 966 | 56 |  | 0.057971 | 0.39538
|  |  |  | Messenger Clamps | 593 | 303 |  | 0.51096
|  |  |  | Messenger Wire Pull | 32 | 24 |  | 0.75
|  |  |  | Messenger Wire Tension | 539 | 319 |  | 0.59184
|  |  |  | # Cables Pulled | 18 | 6 |  | 0.33333
|  |  |  | Messenger Straps | 39 | 5 |  | 0.12821
97670 | 97580 | E1 | CLASSON | 24" CMRS Install | 264 | 200 |  | 0.75758 | 0.61718
|  |  |  | Column Clamp | 468 | 132 |  | 0.28205
|  |  |  | Station Brackets | 486 | 469 |  | 0.96502
|  |  |  | Grounding | 574 | 290 |  | 0.50523
|  |  |  | Obstruction Brackets | 966 | 761 |  | 0.78778
|  |  |  | # Cables Pulled | 148 | 60 |  | 0.40541
97580 | 97230 | E1 | CLASSON | 24" CMRS Install | 351 | 109 |  | 0.31054 | 0.5302
|  |  |  | Column Clamp | 552 | 509 |  | 0.9221
|  |  |  | Station Brackets | 420 | 41 |  | 0.097619
|  |  |  | Grounding | 10 | 10 |  | 1
|  |  |  | Obstruction Brackets | 949 | 205 |  | 0.21602
|  |  |  | # Cables Pulled | 830 | 527 |  | 0.63494
97230 | 96920 | E1 | CLASSON | 24" CMRS Install | 288 | 237 |  | 0.82292 | 0.45597
|  |  |  | Column Clamp | 183 | 57 |  | 0.31148
|  |  |  | Station Brackets | 278 | 180 |  | 0.64748
|  |  |  | Grounding | 302 | 67 |  | 0.22185
|  |  |  | Obstruction Brackets | 806 | 218 |  | 0.27047
|  |  |  | # Cables Pulled | 769 | 355 |  | 0.46164
96920 | 96685 | E1 | CLI-CLA | Steel Mess Supports | 969 | 336 |  | 0.34675 | 0.56385
|  |  |  | Messenger Clamps | 567 | 467 |  | 0.82363
|  |  |  | Messenger Wire Pull | 969 | 683 |  | 0.70485
|  |  |  | Messenger Wire Tension | 265 | 95 |  | 0.35849
|  |  |  | # Cables Pulled | 587 | 479 |  | 0.81601
|  |  |  | Messenger Straps | 69 | 23 |  | 0.33333
96685 | 96460 | E1 | CLI-CLA | 24" CMRS Install | 298 | 222 |  | 0.74497 | 0.62562
|  |  |  | Column Clamp | 805 | 655 |  | 0.81366
|  |  |  | Station Brackets | 802 | 61 |  | 0.07606
|  |  |  | Grounding | 498 | 333 |  | 0.66867
|  |  |  | Obstruction Brackets | 757 | 549 |  | 0.72523
|  |  |  | # Cables Pulled | 171 | 124 |  | 0.72515
96460 | 96387 | E1 | CLI-CLA | 24" CMRS Install | 542 | 269 |  | 0.49631 | 0.37825
|  |  |  | Column Clamp | 417 | 15 |  | 0.035971
|  |  |  | Station Brackets | 679 | 477 |  | 0.7025
|  |  |  | Grounding | 633 | 259 |  | 0.40916
|  |  |  | Obstruction Brackets | 452 | 237 |  | 0.52434
|  |  |  | # Cables Pulled | 998 | 101 |  | 0.1012
96387 | 96051 | E1 | CLI-CLA | 24" CMRS Install | 213 | 32 |  | 0.15023 | 0.49108
|  |  |  | Column Clamp | 992 | 460 |  | 0.46371
|  |  |  | Station Brackets | 41 | 23 |  | 0.56098
|  |  |  | Grounding | 401 | 239 |  | 0.59601
|  |  |  | Obstruction Brackets | 626 | 166 |  | 0.26518
|  |  |  | # Cables Pulled | 357 | 325 |  | 0.91036
96038 | 95998 | E1 | CLI-CLA | 24" CMRS Install | 538 | 0 |  | 0 | 0.39779
|  |  |  | Column Clamp | 539 | 443 |  | 0.82189
|  |  |  | Station Brackets | 658 | 131 |  | 0.19909
|  |  |  | Grounding | 248 | 47 |  | 0.18952
|  |  |  | Obstruction Brackets | 805 | 438 |  | 0.5441
|  |  |  | # Cables Pulled | 878 | 555 |  | 0.63212
95998 | 95873 | E1 | CLI-CLA | 24" CMRS Install | 85 | 40 |  | 0.47059 | 0.47222
|  |  |  | Column Clamp | 880 | 119 |  | 0.13523
|  |  |  | Station Brackets | 985 | 798 |  | 0.81015
|  |  |  | Grounding | 330 | 182 |  | 0.55152
|  |  |  | Obstruction Brackets | 80 | 61 |  | 0.7625
|  |  |  | # Cables Pulled | 871 | 90 |  | 0.10333
95873 | 95781 | E1 | CLINTON-WASHINGTON | 24" CMRS Install | 448 | 171 |  | 0.3817 | 0.4306
|  |  |  | Column Clamp | 566 | 43 |  | 0.075972
|  |  |  | Station Brackets | 756 | 110 |  | 0.1455
|  |  |  | Grounding | 868 | 310 |  | 0.35714
|  |  |  | Obstruction Brackets | 380 | 336 |  | 0.88421
|  |  |  | # Cables Pulled | 525 | 388 |  | 0.73905
95781 | 95695 | E1 | CLINTON-WASHINGTON | 24" CMRS Install | 598 | 56 |  | 0.093645 | 0.38396
|  |  |  | Column Clamp | 471 | 207 |  | 0.43949
|  |  |  | Station Brackets | 485 | 322 |  | 0.66392
|  |  |  | Grounding | 325 | 60 |  | 0.18462
|  |  |  | Obstruction Brackets | 945 | 419 |  | 0.44339
|  |  |  | # Cables Pulled | 798 | 382 |  | 0.4787
95695 | 95544 | E1 | CLINTON-WASHINGTON | 24" CMRS Install | 364 | 277 |  | 0.76099 | 0.38085
|  |  |  | Column Clamp | 681 | 576 |  | 0.84581
|  |  |  | Station Brackets | 554 | 173 |  | 0.31227
|  |  |  | Grounding | 414 | 123 |  | 0.2971
|  |  |  | Obstruction Brackets | 979 | 15 |  | 0.015322
|  |  |  | # Cables Pulled | 168 | 9 |  | 0.053571
95544 | 95155 | E1 | CLINTON-WASHINGTON | 24" CMRS Install | 747 | 50 |  | 0.066934 | 0.47603
|  |  |  | Column Clamp | 773 | 625 |  | 0.80854
|  |  |  | Station Brackets | 321 | 107 |  | 0.33333
|  |  |  | Grounding | 311 | 139 |  | 0.44695
|  |  |  | Obstruction Brackets | 619 | 484 |  | 0.78191
|  |  |  | # Cables Pulled | 638 | 267 |  | 0.4185
95155 | 95004 | E1 | CLINTON-WASHINGTON | 24" CMRS Install | 30 | 15 |  | 0.5 | 0.4309
|  |  |  | Column Clamp | 108 | 53 |  | 0.49074
|  |  |  | Station Brackets | 672 | 240 |  | 0.35714
|  |  |  | Grounding | 451 | 109 |  | 0.24169
|  |  |  | Obstruction Brackets | 757 | 145 |  | 0.19155
|  |  |  | # Cables Pulled | 792 | 637 |  | 0.80429
95004 | 94266 | E1 | FUL-CLI | 24" CMRS Install | 302 | 180 |  | 0.59603 | 0.77679
|  |  |  | Column Clamp | 548 | 396 |  | 0.72263
|  |  |  | Station Brackets | 645 | 531 |  | 0.82326
|  |  |  | Grounding | 44 | 40 |  | 0.90909
|  |  |  | Obstruction Brackets | 445 | 346 |  | 0.77753
|  |  |  | # Cables Pulled | 292 | 243 |  | 0.83219
94266 | 94207 | E1 | FUL-CLI | 24" CMRS Install | 360 | 256 |  | 0.71111 | 0.52615
|  |  |  | Column Clamp | 695 | 310 |  | 0.44604
|  |  |  | Station Brackets | 352 | 129 |  | 0.36648
|  |  |  | Grounding | 807 | 556 |  | 0.68897
|  |  |  | Obstruction Brackets | 655 | 355 |  | 0.54198
|  |  |  | # Cables Pulled | 87 | 35 |  | 0.4023
94207 | 93350 | E1 | FUL-CLI | 24" CMRS Install | 18 | 16 |  | 0.88889 | 0.5473
|  |  |  | Column Clamp | 89 | 69 |  | 0.77528
|  |  |  | Station Brackets | 129 | 26 |  | 0.20155
|  |  |  | Grounding | 516 | 133 |  | 0.25775
|  |  |  | Obstruction Brackets | 866 | 340 |  | 0.39261
|  |  |  | # Cables Pulled | 861 | 661 |  | 0.76771
73350 | 73690 | E1 | FULTON | 15" CMRS Install | 424 | 61 |  | 0.14387 | 0.39458
|  |  |  | Column Clamp | 190 | 116 |  | 0.61053
|  |  |  | Station Brackets | 924 | 9 |  | 0.0097403
|  |  |  | Grounding | 448 | 153 |  | 0.34152
|  |  |  | Obstruction Brackets | 893 | 345 |  | 0.38634
|  |  |  | # Cables Pulled | 490 | 429 |  | 0.87551
73690 | 74030 | E1 | FULTON | 15" CMRS Install | 788 | 761 |  | 0.96574 | 0.60626
|  |  |  | Column Clamp | 829 | 567 |  | 0.68396
|  |  |  | Station Brackets | 882 | 645 |  | 0.73129
|  |  |  | Grounding | 712 | 410 |  | 0.57584
|  |  |  | Obstruction Brackets | 73 | 21 |  | 0.28767
|  |  |  | # Cables Pulled | 173 | 68 |  | 0.39306
|  | E1 | FULTON | 15" CMRS Install | 246 | 98 |  | 0.39837 | 0.59151
|  |  |  | Column Clamp | 45 | 18 |  | 0.4
|  |  |  | Station Brackets | 854 | 287 |  | 0.33607
|  |  |  | Grounding | 309 | 271 |  | 0.87702
|  |  |  | Obstruction Brackets | 906 | 772 |  | 0.8521
|  |  |  | # Cables Pulled | 938 | 643 |  | 0.6855
74030 | 76085 | E1 | HOY-FUL | 24" CMRS Install | 886 | 98 |  | 0.11061 | 0.55874
|  |  |  | Column Clamp | 29 | 19 |  | 0.65517
|  |  |  | Station Brackets | 321 | 245 |  | 0.76324
|  |  |  | Grounding | 429 | 286 |  | 0.66667
|  |  |  | Obstruction Brackets | 665 | 321 |  | 0.48271
|  |  |  | # Cables Pulled | 405 | 273 |  | 0.67407
76085 | 76110 | E1 | HOY-FUL | 15" CMRS Install | 749 | 6 |  | 0.0080107 | 0.29113
|  |  |  | Column Clamp | 803 | 8 |  | 0.0099626
|  |  |  | Station Brackets | 396 | 329 |  | 0.83081
|  |  |  | Grounding | 320 | 151 |  | 0.47187
|  |  |  | Obstruction Brackets | 231 | 56 |  | 0.24242
|  |  |  | # Cables Pulled | 860 | 158 |  | 0.18372
76110 | 76165 | E1 | HOY-FUL | 15" CMRS Install | 659 | 55 |  | 0.08346 | 0.38445
|  |  |  | Column Clamp | 549 | 280 |  | 0.51002
|  |  |  | Station Brackets | 156 | 83 |  | 0.53205
|  |  |  | Grounding | 26 | 7 |  | 0.26923
|  |  |  | Obstruction Brackets | 629 | 193 |  | 0.30684
|  |  |  | # Cables Pulled | 195 | 118 |  | 0.60513
76165 | 77470 | E1 | HOYT SCHERMERHORN | 15" CMRS Install | 625 | 65 |  | 0.104 | 0.43626
|  |  |  | Column Clamp | 874 | 26 |  | 0.029748
|  |  |  | Station Brackets | 633 | 354 |  | 0.55924
|  |  |  | Grounding | 621 | 178 |  | 0.28663
|  |  |  | Obstruction Brackets | 852 | 731 |  | 0.85798
|  |  |  | # Cables Pulled | 709 | 553 |  | 0.77997
77470 | 77595 | E1 | BER-HOY | 15" CMRS Install | 120 | 64 |  | 0.53333 | 0.55551
|  |  |  | Column Clamp | 519 | 233 |  | 0.44894
|  |  |  | Station Brackets | 319 | 258 |  | 0.80878
|  |  |  | Grounding | 143 | 101 |  | 0.70629
|  |  |  | Obstruction Brackets | 242 | 110 |  | 0.45455
|  |  |  | # Cables Pulled | 404 | 154 |  | 0.38119
77595 | 78230 | E1 | BER-HOY | 24" CMRS Install | 867 | 39 |  | 0.044983 | 0.38825
|  |  |  | Column Clamp | 819 | 106 |  | 0.12943
|  |  |  | Station Brackets | 327 | 305 |  | 0.93272
|  |  |  | Grounding | 565 | 154 |  | 0.27257
|  |  |  | Obstruction Brackets | 714 | 269 |  | 0.37675
|  |  |  | # Cables Pulled | 178 | 102 |  | 0.57303
78230 | 78515 | E1 | BER-HOY | 24" CMRS Install | 528 | 108 |  | 0.20455 | 0.28768
|  |  |  | Column Clamp | 319 | 193 |  | 0.60502
|  |  |  | Station Brackets | 771 | 18 |  | 0.023346
|  |  |  | Grounding | 312 | 12 |  | 0.038462
|  |  |  | Obstruction Brackets | 946 | 638 |  | 0.67442
|  |  |  | # Cables Pulled | 538 | 97 |  | 0.1803
|  | E2 | BERGEN | Cable Tray Brackets | 242 | 125 |  | 0.51653 | 0.46105
|  |  |  | Installing Tray | 899 | 698 |  | 0.77642
|  |  |  | Core Drilling | 686 | 233 |  | 0.33965
|  |  |  | Cable Pull | 794 | 168 |  | 0.21159
78515 | 78315 | E2 | BER-HOY | Steel Mess Supports | 304 | 169 |  | 0.55592 | 0.54201
|  |  |  | Messenger Clamps | 849 | 442 |  | 0.52061
|  |  |  | Messenger Wire Pull | 517 | 90 |  | 0.17408
|  |  |  | Messenger Wire Tension | 198 | 62 |  | 0.31313
|  |  |  | # Cables Pulled | 789 | 562 |  | 0.71229
|  |  |  | Messenger Straps | 375 | 366 |  | 0.976
78315 | 77655 | E2 | BER-HOY | 24" CMRS Install | 79 | 50 |  | 0.63291 | 0.50898
|  |  |  | Column Clamp | 863 | 219 |  | 0.25377
|  |  |  | Station Brackets | 943 | 782 |  | 0.82927
|  |  |  | Grounding | 90 | 72 |  | 0.8
|  |  |  | Obstruction Brackets | 96 | 36 |  | 0.375
|  |  |  | # Cables Pulled | 933 | 152 |  | 0.16292
77655 | 77585 | E2 | BER-HOY | 24" CMRS Install | 331 | 108 |  | 0.32628 | 0.3888
|  |  |  | Column Clamp | 584 | 468 |  | 0.80137
|  |  |  | Station Brackets | 650 | 551 |  | 0.84769
|  |  |  | Grounding | 576 | 12 |  | 0.020833
|  |  |  | Obstruction Brackets | 211 | 4 |  | 0.018957
|  |  |  | # Cables Pulled | 554 | 176 |  | 0.31769
77585 | 76845 | E2 | BER-HOY | 24" CMRS Install | 307 | 173 |  | 0.56352 | 0.39662
|  |  |  | Column Clamp | 724 | 11 |  | 0.015193
|  |  |  | Station Brackets | 693 | 256 |  | 0.36941
|  |  |  | Grounding | 78 | 58 |  | 0.74359
|  |  |  | Obstruction Brackets | 30 | 2 |  | 0.066667
|  |  |  | # Cables Pulled | 618 | 384 |  | 0.62136
76845 | 76150 | E2 | HOYT SCHERMERHORN | 24" CMRS Install | 190 | 100 |  | 0.52632 | 0.42695
|  |  |  | Column Clamp | 757 | 80 |  | 0.10568
|  |  |  | Station Brackets | 269 | 44 |  | 0.16357
|  |  |  | Grounding | 775 | 700 |  | 0.90323
|  |  |  | Obstruction Brackets | 789 | 472 |  | 0.59823
|  |  |  | # Cables Pulled | 699 | 185 |  | 0.26466
76150 | 76090 | E2 | HOY-FUL | 24" CMRS Install | 403 | 282 |  | 0.69975 | 0.46108
|  |  |  | Column Clamp | 933 | 664 |  | 0.71168
|  |  |  | Station Brackets | 391 | 66 |  | 0.1688
|  |  |  | Grounding | 879 | 103 |  | 0.11718
|  |  |  | Obstruction Brackets | 949 | 503 |  | 0.53003
|  |  |  | # Cables Pulled | 128 | 69 |  | 0.53906
76090 | 75950 | E2 | HOY-FUL | 24" CMRS Install | 441 | 193 |  | 0.43764 | 0.42026
|  |  |  | Column Clamp | 402 | 156 |  | 0.38806
|  |  |  | Station Brackets | 720 | 201 |  | 0.27917
|  |  |  | Grounding | 602 | 160 |  | 0.26578
|  |  |  | Obstruction Brackets | 296 | 279 |  | 0.94257
|  |  |  | # Cables Pulled | 48 | 10 |  | 0.20833
75950 | 75900 | E2 | HOY-FUL | Steel Mess Supports | 331 | 170 |  | 0.5136 | 0.39465
|  |  |  | Messenger Clamps | 36 | 21 |  | 0.58333
|  |  |  | Messenger Wire Pull | 470 | 56 |  | 0.11915
|  |  |  | Messenger Wire Tension | 211 | 147 |  | 0.69668
|  |  |  | # Cables Pulled | 371 | 45 |  | 0.12129
|  |  |  | Messenger Straps | 668 | 223 |  | 0.33383
75900 | 74590 | E2 | HOY-FUL | 24" CMRS Install | 148 | 51 |  | 0.34459 | 0.32704
|  |  |  | Column Clamp | 865 | 12 |  | 0.013873
|  |  |  | Station Brackets | 635 | 273 |  | 0.42992
|  |  |  | Grounding | 567 | 510 |  | 0.89947
|  |  |  | Obstruction Brackets | 444 | 36 |  | 0.081081
|  |  |  | # Cables Pulled | 238 | 46 |  | 0.19328
74590 | 74450 | E2 | HOY-FUL | Steel Mess Supports | 699 | 293 |  | 0.41917 | 0.51673
|  |  |  | Messenger Clamps | 522 | 227 |  | 0.43487
|  |  |  | Messenger Wire Pull | 542 | 413 |  | 0.76199
|  |  |  | Messenger Wire Tension | 617 | 304 |  | 0.49271
|  |  |  | # Cables Pulled | 308 | 47 |  | 0.1526
|  |  |  | Messenger Straps | 615 | 516 |  | 0.83902
74450 | 74070 | E2 | HOY-FUL | 24" CMRS Install | 284 | 78 |  | 0.27465 | 0.37624
|  |  |  | Column Clamp | 442 | 158 |  | 0.35747
|  |  |  | Station Brackets | 243 | 235 |  | 0.96708
|  |  |  | Grounding | 917 | 424 |  | 0.46238
|  |  |  | Obstruction Brackets | 402 | 54 |  | 0.13433
|  |  |  | # Cables Pulled | 585 | 36 |  | 0.061538
74070 | 74030 | E2 | HOY-FUL | 24" CMRS Install | 160 | 14 |  | 0.0875 | 0.63087
|  |  |  | Column Clamp | 478 | 420 |  | 0.87866
|  |  |  | Station Brackets | 190 | 112 |  | 0.58947
|  |  |  | Grounding | 855 | 812 |  | 0.94971
|  |  |  | Obstruction Brackets | 289 | 92 |  | 0.31834
|  |  |  | # Cables Pulled | 104 | 100 |  | 0.96154
74030 | 73690 | E2 | FULTON | 15" CMRS Install | 696 | 663 |  | 0.95259 | 0.39769
|  |  |  | Column Clamp | 723 | 241 |  | 0.33333
|  |  |  | Station Brackets | 923 | 53 |  | 0.057421
|  |  |  | Grounding | 291 | 170 |  | 0.58419
|  |  |  | Obstruction Brackets | 679 | 12 |  | 0.017673
|  |  |  | # Cables Pulled | 601 | 265 |  | 0.44093
73690 | 73250 | E2 | FULTON | 15" CMRS Install | 330 | 277 |  | 0.83939 | 0.38597 | Cable Management Takeoffs Cell F110* - 147LF instead of 440LF | Cable Management Takeoffs Cell F110* - 147LF instead of 440LF
|  |  |  | Column Clamp | 426 | 69 |  | 0.16197
|  |  |  | Station Brackets | 233 | 199 |  | 0.85408
|  |  |  | Grounding | 853 | 246 |  | 0.28839
|  |  |  | Obstruction Brackets | 463 | 48 |  | 0.10367
|  |  |  | # Cables Pulled | 161 | 11 |  | 0.068323
|  | E2 | FULTON | 15" CMRS Install | 752 | 0 |  | 0 | 0.33443
|  |  |  | Column Clamp | 56 | 1 |  | 0.017857
|  |  |  | Station Brackets | 696 | 80 |  | 0.11494
|  |  |  | Grounding | 916 | 823 |  | 0.89847
|  |  |  | Obstruction Brackets | 90 | 3 |  | 0.033333
|  |  |  | # Cables Pulled | 500 | 471 |  | 0.942
73250 | 72315 | E2 | FUL-CLI | 24" CMRS Install | 465 | 392 |  | 0.84301 | 0.73189
|  |  |  | Column Clamp | 514 | 375 |  | 0.72957
|  |  |  | Station Brackets | 964 | 753 |  | 0.78112
|  |  |  | Grounding | 649 | 561 |  | 0.86441
|  |  |  | Obstruction Brackets | 319 | 148 |  | 0.46395
|  |  |  | # Cables Pulled | 86 | 61 |  | 0.7093
94400 | 94989 | E2 | FUL-CLI | 24" CMRS Install | 167 | 90 |  | 0.53892 | 0.56032
|  |  |  | Column Clamp | 904 | 514 |  | 0.56858
|  |  |  | Station Brackets | 237 | 233 |  | 0.98312
|  |  |  | Grounding | 140 | 99 |  | 0.70714
|  |  |  | Obstruction Brackets | 982 | 327 |  | 0.33299
|  |  |  | # Cables Pulled | 848 | 196 |  | 0.23113
94989 | 95114 | E2 | FUL-CLI | 24" CMRS Install | 903 | 258 |  | 0.28571 | 0.45431
|  |  |  | Column Clamp | 591 | 514 |  | 0.86971
|  |  |  | Station Brackets | 379 | 179 |  | 0.4723
|  |  |  | Grounding | 134 | 7 |  | 0.052239
|  |  |  | Obstruction Brackets | 335 | 282 |  | 0.84179
|  |  |  | # Cables Pulled | 632 | 129 |  | 0.20411
94989 | 95114 | E2 | CLINTON-WASHINGTON | 24" CMRS Install | 860 | 541 |  | 0.62907 | 0.50047
|  |  |  | Column Clamp | 295 | 98 |  | 0.3322
|  |  |  | Station Brackets | 984 | 300 |  | 0.30488
|  |  |  | Grounding | 122 | 82 |  | 0.67213
|  |  |  | Obstruction Brackets | 593 | 410 |  | 0.6914
|  |  |  | # Cables Pulled | 737 | 275 |  | 0.37313
95503 | 95701 | E2 | CLINTON-WASHINGTON | 24" CMRS Install | 413 | 193 |  | 0.46731 | 0.57097
|  |  |  | Column Clamp | 886 | 625 |  | 0.70542
|  |  |  | Station Brackets | 118 | 50 |  | 0.42373
|  |  |  | Grounding | 227 | 154 |  | 0.67841
|  |  |  | Obstruction Brackets | 207 | 61 |  | 0.29469
|  |  |  | # Cables Pulled | 967 | 828 |  | 0.85626
95767 | 95852 | E2 | CLINTON-WASHINGTON | 24" CMRS Install | 694 | 5 |  | 0.0072046 | 0.52452
|  |  |  | Column Clamp | 669 | 617 |  | 0.92227
|  |  |  | Station Brackets | 526 | 217 |  | 0.41255
|  |  |  | Grounding | 911 | 779 |  | 0.8551
|  |  |  | Obstruction Brackets | 206 | 167 |  | 0.81068
|  |  |  | # Cables Pulled | 567 | 79 |  | 0.13933
95852 | 96366 | E2 | CLINTON-WASHINGTON | 24" CMRS Install | 266 | 253 |  | 0.95113 | 0.70251
|  |  |  | Column Clamp | 75 | 18 |  | 0.24
|  |  |  | Station Brackets | 604 | 480 |  | 0.7947
|  |  |  | Grounding | 403 | 374 |  | 0.92804
|  |  |  | Obstruction Brackets | 235 | 73 |  | 0.31064
|  |  |  | # Cables Pulled | 106 | 105 |  | 0.99057
96366 | 96432 | E2 | CLINTON-WASHINGTON | 24" CMRS Install | 889 | 143 |  | 0.16085 | 0.52501
|  |  |  | Column Clamp | 761 | 682 |  | 0.89619
|  |  |  | Station Brackets | 765 | 289 |  | 0.37778
|  |  |  | Grounding | 471 | 286 |  | 0.60722
|  |  |  | Obstruction Brackets | 55 | 39 |  | 0.70909
|  |  |  | # Cables Pulled | 183 | 73 |  | 0.39891
96432 | 96649 | E2 | CLINTON-WASHINGTON | 24" CMRS Install | 65 | 5 |  | 0.076923 | 0.57701
|  |  |  | Column Clamp | 123 | 118 |  | 0.95935
|  |  |  | Station Brackets | 379 | 167 |  | 0.44063
|  |  |  | Grounding | 199 | 75 |  | 0.37688
|  |  |  | Obstruction Brackets | 789 | 486 |  | 0.61597
|  |  |  | # Cables Pulled | 130 | 129 |  | 0.99231
95767 | 95852 | E2 | CLINTON-WASHINGTON | 24" CMRS Install | 444 | 227 |  | 0.51126 | 0.52993
|  |  |  | Column Clamp | 622 | 43 |  | 0.069132
|  |  |  | Station Brackets | 275 | 210 |  | 0.76364
|  |  |  | Grounding | 610 | 561 |  | 0.91967
|  |  |  | Obstruction Brackets | 580 | 203 |  | 0.35
|  |  |  | # Cables Pulled | 129 | 73 |  | 0.56589
95852 | 96366 | E2 | CLI-CLA | 24" CMRS Install | 427 | 319 |  | 0.74707 | 0.52246
|  |  |  | Column Clamp | 969 | 376 |  | 0.38803
|  |  |  | Station Brackets | 419 | 16 |  | 0.038186
|  |  |  | Grounding | 848 | 305 |  | 0.35967
|  |  |  | Obstruction Brackets | 618 | 617 |  | 0.99838
|  |  |  | # Cables Pulled | 464 | 280 |  | 0.60345
96366 | 96432 | E2 | CLI-CLA | 24" CMRS Install | 88 | 5 |  | 0.056818 | 0.35065
|  |  |  | Column Clamp | 476 | 303 |  | 0.63655
|  |  |  | Station Brackets | 300 | 102 |  | 0.34
|  |  |  | Grounding | 610 | 0 |  | 0
|  |  |  | Obstruction Brackets | 923 | 127 |  | 0.13759
|  |  |  | # Cables Pulled | 641 | 598 |  | 0.93292
96432 | 96649 | E2 | CLI-CLA | 24" CMRS Install | 711 | 551 |  | 0.77496 | 0.5447
|  |  |  | Column Clamp | 922 | 638 |  | 0.69197
|  |  |  | Station Brackets | 92 | 29 |  | 0.31522
|  |  |  | Grounding | 853 | 403 |  | 0.47245
|  |  |  | Obstruction Brackets | 873 | 515 |  | 0.58992
|  |  |  | # Cables Pulled | 701 | 297 |  | 0.42368
96649 | 96770 | E2 | CLI-CLA | 24" CMRS Install | 89 | 16 |  | 0.17978 | 0.2235
|  |  |  | Column Clamp | 885 | 406 |  | 0.45876
|  |  |  | Station Brackets | 324 | 102 |  | 0.31481
|  |  |  | Grounding | 24 | 4 |  | 0.16667
|  |  |  | Obstruction Brackets | 334 | 21 |  | 0.062874
|  |  |  | # Cables Pulled | 936 | 148 |  | 0.15812
96770 | 96990 | E2 | CLI-CLA | Steel Mess Supports | 742 | 426 |  | 0.57412 | 0.64221
|  |  |  | Messenger Clamps | 602 | 322 |  | 0.53488
|  |  |  | Messenger Wire Pull | 401 | 283 |  | 0.70574
|  |  |  | Messenger Wire Tension | 440 | 314 |  | 0.71364
|  |  |  | # Cables Pulled | 636 | 299 |  | 0.47013
|  |  |  | Messenger Straps | 661 | 565 |  | 0.85477
96990 | 97230 | E2 | CLASSON | 24" CMRS Install | 729 | 308 |  | 0.4225 | 0.55002
|  |  |  | Column Clamp | 493 | 469 |  | 0.95132
|  |  |  | Station Brackets | 198 | 150 |  | 0.75758
|  |  |  | Grounding | 59 | 17 |  | 0.28814
|  |  |  | Obstruction Brackets | 697 | 584 |  | 0.83788
|  |  |  | # Cables Pulled | 936 | 40 |  | 0.042735
97230 | 97538 | E2 | CLASSON | 24" CMRS Install | 887 | 664 |  | 0.74859 | 0.47323
|  |  |  | Column Clamp | 332 | 59 |  | 0.17771
|  |  |  | Station Brackets | 786 | 254 |  | 0.32316
|  |  |  | Grounding | 805 | 443 |  | 0.55031
|  |  |  | Obstruction Brackets | 463 | 115 |  | 0.24838
|  |  |  | # Cables Pulled | 206 | 163 |  | 0.79126
97538 | 97670 | E2 | CLASSON | 24" CMRS Install | 726 | 497 |  | 0.68457 | 0.62814
|  |  |  | Column Clamp | 614 | 328 |  | 0.5342
|  |  |  | Station Brackets | 156 | 112 |  | 0.71795
|  |  |  | Grounding | 718 | 218 |  | 0.30362
|  |  |  | Obstruction Brackets | 557 | 495 |  | 0.88869
|  |  |  | # Cables Pulled | 744 | 476 |  | 0.63978
97670 | 98015 | E2 | CLA-BED | Steel Mess Supports | 605 | 163 |  | 0.26942 | 0.71105
|  |  |  | Messenger Clamps | 579 | 466 |  | 0.80484
|  |  |  | Messenger Wire Pull | 283 | 124 |  | 0.43816
|  |  |  | Messenger Wire Tension | 65 | 65 |  | 1
|  |  |  | # Cables Pulled | 937 | 838 |  | 0.89434
|  |  |  | Messenger Straps | 591 | 508 |  | 0.85956
98015 | 98125 | E2 | CLA-BED | 24" CMRS Install | 497 | 341 |  | 0.68612 | 0.52141
|  |  |  | Column Clamp | 504 | 410 |  | 0.81349
|  |  |  | Station Brackets | 871 | 194 |  | 0.22273
|  |  |  | Grounding | 55 | 24 |  | 0.43636
|  |  |  | Obstruction Brackets | 191 | 141 |  | 0.73822
|  |  |  | # Cables Pulled | 596 | 138 |  | 0.23154
98125 | 98185 | E2 | CLA-BED | 24" CMRS Install | 935 | 488 |  | 0.52193 | 0.49256
|  |  |  | Column Clamp | 448 | 245 |  | 0.54688
|  |  |  | Station Brackets | 274 | 54 |  | 0.19708
|  |  |  | Grounding | 994 | 709 |  | 0.71328
|  |  |  | Obstruction Brackets | 410 | 276 |  | 0.67317
|  |  |  | # Cables Pulled | 693 | 210 |  | 0.30303
98185 | 98440 | E2 | CLA-BED | 24" CMRS Install | 684 | 599 |  | 0.87573 | 0.58913
|  |  |  | Column Clamp | 372 | 88 |  | 0.23656
|  |  |  | Station Brackets | 508 | 388 |  | 0.76378
|  |  |  | Grounding | 965 | 532 |  | 0.5513
|  |  |  | Obstruction Brackets | 125 | 86 |  | 0.688
|  |  |  | # Cables Pulled | 453 | 190 |  | 0.41943
|  | E2 | CLA-BED | Crossover (Arch Bar Installation) | 857 | 515 |  | 0.60093
98440 | 98586 | E2 | CLA-BED | 24" CMRS Install | 894 | 131 |  | 0.14653 | 0.43805
|  |  |  | Column Clamp | 926 | 785 |  | 0.84773
|  |  |  | Station Brackets | 794 | 642 |  | 0.80856
|  |  |  | Grounding | 639 | 361 |  | 0.56495
|  |  |  | Obstruction Brackets | 870 | 10 |  | 0.011494
|  |  |  | # Cables Pulled | 502 | 125 |  | 0.249
98586 | 98836 | E2 | CLA-BED | Steel Mess Supports | 627 | 624 |  | 0.99522 | 0.51566
|  |  |  | Messenger Clamps | 989 | 845 |  | 0.8544
|  |  |  | Messenger Wire Pull | 169 | 105 |  | 0.6213
|  |  |  | Messenger Wire Tension | 906 | 190 |  | 0.20971
|  |  |  | # Cables Pulled | 927 | 16 |  | 0.01726
|  |  |  | Messenger Straps | 813 | 322 |  | 0.39606
98836 | 99505 | E2 | BEDFORD NOSTRAND | Cable Tray Brackets | 101 | 89 |  | 0.88119 | 0.74845
|  |  |  | Installing Tray | 496 | 257 |  | 0.51815
|  |  |  | Core Drilling | 483 | 367 |  | 0.75983
|  |  |  | Cable Pull | 387 | 323 |  | 0.83463
99505 | 99950 | E2 | BED-MYR | Steel Mess Supports | 867 | 244 |  | 0.28143 | 0.36274
|  |  |  | Messenger Clamps | 284 | 176 |  | 0.61972
|  |  |  | Messenger Wire Pull | 962 | 457 |  | 0.47505
|  |  |  | Messenger Wire Tension | 951 | 91 |  | 0.095689
|  |  |  | # Cables Pulled | 768 | 495 |  | 0.64453
|  |  |  | Messenger Straps | 250 | 15 |  | 0.06
|  | E2 | CLA-BED | Crossover (Arch Bar Installation) | 60 | 14 |  | 0.23333
99950 | 100290 | E2 | BED-MYR | 24" CMRS Install | 42 | 0 |  | 0 | 0.49641
|  |  |  | Column Clamp | 29 | 13 |  | 0.44828
|  |  |  | Station Brackets | 402 | 78 |  | 0.19403
|  |  |  | Grounding | 650 | 594 |  | 0.91385
|  |  |  | Obstruction Brackets | 780 | 761 |  | 0.97564
|  |  |  | # Cables Pulled | 694 | 310 |  | 0.44669
100290 | 100740 | E2 | BED-MYR | 24" CMRS Install | 428 | 158 |  | 0.36916 | 0.4605
|  |  |  | Column Clamp | 680 | 367 |  | 0.53971
|  |  |  | Station Brackets | 583 | 316 |  | 0.54202
|  |  |  | Grounding | 34 | 13 |  | 0.38235
|  |  |  | Obstruction Brackets | 179 | 120 |  | 0.67039
|  |  |  | # Cables Pulled | 694 | 180 |  | 0.25937
100740 | 100792 | E2 | BED-MYR | 24" CMRS Install | 785 | 524 |  | 0.66752 | 0.44647
|  |  |  | Column Clamp | 200 | 6 |  | 0.03
|  |  |  | Station Brackets | 724 | 42 |  | 0.058011
|  |  |  | Grounding | 856 | 452 |  | 0.52804
|  |  |  | Obstruction Brackets | 698 | 518 |  | 0.74212
|  |  |  | # Cables Pulled | 369 | 241 |  | 0.65312
100792 | 101595 | E2 | BED-MYR | 24" CMRS Install | 954 | 486 |  | 0.50943 | 0.43679
|  |  |  | Column Clamp | 696 | 424 |  | 0.6092
|  |  |  | Station Brackets | 823 | 635 |  | 0.77157
|  |  |  | Grounding | 164 | 0 |  | 0
|  |  |  | Obstruction Brackets | 291 | 206 |  | 0.7079
|  |  |  | # Cables Pulled | 973 | 22 |  | 0.02261
101595 | 101688 | E2 | BED-MYR | 24" CMRS Install | 563 | 552 |  | 0.98046 | 0.60899
|  |  |  | Column Clamp | 885 | 840 |  | 0.94915
|  |  |  | Station Brackets | 501 | 48 |  | 0.095808
|  |  |  | Grounding | 64 | 62 |  | 0.96875
|  |  |  | Obstruction Brackets | 628 | 89 |  | 0.14172
|  |  |  | # Cables Pulled | 830 | 430 |  | 0.51807
101688 | 102400 | E2 | MYRTLE AVE | 15" CMRS Install | 927 | 399 |  | 0.43042 | 0.30674
|  |  |  | Column Clamp | 384 | 47 |  | 0.1224
|  |  |  | Station Brackets | 993 | 895 |  | 0.90131
|  |  |  | Grounding | 802 | 1 |  | 0.0012469
|  |  |  | Obstruction Brackets | 555 | 2 |  | 0.0036036
|  |  |  | # Cables Pulled | 270 | 103 |  | 0.38148
102400 | 102550 | E2 | MYR-FLU | Steel Mess Supports | 282 | 209 |  | 0.74113 | 0.65939
|  |  |  | Messenger Clamps | 930 | 871 |  | 0.93656
|  |  |  | Messenger Wire Pull | 340 | 265 |  | 0.77941
|  |  |  | Messenger Wire Tension | 770 | 583 |  | 0.75714
|  |  |  | # Cables Pulled | 807 | 531 |  | 0.65799
|  |  |  | Messenger Straps | 999 | 84 |  | 0.084084
102550 | 103165 | E2 | MYR-FLU | 15" CMRS Install | 100 | 79 |  | 0.79 | 0.51024
|  |  |  | Column Clamp | 170 | 33 |  | 0.19412
|  |  |  | Station Brackets | 303 | 83 |  | 0.27393
|  |  |  | Grounding | 579 | 213 |  | 0.36788
|  |  |  | Obstruction Brackets | 258 | 191 |  | 0.74031
|  |  |  | # Cables Pulled | 584 | 406 |  | 0.69521
103165 | 103230 | E2 | MYR-FLU | 15" CMRS Install | 341 | 277 |  | 0.81232 | 0.43045
|  |  |  | Column Clamp | 16 | 7 |  | 0.4375
|  |  |  | Station Brackets | 558 | 342 |  | 0.6129
|  |  |  | Grounding | 444 | 30 |  | 0.067568
|  |  |  | Obstruction Brackets | 562 | 291 |  | 0.51779
|  |  |  | # Cables Pulled | 869 | 117 |  | 0.13464
103230 | 103809 | E2 | MYR-FLU | 15" CMRS Install | 186 | 25 |  | 0.13441 | 0.41612
|  |  |  | Column Clamp | 55 | 25 |  | 0.45455
|  |  |  | Station Brackets | 417 | 325 |  | 0.77938
|  |  |  | Grounding | 992 | 289 |  | 0.29133
|  |  |  | Obstruction Brackets | 54 | 10 |  | 0.18519
|  |  |  | # Cables Pulled | 925 | 603 |  | 0.65189
103809 | 103902 | E2 | MYR-FLU | 15" CMRS Install | 660 | 468 |  | 0.70909 | 0.55875
|  |  |  | Column Clamp | 95 | 72 |  | 0.75789
|  |  |  | Station Brackets | 997 | 583 |  | 0.58475
|  |  |  | Grounding | 273 | 27 |  | 0.098901
|  |  |  | Obstruction Brackets | 639 | 587 |  | 0.91862
|  |  |  | # Cables Pulled | 745 | 211 |  | 0.28322
103902 | 104595 | E2 | FLUSHING | 15" CMRS Install | 542 | 215 |  | 0.39668 | 0.48294
|  |  |  | Column Clamp | 866 | 68 |  | 0.078522
|  |  |  | Station Brackets | 992 | 413 |  | 0.41633
|  |  |  | Grounding | 29 | 10 |  | 0.34483
|  |  |  | Obstruction Brackets | 46 | 32 |  | 0.69565
|  |  |  | # Cables Pulled | 291 | 281 |  | 0.96564
104595 | 104750 | E2 | FLU-BRO | Steel Mess Supports | 83 | 22 |  | 0.26506 | 0.19891
|  |  |  | Messenger Clamps | 173 | 88 |  | 0.50867
|  |  |  | Messenger Wire Pull | 307 | 44 |  | 0.14332
|  |  |  | Messenger Wire Tension | 505 | 61 |  | 0.12079
|  |  |  | # Cables Pulled | 686 | 65 |  | 0.094752
|  |  |  | Messenger Straps | 690 | 42 |  | 0.06087
104750 | 105270 | E2 | FLU-BRO | 15" CMRS Install | 904 | 506 |  | 0.55973 | 0.51039
|  |  |  | Column Clamp | 462 | 139 |  | 0.30087
|  |  |  | Station Brackets | 941 | 313 |  | 0.33262
|  |  |  | Grounding | 409 | 209 |  | 0.511
|  |  |  | Obstruction Brackets | 449 | 184 |  | 0.4098
|  |  |  | # Cables Pulled | 716 | 679 |  | 0.94832
105270 | 105930 | E2 | FLU-BRO | 15" CMRS Install | 672 | 313 |  | 0.46577 | 0.36168
|  |  |  | Column Clamp | 69 | 0 |  | 0
|  |  |  | Station Brackets | 290 | 58 |  | 0.2
|  |  |  | Grounding | 356 | 193 |  | 0.54213
|  |  |  | Obstruction Brackets | 485 | 1 |  | 0.0020619
|  |  |  | # Cables Pulled | 878 | 843 |  | 0.96014
105930 | 106003 | E2 | FLU-BRO | 15" CMRS Install | 693 | 494 |  | 0.71284 | 0.50563
|  |  |  | Column Clamp | 421 | 51 |  | 0.12114
|  |  |  | Station Brackets | 63 | 47 |  | 0.74603
|  |  |  | Grounding | 550 | 363 |  | 0.66
|  |  |  | Obstruction Brackets | 448 | 273 |  | 0.60938
|  |  |  | # Cables Pulled | 282 | 52 |  | 0.1844
106003 | 106648 | E2 | BROADWAY | 15" CMRS Install | 283 | 225 |  | 0.79505 | 0.63341
|  |  |  | Column Clamp | 977 | 87 |  | 0.089048
|  |  |  | Station Brackets | 90 | 47 |  | 0.52222
|  |  |  | Grounding | 341 | 262 |  | 0.76833
|  |  |  | Obstruction Brackets | 669 | 578 |  | 0.86398
|  |  |  | # Cables Pulled | 970 | 739 |  | 0.76186
|  | E2 | BROADWAY | 15" CMRS Install | 260 | 92 |  | 0.35385 | 0.57887
|  |  |  | Column Clamp | 167 | 122 |  | 0.73054
|  |  |  | Station Brackets | 691 | 296 |  | 0.42836
|  |  |  | Grounding | 312 | 212 |  | 0.67949
|  |  |  | Obstruction Brackets | 611 | 599 |  | 0.98036
|  |  |  | # Cables Pulled | 489 | 147 |  | 0.30061
|  | E2 | BROADWAY | 15" CMRS Install | 121 | 4 |  | 0.033058 | 0.44481
|  |  |  | Column Clamp | 868 | 764 |  | 0.88018
|  |  |  | Station Brackets | 489 | 110 |  | 0.22495
|  |  |  | Grounding | 638 | 331 |  | 0.51881
|  |  |  | Obstruction Brackets | 914 | 708 |  | 0.77462
|  |  |  | # Cables Pulled | 451 | 107 |  | 0.23725
106650 | 106920 | E2 | BRO-MET | Steel Mess Supports | 620 | 455 |  | 0.73387 | 0.30889
|  |  |  | Messenger Clamps | 324 | 117 |  | 0.36111
|  |  |  | Messenger Wire Pull | 387 | 44 |  | 0.1137
|  |  |  | Messenger Wire Tension | 403 | 147 |  | 0.36476
|  |  |  | # Cables Pulled | 795 | 90 |  | 0.11321
|  |  |  | Messenger Straps | 216 | 36 |  | 0.16667
106918 | 107620 | E2 | BRO-MET | 15" CMRS Install | 738 | 234 |  | 0.31707 | 0.39675
|  |  |  | Column Clamp | 628 | 110 |  | 0.17516
|  |  |  | Station Brackets | 109 | 22 |  | 0.20183
|  |  |  | Grounding | 479 | 218 |  | 0.45511
|  |  |  | Obstruction Brackets | 757 | 647 |  | 0.85469
|  |  |  | # Cables Pulled | 624 | 235 |  | 0.3766
107620 | 107683 | E2 | BRO-MET | 15" CMRS Install | 503 | 336 |  | 0.66799 | 0.57088
|  |  |  | Column Clamp | 695 | 569 |  | 0.81871
|  |  |  | Station Brackets | 413 | 9 |  | 0.021792
|  |  |  | Grounding | 947 | 547 |  | 0.57761
|  |  |  | Obstruction Brackets | 906 | 412 |  | 0.45475
|  |  |  | # Cables Pulled | 701 | 620 |  | 0.88445
107683 | 108360 | E2 | BRO-MET | 15" CMRS Install | 635 | 344 |  | 0.54173 | 0.33446
|  |  |  | Column Clamp | 805 | 68 |  | 0.084472
|  |  |  | Station Brackets | 278 | 266 |  | 0.95683
|  |  |  | Grounding | 669 | 9 |  | 0.013453
|  |  |  | Obstruction Brackets | 127 | 22 |  | 0.17323
|  |  |  | # Cables Pulled | 751 | 178 |  | 0.23702
108360 | 109235 | E2 | METROPOLITAN | 15" CMRS Install | 994 | 450 |  | 0.45272 | 0.27089
|  |  |  | Column Clamp | 930 | 54 |  | 0.058065
|  |  |  | Station Brackets | 481 | 121 |  | 0.25156
|  |  |  | Grounding | 575 | 18 |  | 0.031304
|  |  |  | Obstruction Brackets | 320 | 152 |  | 0.475
|  |  |  | # Cables Pulled | 614 | 219 |  | 0.35668
109235 | 110795 | E2 | MET-NAS | 24" CMRS Install | 810 | 113 |  | 0.13951 | 0.39597
|  |  |  | Column Clamp | 995 | 425 |  | 0.42714
|  |  |  | Station Brackets | 845 | 797 |  | 0.9432
|  |  |  | Grounding | 638 | 78 |  | 0.12226
|  |  |  | Obstruction Brackets | 672 | 144 |  | 0.21429
|  |  |  | # Cables Pulled | 272 | 144 |  | 0.52941
110795 | 110865 | E2 | MET-NAS | 24" CMRS Install | 986 | 447 |  | 0.45335 | 0.38781
|  |  |  | Column Clamp | 64 | 23 |  | 0.35938
|  |  |  | Station Brackets | 542 | 1 |  | 0.001845
|  |  |  | Grounding | 652 | 414 |  | 0.63497
|  |  |  | Obstruction Brackets | 416 | 166 |  | 0.39904
|  |  |  | # Cables Pulled | 253 | 121 |  | 0.47826
110865 | 113020 | E2 | MET-NAS | 24" CMRS Install | 44 | 30 |  | 0.68182 | 0.45692
|  |  |  | Column Clamp | 326 | 145 |  | 0.44479
|  |  |  | Station Brackets | 633 | 389 |  | 0.61453
|  |  |  | Grounding | 655 | 334 |  | 0.50992
|  |  |  | Obstruction Brackets | 958 | 348 |  | 0.36326
|  |  |  | # Cables Pulled | 967 | 123 |  | 0.1272
113020 | 113155 | E2 | MET-NAS | 24" CMRS Install | 455 | 38 |  | 0.083516 | 0.31296
|  |  |  | Column Clamp | 557 | 41 |  | 0.073609
|  |  |  | Station Brackets | 34 | 18 |  | 0.52941
|  |  |  | Grounding | 825 | 365 |  | 0.44242
|  |  |  | Obstruction Brackets | 661 | 326 |  | 0.49319
|  |  |  | # Cables Pulled | 579 | 148 |  | 0.25561
113155 | 113815 | E2 | NASSAU | 24" CMRS Install | 697 | 312 |  | 0.44763 | 0.46238
|  |  |  | Column Clamp | 14 | 5 |  | 0.35714
|  |  |  | Station Brackets | 936 | 591 |  | 0.63141
|  |  |  | Grounding | 928 | 740 |  | 0.79741
|  |  |  | Obstruction Brackets | 738 | 192 |  | 0.26016
|  |  |  | # Cables Pulled | 328 | 92 |  | 0.28049
113815 | 114105 | E2 | NAS-GRE | Steel Mess Supports | 185 | 102 |  | 0.55135 | 0.37209
|  |  |  | Messenger Clamps | 725 | 25 |  | 0.034483
|  |  |  | Messenger Wire Pull | 629 | 30 |  | 0.047695
|  |  |  | Messenger Wire Tension | 917 | 601 |  | 0.6554
|  |  |  | # Cables Pulled | 87 | 51 |  | 0.58621
|  |  |  | Messenger Straps | 982 | 351 |  | 0.35743
114105 | 114730 | E2 | NAS-GRE | 24" CMRS Install | 357 | 263 |  | 0.73669 | 0.40009
|  |  |  | Column Clamp | 336 | 22 |  | 0.065476
|  |  |  | Station Brackets | 274 | 96 |  | 0.35036
|  |  |  | Grounding | 522 | 234 |  | 0.44828
|  |  |  | Obstruction Brackets | 935 | 508 |  | 0.54332
|  |  |  | # Cables Pulled | 979 | 251 |  | 0.25638
114730 | 114910 | E2 | NAS-GRE | Steel Mess Supports | 149 | 73 |  | 0.48993 | 0.33749
|  |  |  | Messenger Clamps | 245 | 114 |  | 0.46531
|  |  |  | Messenger Wire Pull | 520 | 124 |  | 0.23846
|  |  |  | Messenger Wire Tension | 106 | 43 |  | 0.40566
|  |  |  | # Cables Pulled | 40 | 13 |  | 0.325
|  |  |  | Messenger Straps | 537 | 54 |  | 0.10056
114910 | 115625 | E2 | NAS-GRE | 24" CMRS Install | 280 | 175 |  | 0.625 | 0.55551
|  |  |  | Column Clamp | 943 | 330 |  | 0.34995
|  |  |  | Station Brackets | 989 | 610 |  | 0.61678
|  |  |  | Grounding | 920 | 829 |  | 0.90109
|  |  |  | Obstruction Brackets | 663 | 417 |  | 0.62896
|  |  |  | # Cables Pulled | 71 | 15 |  | 0.21127
115625 | 116435 | E2 | GREENPOINT | 24" CMRS Install | 662 | 215 |  | 0.32477 | 0.64963
|  |  |  | Column Clamp | 92 | 59 |  | 0.6413
|  |  |  | Station Brackets | 451 | 404 |  | 0.89579
|  |  |  | Grounding | 743 | 269 |  | 0.36205
|  |  |  | Obstruction Brackets | 279 | 253 |  | 0.90681
|  |  |  | # Cables Pulled | 425 | 326 |  | 0.76706
116435 | 117130 | E2 | GRE-21S | 24" CMRS Install | 534 | 443 |  | 0.82959 | 0.55657
|  |  |  | Column Clamp | 83 | 33 |  | 0.39759
|  |  |  | Station Brackets | 293 | 175 |  | 0.59727
|  |  |  | Grounding | 718 | 160 |  | 0.22284
|  |  |  | Obstruction Brackets | 503 | 282 |  | 0.56064
|  |  |  | # Cables Pulled | 581 | 425 |  | 0.7315
|  | E2 | GRE-21S | Crossover (Arch Bar Installation) | 270 | 217 |  | 0.8037
117130 | 121035 | E2 | GRE-21S | 24" CMRS Install | 34 | 28 |  | 0.82353 | 0.56983
|  |  |  | Column Clamp | 939 | 4 |  | 0.0042599
|  |  |  | Station Brackets | 888 | 405 |  | 0.45608
|  |  |  | Grounding | 62 | 33 |  | 0.53226
|  |  |  | Obstruction Brackets | 173 | 169 |  | 0.97688
|  |  |  | # Cables Pulled | 500 | 313 |  | 0.626
121035 | 122030 | E2 | 21ST STATION | Steel Mess Supports | 706 | 2 |  | 0.0028329 | 0.50589
|  |  |  | Messenger Clamps | 787 | 469 |  | 0.59593
|  |  |  | Messenger Wire Pull | 959 | 534 |  | 0.55683
|  |  |  | Messenger Wire Tension | 712 | 645 |  | 0.9059
|  |  |  | # Cables Pulled | 731 | 458 |  | 0.62654
|  |  |  | Messenger Straps | 406 | 141 |  | 0.34729
122030 | 122430 | E2 | 21S-COU | 24" CMRS Install | 237 | 188 |  | 0.79325 | 0.62004
|  |  |  | Column Clamp | 842 | 32 |  | 0.038005
|  |  |  | Station Brackets | 292 | 255 |  | 0.87329
|  |  |  | Grounding | 703 | 498 |  | 0.70839
|  |  |  | Obstruction Brackets | 152 | 101 |  | 0.66447
|  |  |  | # Cables Pulled | 14 | 9 |  | 0.64286
122430 | 122660 | E2 | 21S-COU | Steel Mess Supports | 297 | 53 |  | 0.17845 | 0.55536
|  |  |  | Messenger Clamps | 472 | 180 |  | 0.38136
|  |  |  | Messenger Wire Pull | 177 | 67 |  | 0.37853
|  |  |  | Messenger Wire Tension | 102 | 59 |  | 0.57843
|  |  |  | # Cables Pulled | 331 | 326 |  | 0.98489
|  |  |  | Messenger Straps | 59 | 49 |  | 0.83051
122660 | 122827 | E2 | 21S-COU | 24" CMRS Install | 45 | 6 |  | 0.13333 | 0.43219
|  |  |  | Column Clamp | 395 | 242 |  | 0.61266
|  |  |  | Station Brackets | 681 | 568 |  | 0.83407
|  |  |  | Grounding | 33 | 2 |  | 0.060606
|  |  |  | Obstruction Brackets | 431 | 186 |  | 0.43155
|  |  |  | # Cables Pulled | 979 | 510 |  | 0.52094
122827 | 123085 | E2 | 21S-COU | Steel Mess Supports | 253 | 122 |  | 0.48221 | 0.3882
|  |  |  | Messenger Clamps | 559 | 512 |  | 0.91592
|  |  |  | Messenger Wire Pull | 560 | 78 |  | 0.13929
|  |  |  | Messenger Wire Tension | 412 | 51 |  | 0.12379
|  |  |  | # Cables Pulled | 732 | 22 |  | 0.030055
|  |  |  | Messenger Straps | 696 | 444 |  | 0.63793
123085 | 123690 | E2 | COURT SQ | Cable Tray Brackets | 514 | 103 |  | 0.20039 | 0.38436
|  |  |  | Installing Tray | 716 | 501 |  | 0.69972
|  |  |  | Core Drilling | 561 | 35 |  | 0.062389
|  |  |  | Cable Pull | 654 | 376 |  | 0.57492
123690 | 123750 | E2 | COU-QUE | Steel Mess Supports | 148 | 80 |  | 0.54054 | 0.38272
|  |  |  | Messenger Clamps | 266 | 61 |  | 0.22932
|  |  |  | Messenger Wire Pull | 363 | 95 |  | 0.26171
|  |  |  | Messenger Wire Tension | 177 | 28 |  | 0.15819
|  |  |  | # Cables Pulled | 521 | 59 |  | 0.11324
|  |  |  | Messenger Straps | 150 | 149 |  | 0.99333
123750 | 123950 | E2 | COU-QUE | Steel Mess Supports | 811 | 383 |  | 0.47226 | 0.50413
|  |  |  | Messenger Clamps | 166 | 20 |  | 0.12048
|  |  |  | Messenger Wire Pull | 32 | 24 |  | 0.75
|  |  |  | Messenger Wire Tension | 144 | 140 |  | 0.97222
|  |  |  | # Cables Pulled | 228 | 37 |  | 0.16228
|  |  |  | Messenger Straps | 694 | 380 |  | 0.54755
123950 | 124050 | E2 | COU-QUE | Steel Mess Supports | 987 | 158 |  | 0.16008 | 0.57918
|  |  |  | Messenger Clamps | 18 | 15 |  | 0.83333
|  |  |  | Messenger Wire Pull | 727 | 545 |  | 0.74966
|  |  |  | Messenger Wire Tension | 254 | 201 |  | 0.79134
|  |  |  | # Cables Pulled | 272 | 152 |  | 0.55882
|  |  |  | Messenger Straps | 728 | 278 |  | 0.38187
124050 | 124190 | E2 | COU-QUE | Steel Mess Supports | 476 | 428 |  | 0.89916 | 0.73627
|  |  |  | Messenger Clamps | 842 | 698 |  | 0.82898
|  |  |  | Messenger Wire Pull | 460 | 296 |  | 0.64348
|  |  |  | Messenger Wire Tension | 838 | 746 |  | 0.89021
|  |  |  | # Cables Pulled | 713 | 320 |  | 0.44881
|  |  |  | Messenger Straps | 604 | 427 |  | 0.70695
124190 | 124490 | E2 | COU-QUE | Steel Mess Supports | 871 | 308 |  | 0.35362 | 0.26592
|  |  |  | Messenger Clamps | 436 | 52 |  | 0.11927
|  |  |  | Messenger Wire Pull | 823 | 444 |  | 0.53949
|  |  |  | Messenger Wire Tension | 648 | 84 |  | 0.12963
|  |  |  | # Cables Pulled | 252 | 99 |  | 0.39286
|  |  |  | Messenger Straps | 511 | 31 |  | 0.060665
124490 | 124700 | E2 | COU-QUE | Steel Mess Supports | 699 | 512 |  | 0.73247 | 0.6118
|  |  |  | Messenger Clamps | 587 | 573 |  | 0.97615
|  |  |  | Messenger Wire Pull | 568 | 28 |  | 0.049296
|  |  |  | Messenger Wire Tension | 948 | 760 |  | 0.80169
|  |  |  | # Cables Pulled | 150 | 64 |  | 0.42667
|  |  |  | Messenger Straps | 542 | 371 |  | 0.6845
124700 | 125010 | E2 | COU-QUE | Steel Mess Supports | 353 | 278 |  | 0.78754 | 0.60364
|  |  |  | Messenger Clamps | 714 | 454 |  | 0.63585
|  |  |  | Messenger Wire Pull | 336 | 164 |  | 0.4881
|  |  |  | Messenger Wire Tension | 378 | 0 |  | 0
|  |  |  | # Cables Pulled | 353 | 319 |  | 0.90368
|  |  |  | Messenger Straps | 269 | 217 |  | 0.80669
|  | E2 | COU-QUE | Crossover (Arch Bar Installation) | 859 | 507 |  | 0.59022
75650 | 78244 | B3 | BERGEN ST | Steel Mess Supports | 68 | 22 |  | 0.32353 | 0.46455
|  |  |  | Messenger Clamps | 996 | 556 |  | 0.55823
|  |  |  | Messenger Wire Pull | 448 | 12 |  | 0.026786
|  |  |  | Messenger Wire Tension | 196 | 130 |  | 0.66327
|  |  |  | # Cables Pulled | 280 | 94 |  | 0.33571
|  |  |  | Messenger Straps | 183 | 161 |  | 0.87978
|  | B3 | BER-JAY | Steel Mess Supports | 12 | 4 |  | 0.33333 | 0.64136
|  |  |  | Messenger Clamps | 144 | 112 |  | 0.77778
|  |  |  | Messenger Wire Pull | 529 | 515 |  | 0.97353
|  |  |  | Messenger Wire Tension | 528 | 9 |  | 0.017045
|  |  |  | # Cables Pulled | 558 | 490 |  | 0.87814
|  |  |  | Messenger Straps | 319 | 277 |  | 0.86834
|  | B4 | BER-JAY | Steel Mess Supports | 201 | 76 |  | 0.37811 | 0.57456
|  |  |  | Messenger Clamps | 579 | 424 |  | 0.7323
|  |  |  | Messenger Wire Pull | 863 | 449 |  | 0.52028
|  |  |  | Messenger Wire Tension | 516 | 297 |  | 0.57558
|  |  |  | # Cables Pulled | 998 | 478 |  | 0.47896
|  |  |  | Messenger Straps | 185 | 141 |  | 0.76216
|  | E3/E4 | COURT SQ | Steel Mess Supports | 249 | 49 |  | 0.19679 | 0.45195
|  |  |  | Messenger Clamps | 948 | 352 |  | 0.37131
|  |  |  | Messenger Wire Pull | 711 | 528 |  | 0.74262
|  |  |  | Messenger Wire Tension | 21 | 7 |  | 0.33333
|  |  |  | # Cables Pulled | 311 | 226 |  | 0.72669
|  |  |  | Messenger Straps | 698 | 238 |  | 0.34097
75640 | 75300 | B1 | BER-CAR | Steel Mess Supports | 379 | 188 |  | 0.49604 | 0.546
|  |  |  | Messenger Clamps | 378 | 299 |  | 0.79101
|  |  |  | Messenger Wire Pull | 293 | 67 |  | 0.22867
|  |  |  | Messenger Wire Tension | 360 | 100 |  | 0.27778
|  |  |  | # Cables Pulled | 108 | 100 |  | 0.92593
|  |  |  | Messenger Straps | 221 | 123 |  | 0.55656
68570 | 68330 | B3 | 4TH AVE | Steel Mess Supports | 262 | 58 |  | 0.22137 | 0.55418
|  |  |  | Messenger Clamps | 23 | 16 |  | 0.69565
|  |  |  | Messenger Wire Pull | 758 | 574 |  | 0.75726
|  |  |  | Messenger Wire Tension | 402 | 11 |  | 0.027363
|  |  |  | # Cables Pulled | 618 | 424 |  | 0.68608
|  |  |  | Messenger Straps | 367 | 344 |  | 0.93733
68330 | 68030 | B3 | 4AV-7AV | Steel Mess Supports | 980 | 763 |  | 0.77857 | 0.4047
|  |  |  | Messenger Clamps | 495 | 121 |  | 0.24444
|  |  |  | Messenger Wire Pull | 867 | 0 |  | 0
|  |  |  | Messenger Wire Tension | 840 | 133 |  | 0.15833
|  |  |  | # Cables Pulled | 943 | 483 |  | 0.5122
|  |  |  | Messenger Straps | 863 | 634 |  | 0.73465
66070 | 66000 | B3 | 4AV-7AV | Steel Mess Supports | 305 | 12 |  | 0.039344 | 0.42153
|  |  |  | Messenger Clamps | 164 | 136 |  | 0.82927
|  |  |  | Messenger Wire Pull | 207 | 47 |  | 0.22705
|  |  |  | Messenger Wire Tension | 307 | 206 |  | 0.67101
|  |  |  | # Cables Pulled | 234 | 139 |  | 0.59402
|  |  |  | Messenger Straps | 368 | 62 |  | 0.16848
60350 | 60000 | B1 | 15S-FOR | Steel Mess Supports | 810 | 105 |  | 0.12963 | 0.46894
|  |  |  | Messenger Clamps | 336 | 29 |  | 0.08631
|  |  |  | Messenger Wire Pull | 520 | 356 |  | 0.68462
|  |  |  | Messenger Wire Tension | 889 | 874 |  | 0.98313
|  |  |  | # Cables Pulled | 159 | 130 |  | 0.81761
|  |  |  | Messenger Straps | 454 | 51 |  | 0.11233
56440 | 56350 | B1 | FOR-CHU | Steel Mess Supports | 661 | 609 |  | 0.92133 | 0.59377
|  |  |  | Messenger Clamps | 713 | 301 |  | 0.42216
|  |  |  | Messenger Wire Pull | 671 | 360 |  | 0.53651
|  |  |  | Messenger Wire Tension | 682 | 681 |  | 0.99853
|  |  |  | # Cables Pulled | 886 | 22 |  | 0.024831
|  |  |  | Messenger Straps | 540 | 356 |  | 0.65926
55580 | 54500 | B2 | CHU-DIT | Steel Mess Supports | 162 | 157 |  | 0.96914 | 0.5497
|  |  |  | Messenger Clamps | 301 | 76 |  | 0.25249
|  |  |  | Messenger Wire Pull | 900 | 49 |  | 0.054444
|  |  |  | Messenger Wire Tension | 785 | 734 |  | 0.93503
|  |  |  | # Cables Pulled | 71 | 44 |  | 0.61972
|  |  |  | Messenger Straps | 674 | 315 |  | 0.46736
54730 | 55000 | B2 | CHU-DIT | Steel Mess Supports | 862 | 665 |  | 0.77146 | 0.57647
|  |  |  | Messenger Clamps | 877 | 150 |  | 0.17104
|  |  |  | Messenger Wire Pull | 865 | 865 |  | 1
|  |  |  | Messenger Wire Tension | 703 | 219 |  | 0.31152
|  |  |  | # Cables Pulled | 342 | 181 |  | 0.52924
|  |  |  | Messenger Straps | 413 | 279 |  | 0.67554
55485 | 55725 | B2 | CHU-DIT | Steel Mess Supports | 686 | 222 |  | 0.32362 | 0.48279
|  |  |  | Messenger Clamps | 494 | 367 |  | 0.74291
|  |  |  | Messenger Wire Pull | 554 | 543 |  | 0.98014
|  |  |  | Messenger Wire Tension | 620 | 196 |  | 0.31613
|  |  |  | # Cables Pulled | 781 | 62 |  | 0.079385
|  |  |  | Messenger Straps | 165 | 75 |  | 0.45455
55725 | 56635 | B2 | CHURCH AVE | Steel Mess Supports | 232 | 227 |  | 0.97845 | 0.68678
|  |  |  | Messenger Clamps | 367 | 219 |  | 0.59673
|  |  |  | Messenger Wire Pull | 909 | 764 |  | 0.84048
|  |  |  | Messenger Wire Tension | 866 | 484 |  | 0.55889
|  |  |  | # Cables Pulled | 83 | 50 |  | 0.60241
|  |  |  | Messenger Straps | 572 | 311 |  | 0.54371
57320 | 57445 | B2 | CHU-FOR | Steel Mess Supports | 77 | 9 |  | 0.11688 | 0.63631
|  |  |  | Messenger Clamps | 266 | 124 |  | 0.46617
|  |  |  | Messenger Wire Pull | 184 | 154 |  | 0.83696
|  |  |  | Messenger Wire Tension | 940 | 808 |  | 0.85957
|  |  |  | # Cables Pulled | 508 | 296 |  | 0.58268
|  |  |  | Messenger Straps | 293 | 280 |  | 0.95563
60165 | 60620 | B2 | 15S-FOR | Steel Mess Supports | 845 | 7 |  | 0.008284 | 0.45517
|  |  |  | Messenger Clamps | 793 | 691 |  | 0.87137
|  |  |  | Messenger Wire Pull | 71 | 10 |  | 0.14085
|  |  |  | Messenger Wire Tension | 259 | 115 |  | 0.44402
|  |  |  | # Cables Pulled | 231 | 190 |  | 0.82251
|  |  |  | Messenger Straps | 241 | 107 |  | 0.44398
62560 | 63425 | B2 | 15TH STREET PROSPECT PARK | Steel Mess Supports | 765 | 765 |  | 1 | 0.60286
|  |  |  | Messenger Clamps | 27 | 11 |  | 0.40741
|  |  |  | Messenger Wire Pull | 743 | 437 |  | 0.58816
|  |  |  | Messenger Wire Tension | 877 | 251 |  | 0.2862
|  |  |  | # Cables Pulled | 560 | 506 |  | 0.90357
|  |  |  | Messenger Straps | 88 | 38 |  | 0.43182
67950 | 68330 | B4/B2 | 4AV-7AV | Steel Mess Supports | 33 | 11 |  | 0.33333 | 0.43962
|  |  |  | Messenger Clamps | 490 | 159 |  | 0.32449
|  |  |  | Messenger Wire Pull | 492 | 462 |  | 0.93902
|  |  |  | Messenger Wire Tension | 446 | 288 |  | 0.64574
|  |  |  | # Cables Pulled | 306 | 1 |  | 0.003268
|  |  |  | Messenger Straps | 911 | 357 |  | 0.39188
74740 | 74840 | B2 | CAR-BER | Steel Mess Supports | 827 | 411 |  | 0.49698 | 0.43331
|  |  |  | Messenger Clamps | 42 | 8 |  | 0.19048
|  |  |  | Messenger Wire Pull | 543 | 105 |  | 0.19337
|  |  |  | Messenger Wire Tension | 384 | 146 |  | 0.38021
|  |  |  | # Cables Pulled | 339 | 213 |  | 0.62832
|  |  |  | Messenger Straps | 38 | 27 |  | 0.71053
75395 | 75650 | B2 | CAR-BER | Steel Mess Supports | 726 | 462 |  | 0.63636 | 0.68446
|  |  |  | Messenger Clamps | 73 | 44 |  | 0.60274
|  |  |  | Messenger Wire Pull | 443 | 223 |  | 0.50339
|  |  |  | Messenger Wire Tension | 269 | 169 |  | 0.62825
|  |  |  | # Cables Pulled | 859 | 651 |  | 0.75786
|  |  |  | Messenger Straps | 916 | 896 |  | 0.97817
78905 | 75950 | B3 | JAY-BER | Steel Mess Supports | 777 | 702 |  | 0.90347 | 0.44541
|  |  |  | Messenger Clamps | 842 | 56 |  | 0.066508
|  |  |  | Messenger Wire Pull | 732 | 463 |  | 0.63251
|  |  |  | Messenger Wire Tension | 142 | 51 |  | 0.35915
|  |  |  | # Cables Pulled | 995 | 421 |  | 0.42312
|  |  |  | Messenger Straps | 431 | 124 |  | 0.2877
75950 | 75650 | B3 | BERGEN ST | Steel Mess Supports | 584 | 58 |  | 0.099315 | 0.56238
|  |  |  | Messenger Clamps | 445 | 161 |  | 0.3618
|  |  |  | Messenger Wire Pull | 186 | 112 |  | 0.60215
|  |  |  | Messenger Wire Tension | 566 | 467 |  | 0.82509
|  |  |  | # Cables Pulled | 570 | 363 |  | 0.63684
|  |  |  | Messenger Straps | 603 | 512 |  | 0.84909
75650 | 75420 | B3 | BER-CAR | Steel Mess Supports | 385 | 116 |  | 0.3013 | 0.4171
|  |  |  | Messenger Clamps | 430 | 46 |  | 0.10698
|  |  |  | Messenger Wire Pull | 473 | 439 |  | 0.92812
|  |  |  | Messenger Wire Tension | 179 | 3 |  | 0.01676
|  |  |  | # Cables Pulled | 285 | 58 |  | 0.20351
|  |  |  | Messenger Straps | 37 | 35 |  | 0.94595
73285 | 72960 | B3 | BER-CAR | Steel Mess Supports | 239 | 165 |  | 0.69038 | 0.51703
|  |  |  | Messenger Clamps | 148 | 127 |  | 0.85811
|  |  |  | Messenger Wire Pull | 797 | 190 |  | 0.23839
|  |  |  | Messenger Wire Tension | 572 | 569 |  | 0.99476
|  |  |  | # Cables Pulled | 756 | 212 |  | 0.28042
|  |  |  | Messenger Straps | 424 | 17 |  | 0.040094
72960 | 72035 | B3/B4 | CAR-4TH | Steel Mess Supports | 604 | 152 |  | 0.25166 | 0.55249
|  |  |  | Messenger Clamps | 527 | 503 |  | 0.95446
|  |  |  | Messenger Wire Pull | 845 | 605 |  | 0.71598
|  |  |  | Messenger Wire Tension | 461 | 237 |  | 0.5141
|  |  |  | # Cables Pulled | 973 | 438 |  | 0.45015
|  |  |  | Messenger Straps | 826 | 354 |  | 0.42857
71150 | 70965 | B3/B4 | CAR-4TH | Steel Mess Supports | 126 | 20 |  | 0.15873 | 0.43001
|  |  |  | Messenger Clamps | 490 | 156 |  | 0.31837
|  |  |  | Messenger Wire Pull | 213 | 40 |  | 0.18779
|  |  |  | Messenger Wire Tension | 57 | 47 |  | 0.82456
|  |  |  | # Cables Pulled | 68 | 39 |  | 0.57353
|  |  |  | Messenger Straps | 878 | 454 |  | 0.51708
70965 | 70445 | B3/B6 | CAR-4TH | Steel Mess Supports | 268 | 246 |  | 0.91791 | 0.72991
|  |  |  | Messenger Clamps | 763 | 719 |  | 0.94233
|  |  |  | Messenger Wire Pull | 942 | 423 |  | 0.44904
|  |  |  | Messenger Wire Tension | 171 | 72 |  | 0.42105
|  |  |  | # Cables Pulled | 394 | 359 |  | 0.91117
|  |  |  | Messenger Straps | 145 | 107 |  | 0.73793
70445 | 70045 | B3/B7 | CAR-4TH | Steel Mess Supports | 953 | 243 |  | 0.25498 | 0.43312
|  |  |  | Messenger Clamps | 878 | 754 |  | 0.85877
|  |  |  | Messenger Wire Pull | 531 | 225 |  | 0.42373
|  |  |  | Messenger Wire Tension | 615 | 441 |  | 0.71707
|  |  |  | # Cables Pulled | 93 | 5 |  | 0.053763
|  |  |  | Messenger Straps | 427 | 124 |  | 0.2904
68625 | 68400 | B3/B8 | CAR-4TH | Steel Mess Supports | 15 | 11 |  | 0.73333 | 0.45529
|  |  |  | Messenger Clamps | 879 | 482 |  | 0.54835
|  |  |  | Messenger Wire Pull | 273 | 80 |  | 0.29304
|  |  |  | Messenger Wire Tension | 741 | 335 |  | 0.45209
|  |  |  | # Cables Pulled | 159 | 57 |  | 0.35849
|  |  |  | Messenger Straps | 306 | 106 |  | 0.34641
68400 | 68330 | B3/B9 | CAR-4TH | Steel Mess Supports | 505 | 160 |  | 0.31683 | 0.4672
|  |  |  | Messenger Clamps | 13 | 4 |  | 0.30769
|  |  |  | Messenger Wire Pull | 561 | 393 |  | 0.70053
|  |  |  | Messenger Wire Tension | 555 | 99 |  | 0.17838
|  |  |  | # Cables Pulled | 758 | 752 |  | 0.99208
|  |  |  | Messenger Straps | 117 | 36 |  | 0.30769

## AXLE COUNTER
Stationing | Track No | Location | Activity | Date | Progress | General Progress | Notes | DWG REF.
54600 | B1 | DIT-CHU | Axle Counter Installation |  | 0% | 0% | STATIONING SHOWN IS THAT OF THE NEAREST IJ, AXC STATIONING DOES NOT EXIST | B1-546
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B1 |  | Axle Counter Installation |  | 0% | 0% | NO INFO | B1-547
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
59297 | B1 | FOR-15S | Axle Counter Installation |  | 0% | 0% |  | B1-553
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B1 |  | Axle Counter Installation |  | 0% | 0% | NO INFO | B1-554
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
55687 | B1 | DIT-CHU | Axle Counter Installation |  | 0% | 0% |  | B1-557
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
56367 | B1 | CHU-FOR | Axle Counter Installation |  | 0% | 0% |  | B1-564
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
58524.6 | B1 | FORT HAMILTON PARKWAY | Axle Counter Installation |  | 0% | 0% |  | B1-585
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
59210.25 | B1 | FOR-15S | Axle Counter Installation |  | 0% | 0% |  | B1-592
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
62572.5 | B1 | FOR-15S | Axle Counter Installation |  | 0% | 0% |  | B1-626
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
63251.4 | B1 | 15S-7AV | Axle Counter Installation |  | 0% | 0% |  | B1-632
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
65387.3 | B1 | 15S-7AV | Axle Counter Installation |  | 0% | 0% |  | B1-654
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
66076 | B1 | 7AV-4TH | Axle Counter Installation |  | 0% | 0% |  | B1-661
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
73206.7 | B1 | SMI-CAR | Axle Counter Installation |  | 0% | 0% |  | B1-732
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
73932 | B1 | CAR-BER | Axle Counter Installation |  | 0% | 0% |  | B1-739
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
75408 | B1 | CAR-BER | Axle Counter Installation |  | 0% | 0% |  | B1-755
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
75669 | B1 | CAR-BER | Axle Counter Installation |  | 0% | 0% |  | B1-756
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
76352 | B1 | BER-HOY | Axle Counter Installation |  | 0% | 0% |  | B1-763, B1-764
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
76589 | B1 | HOYT-SCHERMERHORN | Axle Counter Installation |  | 0% | 0% |  | B1-766
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
76901.5 | B1 | HOY-FUL | Axle Counter Installation |  | 0% | 0% |  | B1-770
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
77088 | B1 | FUL-CLI | Axle Counter Installation |  | 0% | 0% |  | B1-771
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
54737 | B2 | DIT-CHU | Axle Counter Installation |  | 0% | 0% |  | B2-546
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
54731 | B2 |  | Axle Counter Installation |  | 0% | 0% |  | B2-547
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
55000 | B2 | DIT-CHU | Axle Counter Installation |  | 0% | 0% |  | B2-549
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
55498 | B2 | DIT-CHU | Axle Counter Installation |  | 0% | 0% |  | B2-554
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B2 |  | Axle Counter Installation |  | 0% | 0% | NO REF DWG EXISTS | B2-555
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B2 |  | Axle Counter Installation |  | 0% | 0% | NO REF DWG EXISTS | B2-556
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
55857 | B2 | CHURCH AVE | Axle Counter Installation |  | 0% | 0% |  | B2-558
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
58500 | B2 | FORT HAMILTON PARKWAY | Axle Counter Installation |  | 0% | 0% |  | B2-585
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
59203.8 | B2 | FOR-15S | Axle Counter Installation |  | 0% | 0% |  | B2-592
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
62550.6 | B2 |  | Axle Counter Installation |  | 0% | 0% |  | B2-625
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
65375.3 | B2 | 15S-7AV | Axle Counter Installation |  | 0% | 0% |  | B2-654
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
66062.3 | B2 | 7AV-4TH | Axle Counter Installation |  | 0% | 0% |  | B2-661
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B2 |  | Axle Counter Installation |  | 0% | 0% | NO REF DWG EXISTS | B2-665
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B2 |  | Axle Counter Installation |  | 0% | 0% | NO REF DWG EXISTS | B2-684
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B2 |  | Axle Counter Installation |  | 0% | 0% | NO REF DWG EXISTS | B2-691
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B2 |  | Axle Counter Installation |  | 0% | 0% | NO REF DWG EXISTS | B2-692
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B2 |  | Axle Counter Installation |  | 0% | 0% | NO REF DWG EXISTS | B2-692A
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B2 |  | Axle Counter Installation |  | 0% | 0% | NO REF DWG EXISTS | B2-693
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B2 |  | Axle Counter Installation |  | 0% | 0% | NO REF DWG EXISTS | B2-705
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B2 |  | Axle Counter Installation |  | 0% | 0% | NO REF DWG EXISTS | B2-712
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B2 |  | Axle Counter Installation |  | 0% | 0% | DWG EXISTS, BUT EMPTY | B2-732
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
73926.3 | B2 | CARROLL STREET | Axle Counter Installation |  | 0% | 0% |  | B2-739
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
75267 | B2 | CAR-BER | Axle Counter Installation |  | 0% | 0% |  | B2-753
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B2 |  | Axle Counter Installation |  | 0% | 0% | NO REF DWG EXISTS | B2-755
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
75646 | B2 | CAR-BER | Axle Counter Installation |  | 0% | 0% |  | B2-756
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
76352 | B2 |  | Axle Counter Installation |  | 0% | 0% |  | B2-763, B2-764
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
76536 | B2 |  | Axle Counter Installation |  | 0% | 0% |  | B2-765
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
76797 | B2 |  | Axle Counter Installation |  | 0% | 0% |  | B2-768
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
77116 | B2 |  | Axle Counter Installation |  | 0% | 0% |  | B2-770
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B3 |  | Axle Counter Installation |  | 0% | 0% | REF DWG EXISTS, NO STATIONINGS SHOWN | B3-546
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B3 |  | Axle Counter Installation |  | 0% | 0% | REF DWG EXISTS, NO STATIONINGS SHOWN | B3-548
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
53361 | B3 |  | Axle Counter Installation |  | 0% | 0% |  | B3-554
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
55626 | B3 |  | Axle Counter Installation |  | 0% | 0% |  | B3-555
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B3 |  | Axle Counter Installation |  | 0% | 0% | REF DWG EXISTS, NO STATIONINGS SHOWN | B3-556
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B3 |  | Axle Counter Installation |  | 0% | 0% | REF DWG EXISTS, NO STATIONINGS SHOWN | B3-557
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B3 |  | Axle Counter Installation |  | 0% | 0% | NO REF DWG EXISTS | B3-565
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
65384.6 | B3 |  | Axle Counter Installation |  | 0% | 0% |  | B3-654
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
66073.4 | B3 |  | Axle Counter Installation |  | 0% | 0% |  | B3-661
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B3 |  | Axle Counter Installation |  | 0% | 0% | NO REF DWG EXISTS | B3-689
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B3 |  | Axle Counter Installation |  | 0% | 0% | NO REF DWG EXISTS | B3-690
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B3 |  | Axle Counter Installation |  | 0% | 0% | NO REF DWG EXISTS | B3-691
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B3 |  | Axle Counter Installation |  | 0% | 0% | NO REF DWG EXISTS | B3-692
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B3 |  | Axle Counter Installation |  | 0% | 0% | NO REF DWG EXISTS | B3-693
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B3 |  | Axle Counter Installation |  | 0% | 0% | NO REF DWG EXISTS | B3-694
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B3 |  | Axle Counter Installation |  | 0% | 0% | NO REF DWG EXISTS | B3-695
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B3 |  | Axle Counter Installation |  | 0% | 0% | NO REF DWG EXISTS | B3-696
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
75405 | B3 |  | Axle Counter Installation |  | 0% | 0% |  | B3-754
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B3 |  | Axle Counter Installation |  | 0% | 0% | NO REF DWG EXISTS | B3-755
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
75405 | B3 |  | Axle Counter Installation |  | 0% | 0% |  | B3-756
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
76383 | B3 |  | Axle Counter Installation |  | 0% | 0% |  | B3-764
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
76920 | B3 |  | Axle Counter Installation |  | 0% | 0% |  | B3-769
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B4 |  | Axle Counter Installation |  | 0% | 0% | REF DWG EXISTS, NO STATIONINGS SHOWN | B4-547
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B4 |  | Axle Counter Installation |  | 0% | 0% | REF DWG EXISTS, NO STATIONINGS SHOWN | B4-551
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B4 |  | Axle Counter Installation |  | 0% | 0% | NO REF DWG EXISTS, AWAITING RESPONSE FROM THALES ON WHETHER THIS AXC WILL BE INSTALLED | B4-554A, B4-554B
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
55533 | B4 |  | Axle Counter Installation |  | 0% | 0% |  | B4-555
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
55685 | B4 |  | Axle Counter Installation |  | 0% | 0% |  | B4-556
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
56396.5 | B4 |  | Axle Counter Installation |  | 0% | 0% |  | B4-564
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%

## SIGNALS
Stationing | Track No | Signal Type | Location | Activity | Date | Progress | General Progress | Notes
74076 | E1 | APPROACH |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
98643 | E1 | HOME |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
98903 | E1 | HOME |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
100068 | E1 | HOME |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
106031 | E1 | APPROACH |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
113852 | E1 | HOME |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
114110 | E1 | HOME |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
114869 | E1 | HOME |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
119024 | E1 | APPROACH |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
119485 | E1 | APPROACH |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
| E1 | APPROACH |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
121810 | E1 | HOME |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
122198 | E1 | HOME |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
122570 | E1 | HOME |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
122987 | E1 | HOME |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
123669 | D1 | HOME |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
73318 | E2 | APPROACH |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
98565 | E2 | HOME |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
99593 | E2 | HOME |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
99970 | E2 | HOME |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
106749 | E2 | APPROACH |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
112529 | E2 | HOME |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
113850 | E2 | HOME |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
118065 | E2 | APPROACH |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
119215 | E2 | APPROACH |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
123687 | D2 | HOME |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
124043 | D2 | HOME |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
99806 | E3 | HOME |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
100019 | E3 | HOME |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
99592 | E4 | HOME |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
122071 | E5 | HOME |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
122687 | E5 | HOME |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0

## SWITCH
Name | Stationing | Track No | Location | Activity | Date | Progress | General Progress | Notes
B331 | 76395 | B1 |  | Switch Machine Installation |  | 0 | 0
|  |  |  | Switch JB Installation |  | 0
|  |  |  | Switch Cable Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
B325 | 76395 | E2 |  | Switch Machine Installation |  | 0 | 0
|  |  |  | Switch JB Installation |  | 0
|  |  |  | Switch Cable Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
633A | 99999 | E1 |  | Switch Machine Installation |  | 0 | 0
|  |  |  | Switch JB Installation |  | 0
|  |  |  | Switch Cable Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
633B | 98900 | E3-4 |  | Switch Machine Installation |  | 0 | 0
|  |  |  | Switch JB Installation |  | 0
|  |  |  | Switch Cable Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
625A | 98808 | E3-4 |  | Switch Machine Installation |  | 0 | 0
|  |  |  | Switch JB Installation |  | 0
|  |  |  | Switch Cable Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
625B | 99949 | E2 |  | Switch Machine Installation |  | 0 | 0
|  |  |  | Switch JB Installation |  | 0
|  |  |  | Switch Cable Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
663 | 99628 | E3-4 |  | Switch Machine Installation |  | 0 | 0
|  |  |  | Switch JB Installation |  | 0
|  |  |  | Switch Cable Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
673A | 99999 | E1 |  | Switch Machine Installation |  | 0 | 0
|  |  |  | Switch JB Installation |  | 0
|  |  |  | Switch Cable Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
673B | 99826 | E3 |  | Switch Machine Installation |  | 0 | 0
|  |  |  | Switch JB Installation |  | 0
|  |  |  | Switch Cable Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
651A | 99761 | E4 |  | Switch Machine Installation |  | 0 | 0
|  |  |  | Switch JB Installation |  | 0
|  |  |  | Switch Cable Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
651B | 99949 | E2 |  | Switch Machine Installation |  | 0 | 0
|  |  |  | Switch JB Installation |  | 0
|  |  |  | Switch Cable Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
757A | 113880 | E1 |  | Switch Machine Installation |  | 0 | 0
|  |  |  | Switch JB Installation |  | 0
|  |  |  | Switch Cable Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
757B | 114010 | E2 |  | Switch Machine Installation |  | 0 | 0
|  |  |  | Switch JB Installation |  | 0
|  |  |  | Switch Cable Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
753A | 114010 | E1 |  | Switch Machine Installation |  | 0 | 0
|  |  |  | Switch JB Installation |  | 0
|  |  |  | Switch Cable Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
753B | 113880 | E2 |  | Switch Machine Installation |  | 0 | 0
|  |  |  | Switch JB Installation |  | 0
|  |  |  | Switch Cable Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
825 |  | E1 |  | Switch Machine Installation |  | 0 | 0 | Stationing missing
|  |  |  | Switch JB Installation |  | 0
|  |  |  | Switch Cable Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
815A | 121995 | E5 |  | Switch Machine Installation |  | 0 | 0
|  |  |  | Switch JB Installation |  | 0
|  |  |  | Switch Cable Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
815B | 121831 | E2 |  | Switch Machine Installation |  | 0 | 0
|  |  |  | Switch JB Installation |  | 0
|  |  |  | Switch Cable Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
851B | 122757 | E5 |  | Switch Machine Installation |  | 0 | 0
|  |  |  | Switch JB Installation |  | 0
|  |  |  | Switch Cable Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
851A | 122923 | E1 |  | Switch Machine Installation |  | 0 | 0
|  |  |  | Switch JB Installation |  | 0
|  |  |  | Switch Cable Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
841 | 122923 | E2 |  | Switch Machine Installation |  | 0 | 0
|  |  |  | Switch JB Installation |  | 0
|  |  |  | Switch Cable Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
753B | 113880 | E2 |  | Switch Machine Installation |  | 0 | 0
|  |  |  | Switch JB Installation |  | 0
|  |  |  | Switch Cable Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0

## WRU
Stationing | Track No | Location | Activity | Date | Progress | General Progress | Notes
54000 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
54000 | B3 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
54000 | B4 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
54000 | B2 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
54000 | B5 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
55500 | B2 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
55500 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
56300 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
56500 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
57200 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
57400 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
58300 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
58400 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
59400 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
59700 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
60500 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
60800 | B2 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
60800 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
61900 | B2 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
61900 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
62300 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
63200 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
63300 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
64200 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
64300 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
65200 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
65200 | B2 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
66300 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
66300 | B2 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
67500 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
67500 | B2 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
68300 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
68300 | B2 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
69900 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
71400 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
73000 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
73000 | B2 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
74100 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
75300 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
75300 | B2 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
88300 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
88600 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
90800 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
92400 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
93600 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
95000 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
96500 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
98200 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
99700 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
99700 | E2 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
100400 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
100600 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
101500 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
102600 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
103800 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
104700 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
105900 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
106900 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
108300 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
109900 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
111100 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
112200 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
113000 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
114300 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
115500 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
116900 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
118300 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
118300 | E2 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
119500 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
119500 | E2 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
120800 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
120800 | E2 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
121900 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
122800 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
123900 | D1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
124900 | D1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
125900 | D1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
123900 | D2 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
124900 | D2 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
125900 | D2 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0

## Z-CASE
Stationing | Track No | Location | Activity | Date | Progress | General Progress | Notes
|  |  | CASE Install |  |  |  | Z-CASE IS BY E1-986 (Z)
Cable Connection/Termination
Pre-Op testing
|  |  | CASE Install |  |  |  | Z-CASE IS BY E1-1006 (Z)
Cable Connection/Termination
Pre-Op testing
|  |  | CASE Install |  |  |  | Z-CASE IS BY E1-1030 (Z)
Cable Connection/Termination
Pre-Op testing
|  |  | CASE Install |  |  |  | Z-CASE IS BY E1-1068 (Z)
Cable Connection/Termination
Pre-Op testing
115725 | E1 |  | CASE Install |  |  |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
Cable Connection/Termination
Pre-Op testing
121810 | E1 |  | CASE Install |  |  |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
Cable Connection/Termination
Pre-Op testing
| E1 |  | CASE Install |  |  |  | Z-CASE IS BY E1-1229 (Z)
Cable Connection/Termination
Pre-Op testing
| E1 |  | CASE Install |  |  |  | Z-CASE IS BY E1-1230 (Z)
Cable Connection/Termination
Pre-Op testing
98565 | E2 |  | CASE Install |  |  |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
Cable Connection/Termination
Pre-Op testing
114869 | E2 |  | CASE Install |  |  |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
Cable Connection/Termination
Pre-Op testing
| E2 |  | CASE Install |  |  |  | Z-CASE IS BY E2-1230(Z)
Cable Connection/Termination
Pre-Op testing
122071 | E5 |  | CASE Install |  |  |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
Cable Connection/Termination
Pre-Op testing
122687 | E5 |  | CASE Install |  |  |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
Cable Connection/Termination
Pre-Op testing

## TOPB
Stationing | Track No | Location | Activity | Date | Progress | General Progress | Notes
121810 | E1 |  | TOPB Install |  |  |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
Cable Connection/Termination
Pre-Op testing
122987 | E1 |  | TOPB Install |  |  |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
Cable Connection/Termination
Pre-Op testing
|  |  | TOPB Install |  |  |  | TOPB @ ~D1-1239
Cable Connection/Termination
Pre-Op testing
121809 | E2 |  | TOPB Install |  |  |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
Cable Connection/Termination
Pre-Op testing
122970 | E2 |  | TOPB Install |  |  |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
Cable Connection/Termination
Pre-Op testing
124043 | D2 |  | TOPB Install |  |  |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
Cable Connection/Termination
Pre-Op testing

## Report Screenshot
Tasks | Total Quantity | Installed/Tested Quantity
Acceptance Test (Ea) | 29 | 3
Antenna Cable (ft) | 61885 | 58432
Brackets (Ea) | 12147 | 11856
Coax Cable (Ea) | 59 | 59
Insertion Loss (Segment) (ft) | 47445 | 43615
Removals (ft) | 30946 | 2380
Coupler Plates | 27 | 27
DC Resistance (Segment) | 47410 | 43580
Megger (Segment) | 47445 | 43615
VSWR (Segment) | 47445 | 43615
End-To-End | 47445 | 33565
Heat Map Test | 47445 | 29175
Coverage Test/Survey | 47445 | 3160
Megger Coax Cable (Reel) | 4000 | 4000
Megger Antenna Cable (Reel) | 80000 | 80000
Megger 1/2in Cable (Reel) | 100 | 100
DC Resistance Coax Cable (Reel) | 4000 | 4000
DC Resistance Antenna Cable (Reel) | 80000 | 80000
DC Resistance 1/2in Cable (Reel) | 100 | 100

## Dashboard
RADIO INSTALLATION DASHBOARD
OVERALL TASK COMPLETION (ALL TRACKS)
TASK PERCENT COMPLETION (PER TRACK)
OVERALL INSTALLATION PROGRESS PER TRACK SECTION
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.