## Reference
Track No. | Column Side | Activities | Bracket Type | Station | Track Stationing | Tunnel | Description | Track Stationing | Notes
B1 | W | Steel Messenger Supports | 1 | Church Avenue | 556+96 to 563+56 | CHU-FOR | Church Ave to Fort Hamilton | 563+56 to 584+88
B2 | E | Messenger Clamps | 2 | Fort Hamilton Parkway | 584+88 to 591+90 | FOR-15S | Fort Hamilton to 15th Street | 591+90 to 625+70
B3 | W | Messenger Wire Pull | 3 | 15th Street Prospect Park | 625+70 to 632+30 | 15S-7AV | 15th Street to 7th Avenue | 632+30 to 653+96
B4 | E | Messenger Wire Tension | 4 | 7th Avenue | 653+96 to 660+56 | 7AV-4TH | 7th Avenue to 4th & 9th Street | 660+56-683+83
E1 | W | Cable Pull | 4A | 4th & 9th Street | 683+83 to 690+91 | 4TH-SMI | 4th & 9th Street to Smith & 9th Street | 690+91 to 705+11
E2 | E | Messenger Straps | 5 | Smith & 9th Street | 705+11 to 712+32 | SMI-CAR | Smith & 9th Street to Carroll Street | 712+32 to 732+89
E3 |  | 15inch CMRS |  | Carroll Street | 732+39 to 738+99 | CAR-BER | Carroll Street to Bergen Street | 738+99 to 756+82
E4 |  | 24inch CMRS |  | Bergen Street | 756+82 to 763+42 | BER-HOY | Bergen Street to Hoyt Schermerhorn | 763+42 to 761+84 | track goes from 768+XX to 693+95
E5 |  | Column mount CMRS |  | Hoyt Schermerhorn | 761+84 to 768+87 | HOY-FUL | Hoyt Schermerhorn to Fulton | 768+87 to 740+30
|  | Station Brackets |  | Fulton Street | 740+30 to 733+70 | FUL-CLI | Fulton to Clinton Washington | 733+70 to 951+82 | track goes from 733+15 to 934+96
Location |  | Grounding |  | Clinton Washington Avenue | 951+82 to 958+42 | CLI-CLA | Clinton Washington to Classon | 958+42 to 970+82
Church Avenue |  | Obstruction Brackets |  | Classon Avenue | 970+82 to 977+42 | CLA-BED | Classon to Bedford Nostand | 977+42 to 989+22
CHU-FOR |  | Cable Pull |  | Bedford Nostrand Avenue | 989+22 to 995+82 | BED-MYR | Bedford Nostrand to Myrtle Willoughby | 995+82 to 1017+47
Fort Hamilton Parkway |  | Cable Tray Brackets |  | Myrtle Willoughby Ave | 1017+47 to 1024+52 | MYR-FLU | Myrtle Willoughby to Flushing Avenue | 1024+52 to 1039+42
FOR-15S |  | Installing Tray |  | Flushing Avenue Station | 1039+42 to 1046+20 | FLU-BRO | Flushing Avenue to Broadway | 1046+20 to 1060+52
15th Street Prospect Park |  | Core Drilling |  | Broadway | 1060+52 to 1067+12 | BRO-MET | Broadway to Metropolitan | 1067+12 to 1132+45
15S-7AV |  | Cable Pull |  | Metropolitan Avenue | 1132+45 to 1139+50 | MET-NAS | Metropolitan to Nassau | 1139+50 to 1131+52
7th Avenue |  | Arch Bar Installation |  | Nassau Avenue | 1131+52 to 1138+32 | NAS-GRE | Nassau to Greenpoint | 1138+32 to 1157+00
7AV-4TH |  |  |  | Greenpoint Avenue | 1157+00 to 1164+32 | GRE-21S | Greenpoint to 21 St | 1164+32 to 1211+33
4th & 9th Street |  |  |  | 21 St Station | 1211+33 to 1217+92 | 21S-COU | 21 St to Court Square | 1217+92 to 1229+23
4TH-SMI |  |  |  | Court Square | 1229+23 to 1236+66 | COU-QUE | Court Square to Queens Plaza | 1236+66 to 1250+65
Smith & 9th Street |  |  |  | Queens Plaza | 1250+65 to 1257+27
SMI-CAR
Carroll Street |  |  |  | Signal Types
CAR-BER |  |  |  | HOME
Bergen Street* |  |  |  | APPROACH
BER-HOY |  |  |  | BUMPER
Hoyt Schermerhorn |  |  |  | REV. HOME
HOY-FUL |  |  |  | REV. APPROACH
Fulton Street
FUL-CLI
Clinton Washington Avenue
CLI-CLA
Classon Avenue
CLA-BED
Bedford Nostrand Avenue
BED-MYR
Myrtle Willoughby Ave
MYR-FLU
Flushing Avenue Station
FLU-BRO
Broadway
BRO-MET
Metropolitan Avenue
MET-NAS
Nassau Avenue
NAS-GRE
Greenpoint Avenue
GRE-21S
21 St Station
21S-COU
Court Square
COU-QUE
Queens Plaza

## Work Sheet (hidden)
OVERALL INSTALLATION PER AREA
Status | Count
Not Started | #REF!
In Progress | #REF!
Completed | #REF!
Remaining | #REF!
Total Tasks | #REF!
Completed Sections | #REF!
Remaining Sections | #REF!

## Ref Activity Bar (hidden)
RADIO INSTALLATION DASHBOARD
TRACK | C3/C4
TASK | COMPLETION PROGRESS
Removals | 12.5%
Grand Total | 12.5%

## Ref Progress per Activity (hidden)
TASK | Acceptance Test
|  | Not Started | 0 | Completed Sections | 13.04%
TRACK | Average of PROGRESS | In Progress | 0 | Remaining Sections | 86.96%
C1 | 16.67% | Completed | 0
C2 | 16.67%
C3 | 0%
C3/C4 | 14.29%
C4 | 0%
C5 | 0%
C6 | 0%
Grand Total | 13.04%

## CMRS
Start | Finish | Track No | Location | Activity | Total Quantity | QTY Installed | Date | Progress | General Progress | Notes | Notes
124510 | 124500 | D1 | COU-QUE | Steel Mess Supports | 608 | 284 |  | 0.46711 | 0.49838
|  |  |  | Messenger Clamps | 803 | 81 |  | 0.10087
|  |  |  | Messenger Wire Pull | 387 | 377 |  | 0.97416
|  |  |  | Messenger Wire Tension | 897 | 352 |  | 0.39242
|  |  |  | # Cables Pulled | 733 | 503 |  | 0.68622
|  |  |  | Messenger Straps | 249 | 92 |  | 0.36948
124500 | 124320 | D1 | COU-QUE | Steel Mess Supports | 962 | 265 |  | 0.27547 | 0.59214
|  |  |  | Messenger Clamps | 47 | 39 |  | 0.82979
|  |  |  | Messenger Wire Pull | 189 | 101 |  | 0.53439
|  |  |  | Messenger Wire Tension | 256 | 215 |  | 0.83984
|  |  |  | # Cables Pulled | 344 | 96 |  | 0.27907
|  |  |  | Messenger Straps | 666 | 529 |  | 0.79429
124320 | 124100 | D1 | COU-QUE | Steel Mess Supports | 180 | 142 |  | 0.78889 | 0.37419
|  |  |  | Messenger Clamps | 247 | 89 |  | 0.36032
|  |  |  | Messenger Wire Pull | 821 | 470 |  | 0.57247
|  |  |  | Messenger Wire Tension | 19 | 3 |  | 0.15789
|  |  |  | # Cables Pulled | 215 | 18 |  | 0.083721
|  |  |  | Messenger Straps | 699 | 197 |  | 0.28183
124100 | 123970 | D1 | COU-QUE | Steel Mess Supports | 667 | 541 |  | 0.81109 | 0.34955
|  |  |  | Messenger Clamps | 164 | 22 |  | 0.13415
|  |  |  | Messenger Wire Pull | 488 | 26 |  | 0.053279
|  |  |  | Messenger Wire Tension | 333 | 79 |  | 0.23724
|  |  |  | # Cables Pulled | 855 | 691 |  | 0.80819
|  |  |  | Messenger Straps | 75 | 4 |  | 0.053333
123970 | 123930 | D1 | COU-QUE | 15" CMRS Install | 584 | 413 |  | 0.70719 | 0.55493
|  |  |  | Column Clamp | 673 | 456 |  | 0.67756
|  |  |  | Station Brackets | 157 | 83 |  | 0.52866
|  |  |  | Grounding | 417 | 61 |  | 0.14628
|  |  |  | Obstruction Brackets | 817 | 707 |  | 0.86536
|  |  |  | # Cables Pulled | 89 | 36 |  | 0.40449
123930 | 123715 | D1 | COU-QUE | 15" CMRS Install | 298 | 0 |  | 0 | 0.28024
|  |  |  | Column Clamp | 395 | 126 |  | 0.31899
|  |  |  | Station Brackets | 896 | 173 |  | 0.19308
|  |  |  | Grounding | 323 | 185 |  | 0.57276
|  |  |  | Obstruction Brackets | 525 | 130 |  | 0.24762
|  |  |  | # Cables Pulled | 596 | 208 |  | 0.34899
|  | D1 | COU-QUE | Crossover (Arch Bar Installation) | 450 | 211 |  | 0.46889
122975 | 122827 | E1 | 21S-COU | Steel Mess Supports | 693 | 53 |  | 0.076479 | 0.4099
|  |  |  | Messenger Clamps | 668 | 410 |  | 0.61377
|  |  |  | Messenger Wire Pull | 213 | 194 |  | 0.9108
|  |  |  | Messenger Wire Tension | 568 | 42 |  | 0.073944
|  |  |  | # Cables Pulled | 440 | 37 |  | 0.084091
|  |  |  | Messenger Straps | 654 | 458 |  | 0.70031
122827 | 122250 | E1 | 21S-COU | 24" CMRS Install | 224 | 137 |  | 0.61161 | 0.5144
|  |  |  | Column Clamp | 179 | 32 |  | 0.17877
|  |  |  | Station Brackets | 15 | 5 |  | 0.33333
|  |  |  | Grounding | 118 | 89 |  | 0.75424
|  |  |  | Obstruction Brackets | 693 | 297 |  | 0.42857
|  |  |  | # Cables Pulled | 904 | 705 |  | 0.77987
122250 | 121833 | E1 | 21S-COU | Steel Mess Supports | 429 | 256 |  | 0.59674 | 0.49595
|  |  |  | Messenger Clamps | 792 | 351 |  | 0.44318
|  |  |  | Messenger Wire Pull | 888 | 573 |  | 0.64527
|  |  |  | Messenger Wire Tension | 924 | 370 |  | 0.40043
|  |  |  | # Cables Pulled | 822 | 38 |  | 0.046229
|  |  |  | Messenger Straps | 858 | 724 |  | 0.84382
121833 | 121030 | E1 | 21 STREET | Steel Mess Supports | 888 | 609 |  | 0.68581 | 0.40333
|  |  |  | Messenger Clamps | 625 | 192 |  | 0.3072
|  |  |  | Messenger Wire Pull | 473 | 149 |  | 0.31501
|  |  |  | Messenger Wire Tension | 760 | 192 |  | 0.25263
|  |  |  | # Cables Pulled | 84 | 34 |  | 0.40476
|  |  |  | Messenger Straps | 418 | 190 |  | 0.45455
121030 | 117010 | E1 | GRE-21S | 15" CMRS Install | 937 | 615 |  | 0.65635 | 0.66657
|  |  |  | Column Clamp | 90 | 76 |  | 0.84444
|  |  |  | Station Brackets | 590 | 537 |  | 0.91017
|  |  |  | Grounding | 307 | 296 |  | 0.96417
|  |  |  | Obstruction Brackets | 419 | 161 |  | 0.38425
|  |  |  | # Cables Pulled | 679 | 163 |  | 0.24006
117010 | 116810 | E1 | GRE-21S | 15" CMRS Install | 858 | 76 |  | 0.088578 | 0.36657
|  |  |  | Column Clamp | 406 | 174 |  | 0.42857
|  |  |  | Station Brackets | 465 | 49 |  | 0.10538
|  |  |  | Grounding | 650 | 352 |  | 0.54154
|  |  |  | Obstruction Brackets | 167 | 29 |  | 0.17365
|  |  |  | # Cables Pulled | 441 | 380 |  | 0.86168
116810 | 116471 | E1 | GRE-21S | 15" CMRS Install | 148 | 28 |  | 0.18919 | 0.54558
|  |  |  | Column Clamp | 423 | 381 |  | 0.90071
|  |  |  | Station Brackets | 908 | 430 |  | 0.47357
|  |  |  | Grounding | 885 | 575 |  | 0.64972
|  |  |  | Obstruction Brackets | 939 | 278 |  | 0.29606
|  |  |  | # Cables Pulled | 861 | 658 |  | 0.76423
116471 | 115694 | E1 | GREENPOINT | 24" CMRS Install | 643 | 108 |  | 0.16796 | 0.42749
|  |  |  | Column Clamp | 538 | 276 |  | 0.51301
|  |  |  | Station Brackets | 605 | 208 |  | 0.3438
|  |  |  | Grounding | 954 | 435 |  | 0.45597
|  |  |  | Obstruction Brackets | 307 | 123 |  | 0.40065
|  |  |  | # Cables Pulled | 79 | 54 |  | 0.68354
115694 | 115628 | E1 | NAS-GRE | 24" CMRS Install | 52 | 10 |  | 0.19231 | 0.5412
|  |  |  | Column Clamp | 843 | 683 |  | 0.8102
|  |  |  | Station Brackets | 744 | 53 |  | 0.071237
|  |  |  | Grounding | 94 | 51 |  | 0.54255
|  |  |  | Obstruction Brackets | 480 | 329 |  | 0.68542
|  |  |  | # Cables Pulled | 110 | 104 |  | 0.94545
115628 | 114897 | E1 | NAS-GRE | 24" CMRS Install | 768 | 248 |  | 0.32292 | 0.18143
|  |  |  | Column Clamp | 286 | 74 |  | 0.25874
|  |  |  | Station Brackets | 501 | 61 |  | 0.12176
|  |  |  | Grounding | 172 | 14 |  | 0.081395
|  |  |  | Obstruction Brackets | 237 | 72 |  | 0.3038
|  |  |  | # Cables Pulled | 343 | 0 |  | 0
114897 | 114719 | E1 | NAS-GRE | Steel Mess Supports | 83 | 76 |  | 0.91566 | 0.78454
|  |  |  | Messenger Clamps | 837 | 639 |  | 0.76344
|  |  |  | Messenger Wire Pull | 80 | 79 |  | 0.9875
|  |  |  | Messenger Wire Tension | 30 | 12 |  | 0.4
|  |  |  | # Cables Pulled | 358 | 300 |  | 0.83799
|  |  |  | Messenger Straps | 76 | 61 |  | 0.80263
114719 | 114040 | E1 | NAS-GRE | 24" CMRS Install | 317 | 38 |  | 0.11987 | 0.3114
|  |  |  | Column Clamp | 10 | 1 |  | 0.1
|  |  |  | Station Brackets | 971 | 493 |  | 0.50772
|  |  |  | Grounding | 978 | 203 |  | 0.20757
|  |  |  | Obstruction Brackets | 96 | 20 |  | 0.20833
|  |  |  | # Cables Pulled | 349 | 253 |  | 0.72493
114040 | 113815 | E1 | NAS-GRE | Steel Mess Supports | 899 | 41 |  | 0.045606 | 0.44096
|  |  |  | Messenger Clamps | 879 | 703 |  | 0.79977
|  |  |  | Messenger Wire Pull | 720 | 3 |  | 0.0041667
|  |  |  | Messenger Wire Tension | 501 | 463 |  | 0.92415
|  |  |  | # Cables Pulled | 247 | 4 |  | 0.016194
|  |  |  | Messenger Straps | 340 | 291 |  | 0.85588
113815 | 113019 | E1 | NASSAU | 24" CMRS Install | 270 | 99 |  | 0.36667 | 0.41028 |  | weight: 6.7 lb/ft
|  |  |  | Column Clamp | 664 | 495 |  | 0.74548
|  |  |  | Station Brackets | 307 | 270 |  | 0.87948
|  |  |  | Grounding | 299 | 20 |  | 0.06689
|  |  |  | Obstruction Brackets | 477 | 14 |  | 0.02935
|  |  |  | # Cables Pulled | 519 | 194 |  | 0.3738
|  | E1 | NASSAU | 24" CMRS Install | 692 | 414 |  | 0.59827 | 0.62996
|  |  |  | Column Clamp | 27 | 7 |  | 0.25926
|  |  |  | Station Brackets | 918 | 580 |  | 0.63181
|  |  |  | Grounding | 480 | 401 |  | 0.83542
|  |  |  | Obstruction Brackets | 928 | 584 |  | 0.62931
|  |  |  | # Cables Pulled | 482 | 398 |  | 0.82573
113019 | 112700 | E1 | MET-NAS | 24" CMRS Install | 563 | 213 |  | 0.37833 | 0.51795
|  |  |  | Column Clamp | 702 | 569 |  | 0.81054
|  |  |  | Station Brackets | 669 | 111 |  | 0.16592
|  |  |  | Grounding | 270 | 172 |  | 0.63704
|  |  |  | Obstruction Brackets | 772 | 267 |  | 0.34585
|  |  |  | # Cables Pulled | 574 | 442 |  | 0.77003
112700 | 110878 | E1 | MET-NAS | 15" CMRS Install | 880 | 227 |  | 0.25795 | 0.29415
|  |  |  | Column Clamp | 460 | 50 |  | 0.1087
|  |  |  | Station Brackets | 621 | 255 |  | 0.41063
|  |  |  | Grounding | 667 | 342 |  | 0.51274
|  |  |  | Obstruction Brackets | 313 | 146 |  | 0.46645
|  |  |  | # Cables Pulled | 948 | 8 |  | 0.0084388
110878 | 110793 | E1 | MET-NAS | 15" CMRS Install | 448 | 144 |  | 0.32143 | 0.61776
|  |  |  | Column Clamp | 931 | 902 |  | 0.96885
|  |  |  | Station Brackets | 790 | 245 |  | 0.31013
|  |  |  | Grounding | 998 | 842 |  | 0.84369
|  |  |  | Obstruction Brackets | 41 | 11 |  | 0.26829
|  |  |  | # Cables Pulled | 686 | 682 |  | 0.99417
110793 | 109251 | E1 | MET-NAS | 15" CMRS Install | 432 | 110 |  | 0.25463 | 0.69927
|  |  |  | Column Clamp | 900 | 537 |  | 0.59667
|  |  |  | Station Brackets | 603 | 577 |  | 0.95688
|  |  |  | Grounding | 500 | 328 |  | 0.656
|  |  |  | Obstruction Brackets | 40 | 37 |  | 0.925
|  |  |  | # Cables Pulled | 155 | 125 |  | 0.80645
109251 | 109133 | E1 | MET-NAS | 15" CMRS Install | 76 | 53 |  | 0.69737 | 0.2912
|  |  |  | Column Clamp | 207 | 22 |  | 0.10628
|  |  |  | Station Brackets | 720 | 79 |  | 0.10972
|  |  |  | Grounding | 489 | 249 |  | 0.5092
|  |  |  | Obstruction Brackets | 674 | 2 |  | 0.0029674
|  |  |  | # Cables Pulled | 687 | 221 |  | 0.32169
109133 | 108356 | E1 | METROPOLITAN | 15" CMRS Install | 530 | 351 |  | 0.66226 | 0.50684
|  |  |  | Column Clamp | 931 | 23 |  | 0.024705
|  |  |  | Station Brackets | 893 | 581 |  | 0.65062
|  |  |  | Grounding | 991 | 409 |  | 0.41271
|  |  |  | Obstruction Brackets | 515 | 175 |  | 0.33981
|  |  |  | # Cables Pulled | 469 | 446 |  | 0.95096
108356 | 107651 | E1 | BRO-MET | 15" CMRS Install | 407 | 405 |  | 0.99509 | 0.6449
|  |  |  | Column Clamp | 113 | 88 |  | 0.77876
|  |  |  | Station Brackets | 786 | 117 |  | 0.14885
|  |  |  | Grounding | 403 | 366 |  | 0.90819
|  |  |  | Obstruction Brackets | 83 | 8 |  | 0.096386
|  |  |  | # Cables Pulled | 190 | 179 |  | 0.94211
107651 | 107611 | E1 | BRO-MET | 15" CMRS Install | 979 | 294 |  | 0.30031 | 0.35587 |  | Check endings for specific stationings (DWG 48012-17N-006.0) where cable switches from 1 to 2
|  |  |  | Column Clamp | 944 | 2 |  | 0.0021186
|  |  |  | Station Brackets | 639 | 39 |  | 0.061033
|  |  |  | Grounding | 270 | 170 |  | 0.62963
|  |  |  | Obstruction Brackets | 316 | 239 |  | 0.75633
|  |  |  | # Cables Pulled | 972 | 375 |  | 0.3858
107611 | 106768 | E1 | BRO-MET | 15" CMRS Install | 114 | 27 |  | 0.23684 | 0.41131
|  |  |  | Column Clamp | 449 | 284 |  | 0.63252
|  |  |  | Station Brackets | 429 | 107 |  | 0.24942
|  |  |  | Grounding | 914 | 4 |  | 0.0043764
|  |  |  | Obstruction Brackets | 604 | 404 |  | 0.66887
|  |  |  | # Cables Pulled | 839 | 567 |  | 0.6758
106768 | 106702 | E1 | BRO-MET | 15" CMRS Install | 831 | 756 |  | 0.90975 | 0.73636
|  |  |  | Column Clamp | 872 | 58 |  | 0.066514
|  |  |  | Station Brackets | 125 | 108 |  | 0.864
|  |  |  | Grounding | 990 | 917 |  | 0.92626
|  |  |  | Obstruction Brackets | 913 | 910 |  | 0.99671
|  |  |  | # Cables Pulled | 313 | 205 |  | 0.65495
106702 | 106011 | E1 | BROADWAY | 15" CMRS Install | 317 | 216 |  | 0.68139 | 0.78894
|  |  |  | Column Clamp | 476 | 293 |  | 0.61555
|  |  |  | Station Brackets | 126 | 106 |  | 0.84127
|  |  |  | Grounding | 261 | 201 |  | 0.77011
|  |  |  | Obstruction Brackets | 175 | 173 |  | 0.98857
|  |  |  | # Cables Pulled | 196 | 164 |  | 0.83673
|  | E1 | BROADWAY | 15" CMRS Install | 392 | 198 |  | 0.5051 | 0.64105
|  |  |  | Column Clamp | 976 | 817 |  | 0.83709
|  |  |  | Station Brackets | 342 | 305 |  | 0.89181
|  |  |  | Grounding | 225 | 106 |  | 0.47111
|  |  |  | Obstruction Brackets | 649 | 347 |  | 0.53467
|  |  |  | # Cables Pulled | 986 | 598 |  | 0.60649
|  | E1 | BROADWAY | 15" CMRS Install | 152 | 148 |  | 0.97368 | 0.51251
|  |  |  | Column Clamp | 574 | 115 |  | 0.20035
|  |  |  | Station Brackets | 180 | 125 |  | 0.69444
|  |  |  | Grounding | 954 | 740 |  | 0.77568
|  |  |  | Obstruction Brackets | 574 | 74 |  | 0.12892
|  |  |  | # Cables Pulled | 755 | 228 |  | 0.30199
106011 | 105293 | E1 | FLU-BRO | 15" CMRS Install | 182 | 118 |  | 0.64835 | 0.35703
|  |  |  | Column Clamp | 965 | 51 |  | 0.05285
|  |  |  | Station Brackets | 22 | 13 |  | 0.59091
|  |  |  | Grounding | 752 | 139 |  | 0.18484
|  |  |  | Obstruction Brackets | 139 | 60 |  | 0.43165
|  |  |  | # Cables Pulled | 655 | 153 |  | 0.23359
105293 | 104667 | E1 | FLU-BRO | 15" CMRS Install | 13 | 6 |  | 0.46154 | 0.367
|  |  |  | Column Clamp | 968 | 312 |  | 0.32231
|  |  |  | Station Brackets | 529 | 408 |  | 0.77127
|  |  |  | Grounding | 190 | 1 |  | 0.0052632
|  |  |  | Obstruction Brackets | 994 | 177 |  | 0.17807
|  |  |  | # Cables Pulled | 576 | 267 |  | 0.46354
104667 | 103784 | E1 | FLUSHING | 15" CMRS Install | 73 | 10 |  | 0.13699 | 0.20662
|  |  |  | Column Clamp | 480 | 197 |  | 0.41042
|  |  |  | Station Brackets | 817 | 112 |  | 0.13709
|  |  |  | Grounding | 104 | 11 |  | 0.10577
|  |  |  | Obstruction Brackets | 277 | 10 |  | 0.036101
|  |  |  | # Cables Pulled | 479 | 198 |  | 0.41336
103784 | 103231 | E1 | MYR-FLU | 15" CMRS Install | 237 | 70 |  | 0.29536 | 0.26751
|  |  |  | Column Clamp | 785 | 37 |  | 0.047134
|  |  |  | Station Brackets | 428 | 33 |  | 0.077103
|  |  |  | Grounding | 840 | 242 |  | 0.2881
|  |  |  | Obstruction Brackets | 761 | 341 |  | 0.44809
|  |  |  | # Cables Pulled | 917 | 412 |  | 0.44929
103231 | 103165 | E1 | MYR-FLU | 15" CMRS Install | 141 | 12 |  | 0.085106 | 0.52554
|  |  |  | Column Clamp | 260 | 227 |  | 0.87308
|  |  |  | Station Brackets | 223 | 149 |  | 0.66816
|  |  |  | Grounding | 258 | 136 |  | 0.52713
|  |  |  | Obstruction Brackets | 253 | 139 |  | 0.54941
|  |  |  | # Cables Pulled | 453 | 204 |  | 0.45033
103165 | 102533 | E1 | MYR-FLU | 15" CMRS Install | 515 | 468 |  | 0.90874 | 0.43185
|  |  |  | Column Clamp | 873 | 240 |  | 0.27491
|  |  |  | Station Brackets | 582 | 16 |  | 0.027491
|  |  |  | Grounding | 255 | 56 |  | 0.21961
|  |  |  | Obstruction Brackets | 419 | 209 |  | 0.49881
|  |  |  | # Cables Pulled | 130 | 86 |  | 0.66154
102533 | 101595 | E1 | MYRTLE | 24" CMRS Install | 388 | 139 |  | 0.35825 | 0.54215
|  |  |  | Column Clamp | 216 | 78 |  | 0.36111
|  |  |  | Station Brackets | 914 | 765 |  | 0.83698
|  |  |  | Grounding | 271 | 149 |  | 0.54982
|  |  |  | Obstruction Brackets | 745 | 643 |  | 0.86309
|  |  |  | # Cables Pulled | 490 | 139 |  | 0.28367
101595 | 101558 | E1 | BED-MYR | 24" CMRS Install | 931 | 265 |  | 0.28464 | 0.5605
|  |  |  | Column Clamp | 812 | 107 |  | 0.13177
|  |  |  | Station Brackets | 666 | 549 |  | 0.82432
|  |  |  | Grounding | 522 | 244 |  | 0.46743
|  |  |  | Obstruction Brackets | 115 | 110 |  | 0.95652
|  |  |  | # Cables Pulled | 474 | 331 |  | 0.69831
101558 | 101050 | E1 | BED-MYR | 24" CMRS Install | 460 | 150 |  | 0.32609 | 0.398
|  |  |  | Column Clamp | 359 | 322 |  | 0.89694
|  |  |  | Station Brackets | 189 | 83 |  | 0.43915
|  |  |  | Grounding | 946 | 429 |  | 0.45349
|  |  |  | Obstruction Brackets | 853 | 208 |  | 0.24385
|  |  |  | # Cables Pulled | 386 | 11 |  | 0.028497
101050 | 101015 | E1 | BED-MYR | 24" CMRS Install | 957 | 681 |  | 0.7116 | 0.55525
|  |  |  | Column Clamp | 760 | 609 |  | 0.80132
|  |  |  | Station Brackets | 245 | 35 |  | 0.14286
|  |  |  | Grounding | 765 | 135 |  | 0.17647
|  |  |  | Obstruction Brackets | 298 | 284 |  | 0.95302
|  |  |  | # Cables Pulled | 692 | 378 |  | 0.54624
101015 | 100530 | E1 | BED-MYR | 24" CMRS Install | 928 | 859 |  | 0.92565 | 0.58835
|  |  |  | Column Clamp | 984 | 130 |  | 0.13211
|  |  |  | Station Brackets | 552 | 295 |  | 0.53442
|  |  |  | Grounding | 635 | 344 |  | 0.54173
|  |  |  | Obstruction Brackets | 912 | 586 |  | 0.64254
|  |  |  | # Cables Pulled | 617 | 465 |  | 0.75365
100530 | 100383 | E1 | BED-MYR | Steel Mess Supports | 332 | 72 |  | 0.21687 | 0.44019
|  |  |  | Messenger Clamps | 975 | 367 |  | 0.37641
|  |  |  | Messenger Wire Pull | 226 | 117 |  | 0.5177
|  |  |  | Messenger Wire Tension | 515 | 120 |  | 0.23301
|  |  |  | # Cables Pulled | 998 | 575 |  | 0.57615
|  |  |  | Messenger Straps | 466 | 336 |  | 0.72103
|  | E1 | BED-MYR | Crossover (Arch Bar Installation) | 452 | 389 |  | 0.86062
100383 | 100282 | E1 | BED-MYR | Steel Mess Supports | 386 | 344 |  | 0.89119 | 0.50503
|  |  |  | Messenger Clamps | 286 | 31 |  | 0.10839
|  |  |  | Messenger Wire Pull | 523 | 15 |  | 0.028681
|  |  |  | Messenger Wire Tension | 704 | 262 |  | 0.37216
|  |  |  | # Cables Pulled | 472 | 374 |  | 0.79237
|  |  |  | Messenger Straps | 658 | 551 |  | 0.83739
100282 | 100036 | E1 | BED-MYR | Steel Mess Supports | 199 | 127 |  | 0.63819 | 0.61437
|  |  |  | Messenger Clamps | 751 | 274 |  | 0.36485
|  |  |  | Messenger Wire Pull | 450 | 392 |  | 0.87111
|  |  |  | Messenger Wire Tension | 214 | 78 |  | 0.36449
|  |  |  | # Cables Pulled | 794 | 649 |  | 0.81738
|  |  |  | Messenger Straps | 265 | 167 |  | 0.63019
100036 | 99560 | E1 | BED-MYR | Steel Mess Supports | 989 | 19 |  | 0.019211 | 0.35624
|  |  |  | Messenger Clamps | 626 | 35 |  | 0.055911
|  |  |  | Messenger Wire Pull | 342 | 179 |  | 0.52339
|  |  |  | Messenger Wire Tension | 815 | 143 |  | 0.17546
|  |  |  | # Cables Pulled | 286 | 136 |  | 0.47552
|  |  |  | Messenger Straps | 241 | 214 |  | 0.88797
98845 | 98555 | E1 | CLA-BED | 24" CMRS Install | 316 | 2 |  | 0.0063291 | 0.21827
|  |  |  | Column Clamp | 269 | 149 |  | 0.5539
|  |  |  | Station Brackets | 66 | 6 |  | 0.090909
|  |  |  | Grounding | 227 | 30 |  | 0.13216
|  |  |  | Obstruction Brackets | 269 | 3 |  | 0.011152
|  |  |  | # Cables Pulled | 33 | 17 |  | 0.51515
|  | E1 | CLA-BED | Crossover (Arch Bar Installation) | 804 | 481 |  | 0.59826
98555 | 98220 | E1 | CLA-BED | 24" CMRS Install | 872 | 296 |  | 0.33945 | 0.66168
|  |  |  | Column Clamp | 588 | 479 |  | 0.81463
|  |  |  | Station Brackets | 103 | 59 |  | 0.57282
|  |  |  | Grounding | 659 | 526 |  | 0.79818
|  |  |  | Obstruction Brackets | 618 | 372 |  | 0.60194
|  |  |  | # Cables Pulled | 325 | 274 |  | 0.84308
98220 | 98140 | E1 | CLA-BED | 24" CMRS Install | 681 | 389 |  | 0.57122 | 0.51948
|  |  |  | Column Clamp | 414 | 84 |  | 0.2029
|  |  |  | Station Brackets | 764 | 718 |  | 0.93979
|  |  |  | Grounding | 93 | 70 |  | 0.75269
|  |  |  | Obstruction Brackets | 590 | 187 |  | 0.31695
|  |  |  | # Cables Pulled | 288 | 96 |  | 0.33333
98140 | 97920 | E1 | CLA-BED | 24" CMRS Install | 204 | 174 |  | 0.85294 | 0.63015
|  |  |  | Column Clamp | 825 | 708 |  | 0.85818
|  |  |  | Station Brackets | 504 | 406 |  | 0.80556
|  |  |  | Grounding | 155 | 74 |  | 0.47742
|  |  |  | Obstruction Brackets | 92 | 7 |  | 0.076087
|  |  |  | # Cables Pulled | 121 | 86 |  | 0.71074
97920 | 97670 | E1 | CLA-BED | Steel Mess Supports | 198 | 47 |  | 0.23737 | 0.45115
|  |  |  | Messenger Clamps | 374 | 215 |  | 0.57487
|  |  |  | Messenger Wire Pull | 771 | 624 |  | 0.80934
|  |  |  | Messenger Wire Tension | 989 | 581 |  | 0.58746
|  |  |  | # Cables Pulled | 707 | 352 |  | 0.49788
|  |  |  | Messenger Straps | 325 | 0 |  | 0
97670 | 97580 | E1 | CLASSON | 24" CMRS Install | 747 | 550 |  | 0.73628 | 0.67519
|  |  |  | Column Clamp | 582 | 240 |  | 0.41237
|  |  |  | Station Brackets | 544 | 501 |  | 0.92096
|  |  |  | Grounding | 29 | 25 |  | 0.86207
|  |  |  | Obstruction Brackets | 293 | 251 |  | 0.85666
|  |  |  | # Cables Pulled | 156 | 41 |  | 0.26282
97580 | 97230 | E1 | CLASSON | 24" CMRS Install | 524 | 165 |  | 0.31489 | 0.37422
|  |  |  | Column Clamp | 390 | 91 |  | 0.23333
|  |  |  | Station Brackets | 466 | 260 |  | 0.55794
|  |  |  | Grounding | 618 | 333 |  | 0.53883
|  |  |  | Obstruction Brackets | 53 | 27 |  | 0.50943
|  |  |  | # Cables Pulled | 44 | 4 |  | 0.090909
97230 | 96920 | E1 | CLASSON | 24" CMRS Install | 607 | 506 |  | 0.83361 | 0.4448
|  |  |  | Column Clamp | 194 | 69 |  | 0.35567
|  |  |  | Station Brackets | 958 | 71 |  | 0.074113
|  |  |  | Grounding | 361 | 12 |  | 0.033241
|  |  |  | Obstruction Brackets | 734 | 352 |  | 0.47956
|  |  |  | # Cables Pulled | 596 | 532 |  | 0.89262
96920 | 96685 | E1 | CLI-CLA | Steel Mess Supports | 202 | 41 |  | 0.20297 | 0.34375
|  |  |  | Messenger Clamps | 885 | 51 |  | 0.057627
|  |  |  | Messenger Wire Pull | 83 | 43 |  | 0.51807
|  |  |  | Messenger Wire Tension | 712 | 526 |  | 0.73876
|  |  |  | # Cables Pulled | 244 | 133 |  | 0.54508
|  |  |  | Messenger Straps | 23 | 0 |  | 0
96685 | 96460 | E1 | CLI-CLA | 24" CMRS Install | 122 | 86 |  | 0.70492 | 0.63012
|  |  |  | Column Clamp | 370 | 40 |  | 0.10811
|  |  |  | Station Brackets | 606 | 525 |  | 0.86634
|  |  |  | Grounding | 100 | 94 |  | 0.94
|  |  |  | Obstruction Brackets | 691 | 565 |  | 0.81766
|  |  |  | # Cables Pulled | 771 | 265 |  | 0.34371
96460 | 96387 | E1 | CLI-CLA | 24" CMRS Install | 909 | 322 |  | 0.35424 | 0.40815
|  |  |  | Column Clamp | 664 | 364 |  | 0.54819
|  |  |  | Station Brackets | 237 | 23 |  | 0.097046
|  |  |  | Grounding | 773 | 325 |  | 0.42044
|  |  |  | Obstruction Brackets | 174 | 55 |  | 0.31609
|  |  |  | # Cables Pulled | 606 | 432 |  | 0.71287
96387 | 96051 | E1 | CLI-CLA | 24" CMRS Install | 980 | 749 |  | 0.76429 | 0.58642
|  |  |  | Column Clamp | 956 | 366 |  | 0.38285
|  |  |  | Station Brackets | 391 | 356 |  | 0.91049
|  |  |  | Grounding | 132 | 128 |  | 0.9697
|  |  |  | Obstruction Brackets | 764 | 125 |  | 0.16361
|  |  |  | # Cables Pulled | 232 | 76 |  | 0.32759
96038 | 95998 | E1 | CLI-CLA | 24" CMRS Install | 51 | 17 |  | 0.33333 | 0.37392
|  |  |  | Column Clamp | 333 | 115 |  | 0.34535
|  |  |  | Station Brackets | 904 | 348 |  | 0.38496
|  |  |  | Grounding | 239 | 48 |  | 0.20084
|  |  |  | Obstruction Brackets | 571 | 362 |  | 0.63398
|  |  |  | # Cables Pulled | 852 | 294 |  | 0.34507
95998 | 95873 | E1 | CLI-CLA | 24" CMRS Install | 875 | 197 |  | 0.22514 | 0.44021
|  |  |  | Column Clamp | 383 | 49 |  | 0.12794
|  |  |  | Station Brackets | 178 | 82 |  | 0.46067
|  |  |  | Grounding | 947 | 406 |  | 0.42872
|  |  |  | Obstruction Brackets | 515 | 244 |  | 0.47379
|  |  |  | # Cables Pulled | 200 | 185 |  | 0.925
95873 | 95781 | E1 | CLINTON-WASHINGTON | 24" CMRS Install | 801 | 594 |  | 0.74157 | 0.44533
|  |  |  | Column Clamp | 973 | 328 |  | 0.3371
|  |  |  | Station Brackets | 498 | 132 |  | 0.26506
|  |  |  | Grounding | 395 | 265 |  | 0.67089
|  |  |  | Obstruction Brackets | 910 | 364 |  | 0.4
|  |  |  | # Cables Pulled | 307 | 79 |  | 0.25733
95781 | 95695 | E1 | CLINTON-WASHINGTON | 24" CMRS Install | 699 | 330 |  | 0.4721 | 0.5722
|  |  |  | Column Clamp | 731 | 420 |  | 0.57456
|  |  |  | Station Brackets | 832 | 28 |  | 0.033654
|  |  |  | Grounding | 622 | 348 |  | 0.55949
|  |  |  | Obstruction Brackets | 111 | 99 |  | 0.89189
|  |  |  | # Cables Pulled | 721 | 650 |  | 0.90153
95695 | 95544 | E1 | CLINTON-WASHINGTON | 24" CMRS Install | 287 | 136 |  | 0.47387 | 0.58576
|  |  |  | Column Clamp | 474 | 314 |  | 0.66245
|  |  |  | Station Brackets | 667 | 519 |  | 0.77811
|  |  |  | Grounding | 982 | 593 |  | 0.60387
|  |  |  | Obstruction Brackets | 47 | 43 |  | 0.91489
|  |  |  | # Cables Pulled | 86 | 7 |  | 0.081395
95544 | 95155 | E1 | CLINTON-WASHINGTON | 24" CMRS Install | 375 | 180 |  | 0.48 | 0.53734
|  |  |  | Column Clamp | 562 | 356 |  | 0.63345
|  |  |  | Station Brackets | 850 | 692 |  | 0.81412
|  |  |  | Grounding | 523 | 463 |  | 0.88528
|  |  |  | Obstruction Brackets | 814 | 294 |  | 0.36118
|  |  |  | # Cables Pulled | 340 | 17 |  | 0.05
95155 | 95004 | E1 | CLINTON-WASHINGTON | 24" CMRS Install | 531 | 44 |  | 0.082863 | 0.49789
|  |  |  | Column Clamp | 473 | 433 |  | 0.91543
|  |  |  | Station Brackets | 309 | 164 |  | 0.53074
|  |  |  | Grounding | 867 | 540 |  | 0.62284
|  |  |  | Obstruction Brackets | 722 | 266 |  | 0.36842
|  |  |  | # Cables Pulled | 561 | 262 |  | 0.46702
95004 | 94266 | E1 | FUL-CLI | 24" CMRS Install | 720 | 69 |  | 0.095833 | 0.44646
|  |  |  | Column Clamp | 736 | 524 |  | 0.71196
|  |  |  | Station Brackets | 863 | 167 |  | 0.19351
|  |  |  | Grounding | 733 | 699 |  | 0.95362
|  |  |  | Obstruction Brackets | 960 | 155 |  | 0.16146
|  |  |  | # Cables Pulled | 505 | 284 |  | 0.56238
94266 | 94207 | E1 | FUL-CLI | 24" CMRS Install | 806 | 788 |  | 0.97767 | 0.63479
|  |  |  | Column Clamp | 762 | 701 |  | 0.91995
|  |  |  | Station Brackets | 616 | 411 |  | 0.66721
|  |  |  | Grounding | 855 | 46 |  | 0.053801
|  |  |  | Obstruction Brackets | 393 | 111 |  | 0.28244
|  |  |  | # Cables Pulled | 444 | 403 |  | 0.90766
94207 | 93350 | E1 | FUL-CLI | 24" CMRS Install | 134 | 3 |  | 0.022388 | 0.39588
|  |  |  | Column Clamp | 718 | 467 |  | 0.65042
|  |  |  | Station Brackets | 152 | 21 |  | 0.13816
|  |  |  | Grounding | 250 | 27 |  | 0.108
|  |  |  | Obstruction Brackets | 404 | 266 |  | 0.65842
|  |  |  | # Cables Pulled | 94 | 75 |  | 0.79787
73350 | 73690 | E1 | FULTON | 15" CMRS Install | 708 | 447 |  | 0.63136 | 0.40653
|  |  |  | Column Clamp | 416 | 169 |  | 0.40625
|  |  |  | Station Brackets | 926 | 464 |  | 0.50108
|  |  |  | Grounding | 733 | 555 |  | 0.75716
|  |  |  | Obstruction Brackets | 70 | 1 |  | 0.014286
|  |  |  | # Cables Pulled | 124 | 16 |  | 0.12903
73690 | 74030 | E1 | FULTON | 15" CMRS Install | 885 | 667 |  | 0.75367 | 0.69108
|  |  |  | Column Clamp | 998 | 867 |  | 0.86874
|  |  |  | Station Brackets | 911 | 711 |  | 0.78046
|  |  |  | Grounding | 732 | 250 |  | 0.34153
|  |  |  | Obstruction Brackets | 180 | 80 |  | 0.44444
|  |  |  | # Cables Pulled | 637 | 610 |  | 0.95761
|  | E1 | FULTON | 15" CMRS Install | 882 | 502 |  | 0.56916 | 0.47781
|  |  |  | Column Clamp | 781 | 701 |  | 0.89757
|  |  |  | Station Brackets | 194 | 76 |  | 0.39175
|  |  |  | Grounding | 654 | 302 |  | 0.46177
|  |  |  | Obstruction Brackets | 736 | 45 |  | 0.061141
|  |  |  | # Cables Pulled | 585 | 284 |  | 0.48547
74030 | 76085 | E1 | HOY-FUL | 24" CMRS Install | 248 | 199 |  | 0.80242 | 0.63273
|  |  |  | Column Clamp | 207 | 40 |  | 0.19324
|  |  |  | Station Brackets | 169 | 128 |  | 0.7574
|  |  |  | Grounding | 767 | 509 |  | 0.66362
|  |  |  | Obstruction Brackets | 202 | 134 |  | 0.66337
|  |  |  | # Cables Pulled | 631 | 452 |  | 0.71632
76085 | 76110 | E1 | HOY-FUL | 15" CMRS Install | 84 | 6 |  | 0.071429 | 0.23858
|  |  |  | Column Clamp | 240 | 19 |  | 0.079167
|  |  |  | Station Brackets | 128 | 23 |  | 0.17969
|  |  |  | Grounding | 443 | 110 |  | 0.24831
|  |  |  | Obstruction Brackets | 78 | 44 |  | 0.5641
|  |  |  | # Cables Pulled | 561 | 162 |  | 0.28877
76110 | 76165 | E1 | HOY-FUL | 15" CMRS Install | 828 | 764 |  | 0.92271 | 0.43782
|  |  |  | Column Clamp | 580 | 336 |  | 0.57931
|  |  |  | Station Brackets | 121 | 32 |  | 0.26446
|  |  |  | Grounding | 709 | 182 |  | 0.2567
|  |  |  | Obstruction Brackets | 572 | 100 |  | 0.17483
|  |  |  | # Cables Pulled | 886 | 380 |  | 0.42889
76165 | 77470 | E1 | HOYT SCHERMERHORN | 15" CMRS Install | 892 | 832 |  | 0.93274 | 0.43861
|  |  |  | Column Clamp | 422 | 103 |  | 0.24408
|  |  |  | Station Brackets | 969 | 422 |  | 0.4355
|  |  |  | Grounding | 381 | 17 |  | 0.044619
|  |  |  | Obstruction Brackets | 106 | 37 |  | 0.34906
|  |  |  | # Cables Pulled | 911 | 570 |  | 0.62569
77470 | 77595 | E1 | BER-HOY | 15" CMRS Install | 388 | 221 |  | 0.56959 | 0.34202
|  |  |  | Column Clamp | 506 | 179 |  | 0.35375
|  |  |  | Station Brackets | 511 | 186 |  | 0.36399
|  |  |  | Grounding | 699 | 126 |  | 0.18026
|  |  |  | Obstruction Brackets | 48 | 27 |  | 0.5625
|  |  |  | # Cables Pulled | 499 | 11 |  | 0.022044
77595 | 78230 | E1 | BER-HOY | 24" CMRS Install | 260 | 224 |  | 0.86154 | 0.57832
|  |  |  | Column Clamp | 240 | 86 |  | 0.35833
|  |  |  | Station Brackets | 657 | 574 |  | 0.87367
|  |  |  | Grounding | 730 | 46 |  | 0.063014
|  |  |  | Obstruction Brackets | 214 | 112 |  | 0.52336
|  |  |  | # Cables Pulled | 919 | 726 |  | 0.78999
78230 | 78515 | E1 | BER-HOY | 24" CMRS Install | 576 | 219 |  | 0.38021 | 0.62055
|  |  |  | Column Clamp | 974 | 765 |  | 0.78542
|  |  |  | Station Brackets | 189 | 157 |  | 0.83069
|  |  |  | Grounding | 197 | 147 |  | 0.74619
|  |  |  | Obstruction Brackets | 760 | 392 |  | 0.51579
|  |  |  | # Cables Pulled | 714 | 332 |  | 0.46499
|  | E2 | BERGEN | Cable Tray Brackets | 544 | 20 |  | 0.036765 | 0.44874
|  |  |  | Installing Tray | 919 | 531 |  | 0.5778
|  |  |  | Core Drilling | 66 | 26 |  | 0.39394
|  |  |  | Cable Pull | 988 | 777 |  | 0.78644
78515 | 78315 | E2 | BER-HOY | Steel Mess Supports | 467 | 112 |  | 0.23983 | 0.50717
|  |  |  | Messenger Clamps | 305 | 293 |  | 0.96066
|  |  |  | Messenger Wire Pull | 269 | 215 |  | 0.79926
|  |  |  | Messenger Wire Tension | 622 | 204 |  | 0.32797
|  |  |  | # Cables Pulled | 651 | 7 |  | 0.010753
|  |  |  | Messenger Straps | 941 | 663 |  | 0.70457
78315 | 77655 | E2 | BER-HOY | 24" CMRS Install | 871 | 666 |  | 0.76464 | 0.55837
|  |  |  | Column Clamp | 521 | 251 |  | 0.48177
|  |  |  | Station Brackets | 729 | 242 |  | 0.33196
|  |  |  | Grounding | 305 | 93 |  | 0.30492
|  |  |  | Obstruction Brackets | 157 | 120 |  | 0.76433
|  |  |  | # Cables Pulled | 343 | 241 |  | 0.70262
77655 | 77585 | E2 | BER-HOY | 24" CMRS Install | 509 | 171 |  | 0.33595 | 0.50503
|  |  |  | Column Clamp | 743 | 392 |  | 0.52759
|  |  |  | Station Brackets | 739 | 173 |  | 0.2341
|  |  |  | Grounding | 736 | 171 |  | 0.23234
|  |  |  | Obstruction Brackets | 537 | 399 |  | 0.74302
|  |  |  | # Cables Pulled | 888 | 850 |  | 0.95721
77585 | 76845 | E2 | BER-HOY | 24" CMRS Install | 798 | 753 |  | 0.94361 | 0.60707
|  |  |  | Column Clamp | 282 | 135 |  | 0.47872
|  |  |  | Station Brackets | 369 | 194 |  | 0.52575
|  |  |  | Grounding | 201 | 71 |  | 0.35323
|  |  |  | Obstruction Brackets | 825 | 691 |  | 0.83758
|  |  |  | # Cables Pulled | 141 | 71 |  | 0.50355
76845 | 76150 | E2 | HOYT SCHERMERHORN | 24" CMRS Install | 288 | 100 |  | 0.34722 | 0.58379
|  |  |  | Column Clamp | 515 | 413 |  | 0.80194
|  |  |  | Station Brackets | 938 | 865 |  | 0.92217
|  |  |  | Grounding | 169 | 151 |  | 0.89349
|  |  |  | Obstruction Brackets | 747 | 103 |  | 0.13788
|  |  |  | # Cables Pulled | 15 | 6 |  | 0.4
76150 | 76090 | E2 | HOY-FUL | 24" CMRS Install | 230 | 187 |  | 0.81304 | 0.67006
|  |  |  | Column Clamp | 563 | 550 |  | 0.97691
|  |  |  | Station Brackets | 654 | 299 |  | 0.45719
|  |  |  | Grounding | 505 | 439 |  | 0.86931
|  |  |  | Obstruction Brackets | 53 | 32 |  | 0.60377
|  |  |  | # Cables Pulled | 763 | 229 |  | 0.30013
76090 | 75950 | E2 | HOY-FUL | 24" CMRS Install | 927 | 729 |  | 0.78641 | 0.45166
|  |  |  | Column Clamp | 472 | 104 |  | 0.22034
|  |  |  | Station Brackets | 593 | 51 |  | 0.086003
|  |  |  | Grounding | 514 | 274 |  | 0.53307
|  |  |  | Obstruction Brackets | 239 | 180 |  | 0.75314
|  |  |  | # Cables Pulled | 710 | 235 |  | 0.33099
75950 | 75900 | E2 | HOY-FUL | Steel Mess Supports | 727 | 53 |  | 0.072902 | 0.28667
|  |  |  | Messenger Clamps | 103 | 72 |  | 0.69903
|  |  |  | Messenger Wire Pull | 449 | 159 |  | 0.35412
|  |  |  | Messenger Wire Tension | 713 | 45 |  | 0.063114
|  |  |  | # Cables Pulled | 895 | 125 |  | 0.13966
|  |  |  | Messenger Straps | 905 | 354 |  | 0.39116
75900 | 74590 | E2 | HOY-FUL | 24" CMRS Install | 351 | 271 |  | 0.77208 | 0.47904
|  |  |  | Column Clamp | 344 | 61 |  | 0.17733
|  |  |  | Station Brackets | 951 | 426 |  | 0.44795
|  |  |  | Grounding | 706 | 333 |  | 0.47167
|  |  |  | Obstruction Brackets | 406 | 25 |  | 0.061576
|  |  |  | # Cables Pulled | 692 | 653 |  | 0.94364
74590 | 74450 | E2 | HOY-FUL | Steel Mess Supports | 71 | 46 |  | 0.64789 | 0.50088
|  |  |  | Messenger Clamps | 518 | 483 |  | 0.93243
|  |  |  | Messenger Wire Pull | 13 | 2 |  | 0.15385
|  |  |  | Messenger Wire Tension | 690 | 246 |  | 0.35652
|  |  |  | # Cables Pulled | 753 | 197 |  | 0.26162
|  |  |  | Messenger Straps | 559 | 365 |  | 0.65295
74450 | 74070 | E2 | HOY-FUL | 24" CMRS Install | 179 | 88 |  | 0.49162 | 0.32812
|  |  |  | Column Clamp | 476 | 7 |  | 0.014706
|  |  |  | Station Brackets | 496 | 455 |  | 0.91734
|  |  |  | Grounding | 77 | 5 |  | 0.064935
|  |  |  | Obstruction Brackets | 990 | 12 |  | 0.012121
|  |  |  | # Cables Pulled | 406 | 190 |  | 0.46798
74070 | 74030 | E2 | HOY-FUL | 24" CMRS Install | 122 | 95 |  | 0.77869 | 0.5656
|  |  |  | Column Clamp | 835 | 676 |  | 0.80958
|  |  |  | Station Brackets | 1000 | 144 |  | 0.144
|  |  |  | Grounding | 500 | 388 |  | 0.776
|  |  |  | Obstruction Brackets | 707 | 523 |  | 0.73975
|  |  |  | # Cables Pulled | 735 | 107 |  | 0.14558
74030 | 73690 | E2 | FULTON | 15" CMRS Install | 331 | 56 |  | 0.16918 | 0.5559
|  |  |  | Column Clamp | 225 | 52 |  | 0.23111
|  |  |  | Station Brackets | 126 | 101 |  | 0.80159
|  |  |  | Grounding | 787 | 718 |  | 0.91233
|  |  |  | Obstruction Brackets | 990 | 219 |  | 0.22121
|  |  |  | # Cables Pulled | 49 | 49 |  | 1
73690 | 73250 | E2 | FULTON | 15" CMRS Install | 297 | 168 |  | 0.56566 | 0.49098 | Cable Management Takeoffs Cell F110* - 147LF instead of 440LF | Cable Management Takeoffs Cell F110* - 147LF instead of 440LF
|  |  |  | Column Clamp | 958 | 392 |  | 0.40919
|  |  |  | Station Brackets | 622 | 52 |  | 0.083601
|  |  |  | Grounding | 970 | 797 |  | 0.82165
|  |  |  | Obstruction Brackets | 92 | 53 |  | 0.57609
|  |  |  | # Cables Pulled | 921 | 451 |  | 0.48969
|  | E2 | FULTON | 15" CMRS Install | 852 | 107 |  | 0.12559 | 0.39431
|  |  |  | Column Clamp | 166 | 95 |  | 0.57229
|  |  |  | Station Brackets | 701 | 480 |  | 0.68474
|  |  |  | Grounding | 527 | 260 |  | 0.49336
|  |  |  | Obstruction Brackets | 746 | 340 |  | 0.45576
|  |  |  | # Cables Pulled | 703 | 24 |  | 0.034139
73250 | 72315 | E2 | FUL-CLI | 24" CMRS Install | 494 | 435 |  | 0.88057 | 0.70826
|  |  |  | Column Clamp | 911 | 425 |  | 0.46652
|  |  |  | Station Brackets | 682 | 453 |  | 0.66422
|  |  |  | Grounding | 55 | 48 |  | 0.87273
|  |  |  | Obstruction Brackets | 784 | 516 |  | 0.65816
|  |  |  | # Cables Pulled | 745 | 527 |  | 0.70738
94400 | 94989 | E2 | FUL-CLI | 24" CMRS Install | 592 | 519 |  | 0.87669 | 0.43102
|  |  |  | Column Clamp | 241 | 82 |  | 0.34025
|  |  |  | Station Brackets | 733 | 139 |  | 0.18963
|  |  |  | Grounding | 673 | 126 |  | 0.18722
|  |  |  | Obstruction Brackets | 651 | 630 |  | 0.96774
|  |  |  | # Cables Pulled | 488 | 12 |  | 0.02459
94989 | 95114 | E2 | FUL-CLI | 24" CMRS Install | 486 | 108 |  | 0.22222 | 0.5764
|  |  |  | Column Clamp | 375 | 313 |  | 0.83467
|  |  |  | Station Brackets | 401 | 256 |  | 0.6384
|  |  |  | Grounding | 514 | 425 |  | 0.82685
|  |  |  | Obstruction Brackets | 406 | 239 |  | 0.58867
|  |  |  | # Cables Pulled | 515 | 179 |  | 0.34757
94989 | 95114 | E2 | CLINTON-WASHINGTON | 24" CMRS Install | 401 | 16 |  | 0.0399 | 0.39115
|  |  |  | Column Clamp | 111 | 95 |  | 0.85586
|  |  |  | Station Brackets | 409 | 118 |  | 0.28851
|  |  |  | Grounding | 128 | 98 |  | 0.76562
|  |  |  | Obstruction Brackets | 958 | 76 |  | 0.079332
|  |  |  | # Cables Pulled | 957 | 304 |  | 0.31766
95503 | 95701 | E2 | CLINTON-WASHINGTON | 24" CMRS Install | 314 | 262 |  | 0.83439 | 0.56972
|  |  |  | Column Clamp | 770 | 733 |  | 0.95195
|  |  |  | Station Brackets | 936 | 746 |  | 0.79701
|  |  |  | Grounding | 712 | 338 |  | 0.47472
|  |  |  | Obstruction Brackets | 23 | 5 |  | 0.21739
|  |  |  | # Cables Pulled | 21 | 3 |  | 0.14286
95767 | 95852 | E2 | CLINTON-WASHINGTON | 24" CMRS Install | 710 | 525 |  | 0.73944 | 0.62321
|  |  |  | Column Clamp | 303 | 160 |  | 0.52805
|  |  |  | Station Brackets | 662 | 399 |  | 0.60272
|  |  |  | Grounding | 785 | 338 |  | 0.43057
|  |  |  | Obstruction Brackets | 660 | 307 |  | 0.46515
|  |  |  | # Cables Pulled | 225 | 219 |  | 0.97333
95852 | 96366 | E2 | CLINTON-WASHINGTON | 24" CMRS Install | 225 | 82 |  | 0.36444 | 0.47851
|  |  |  | Column Clamp | 373 | 370 |  | 0.99196
|  |  |  | Station Brackets | 54 | 14 |  | 0.25926
|  |  |  | Grounding | 330 | 302 |  | 0.91515
|  |  |  | Obstruction Brackets | 417 | 127 |  | 0.30456
|  |  |  | # Cables Pulled | 308 | 11 |  | 0.035714
96366 | 96432 | E2 | CLINTON-WASHINGTON | 24" CMRS Install | 497 | 52 |  | 0.10463 | 0.42501
|  |  |  | Column Clamp | 607 | 189 |  | 0.31137
|  |  |  | Station Brackets | 350 | 121 |  | 0.34571
|  |  |  | Grounding | 254 | 161 |  | 0.63386
|  |  |  | Obstruction Brackets | 309 | 86 |  | 0.27832
|  |  |  | # Cables Pulled | 937 | 821 |  | 0.8762
96432 | 96649 | E2 | CLINTON-WASHINGTON | 24" CMRS Install | 871 | 244 |  | 0.28014 | 0.46863
|  |  |  | Column Clamp | 82 | 2 |  | 0.02439
|  |  |  | Station Brackets | 76 | 69 |  | 0.90789
|  |  |  | Grounding | 98 | 89 |  | 0.90816
|  |  |  | Obstruction Brackets | 571 | 349 |  | 0.61121
|  |  |  | # Cables Pulled | 75 | 6 |  | 0.08
95767 | 95852 | E2 | CLINTON-WASHINGTON | 24" CMRS Install | 79 | 14 |  | 0.17722 | 0.49416
|  |  |  | Column Clamp | 417 | 219 |  | 0.52518
|  |  |  | Station Brackets | 104 | 63 |  | 0.60577
|  |  |  | Grounding | 841 | 552 |  | 0.65636
|  |  |  | Obstruction Brackets | 386 | 352 |  | 0.91192
|  |  |  | # Cables Pulled | 226 | 20 |  | 0.088496
95852 | 96366 | E2 | CLI-CLA | 24" CMRS Install | 269 | 133 |  | 0.49442 | 0.39198
|  |  |  | Column Clamp | 971 | 566 |  | 0.5829
|  |  |  | Station Brackets | 240 | 36 |  | 0.15
|  |  |  | Grounding | 824 | 450 |  | 0.54612
|  |  |  | Obstruction Brackets | 90 | 15 |  | 0.16667
|  |  |  | # Cables Pulled | 102 | 42 |  | 0.41176
96366 | 96432 | E2 | CLI-CLA | 24" CMRS Install | 371 | 185 |  | 0.49865 | 0.54287
|  |  |  | Column Clamp | 184 | 155 |  | 0.84239
|  |  |  | Station Brackets | 620 | 34 |  | 0.054839
|  |  |  | Grounding | 879 | 755 |  | 0.85893
|  |  |  | Obstruction Brackets | 978 | 433 |  | 0.44274
|  |  |  | # Cables Pulled | 243 | 136 |  | 0.55967
96432 | 96649 | E2 | CLI-CLA | 24" CMRS Install | 115 | 22 |  | 0.1913 | 0.43741
|  |  |  | Column Clamp | 439 | 349 |  | 0.79499
|  |  |  | Station Brackets | 74 | 4 |  | 0.054054
|  |  |  | Grounding | 130 | 14 |  | 0.10769
|  |  |  | Obstruction Brackets | 725 | 530 |  | 0.73103
|  |  |  | # Cables Pulled | 974 | 726 |  | 0.74538
96649 | 96770 | E2 | CLI-CLA | 24" CMRS Install | 28 | 0 |  | 0 | 0.3164
|  |  |  | Column Clamp | 663 | 419 |  | 0.63198
|  |  |  | Station Brackets | 619 | 76 |  | 0.12278
|  |  |  | Grounding | 958 | 178 |  | 0.1858
|  |  |  | Obstruction Brackets | 71 | 6 |  | 0.084507
|  |  |  | # Cables Pulled | 671 | 586 |  | 0.87332
96770 | 96990 | E2 | CLI-CLA | Steel Mess Supports | 62 | 40 |  | 0.64516 | 0.64842
|  |  |  | Messenger Clamps | 806 | 614 |  | 0.76179
|  |  |  | Messenger Wire Pull | 771 | 126 |  | 0.16342
|  |  |  | Messenger Wire Tension | 13 | 7 |  | 0.53846
|  |  |  | # Cables Pulled | 501 | 398 |  | 0.79441
|  |  |  | Messenger Straps | 863 | 852 |  | 0.98725
96990 | 97230 | E2 | CLASSON | 24" CMRS Install | 235 | 212 |  | 0.90213 | 0.33969
|  |  |  | Column Clamp | 279 | 232 |  | 0.83154
|  |  |  | Station Brackets | 102 | 3 |  | 0.029412
|  |  |  | Grounding | 385 | 95 |  | 0.24675
|  |  |  | Obstruction Brackets | 146 | 3 |  | 0.020548
|  |  |  | # Cables Pulled | 772 | 6 |  | 0.007772
97230 | 97538 | E2 | CLASSON | 24" CMRS Install | 727 | 173 |  | 0.23796 | 0.45592
|  |  |  | Column Clamp | 831 | 261 |  | 0.31408
|  |  |  | Station Brackets | 928 | 52 |  | 0.056034
|  |  |  | Grounding | 270 | 215 |  | 0.7963
|  |  |  | Obstruction Brackets | 837 | 427 |  | 0.51016
|  |  |  | # Cables Pulled | 944 | 775 |  | 0.82097
97538 | 97670 | E2 | CLASSON | 24" CMRS Install | 183 | 139 |  | 0.75956 | 0.56298
|  |  |  | Column Clamp | 98 | 23 |  | 0.23469
|  |  |  | Station Brackets | 985 | 716 |  | 0.7269
|  |  |  | Grounding | 265 | 102 |  | 0.38491
|  |  |  | Obstruction Brackets | 331 | 135 |  | 0.40785
|  |  |  | # Cables Pulled | 294 | 254 |  | 0.86395
97670 | 98015 | E2 | CLA-BED | Steel Mess Supports | 970 | 805 |  | 0.8299 | 0.5751
|  |  |  | Messenger Clamps | 842 | 245 |  | 0.29097
|  |  |  | Messenger Wire Pull | 239 | 183 |  | 0.76569
|  |  |  | Messenger Wire Tension | 673 | 111 |  | 0.16493
|  |  |  | # Cables Pulled | 660 | 372 |  | 0.56364
|  |  |  | Messenger Straps | 948 | 792 |  | 0.83544
98015 | 98125 | E2 | CLA-BED | 24" CMRS Install | 179 | 86 |  | 0.48045 | 0.48487
|  |  |  | Column Clamp | 115 | 46 |  | 0.4
|  |  |  | Station Brackets | 32 | 13 |  | 0.40625
|  |  |  | Grounding | 613 | 406 |  | 0.66232
|  |  |  | Obstruction Brackets | 254 | 105 |  | 0.41339
|  |  |  | # Cables Pulled | 203 | 111 |  | 0.5468
98125 | 98185 | E2 | CLA-BED | 24" CMRS Install | 514 | 0 |  | 0 | 0.62769
|  |  |  | Column Clamp | 860 | 850 |  | 0.98837
|  |  |  | Station Brackets | 211 | 188 |  | 0.891
|  |  |  | Grounding | 145 | 138 |  | 0.95172
|  |  |  | Obstruction Brackets | 317 | 34 |  | 0.10726
|  |  |  | # Cables Pulled | 633 | 524 |  | 0.8278
98185 | 98440 | E2 | CLA-BED | 24" CMRS Install | 579 | 419 |  | 0.72366 | 0.51162
|  |  |  | Column Clamp | 107 | 45 |  | 0.42056
|  |  |  | Station Brackets | 289 | 108 |  | 0.3737
|  |  |  | Grounding | 365 | 177 |  | 0.48493
|  |  |  | Obstruction Brackets | 740 | 415 |  | 0.56081
|  |  |  | # Cables Pulled | 83 | 42 |  | 0.50602
|  | E2 | CLA-BED | Crossover (Arch Bar Installation) | 603 | 551 |  | 0.91376
98440 | 98586 | E2 | CLA-BED | 24" CMRS Install | 620 | 429 |  | 0.69194 | 0.62998
|  |  |  | Column Clamp | 865 | 851 |  | 0.98382
|  |  |  | Station Brackets | 356 | 245 |  | 0.6882
|  |  |  | Grounding | 802 | 688 |  | 0.85786
|  |  |  | Obstruction Brackets | 679 | 323 |  | 0.4757
|  |  |  | # Cables Pulled | 522 | 43 |  | 0.082375
98586 | 98836 | E2 | CLA-BED | Steel Mess Supports | 866 | 285 |  | 0.3291 | 0.41427
|  |  |  | Messenger Clamps | 139 | 61 |  | 0.43885
|  |  |  | Messenger Wire Pull | 53 | 31 |  | 0.58491
|  |  |  | Messenger Wire Tension | 574 | 223 |  | 0.3885
|  |  |  | # Cables Pulled | 579 | 116 |  | 0.20035
|  |  |  | Messenger Straps | 945 | 514 |  | 0.54392
98836 | 99505 | E2 | BEDFORD NOSTRAND | Cable Tray Brackets | 325 | 49 |  | 0.15077 | 0.59883
|  |  |  | Installing Tray | 599 | 570 |  | 0.95159
|  |  |  | Core Drilling | 118 | 102 |  | 0.86441
|  |  |  | Cable Pull | 273 | 117 |  | 0.42857
99505 | 99950 | E2 | BED-MYR | Steel Mess Supports | 223 | 205 |  | 0.91928 | 0.5807
|  |  |  | Messenger Clamps | 708 | 360 |  | 0.50847
|  |  |  | Messenger Wire Pull | 362 | 336 |  | 0.92818
|  |  |  | Messenger Wire Tension | 852 | 122 |  | 0.14319
|  |  |  | # Cables Pulled | 444 | 264 |  | 0.59459
|  |  |  | Messenger Straps | 694 | 271 |  | 0.39049
|  | E2 | CLA-BED | Crossover (Arch Bar Installation) | 608 | 143 |  | 0.2352
99950 | 100290 | E2 | BED-MYR | 24" CMRS Install | 120 | 104 |  | 0.86667 | 0.54222
|  |  |  | Column Clamp | 503 | 36 |  | 0.071571
|  |  |  | Station Brackets | 624 | 276 |  | 0.44231
|  |  |  | Grounding | 764 | 259 |  | 0.33901
|  |  |  | Obstruction Brackets | 153 | 133 |  | 0.86928
|  |  |  | # Cables Pulled | 155 | 103 |  | 0.66452
100290 | 100740 | E2 | BED-MYR | 24" CMRS Install | 537 | 532 |  | 0.99069 | 0.58866
|  |  |  | Column Clamp | 772 | 42 |  | 0.054404
|  |  |  | Station Brackets | 850 | 175 |  | 0.20588
|  |  |  | Grounding | 833 | 300 |  | 0.36014
|  |  |  | Obstruction Brackets | 970 | 932 |  | 0.96082
|  |  |  | # Cables Pulled | 50 | 48 |  | 0.96
100740 | 100792 | E2 | BED-MYR | 24" CMRS Install | 180 | 44 |  | 0.24444 | 0.58839
|  |  |  | Column Clamp | 534 | 122 |  | 0.22846
|  |  |  | Station Brackets | 126 | 82 |  | 0.65079
|  |  |  | Grounding | 285 | 231 |  | 0.81053
|  |  |  | Obstruction Brackets | 501 | 410 |  | 0.81836
|  |  |  | # Cables Pulled | 396 | 308 |  | 0.77778
100792 | 101595 | E2 | BED-MYR | 24" CMRS Install | 403 | 344 |  | 0.8536 | 0.63816
|  |  |  | Column Clamp | 62 | 3 |  | 0.048387
|  |  |  | Station Brackets | 493 | 481 |  | 0.97566
|  |  |  | Grounding | 796 | 298 |  | 0.37437
|  |  |  | Obstruction Brackets | 824 | 764 |  | 0.92718
|  |  |  | # Cables Pulled | 591 | 384 |  | 0.64975
101595 | 101688 | E2 | BED-MYR | 24" CMRS Install | 154 | 113 |  | 0.73377 | 0.39707
|  |  |  | Column Clamp | 755 | 263 |  | 0.34834
|  |  |  | Station Brackets | 723 | 20 |  | 0.027663
|  |  |  | Grounding | 329 | 43 |  | 0.1307
|  |  |  | Obstruction Brackets | 477 | 268 |  | 0.56184
|  |  |  | # Cables Pulled | 743 | 431 |  | 0.58008
101688 | 102400 | E2 | MYRTLE AVE | 15" CMRS Install | 872 | 781 |  | 0.89564 | 0.62812
|  |  |  | Column Clamp | 994 | 882 |  | 0.88732
|  |  |  | Station Brackets | 739 | 169 |  | 0.22869
|  |  |  | Grounding | 468 | 459 |  | 0.98077
|  |  |  | Obstruction Brackets | 449 | 1 |  | 0.0022272
|  |  |  | # Cables Pulled | 447 | 346 |  | 0.77405
102400 | 102550 | E2 | MYR-FLU | Steel Mess Supports | 497 | 299 |  | 0.60161 | 0.50341
|  |  |  | Messenger Clamps | 34 | 4 |  | 0.11765
|  |  |  | Messenger Wire Pull | 904 | 799 |  | 0.88385
|  |  |  | Messenger Wire Tension | 806 | 710 |  | 0.88089
|  |  |  | # Cables Pulled | 629 | 152 |  | 0.24165
|  |  |  | Messenger Straps | 882 | 260 |  | 0.29478
102550 | 103165 | E2 | MYR-FLU | 15" CMRS Install | 273 | 72 |  | 0.26374 | 0.58428
|  |  |  | Column Clamp | 865 | 61 |  | 0.07052
|  |  |  | Station Brackets | 752 | 560 |  | 0.74468
|  |  |  | Grounding | 709 | 459 |  | 0.64739
|  |  |  | Obstruction Brackets | 242 | 228 |  | 0.94215
|  |  |  | # Cables Pulled | 694 | 581 |  | 0.83718
103165 | 103230 | E2 | MYR-FLU | 15" CMRS Install | 383 | 269 |  | 0.70235 | 0.67406
|  |  |  | Column Clamp | 62 | 40 |  | 0.64516
|  |  |  | Station Brackets | 450 | 434 |  | 0.96444
|  |  |  | Grounding | 440 | 21 |  | 0.047727
|  |  |  | Obstruction Brackets | 845 | 811 |  | 0.95976
|  |  |  | # Cables Pulled | 647 | 469 |  | 0.72488
103230 | 103809 | E2 | MYR-FLU | 15" CMRS Install | 654 | 353 |  | 0.53976 | 0.49471
|  |  |  | Column Clamp | 383 | 71 |  | 0.18538
|  |  |  | Station Brackets | 238 | 116 |  | 0.48739
|  |  |  | Grounding | 820 | 566 |  | 0.69024
|  |  |  | Obstruction Brackets | 693 | 132 |  | 0.19048
|  |  |  | # Cables Pulled | 864 | 756 |  | 0.875
103809 | 103902 | E2 | MYR-FLU | 15" CMRS Install | 440 | 36 |  | 0.081818 | 0.41692
|  |  |  | Column Clamp | 431 | 99 |  | 0.2297
|  |  |  | Station Brackets | 337 | 231 |  | 0.68546
|  |  |  | Grounding | 489 | 139 |  | 0.28425
|  |  |  | Obstruction Brackets | 295 | 102 |  | 0.34576
|  |  |  | # Cables Pulled | 526 | 460 |  | 0.87452
103902 | 104595 | E2 | FLUSHING | 15" CMRS Install | 779 | 626 |  | 0.80359 | 0.43047
|  |  |  | Column Clamp | 725 | 213 |  | 0.29379
|  |  |  | Station Brackets | 547 | 541 |  | 0.98903
|  |  |  | Grounding | 68 | 18 |  | 0.26471
|  |  |  | Obstruction Brackets | 555 | 64 |  | 0.11532
|  |  |  | # Cables Pulled | 868 | 101 |  | 0.11636
104595 | 104750 | E2 | FLU-BRO | Steel Mess Supports | 732 | 23 |  | 0.031421 | 0.50543
|  |  |  | Messenger Clamps | 794 | 88 |  | 0.11083
|  |  |  | Messenger Wire Pull | 74 | 31 |  | 0.41892
|  |  |  | Messenger Wire Tension | 624 | 609 |  | 0.97596
|  |  |  | # Cables Pulled | 866 | 625 |  | 0.72171
|  |  |  | Messenger Straps | 663 | 513 |  | 0.77376
104750 | 105270 | E2 | FLU-BRO | 15" CMRS Install | 912 | 705 |  | 0.77303 | 0.60425
|  |  |  | Column Clamp | 523 | 420 |  | 0.80306
|  |  |  | Station Brackets | 198 | 156 |  | 0.78788
|  |  |  | Grounding | 233 | 51 |  | 0.21888
|  |  |  | Obstruction Brackets | 812 | 262 |  | 0.32266
|  |  |  | # Cables Pulled | 100 | 72 |  | 0.72
105270 | 105930 | E2 | FLU-BRO | 15" CMRS Install | 690 | 410 |  | 0.5942 | 0.37248
|  |  |  | Column Clamp | 41 | 4 |  | 0.097561
|  |  |  | Station Brackets | 483 | 241 |  | 0.49896
|  |  |  | Grounding | 571 | 385 |  | 0.67426
|  |  |  | Obstruction Brackets | 371 | 53 |  | 0.14286
|  |  |  | # Cables Pulled | 991 | 225 |  | 0.22704
105930 | 106003 | E2 | FLU-BRO | 15" CMRS Install | 408 | 232 |  | 0.56863 | 0.44706
|  |  |  | Column Clamp | 453 | 58 |  | 0.12804
|  |  |  | Station Brackets | 280 | 53 |  | 0.18929
|  |  |  | Grounding | 212 | 205 |  | 0.96698
|  |  |  | Obstruction Brackets | 994 | 780 |  | 0.78471
|  |  |  | # Cables Pulled | 447 | 20 |  | 0.044743
106003 | 106648 | E2 | BROADWAY | 15" CMRS Install | 895 | 28 |  | 0.031285 | 0.34644
|  |  |  | Column Clamp | 785 | 93 |  | 0.11847
|  |  |  | Station Brackets | 633 | 501 |  | 0.79147
|  |  |  | Grounding | 479 | 43 |  | 0.08977
|  |  |  | Obstruction Brackets | 886 | 53 |  | 0.059819
|  |  |  | # Cables Pulled | 494 | 488 |  | 0.98785
|  | E2 | BROADWAY | 15" CMRS Install | 176 | 41 |  | 0.23295 | 0.62983
|  |  |  | Column Clamp | 107 | 105 |  | 0.98131
|  |  |  | Station Brackets | 733 | 482 |  | 0.65757
|  |  |  | Grounding | 419 | 373 |  | 0.89021
|  |  |  | Obstruction Brackets | 893 | 815 |  | 0.91265
|  |  |  | # Cables Pulled | 777 | 81 |  | 0.10425
|  | E2 | BROADWAY | 15" CMRS Install | 715 | 528 |  | 0.73846 | 0.48994
|  |  |  | Column Clamp | 525 | 229 |  | 0.43619
|  |  |  | Station Brackets | 53 | 47 |  | 0.88679
|  |  |  | Grounding | 448 | 11 |  | 0.024554
|  |  |  | Obstruction Brackets | 852 | 119 |  | 0.13967
|  |  |  | # Cables Pulled | 479 | 342 |  | 0.71399
106650 | 106920 | E2 | BRO-MET | Steel Mess Supports | 260 | 54 |  | 0.20769 | 0.50025
|  |  |  | Messenger Clamps | 671 | 436 |  | 0.64978
|  |  |  | Messenger Wire Pull | 84 | 9 |  | 0.10714
|  |  |  | Messenger Wire Tension | 769 | 199 |  | 0.25878
|  |  |  | # Cables Pulled | 289 | 253 |  | 0.87543
|  |  |  | Messenger Straps | 596 | 538 |  | 0.90268
106918 | 107620 | E2 | BRO-MET | 15" CMRS Install | 275 | 10 |  | 0.036364 | 0.39963
|  |  |  | Column Clamp | 650 | 334 |  | 0.51385
|  |  |  | Station Brackets | 557 | 214 |  | 0.3842
|  |  |  | Grounding | 836 | 299 |  | 0.35766
|  |  |  | Obstruction Brackets | 935 | 915 |  | 0.97861
|  |  |  | # Cables Pulled | 889 | 113 |  | 0.12711
107620 | 107683 | E2 | BRO-MET | 15" CMRS Install | 424 | 398 |  | 0.93868 | 0.44769
|  |  |  | Column Clamp | 408 | 193 |  | 0.47304
|  |  |  | Station Brackets | 872 | 251 |  | 0.28784
|  |  |  | Grounding | 869 | 664 |  | 0.7641
|  |  |  | Obstruction Brackets | 744 | 80 |  | 0.10753
|  |  |  | # Cables Pulled | 174 | 20 |  | 0.11494
107683 | 108360 | E2 | BRO-MET | 15" CMRS Install | 405 | 170 |  | 0.41975 | 0.33592
|  |  |  | Column Clamp | 711 | 413 |  | 0.58087
|  |  |  | Station Brackets | 561 | 101 |  | 0.18004
|  |  |  | Grounding | 213 | 39 |  | 0.1831
|  |  |  | Obstruction Brackets | 738 | 80 |  | 0.1084
|  |  |  | # Cables Pulled | 346 | 188 |  | 0.54335
108360 | 109235 | E2 | METROPOLITAN | 15" CMRS Install | 918 | 783 |  | 0.85294 | 0.73043
|  |  |  | Column Clamp | 415 | 305 |  | 0.73494
|  |  |  | Station Brackets | 968 | 541 |  | 0.55888
|  |  |  | Grounding | 178 | 167 |  | 0.9382
|  |  |  | Obstruction Brackets | 403 | 307 |  | 0.76179
|  |  |  | # Cables Pulled | 530 | 284 |  | 0.53585
109235 | 110795 | E2 | MET-NAS | 24" CMRS Install | 792 | 782 |  | 0.98737 | 0.65072
|  |  |  | Column Clamp | 262 | 71 |  | 0.27099
|  |  |  | Station Brackets | 568 | 432 |  | 0.76056
|  |  |  | Grounding | 302 | 209 |  | 0.69205
|  |  |  | Obstruction Brackets | 785 | 239 |  | 0.30446
|  |  |  | # Cables Pulled | 108 | 96 |  | 0.88889
110795 | 110865 | E2 | MET-NAS | 24" CMRS Install | 16 | 3 |  | 0.1875 | 0.34638
|  |  |  | Column Clamp | 502 | 183 |  | 0.36454
|  |  |  | Station Brackets | 40 | 18 |  | 0.45
|  |  |  | Grounding | 655 | 480 |  | 0.73282
|  |  |  | Obstruction Brackets | 273 | 62 |  | 0.22711
|  |  |  | # Cables Pulled | 43 | 5 |  | 0.11628
110865 | 113020 | E2 | MET-NAS | 24" CMRS Install | 632 | 502 |  | 0.7943 | 0.54701
|  |  |  | Column Clamp | 607 | 299 |  | 0.49259
|  |  |  | Station Brackets | 934 | 191 |  | 0.2045
|  |  |  | Grounding | 973 | 614 |  | 0.63104
|  |  |  | Obstruction Brackets | 765 | 200 |  | 0.26144
|  |  |  | # Cables Pulled | 992 | 891 |  | 0.89819
113020 | 113155 | E2 | MET-NAS | 24" CMRS Install | 640 | 77 |  | 0.12031 | 0.48964
|  |  |  | Column Clamp | 351 | 329 |  | 0.93732
|  |  |  | Station Brackets | 138 | 45 |  | 0.32609
|  |  |  | Grounding | 251 | 3 |  | 0.011952
|  |  |  | Obstruction Brackets | 259 | 250 |  | 0.96525
|  |  |  | # Cables Pulled | 26 | 15 |  | 0.57692
113155 | 113815 | E2 | NASSAU | 24" CMRS Install | 946 | 822 |  | 0.86892 | 0.56228
|  |  |  | Column Clamp | 821 | 249 |  | 0.30329
|  |  |  | Station Brackets | 647 | 111 |  | 0.17156
|  |  |  | Grounding | 803 | 673 |  | 0.83811
|  |  |  | Obstruction Brackets | 136 | 85 |  | 0.625
|  |  |  | # Cables Pulled | 277 | 157 |  | 0.56679
113815 | 114105 | E2 | NAS-GRE | Steel Mess Supports | 133 | 72 |  | 0.54135 | 0.6485
|  |  |  | Messenger Clamps | 784 | 508 |  | 0.64796
|  |  |  | Messenger Wire Pull | 561 | 452 |  | 0.8057
|  |  |  | Messenger Wire Tension | 279 | 107 |  | 0.38351
|  |  |  | # Cables Pulled | 642 | 329 |  | 0.51246
|  |  |  | Messenger Straps | 125 | 125 |  | 1
114105 | 114730 | E2 | NAS-GRE | 24" CMRS Install | 899 | 411 |  | 0.45717 | 0.56564
|  |  |  | Column Clamp | 361 | 278 |  | 0.77008
|  |  |  | Station Brackets | 123 | 37 |  | 0.30081
|  |  |  | Grounding | 47 | 30 |  | 0.6383
|  |  |  | Obstruction Brackets | 110 | 74 |  | 0.67273
|  |  |  | # Cables Pulled | 566 | 314 |  | 0.55477
114730 | 114910 | E2 | NAS-GRE | Steel Mess Supports | 650 | 280 |  | 0.43077 | 0.62198
|  |  |  | Messenger Clamps | 264 | 249 |  | 0.94318
|  |  |  | Messenger Wire Pull | 53 | 3 |  | 0.056604
|  |  |  | Messenger Wire Tension | 346 | 188 |  | 0.54335
|  |  |  | # Cables Pulled | 917 | 769 |  | 0.8386
|  |  |  | Messenger Straps | 62 | 57 |  | 0.91935
114910 | 115625 | E2 | NAS-GRE | 24" CMRS Install | 211 | 40 |  | 0.18957 | 0.46422
|  |  |  | Column Clamp | 385 | 359 |  | 0.93247
|  |  |  | Station Brackets | 224 | 92 |  | 0.41071
|  |  |  | Grounding | 612 | 8 |  | 0.013072
|  |  |  | Obstruction Brackets | 201 | 80 |  | 0.39801
|  |  |  | # Cables Pulled | 839 | 706 |  | 0.84148
115625 | 116435 | E2 | GREENPOINT | 24" CMRS Install | 259 | 133 |  | 0.51351 | 0.40021
|  |  |  | Column Clamp | 585 | 62 |  | 0.10598
|  |  |  | Station Brackets | 620 | 384 |  | 0.61935
|  |  |  | Grounding | 741 | 70 |  | 0.094467
|  |  |  | Obstruction Brackets | 624 | 424 |  | 0.67949
|  |  |  | # Cables Pulled | 520 | 202 |  | 0.38846
116435 | 117130 | E2 | GRE-21S | 24" CMRS Install | 156 | 64 |  | 0.41026 | 0.46284
|  |  |  | Column Clamp | 495 | 323 |  | 0.65253
|  |  |  | Station Brackets | 528 | 241 |  | 0.45644
|  |  |  | Grounding | 116 | 18 |  | 0.15517
|  |  |  | Obstruction Brackets | 619 | 574 |  | 0.9273
|  |  |  | # Cables Pulled | 154 | 27 |  | 0.17532
|  | E2 | GRE-21S | Crossover (Arch Bar Installation) | 328 | 327 |  | 0.99695
117130 | 121035 | E2 | GRE-21S | 24" CMRS Install | 824 | 241 |  | 0.29248 | 0.51563
|  |  |  | Column Clamp | 747 | 336 |  | 0.4498
|  |  |  | Station Brackets | 564 | 394 |  | 0.69858
|  |  |  | Grounding | 227 | 144 |  | 0.63436
|  |  |  | Obstruction Brackets | 686 | 220 |  | 0.3207
|  |  |  | # Cables Pulled | 983 | 686 |  | 0.69786
121035 | 122030 | E2 | 21ST STATION | Steel Mess Supports | 65 | 48 |  | 0.73846 | 0.65013
|  |  |  | Messenger Clamps | 400 | 361 |  | 0.9025
|  |  |  | Messenger Wire Pull | 113 | 32 |  | 0.28319
|  |  |  | Messenger Wire Tension | 723 | 517 |  | 0.71508
|  |  |  | # Cables Pulled | 346 | 213 |  | 0.61561
|  |  |  | Messenger Straps | 435 | 281 |  | 0.64598
122030 | 122430 | E2 | 21S-COU | 24" CMRS Install | 521 | 155 |  | 0.2975 | 0.28453
|  |  |  | Column Clamp | 791 | 137 |  | 0.1732
|  |  |  | Station Brackets | 914 | 125 |  | 0.13676
|  |  |  | Grounding | 680 | 63 |  | 0.092647
|  |  |  | Obstruction Brackets | 592 | 551 |  | 0.93074
|  |  |  | # Cables Pulled | 642 | 49 |  | 0.076324
122430 | 122660 | E2 | 21S-COU | Steel Mess Supports | 785 | 727 |  | 0.92611 | 0.43622
|  |  |  | Messenger Clamps | 870 | 622 |  | 0.71494
|  |  |  | Messenger Wire Pull | 344 | 59 |  | 0.17151
|  |  |  | Messenger Wire Tension | 699 | 118 |  | 0.16881
|  |  |  | # Cables Pulled | 935 | 568 |  | 0.60749
|  |  |  | Messenger Straps | 809 | 23 |  | 0.02843
122660 | 122827 | E2 | 21S-COU | 24" CMRS Install | 145 | 4 |  | 0.027586 | 0.33954
|  |  |  | Column Clamp | 633 | 529 |  | 0.8357
|  |  |  | Station Brackets | 322 | 23 |  | 0.071429
|  |  |  | Grounding | 607 | 86 |  | 0.14168
|  |  |  | Obstruction Brackets | 159 | 26 |  | 0.16352
|  |  |  | # Cables Pulled | 370 | 295 |  | 0.7973
122827 | 123085 | E2 | 21S-COU | Steel Mess Supports | 578 | 550 |  | 0.95156 | 0.64393
|  |  |  | Messenger Clamps | 693 | 614 |  | 0.886
|  |  |  | Messenger Wire Pull | 19 | 19 |  | 1
|  |  |  | Messenger Wire Tension | 814 | 160 |  | 0.19656
|  |  |  | # Cables Pulled | 545 | 445 |  | 0.81651
|  |  |  | Messenger Straps | 695 | 9 |  | 0.01295
123085 | 123690 | E2 | COURT SQ | Cable Tray Brackets | 860 | 262 |  | 0.30465 | 0.34077
|  |  |  | Installing Tray | 302 | 6 |  | 0.019868
|  |  |  | Core Drilling | 110 | 69 |  | 0.62727
|  |  |  | Cable Pull | 479 | 197 |  | 0.41127
123690 | 123750 | E2 | COU-QUE | Steel Mess Supports | 533 | 374 |  | 0.70169 | 0.4913
|  |  |  | Messenger Clamps | 390 | 273 |  | 0.7
|  |  |  | Messenger Wire Pull | 457 | 74 |  | 0.16193
|  |  |  | Messenger Wire Tension | 373 | 365 |  | 0.97855
|  |  |  | # Cables Pulled | 843 | 99 |  | 0.11744
|  |  |  | Messenger Straps | 406 | 117 |  | 0.28818
123750 | 123950 | E2 | COU-QUE | Steel Mess Supports | 158 | 98 |  | 0.62025 | 0.42184
|  |  |  | Messenger Clamps | 654 | 90 |  | 0.13761
|  |  |  | Messenger Wire Pull | 278 | 37 |  | 0.13309
|  |  |  | Messenger Wire Tension | 653 | 262 |  | 0.40123
|  |  |  | # Cables Pulled | 616 | 354 |  | 0.57468
|  |  |  | Messenger Straps | 676 | 449 |  | 0.6642
123950 | 124050 | E2 | COU-QUE | Steel Mess Supports | 198 | 115 |  | 0.58081 | 0.39705
|  |  |  | Messenger Clamps | 493 | 144 |  | 0.29209
|  |  |  | Messenger Wire Pull | 767 | 248 |  | 0.32334
|  |  |  | Messenger Wire Tension | 625 | 15 |  | 0.024
|  |  |  | # Cables Pulled | 591 | 546 |  | 0.92386
|  |  |  | Messenger Straps | 701 | 167 |  | 0.23823
124050 | 124190 | E2 | COU-QUE | Steel Mess Supports | 772 | 325 |  | 0.42098 | 0.44823
|  |  |  | Messenger Clamps | 604 | 176 |  | 0.29139
|  |  |  | Messenger Wire Pull | 577 | 281 |  | 0.487
|  |  |  | Messenger Wire Tension | 187 | 1 |  | 0.0053476
|  |  |  | # Cables Pulled | 376 | 221 |  | 0.58777
|  |  |  | Messenger Straps | 388 | 348 |  | 0.89691
124190 | 124490 | E2 | COU-QUE | Steel Mess Supports | 514 | 200 |  | 0.38911 | 0.27499
|  |  |  | Messenger Clamps | 469 | 111 |  | 0.23667
|  |  |  | Messenger Wire Pull | 703 | 153 |  | 0.21764
|  |  |  | Messenger Wire Tension | 346 | 201 |  | 0.58092
|  |  |  | # Cables Pulled | 711 | 90 |  | 0.12658
|  |  |  | Messenger Straps | 101 | 10 |  | 0.09901
124490 | 124700 | E2 | COU-QUE | Steel Mess Supports | 678 | 138 |  | 0.20354 | 0.65464
|  |  |  | Messenger Clamps | 138 | 79 |  | 0.57246
|  |  |  | Messenger Wire Pull | 457 | 358 |  | 0.78337
|  |  |  | Messenger Wire Tension | 199 | 179 |  | 0.8995
|  |  |  | # Cables Pulled | 553 | 266 |  | 0.48101
|  |  |  | Messenger Straps | 83 | 82 |  | 0.98795
124700 | 125010 | E2 | COU-QUE | Steel Mess Supports | 885 | 118 |  | 0.13333 | 0.51593
|  |  |  | Messenger Clamps | 112 | 40 |  | 0.35714
|  |  |  | Messenger Wire Pull | 794 | 125 |  | 0.15743
|  |  |  | Messenger Wire Tension | 671 | 429 |  | 0.63934
|  |  |  | # Cables Pulled | 566 | 529 |  | 0.93463
|  |  |  | Messenger Straps | 190 | 166 |  | 0.87368
|  | E2 | COU-QUE | Crossover (Arch Bar Installation) | 920 | 868 |  | 0.94348
75650 | 78244 | B3 | BERGEN ST | Steel Mess Supports | 508 | 425 |  | 0.83661 | 0.53036
|  |  |  | Messenger Clamps | 717 | 687 |  | 0.95816
|  |  |  | Messenger Wire Pull | 268 | 170 |  | 0.63433
|  |  |  | Messenger Wire Tension | 180 | 17 |  | 0.094444
|  |  |  | # Cables Pulled | 916 | 68 |  | 0.074236
|  |  |  | Messenger Straps | 859 | 502 |  | 0.5844
|  | B3 | BER-JAY | Steel Mess Supports | 452 | 309 |  | 0.68363 | 0.5951
|  |  |  | Messenger Clamps | 170 | 114 |  | 0.67059
|  |  |  | Messenger Wire Pull | 98 | 90 |  | 0.91837
|  |  |  | Messenger Wire Tension | 546 | 236 |  | 0.43223
|  |  |  | # Cables Pulled | 464 | 278 |  | 0.59914
|  |  |  | Messenger Straps | 255 | 68 |  | 0.26667
|  | B4 | BER-JAY | Steel Mess Supports | 315 | 26 |  | 0.08254 | 0.47812
|  |  |  | Messenger Clamps | 500 | 183 |  | 0.366
|  |  |  | Messenger Wire Pull | 755 | 177 |  | 0.23444
|  |  |  | Messenger Wire Tension | 141 | 128 |  | 0.9078
|  |  |  | # Cables Pulled | 38 | 25 |  | 0.65789
|  |  |  | Messenger Straps | 837 | 519 |  | 0.62007
|  | E3/E4 | COURT SQ | Steel Mess Supports | 619 | 443 |  | 0.71567 | 0.38749
|  |  |  | Messenger Clamps | 641 | 482 |  | 0.75195
|  |  |  | Messenger Wire Pull | 462 | 32 |  | 0.069264
|  |  |  | Messenger Wire Tension | 406 | 8 |  | 0.019704
|  |  |  | # Cables Pulled | 742 | 260 |  | 0.3504
|  |  |  | Messenger Straps | 512 | 214 |  | 0.41797
75640 | 75300 | B1 | BER-CAR | Steel Mess Supports | 900 | 216 |  | 0.24 | 0.5303
|  |  |  | Messenger Clamps | 387 | 257 |  | 0.66408
|  |  |  | Messenger Wire Pull | 210 | 208 |  | 0.99048
|  |  |  | Messenger Wire Tension | 599 | 139 |  | 0.23205
|  |  |  | # Cables Pulled | 590 | 119 |  | 0.20169
|  |  |  | Messenger Straps | 867 | 740 |  | 0.85352
68570 | 68330 | B3 | 4TH AVE | Steel Mess Supports | 668 | 444 |  | 0.66467 | 0.43897
|  |  |  | Messenger Clamps | 727 | 429 |  | 0.5901
|  |  |  | Messenger Wire Pull | 967 | 376 |  | 0.38883
|  |  |  | Messenger Wire Tension | 780 | 165 |  | 0.21154
|  |  |  | # Cables Pulled | 916 | 419 |  | 0.45742
|  |  |  | Messenger Straps | 386 | 124 |  | 0.32124
68330 | 68030 | B3 | 4AV-7AV | Steel Mess Supports | 643 | 191 |  | 0.29705 | 0.67716
|  |  |  | Messenger Clamps | 832 | 818 |  | 0.98317
|  |  |  | Messenger Wire Pull | 962 | 337 |  | 0.35031
|  |  |  | Messenger Wire Tension | 24 | 13 |  | 0.54167
|  |  |  | # Cables Pulled | 888 | 833 |  | 0.93806
|  |  |  | Messenger Straps | 423 | 403 |  | 0.95272
66070 | 66000 | B3 | 4AV-7AV | Steel Mess Supports | 372 | 300 |  | 0.80645 | 0.47744
|  |  |  | Messenger Clamps | 97 | 17 |  | 0.17526
|  |  |  | Messenger Wire Pull | 78 | 69 |  | 0.88462
|  |  |  | Messenger Wire Tension | 809 | 452 |  | 0.55871
|  |  |  | # Cables Pulled | 670 | 115 |  | 0.17164
|  |  |  | Messenger Straps | 821 | 220 |  | 0.26797
60350 | 60000 | B1 | 15S-FOR | Steel Mess Supports | 805 | 362 |  | 0.44969 | 0.53537
|  |  |  | Messenger Clamps | 388 | 211 |  | 0.54381
|  |  |  | Messenger Wire Pull | 84 | 1 |  | 0.011905
|  |  |  | Messenger Wire Tension | 524 | 427 |  | 0.81489
|  |  |  | # Cables Pulled | 266 | 231 |  | 0.86842
|  |  |  | Messenger Straps | 829 | 434 |  | 0.52352
56440 | 56350 | B1 | FOR-CHU | Steel Mess Supports | 798 | 416 |  | 0.5213 | 0.48697
|  |  |  | Messenger Clamps | 712 | 228 |  | 0.32022
|  |  |  | Messenger Wire Pull | 923 | 593 |  | 0.64247
|  |  |  | Messenger Wire Tension | 15 | 4 |  | 0.26667
|  |  |  | # Cables Pulled | 285 | 263 |  | 0.92281
|  |  |  | Messenger Straps | 302 | 75 |  | 0.24834
55580 | 54500 | B2 | CHU-DIT | Steel Mess Supports | 661 | 112 |  | 0.16944 | 0.52543
|  |  |  | Messenger Clamps | 579 | 20 |  | 0.034542
|  |  |  | Messenger Wire Pull | 828 | 784 |  | 0.94686
|  |  |  | Messenger Wire Tension | 477 | 245 |  | 0.51363
|  |  |  | # Cables Pulled | 970 | 636 |  | 0.65567
|  |  |  | Messenger Straps | 561 | 467 |  | 0.83244
54730 | 55000 | B2 | CHU-DIT | Steel Mess Supports | 469 | 437 |  | 0.93177 | 0.71795
|  |  |  | Messenger Clamps | 292 | 184 |  | 0.63014
|  |  |  | Messenger Wire Pull | 447 | 384 |  | 0.85906
|  |  |  | Messenger Wire Tension | 495 | 376 |  | 0.7596
|  |  |  | # Cables Pulled | 218 | 139 |  | 0.63761
|  |  |  | Messenger Straps | 525 | 257 |  | 0.48952
55485 | 55725 | B2 | CHU-DIT | Steel Mess Supports | 194 | 130 |  | 0.6701 | 0.51585
|  |  |  | Messenger Clamps | 727 | 643 |  | 0.88446
|  |  |  | Messenger Wire Pull | 596 | 284 |  | 0.47651
|  |  |  | Messenger Wire Tension | 343 | 3 |  | 0.0087464
|  |  |  | # Cables Pulled | 21 | 20 |  | 0.95238
|  |  |  | Messenger Straps | 447 | 46 |  | 0.10291
55725 | 56635 | B2 | CHURCH AVE | Steel Mess Supports | 667 | 272 |  | 0.4078 | 0.47532
|  |  |  | Messenger Clamps | 238 | 55 |  | 0.23109
|  |  |  | Messenger Wire Pull | 761 | 263 |  | 0.3456
|  |  |  | Messenger Wire Tension | 57 | 36 |  | 0.63158
|  |  |  | # Cables Pulled | 195 | 147 |  | 0.75385
|  |  |  | Messenger Straps | 222 | 107 |  | 0.48198
57320 | 57445 | B2 | CHU-FOR | Steel Mess Supports | 794 | 203 |  | 0.25567 | 0.50603
|  |  |  | Messenger Clamps | 24 | 11 |  | 0.45833
|  |  |  | Messenger Wire Pull | 796 | 419 |  | 0.52638
|  |  |  | Messenger Wire Tension | 387 | 255 |  | 0.65891
|  |  |  | # Cables Pulled | 719 | 158 |  | 0.21975
|  |  |  | Messenger Straps | 362 | 332 |  | 0.91713
60165 | 60620 | B2 | 15S-FOR | Steel Mess Supports | 827 | 513 |  | 0.62031 | 0.53801
|  |  |  | Messenger Clamps | 257 | 112 |  | 0.4358
|  |  |  | Messenger Wire Pull | 280 | 30 |  | 0.10714
|  |  |  | Messenger Wire Tension | 186 | 39 |  | 0.20968
|  |  |  | # Cables Pulled | 960 | 869 |  | 0.90521
|  |  |  | Messenger Straps | 559 | 531 |  | 0.94991
62560 | 63425 | B2 | 15TH STREET PROSPECT PARK | Steel Mess Supports | 554 | 168 |  | 0.30325 | 0.6413
|  |  |  | Messenger Clamps | 871 | 603 |  | 0.69231
|  |  |  | Messenger Wire Pull | 554 | 425 |  | 0.76715
|  |  |  | Messenger Wire Tension | 975 | 537 |  | 0.55077
|  |  |  | # Cables Pulled | 171 | 166 |  | 0.97076
|  |  |  | Messenger Straps | 582 | 328 |  | 0.56357
67950 | 68330 | B4/B2 | 4AV-7AV | Steel Mess Supports | 918 | 159 |  | 0.1732 | 0.48839
|  |  |  | Messenger Clamps | 625 | 529 |  | 0.8464
|  |  |  | Messenger Wire Pull | 149 | 102 |  | 0.68456
|  |  |  | Messenger Wire Tension | 483 | 378 |  | 0.78261
|  |  |  | # Cables Pulled | 136 | 13 |  | 0.095588
|  |  |  | Messenger Straps | 592 | 206 |  | 0.34797
74740 | 74840 | B2 | CAR-BER | Steel Mess Supports | 590 | 340 |  | 0.57627 | 0.68403
|  |  |  | Messenger Clamps | 761 | 626 |  | 0.8226
|  |  |  | Messenger Wire Pull | 162 | 41 |  | 0.25309
|  |  |  | Messenger Wire Tension | 536 | 359 |  | 0.66978
|  |  |  | # Cables Pulled | 123 | 115 |  | 0.93496
|  |  |  | Messenger Straps | 118 | 100 |  | 0.84746
75395 | 75650 | B2 | CAR-BER | Steel Mess Supports | 562 | 297 |  | 0.52847 | 0.45144
|  |  |  | Messenger Clamps | 30 | 6 |  | 0.2
|  |  |  | Messenger Wire Pull | 31 | 23 |  | 0.74194
|  |  |  | Messenger Wire Tension | 559 | 38 |  | 0.067979
|  |  |  | # Cables Pulled | 1000 | 991 |  | 0.991
|  |  |  | Messenger Straps | 251 | 45 |  | 0.17928
78905 | 75950 | B3 | JAY-BER | Steel Mess Supports | 854 | 184 |  | 0.21546 | 0.60671
|  |  |  | Messenger Clamps | 447 | 259 |  | 0.57942
|  |  |  | Messenger Wire Pull | 989 | 788 |  | 0.79676
|  |  |  | Messenger Wire Tension | 463 | 292 |  | 0.63067
|  |  |  | # Cables Pulled | 498 | 462 |  | 0.92771
|  |  |  | Messenger Straps | 308 | 151 |  | 0.49026
75950 | 75650 | B3 | BERGEN ST | Steel Mess Supports | 392 | 166 |  | 0.42347 | 0.35255
|  |  |  | Messenger Clamps | 375 | 18 |  | 0.048
|  |  |  | Messenger Wire Pull | 51 | 17 |  | 0.33333
|  |  |  | Messenger Wire Tension | 686 | 450 |  | 0.65598
|  |  |  | # Cables Pulled | 180 | 66 |  | 0.36667
|  |  |  | Messenger Straps | 608 | 175 |  | 0.28783
75650 | 75420 | B3 | BER-CAR | Steel Mess Supports | 517 | 510 |  | 0.98646 | 0.42723
|  |  |  | Messenger Clamps | 840 | 197 |  | 0.23452
|  |  |  | Messenger Wire Pull | 67 | 18 |  | 0.26866
|  |  |  | Messenger Wire Tension | 420 | 55 |  | 0.13095
|  |  |  | # Cables Pulled | 912 | 163 |  | 0.17873
|  |  |  | Messenger Straps | 729 | 557 |  | 0.76406
73285 | 72960 | B3 | BER-CAR | Steel Mess Supports | 587 | 218 |  | 0.37138 | 0.64777
|  |  |  | Messenger Clamps | 853 | 835 |  | 0.9789
|  |  |  | Messenger Wire Pull | 67 | 10 |  | 0.14925
|  |  |  | Messenger Wire Tension | 516 | 456 |  | 0.88372
|  |  |  | # Cables Pulled | 611 | 368 |  | 0.60229
|  |  |  | Messenger Straps | 839 | 756 |  | 0.90107
72960 | 72035 | B3/B4 | CAR-4TH | Steel Mess Supports | 827 | 825 |  | 0.99758 | 0.61748
|  |  |  | Messenger Clamps | 13 | 2 |  | 0.15385
|  |  |  | Messenger Wire Pull | 48 | 41 |  | 0.85417
|  |  |  | Messenger Wire Tension | 991 | 367 |  | 0.37033
|  |  |  | # Cables Pulled | 883 | 592 |  | 0.67044
|  |  |  | Messenger Straps | 164 | 108 |  | 0.65854
71150 | 70965 | B3/B4 | CAR-4TH | Steel Mess Supports | 885 | 724 |  | 0.81808 | 0.56854
|  |  |  | Messenger Clamps | 727 | 277 |  | 0.38102
|  |  |  | Messenger Wire Pull | 655 | 175 |  | 0.26718
|  |  |  | Messenger Wire Tension | 258 | 241 |  | 0.93411
|  |  |  | # Cables Pulled | 740 | 257 |  | 0.3473
|  |  |  | Messenger Straps | 758 | 503 |  | 0.66359
70965 | 70445 | B3/B6 | CAR-4TH | Steel Mess Supports | 368 | 261 |  | 0.70924 | 0.28547
|  |  |  | Messenger Clamps | 59 | 1 |  | 0.016949
|  |  |  | Messenger Wire Pull | 985 | 313 |  | 0.31777
|  |  |  | Messenger Wire Tension | 706 | 10 |  | 0.014164
|  |  |  | # Cables Pulled | 437 | 30 |  | 0.06865
|  |  |  | Messenger Straps | 244 | 143 |  | 0.58607
70445 | 70045 | B3/B7 | CAR-4TH | Steel Mess Supports | 992 | 6 |  | 0.0060484 | 0.43011
|  |  |  | Messenger Clamps | 594 | 375 |  | 0.63131
|  |  |  | Messenger Wire Pull | 600 | 200 |  | 0.33333
|  |  |  | Messenger Wire Tension | 214 | 80 |  | 0.37383
|  |  |  | # Cables Pulled | 909 | 617 |  | 0.67877
|  |  |  | Messenger Straps | 61 | 34 |  | 0.55738
68625 | 68400 | B3/B8 | CAR-4TH | Steel Mess Supports | 996 | 22 |  | 0.022088 | 0.53898
|  |  |  | Messenger Clamps | 772 | 279 |  | 0.3614
|  |  |  | Messenger Wire Pull | 668 | 566 |  | 0.84731
|  |  |  | Messenger Wire Tension | 997 | 603 |  | 0.60481
|  |  |  | # Cables Pulled | 446 | 357 |  | 0.80045
|  |  |  | Messenger Straps | 363 | 217 |  | 0.5978
68400 | 68330 | B3/B9 | CAR-4TH | Steel Mess Supports | 701 | 596 |  | 0.85021 | 0.52016
|  |  |  | Messenger Clamps | 34 | 32 |  | 0.94118
|  |  |  | Messenger Wire Pull | 673 | 184 |  | 0.2734
|  |  |  | Messenger Wire Tension | 626 | 211 |  | 0.33706
|  |  |  | # Cables Pulled | 962 | 475 |  | 0.49376
|  |  |  | Messenger Straps | 608 | 137 |  | 0.22533

## AXLE COUNTER
Stationing | Track No | Location | Activity | Date | Progress | General Progress | Notes | DWG REF.
54600 | B1 | DIT-CHU | Axle Counter Installation |  | 74.56% | 48.15% | STATIONING SHOWN IS THAT OF THE NEAREST IJ, AXC STATIONING DOES NOT EXIST | B1-546
|  |  | JB Installation |  | 40.19%
|  |  | Line Cable Installation |  | 16.41%
|  |  | Express Cable Installation |  | 46.87%
|  |  | Pre-Operation Testing |  | 62.69%
| B1 |  | Axle Counter Installation |  | 65.34% | 45.14% | NO INFO | B1-547
|  |  | JB Installation |  | 59.16%
|  |  | Line Cable Installation |  | 17.73%
|  |  | Express Cable Installation |  | 78.23%
|  |  | Pre-Operation Testing |  | 5.268%
59297 | B1 | FOR-15S | Axle Counter Installation |  | 29.3% | 34.89% |  | B1-553
|  |  | JB Installation |  | 3.958%
|  |  | Line Cable Installation |  | 35.9%
|  |  | Express Cable Installation |  | 19.28%
|  |  | Pre-Operation Testing |  | 86.03%
| B1 |  | Axle Counter Installation |  | 60.28% | 58.41% | NO INFO | B1-554
|  |  | JB Installation |  | 84.46%
|  |  | Line Cable Installation |  | 38.9%
|  |  | Express Cable Installation |  | 35.35%
|  |  | Pre-Operation Testing |  | 73.04%
55687 | B1 | DIT-CHU | Axle Counter Installation |  | 46.01% | 50.16% |  | B1-557
|  |  | JB Installation |  | 94.35%
|  |  | Line Cable Installation |  | 38.81%
|  |  | Express Cable Installation |  | 48.95%
|  |  | Pre-Operation Testing |  | 22.7%
56367 | B1 | CHU-FOR | Axle Counter Installation |  | 88.48% | 50.22% |  | B1-564
|  |  | JB Installation |  | 35.69%
|  |  | Line Cable Installation |  | 37.74%
|  |  | Express Cable Installation |  | 68.15%
|  |  | Pre-Operation Testing |  | 21.05%
58524.6 | B1 | FORT HAMILTON PARKWAY | Axle Counter Installation |  | 95.01% | 63.52% |  | B1-585
|  |  | JB Installation |  | 26.08%
|  |  | Line Cable Installation |  | 91%
|  |  | Express Cable Installation |  | 76.91%
|  |  | Pre-Operation Testing |  | 28.59%
59210.25 | B1 | FOR-15S | Axle Counter Installation |  | 93.68% | 80.21% |  | B1-592
|  |  | JB Installation |  | 96.85%
|  |  | Line Cable Installation |  | 96.3%
|  |  | Express Cable Installation |  | 55.01%
|  |  | Pre-Operation Testing |  | 59.21%
62572.5 | B1 | FOR-15S | Axle Counter Installation |  | 48.76% | 51.35% |  | B1-626
|  |  | JB Installation |  | 60.92%
|  |  | Line Cable Installation |  | 83.95%
|  |  | Express Cable Installation |  | 0.6365%
|  |  | Pre-Operation Testing |  | 62.48%
63251.4 | B1 | 15S-7AV | Axle Counter Installation |  | 20.05% | 44.91% |  | B1-632
|  |  | JB Installation |  | 89.13%
|  |  | Line Cable Installation |  | 43.45%
|  |  | Express Cable Installation |  | 47%
|  |  | Pre-Operation Testing |  | 24.93%
65387.3 | B1 | 15S-7AV | Axle Counter Installation |  | 79.94% | 56.66% |  | B1-654
|  |  | JB Installation |  | 37.35%
|  |  | Line Cable Installation |  | 60.54%
|  |  | Express Cable Installation |  | 7.604%
|  |  | Pre-Operation Testing |  | 97.85%
66076 | B1 | 7AV-4TH | Axle Counter Installation |  | 35.11% | 57.39% |  | B1-661
|  |  | JB Installation |  | 52.66%
|  |  | Line Cable Installation |  | 54.31%
|  |  | Express Cable Installation |  | 69.21%
|  |  | Pre-Operation Testing |  | 75.63%
73206.7 | B1 | SMI-CAR | Axle Counter Installation |  | 56.21% | 36.97% |  | B1-732
|  |  | JB Installation |  | 27.56%
|  |  | Line Cable Installation |  | 37.32%
|  |  | Express Cable Installation |  | 27.55%
|  |  | Pre-Operation Testing |  | 36.23%
73932 | B1 | CAR-BER | Axle Counter Installation |  | 91.31% | 70.05% |  | B1-739
|  |  | JB Installation |  | 71.43%
|  |  | Line Cable Installation |  | 55.17%
|  |  | Express Cable Installation |  | 53.55%
|  |  | Pre-Operation Testing |  | 78.79%
75408 | B1 | CAR-BER | Axle Counter Installation |  | 53.83% | 77.81% |  | B1-755
|  |  | JB Installation |  | 89.91%
|  |  | Line Cable Installation |  | 74.02%
|  |  | Express Cable Installation |  | 90.49%
|  |  | Pre-Operation Testing |  | 80.81%
75669 | B1 | CAR-BER | Axle Counter Installation |  | 56.16% | 71.06% |  | B1-756
|  |  | JB Installation |  | 86.56%
|  |  | Line Cable Installation |  | 80.78%
|  |  | Express Cable Installation |  | 89.74%
|  |  | Pre-Operation Testing |  | 42.04%
76352 | B1 | BER-HOY | Axle Counter Installation |  | 61.09% | 62.88% |  | B1-763, B1-764
|  |  | JB Installation |  | 81.16%
|  |  | Line Cable Installation |  | 0.0004193%
|  |  | Express Cable Installation |  | 73.68%
|  |  | Pre-Operation Testing |  | 98.45%
76589 | B1 | HOYT-SCHERMERHORN | Axle Counter Installation |  | 57.38% | 40.54% |  | B1-766
|  |  | JB Installation |  | 96.23%
|  |  | Line Cable Installation |  | 36.61%
|  |  | Express Cable Installation |  | 1.177%
|  |  | Pre-Operation Testing |  | 11.29%
76901.5 | B1 | HOY-FUL | Axle Counter Installation |  | 9.798% | 55.06% |  | B1-770
|  |  | JB Installation |  | 21.74%
|  |  | Line Cable Installation |  | 94.98%
|  |  | Express Cable Installation |  | 66.95%
|  |  | Pre-Operation Testing |  | 81.85%
77088 | B1 | FUL-CLI | Axle Counter Installation |  | 57.94% | 56.08% |  | B1-771
|  |  | JB Installation |  | 57.08%
|  |  | Line Cable Installation |  | 53.89%
|  |  | Express Cable Installation |  | 48.28%
|  |  | Pre-Operation Testing |  | 63.22%
54737 | B2 | DIT-CHU | Axle Counter Installation |  | 13.93% | 52.36% |  | B2-546
|  |  | JB Installation |  | 93.79%
|  |  | Line Cable Installation |  | 82.37%
|  |  | Express Cable Installation |  | 65.85%
|  |  | Pre-Operation Testing |  | 5.859%
54731 | B2 |  | Axle Counter Installation |  | 1.992% | 34.98% |  | B2-547
|  |  | JB Installation |  | 76.5%
|  |  | Line Cable Installation |  | 9.42%
|  |  | Express Cable Installation |  | 27.65%
|  |  | Pre-Operation Testing |  | 59.34%
55000 | B2 | DIT-CHU | Axle Counter Installation |  | 41.43% | 43.72% |  | B2-549
|  |  | JB Installation |  | 95.61%
|  |  | Line Cable Installation |  | 57.5%
|  |  | Express Cable Installation |  | 18.39%
|  |  | Pre-Operation Testing |  | 5.659%
55498 | B2 | DIT-CHU | Axle Counter Installation |  | 85.67% | 54% |  | B2-554
|  |  | JB Installation |  | 56%
|  |  | Line Cable Installation |  | 10.63%
|  |  | Express Cable Installation |  | 22.74%
|  |  | Pre-Operation Testing |  | 94.98%
| B2 |  | Axle Counter Installation |  | 27.77% | 51.47% | NO REF DWG EXISTS | B2-555
|  |  | JB Installation |  | 11.15%
|  |  | Line Cable Installation |  | 92.37%
|  |  | Express Cable Installation |  | 69%
|  |  | Pre-Operation Testing |  | 57.04%
| B2 |  | Axle Counter Installation |  | 84.48% | 61.96% | NO REF DWG EXISTS | B2-556
|  |  | JB Installation |  | 25.39%
|  |  | Line Cable Installation |  | 53.35%
|  |  | Express Cable Installation |  | 97.37%
|  |  | Pre-Operation Testing |  | 49.23%
55857 | B2 | CHURCH AVE | Axle Counter Installation |  | 89.45% | 59.63% |  | B2-558
|  |  | JB Installation |  | 67.62%
|  |  | Line Cable Installation |  | 32.21%
|  |  | Express Cable Installation |  | 75.18%
|  |  | Pre-Operation Testing |  | 33.68%
58500 | B2 | FORT HAMILTON PARKWAY | Axle Counter Installation |  | 84.58% | 74.57% |  | B2-585
|  |  | JB Installation |  | 95.39%
|  |  | Line Cable Installation |  | 27.44%
|  |  | Express Cable Installation |  | 82.68%
|  |  | Pre-Operation Testing |  | 82.74%
59203.8 | B2 | FOR-15S | Axle Counter Installation |  | 50.4% | 49.63% |  | B2-592
|  |  | JB Installation |  | 74.24%
|  |  | Line Cable Installation |  | 52.59%
|  |  | Express Cable Installation |  | 43.05%
|  |  | Pre-Operation Testing |  | 27.88%
62550.6 | B2 |  | Axle Counter Installation |  | 7.975% | 30.58% |  | B2-625
|  |  | JB Installation |  | 16.7%
|  |  | Line Cable Installation |  | 64.66%
|  |  | Express Cable Installation |  | 46.27%
|  |  | Pre-Operation Testing |  | 17.33%
65375.3 | B2 | 15S-7AV | Axle Counter Installation |  | 99.08% | 45.46% |  | B2-654
|  |  | JB Installation |  | 4.466%
|  |  | Line Cable Installation |  | 13.39%
|  |  | Express Cable Installation |  | 37.11%
|  |  | Pre-Operation Testing |  | 73.25%
66062.3 | B2 | 7AV-4TH | Axle Counter Installation |  | 61.82% | 52.79% |  | B2-661
|  |  | JB Installation |  | 39.95%
|  |  | Line Cable Installation |  | 4.06%
|  |  | Express Cable Installation |  | 89.15%
|  |  | Pre-Operation Testing |  | 68.96%
| B2 |  | Axle Counter Installation |  | 74.6% | 56.05% | NO REF DWG EXISTS | B2-665
|  |  | JB Installation |  | 62.4%
|  |  | Line Cable Installation |  | 42.19%
|  |  | Express Cable Installation |  | 4.902%
|  |  | Pre-Operation Testing |  | 96.13%
| B2 |  | Axle Counter Installation |  | 95.95% | 88.18% | NO REF DWG EXISTS | B2-684
|  |  | JB Installation |  | 99.54%
|  |  | Line Cable Installation |  | 76.69%
|  |  | Express Cable Installation |  | 72.12%
|  |  | Pre-Operation Testing |  | 96.58%
| B2 |  | Axle Counter Installation |  | 49.39% | 58.15% | NO REF DWG EXISTS | B2-691
|  |  | JB Installation |  | 2.237%
|  |  | Line Cable Installation |  | 78.51%
|  |  | Express Cable Installation |  | 89.43%
|  |  | Pre-Operation Testing |  | 71.19%
| B2 |  | Axle Counter Installation |  | 30.06% | 30.91% | NO REF DWG EXISTS | B2-692
|  |  | JB Installation |  | 46.54%
|  |  | Line Cable Installation |  | 73.61%
|  |  | Express Cable Installation |  | 4.255%
|  |  | Pre-Operation Testing |  | 0.06477%
| B2 |  | Axle Counter Installation |  | 65.18% | 51.54% | NO REF DWG EXISTS | B2-692A
|  |  | JB Installation |  | 63.23%
|  |  | Line Cable Installation |  | 91.71%
|  |  | Express Cable Installation |  | 32.18%
|  |  | Pre-Operation Testing |  | 5.385%
| B2 |  | Axle Counter Installation |  | 22.41% | 47.08% | NO REF DWG EXISTS | B2-693
|  |  | JB Installation |  | 10.67%
|  |  | Line Cable Installation |  | 52.63%
|  |  | Express Cable Installation |  | 73.79%
|  |  | Pre-Operation Testing |  | 75.92%
| B2 |  | Axle Counter Installation |  | 38.38% | 57.83% | NO REF DWG EXISTS | B2-705
|  |  | JB Installation |  | 70.01%
|  |  | Line Cable Installation |  | 72.37%
|  |  | Express Cable Installation |  | 72.83%
|  |  | Pre-Operation Testing |  | 35.54%
| B2 |  | Axle Counter Installation |  | 20.42% | 39.56% | NO REF DWG EXISTS | B2-712
|  |  | JB Installation |  | 36.01%
|  |  | Line Cable Installation |  | 46.44%
|  |  | Express Cable Installation |  | 77.14%
|  |  | Pre-Operation Testing |  | 17.8%
| B2 |  | Axle Counter Installation |  | 61.96% | 49.05% | DWG EXISTS, BUT EMPTY | B2-732
|  |  | JB Installation |  | 8.008%
|  |  | Line Cable Installation |  | 60.83%
|  |  | Express Cable Installation |  | 93.73%
|  |  | Pre-Operation Testing |  | 20.7%
73926.3 | B2 | CARROLL STREET | Axle Counter Installation |  | 6.847% | 49.22% |  | B2-739
|  |  | JB Installation |  | 46.93%
|  |  | Line Cable Installation |  | 82.21%
|  |  | Express Cable Installation |  | 10.76%
|  |  | Pre-Operation Testing |  | 99.34%
75267 | B2 | CAR-BER | Axle Counter Installation |  | 76.66% | 39.92% |  | B2-753
|  |  | JB Installation |  | 5.621%
|  |  | Line Cable Installation |  | 20.12%
|  |  | Express Cable Installation |  | 38.52%
|  |  | Pre-Operation Testing |  | 58.71%
| B2 |  | Axle Counter Installation |  | 7.954% | 45.73% | NO REF DWG EXISTS | B2-755
|  |  | JB Installation |  | 61.96%
|  |  | Line Cable Installation |  | 43.16%
|  |  | Express Cable Installation |  | 88.88%
|  |  | Pre-Operation Testing |  | 26.67%
75646 | B2 | CAR-BER | Axle Counter Installation |  | 55.87% | 56.23% |  | B2-756
|  |  | JB Installation |  | 28.72%
|  |  | Line Cable Installation |  | 90.02%
|  |  | Express Cable Installation |  | 14.66%
|  |  | Pre-Operation Testing |  | 91.87%
76352 | B2 |  | Axle Counter Installation |  | 65% | 42.15% |  | B2-763, B2-764
|  |  | JB Installation |  | 89.7%
|  |  | Line Cable Installation |  | 1.366%
|  |  | Express Cable Installation |  | 40.64%
|  |  | Pre-Operation Testing |  | 14.02%
76536 | B2 |  | Axle Counter Installation |  | 80.03% | 73.56% |  | B2-765
|  |  | JB Installation |  | 91.58%
|  |  | Line Cable Installation |  | 42.62%
|  |  | Express Cable Installation |  | 85.13%
|  |  | Pre-Operation Testing |  | 68.41%
76797 | B2 |  | Axle Counter Installation |  | 14.55% | 42.22% |  | B2-768
|  |  | JB Installation |  | 28.36%
|  |  | Line Cable Installation |  | 55.93%
|  |  | Express Cable Installation |  | 18.84%
|  |  | Pre-Operation Testing |  | 93.4%
77116 | B2 |  | Axle Counter Installation |  | 29.26% | 62.87% |  | B2-770
|  |  | JB Installation |  | 23.71%
|  |  | Line Cable Installation |  | 93.18%
|  |  | Express Cable Installation |  | 78.71%
|  |  | Pre-Operation Testing |  | 89.5%
| B3 |  | Axle Counter Installation |  | 67.43% | 57.04% | REF DWG EXISTS, NO STATIONINGS SHOWN | B3-546
|  |  | JB Installation |  | 30.44%
|  |  | Line Cable Installation |  | 84.32%
|  |  | Express Cable Installation |  | 84.95%
|  |  | Pre-Operation Testing |  | 18.06%
| B3 |  | Axle Counter Installation |  | 97.4% | 47.45% | REF DWG EXISTS, NO STATIONINGS SHOWN | B3-548
|  |  | JB Installation |  | 16.1%
|  |  | Line Cable Installation |  | 61.43%
|  |  | Express Cable Installation |  | 48.26%
|  |  | Pre-Operation Testing |  | 14.06%
53361 | B3 |  | Axle Counter Installation |  | 29.58% | 46.63% |  | B3-554
|  |  | JB Installation |  | 76.39%
|  |  | Line Cable Installation |  | 74.7%
|  |  | Express Cable Installation |  | 21.5%
|  |  | Pre-Operation Testing |  | 30.97%
55626 | B3 |  | Axle Counter Installation |  | 82.81% | 58.27% |  | B3-555
|  |  | JB Installation |  | 22.66%
|  |  | Line Cable Installation |  | 93.98%
|  |  | Express Cable Installation |  | 45.97%
|  |  | Pre-Operation Testing |  | 45.93%
| B3 |  | Axle Counter Installation |  | 4.422% | 35.12% | REF DWG EXISTS, NO STATIONINGS SHOWN | B3-556
|  |  | JB Installation |  | 75.13%
|  |  | Line Cable Installation |  | 0.2098%
|  |  | Express Cable Installation |  | 32.76%
|  |  | Pre-Operation Testing |  | 63.07%
| B3 |  | Axle Counter Installation |  | 35.77% | 37.25% | REF DWG EXISTS, NO STATIONINGS SHOWN | B3-557
|  |  | JB Installation |  | 5.529%
|  |  | Line Cable Installation |  | 20.74%
|  |  | Express Cable Installation |  | 49.91%
|  |  | Pre-Operation Testing |  | 74.3%
| B3 |  | Axle Counter Installation |  | 2.239% | 62.23% | NO REF DWG EXISTS | B3-565
|  |  | JB Installation |  | 56.1%
|  |  | Line Cable Installation |  | 72.33%
|  |  | Express Cable Installation |  | 95.18%
|  |  | Pre-Operation Testing |  | 85.3%
65384.6 | B3 |  | Axle Counter Installation |  | 36.62% | 45.89% |  | B3-654
|  |  | JB Installation |  | 12.7%
|  |  | Line Cable Installation |  | 84.21%
|  |  | Express Cable Installation |  | 4.934%
|  |  | Pre-Operation Testing |  | 91.02%
66073.4 | B3 |  | Axle Counter Installation |  | 70.7% | 47.15% |  | B3-661
|  |  | JB Installation |  | 69.34%
|  |  | Line Cable Installation |  | 54.82%
|  |  | Express Cable Installation |  | 30.32%
|  |  | Pre-Operation Testing |  | 10.59%
| B3 |  | Axle Counter Installation |  | 17.15% | 32.94% | NO REF DWG EXISTS | B3-689
|  |  | JB Installation |  | 8.203%
|  |  | Line Cable Installation |  | 38.23%
|  |  | Express Cable Installation |  | 96.47%
|  |  | Pre-Operation Testing |  | 4.625%
| B3 |  | Axle Counter Installation |  | 30.53% | 35.34% | NO REF DWG EXISTS | B3-690
|  |  | JB Installation |  | 64.32%
|  |  | Line Cable Installation |  | 38.37%
|  |  | Express Cable Installation |  | 20.46%
|  |  | Pre-Operation Testing |  | 23.04%
| B3 |  | Axle Counter Installation |  | 13.95% | 20.22% | NO REF DWG EXISTS | B3-691
|  |  | JB Installation |  | 17.9%
|  |  | Line Cable Installation |  | 13.08%
|  |  | Express Cable Installation |  | 24.39%
|  |  | Pre-Operation Testing |  | 31.77%
| B3 |  | Axle Counter Installation |  | 30.89% | 36.74% | NO REF DWG EXISTS | B3-692
|  |  | JB Installation |  | 77.41%
|  |  | Line Cable Installation |  | 1.729%
|  |  | Express Cable Installation |  | 20.27%
|  |  | Pre-Operation Testing |  | 53.43%
| B3 |  | Axle Counter Installation |  | 60.97% | 61.64% | NO REF DWG EXISTS | B3-693
|  |  | JB Installation |  | 12.37%
|  |  | Line Cable Installation |  | 90.55%
|  |  | Express Cable Installation |  | 71.29%
|  |  | Pre-Operation Testing |  | 73.01%
| B3 |  | Axle Counter Installation |  | 69.75% | 58.45% | NO REF DWG EXISTS | B3-694
|  |  | JB Installation |  | 72.22%
|  |  | Line Cable Installation |  | 74.37%
|  |  | Express Cable Installation |  | 11.08%
|  |  | Pre-Operation Testing |  | 64.83%
| B3 |  | Axle Counter Installation |  | 19.39% | 57.14% | NO REF DWG EXISTS | B3-695
|  |  | JB Installation |  | 68.93%
|  |  | Line Cable Installation |  | 2.581%
|  |  | Express Cable Installation |  | 96.82%
|  |  | Pre-Operation Testing |  | 97.98%
| B3 |  | Axle Counter Installation |  | 46.34% | 72.63% | NO REF DWG EXISTS | B3-696
|  |  | JB Installation |  | 98.18%
|  |  | Line Cable Installation |  | 99.15%
|  |  | Express Cable Installation |  | 35.83%
|  |  | Pre-Operation Testing |  | 83.66%
75405 | B3 |  | Axle Counter Installation |  | 22.86% | 40.46% |  | B3-754
|  |  | JB Installation |  | 78.04%
|  |  | Line Cable Installation |  | 50.87%
|  |  | Express Cable Installation |  | 23.99%
|  |  | Pre-Operation Testing |  | 26.54%
| B3 |  | Axle Counter Installation |  | 3.404% | 32.88% | NO REF DWG EXISTS | B3-755
|  |  | JB Installation |  | 77.59%
|  |  | Line Cable Installation |  | 14.48%
|  |  | Express Cable Installation |  | 5.105%
|  |  | Pre-Operation Testing |  | 63.8%
75405 | B3 |  | Axle Counter Installation |  | 22.32% | 64.53% |  | B3-756
|  |  | JB Installation |  | 47.11%
|  |  | Line Cable Installation |  | 69.44%
|  |  | Express Cable Installation |  | 86.67%
|  |  | Pre-Operation Testing |  | 97.09%
76383 | B3 |  | Axle Counter Installation |  | 93.93% | 52.79% |  | B3-764
|  |  | JB Installation |  | 0.7457%
|  |  | Line Cable Installation |  | 2.921%
|  |  | Express Cable Installation |  | 86.18%
|  |  | Pre-Operation Testing |  | 80.16%
76920 | B3 |  | Axle Counter Installation |  | 66.23% | 46.49% |  | B3-769
|  |  | JB Installation |  | 1.74%
|  |  | Line Cable Installation |  | 94.18%
|  |  | Express Cable Installation |  | 46.99%
|  |  | Pre-Operation Testing |  | 23.32%
| B4 |  | Axle Counter Installation |  | 72.82% | 61.13% | REF DWG EXISTS, NO STATIONINGS SHOWN | B4-547
|  |  | JB Installation |  | 42.3%
|  |  | Line Cable Installation |  | 71.25%
|  |  | Express Cable Installation |  | 37%
|  |  | Pre-Operation Testing |  | 82.28%
| B4 |  | Axle Counter Installation |  | 2.755% | 53.61% | REF DWG EXISTS, NO STATIONINGS SHOWN | B4-551
|  |  | JB Installation |  | 67.08%
|  |  | Line Cable Installation |  | 58.95%
|  |  | Express Cable Installation |  | 54.84%
|  |  | Pre-Operation Testing |  | 84.41%
| B4 |  | Axle Counter Installation |  | 24.54% | 45.1% | NO REF DWG EXISTS, AWAITING RESPONSE FROM THALES ON WHETHER THIS AXC WILL BE INSTALLED | B4-554A, B4-554B
|  |  | JB Installation |  | 72.37%
|  |  | Line Cable Installation |  | 15.41%
|  |  | Express Cable Installation |  | 27.99%
|  |  | Pre-Operation Testing |  | 85.18%
55533 | B4 |  | Axle Counter Installation |  | 65.06% | 62.71% |  | B4-555
|  |  | JB Installation |  | 97.08%
|  |  | Line Cable Installation |  | 25.36%
|  |  | Express Cable Installation |  | 73.71%
|  |  | Pre-Operation Testing |  | 52.35%
55685 | B4 |  | Axle Counter Installation |  | 95.29% | 55.5% |  | B4-556
|  |  | JB Installation |  | 60.7%
|  |  | Line Cable Installation |  | 60.44%
|  |  | Express Cable Installation |  | 25.85%
|  |  | Pre-Operation Testing |  | 35.23%
56396.5 | B4 |  | Axle Counter Installation |  | 58.85% | 38.83% |  | B4-564
|  |  | JB Installation |  | 41.66%
|  |  | Line Cable Installation |  | 2.322%
|  |  | Express Cable Installation |  | 65.02%
|  |  | Pre-Operation Testing |  | 26.32%

## SIGNALS
Stationing | Track No | Signal Type | Location | Activity | Date | Progress | General Progress | Notes
74076 | E1 | APPROACH |  | Signal Installation |  | 88.29% | 75.21% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 32.76%
|  |  |  | Stop Machine Installation |  | 87.99%
|  |  |  | Line Cable Installation |  | 44.08%
|  |  |  | Breakdown Testing |  | 59.66%
|  |  |  | Pre-Operation Testing |  | 96%
98643 | E1 | HOME |  | Signal Installation |  | 11.34% | 48.26% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 9.678%
|  |  |  | Stop Machine Installation |  | 76.9%
|  |  |  | Line Cable Installation |  | 46.01%
|  |  |  | Breakdown Testing |  | 52.51%
|  |  |  | Pre-Operation Testing |  | 54.53%
98903 | E1 | HOME |  | Signal Installation |  | 83.63% | 56.46% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 69.51%
|  |  |  | Stop Machine Installation |  | 56.37%
|  |  |  | Line Cable Installation |  | 29.9%
|  |  |  | Breakdown Testing |  | 14.82%
|  |  |  | Pre-Operation Testing |  | 97.55%
100068 | E1 | HOME |  | Signal Installation |  | 36.19% | 28.27% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 2.766%
|  |  |  | Stop Machine Installation |  | 58.91%
|  |  |  | Line Cable Installation |  | 11.12%
|  |  |  | Breakdown Testing |  | 0.9895%
|  |  |  | Pre-Operation Testing |  | 34.14%
106031 | E1 | APPROACH |  | Signal Installation |  | 83.29% | 51.78% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 84.39%
|  |  |  | Stop Machine Installation |  | 58.71%
|  |  |  | Line Cable Installation |  | 38.8%
|  |  |  | Breakdown Testing |  | 46.79%
|  |  |  | Pre-Operation Testing |  | 31.31%
113852 | E1 | HOME |  | Signal Installation |  | 62.44% | 56.48% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 92.94%
|  |  |  | Stop Machine Installation |  | 23.31%
|  |  |  | Line Cable Installation |  | 64.78%
|  |  |  | Breakdown Testing |  | 67.48%
|  |  |  | Pre-Operation Testing |  | 64.38%
114110 | E1 | HOME |  | Signal Installation |  | 50.5% | 55.35% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 72.4%
|  |  |  | Stop Machine Installation |  | 81.64%
|  |  |  | Line Cable Installation |  | 56.86%
|  |  |  | Breakdown Testing |  | 4.869%
|  |  |  | Pre-Operation Testing |  | 82.91%
114869 | E1 | HOME |  | Signal Installation |  | 48.38% | 33.53% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 22.96%
|  |  |  | Stop Machine Installation |  | 6.857%
|  |  |  | Line Cable Installation |  | 23.71%
|  |  |  | Breakdown Testing |  | 4.837%
|  |  |  | Pre-Operation Testing |  | 83.88%
119024 | E1 | APPROACH |  | Signal Installation |  | 1.039% | 27.14% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 83.25%
|  |  |  | Stop Machine Installation |  | 13.42%
|  |  |  | Line Cable Installation |  | 10.12%
|  |  |  | Breakdown Testing |  | 71.36%
|  |  |  | Pre-Operation Testing |  | 39.78%
119485 | E1 | APPROACH |  | Signal Installation |  | 29.31% | 31.34% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 43.18%
|  |  |  | Stop Machine Installation |  | 5.132%
|  |  |  | Line Cable Installation |  | 63.07%
|  |  |  | Breakdown Testing |  | 14.15%
|  |  |  | Pre-Operation Testing |  | 45.04%
| E1 | APPROACH |  | Signal Installation |  | 90.44% | 66.64% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 73.91%
|  |  |  | Stop Machine Installation |  | 44.92%
|  |  |  | Line Cable Installation |  | 50.93%
|  |  |  | Breakdown Testing |  | 62.46%
|  |  |  | Pre-Operation Testing |  | 84.46%
121810 | E1 | HOME |  | Signal Installation |  | 63.79% | 50.07% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 2.491%
|  |  |  | Stop Machine Installation |  | 87.36%
|  |  |  | Line Cable Installation |  | 42.48%
|  |  |  | Breakdown Testing |  | 27.91%
|  |  |  | Pre-Operation Testing |  | 28.83%
122198 | E1 | HOME |  | Signal Installation |  | 82.27% | 59.87% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 85.75%
|  |  |  | Stop Machine Installation |  | 46.92%
|  |  |  | Line Cable Installation |  | 54.12%
|  |  |  | Breakdown Testing |  | 42.45%
|  |  |  | Pre-Operation Testing |  | 73.59%
122570 | E1 | HOME |  | Signal Installation |  | 66.69% | 68.88% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 34.51%
|  |  |  | Stop Machine Installation |  | 56.18%
|  |  |  | Line Cable Installation |  | 96.75%
|  |  |  | Breakdown Testing |  | 62.69%
|  |  |  | Pre-Operation Testing |  | 62.1%
122987 | E1 | HOME |  | Signal Installation |  | 24.64% | 56.57% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 82.7%
|  |  |  | Stop Machine Installation |  | 10.2%
|  |  |  | Line Cable Installation |  | 90.3%
|  |  |  | Breakdown Testing |  | 62.2%
|  |  |  | Pre-Operation Testing |  | 95.52%
123669 | D1 | HOME |  | Signal Installation |  | 1.021% | 60.77% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 17.98%
|  |  |  | Stop Machine Installation |  | 41.27%
|  |  |  | Line Cable Installation |  | 91.09%
|  |  |  | Breakdown Testing |  | 88.91%
|  |  |  | Pre-Operation Testing |  | 81.54%
73318 | E2 | APPROACH |  | Signal Installation |  | 48.49% | 46.78% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 86.07%
|  |  |  | Stop Machine Installation |  | 71.82%
|  |  |  | Line Cable Installation |  | 14.44%
|  |  |  | Breakdown Testing |  | 19.35%
|  |  |  | Pre-Operation Testing |  | 79.81%
98565 | E2 | HOME |  | Signal Installation |  | 64.35% | 59.56% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 33.81%
|  |  |  | Stop Machine Installation |  | 17.56%
|  |  |  | Line Cable Installation |  | 55.6%
|  |  |  | Breakdown Testing |  | 63.18%
|  |  |  | Pre-Operation Testing |  | 97.1%
99593 | E2 | HOME |  | Signal Installation |  | 61.24% | 62.82% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 15.15%
|  |  |  | Stop Machine Installation |  | 20.06%
|  |  |  | Line Cable Installation |  | 40.42%
|  |  |  | Breakdown Testing |  | 97%
|  |  |  | Pre-Operation Testing |  | 95.37%
99970 | E2 | HOME |  | Signal Installation |  | 93.87% | 54.11% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 17.21%
|  |  |  | Stop Machine Installation |  | 2.962%
|  |  |  | Line Cable Installation |  | 87.61%
|  |  |  | Breakdown Testing |  | 71.85%
|  |  |  | Pre-Operation Testing |  | 14.27%
106749 | E2 | APPROACH |  | Signal Installation |  | 3.471% | 61.61% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 67.1%
|  |  |  | Stop Machine Installation |  | 77.39%
|  |  |  | Line Cable Installation |  | 92.7%
|  |  |  | Breakdown Testing |  | 72.23%
|  |  |  | Pre-Operation Testing |  | 62.27%
112529 | E2 | HOME |  | Signal Installation |  | 47.25% | 58.07% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 8.178%
|  |  |  | Stop Machine Installation |  | 76.73%
|  |  |  | Line Cable Installation |  | 76%
|  |  |  | Breakdown Testing |  | 47.82%
|  |  |  | Pre-Operation Testing |  | 42.55%
113850 | E2 | HOME |  | Signal Installation |  | 11.14% | 50.59% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 94.65%
|  |  |  | Stop Machine Installation |  | 66.73%
|  |  |  | Line Cable Installation |  | 59.08%
|  |  |  | Breakdown Testing |  | 40.8%
|  |  |  | Pre-Operation Testing |  | 75.19%
118065 | E2 | APPROACH |  | Signal Installation |  | 38.91% | 37.26% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 11.08%
|  |  |  | Stop Machine Installation |  | 77.43%
|  |  |  | Line Cable Installation |  | 33.08%
|  |  |  | Breakdown Testing |  | 31.88%
|  |  |  | Pre-Operation Testing |  | 4.984%
119215 | E2 | APPROACH |  | Signal Installation |  | 58.32% | 37.78% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 17.74%
|  |  |  | Stop Machine Installation |  | 8.388%
|  |  |  | Line Cable Installation |  | 48.39%
|  |  |  | Breakdown Testing |  | 20.94%
|  |  |  | Pre-Operation Testing |  | 52.89%
123687 | D2 | HOME |  | Signal Installation |  | 85.96% | 55.64% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 70.81%
|  |  |  | Stop Machine Installation |  | 35.71%
|  |  |  | Line Cable Installation |  | 36.83%
|  |  |  | Breakdown Testing |  | 38.43%
|  |  |  | Pre-Operation Testing |  | 81.29%
124043 | D2 | HOME |  | Signal Installation |  | 79.6% | 50.52% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 62.53%
|  |  |  | Stop Machine Installation |  | 38.17%
|  |  |  | Line Cable Installation |  | 35.09%
|  |  |  | Breakdown Testing |  | 45.75%
|  |  |  | Pre-Operation Testing |  | 54.01%
99806 | E3 | HOME |  | Signal Installation |  | 77.69% | 43.35% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 23.75%
|  |  |  | Stop Machine Installation |  | 17.67%
|  |  |  | Line Cable Installation |  | 28.73%
|  |  |  | Breakdown Testing |  | 18.8%
|  |  |  | Pre-Operation Testing |  | 73.88%
100019 | E3 | HOME |  | Signal Installation |  | 95.95% | 39.89% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 60.29%
|  |  |  | Stop Machine Installation |  | 58.38%
|  |  |  | Line Cable Installation |  | 13.81%
|  |  |  | Breakdown Testing |  | 3.915%
|  |  |  | Pre-Operation Testing |  | 27.38%
99592 | E4 | HOME |  | Signal Installation |  | 58.72% | 46.68% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 77.58%
|  |  |  | Stop Machine Installation |  | 13.68%
|  |  |  | Line Cable Installation |  | 33.51%
|  |  |  | Breakdown Testing |  | 52.38%
|  |  |  | Pre-Operation Testing |  | 75.12%
122071 | E5 | HOME |  | Signal Installation |  | 8.402% | 30.37% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 90.83%
|  |  |  | Stop Machine Installation |  | 6.849%
|  |  |  | Line Cable Installation |  | 45.29%
|  |  |  | Breakdown Testing |  | 20.17%
|  |  |  | Pre-Operation Testing |  | 71.13%
122687 | E5 | HOME |  | Signal Installation |  | 79.55% | 63.82% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 99.58%
|  |  |  | Stop Machine Installation |  | 36.16%
|  |  |  | Line Cable Installation |  | 61.78%
|  |  |  | Breakdown Testing |  | 88.94%
|  |  |  | Pre-Operation Testing |  | 52.65%

## SWITCH
Name | Stationing | Track No | Location | Activity | Date | Progress | General Progress | Notes
B331 | 76395 | B1 |  | Switch Machine Installation |  | 91.86% | 65.39%
|  |  |  | Switch JB Installation |  | 97.14%
|  |  |  | Switch Cable Installation |  | 90.6%
|  |  |  | Line Cable Installation |  | 42.25%
|  |  |  | Breakdown Testing |  | 3.433%
|  |  |  | Pre-Operation Testing |  | 98.79%
B325 | 76395 | E2 |  | Switch Machine Installation |  | 19.12% | 43.74%
|  |  |  | Switch JB Installation |  | 79.92%
|  |  |  | Switch Cable Installation |  | 59.27%
|  |  |  | Line Cable Installation |  | 67.98%
|  |  |  | Breakdown Testing |  | 30.82%
|  |  |  | Pre-Operation Testing |  | 41.54%
633A | 99999 | E1 |  | Switch Machine Installation |  | 53.49% | 61.41%
|  |  |  | Switch JB Installation |  | 87.87%
|  |  |  | Switch Cable Installation |  | 76.29%
|  |  |  | Line Cable Installation |  | 58.69%
|  |  |  | Breakdown Testing |  | 66.96%
|  |  |  | Pre-Operation Testing |  | 51.63%
633B | 98900 | E3-4 |  | Switch Machine Installation |  | 96.55% | 62.29%
|  |  |  | Switch JB Installation |  | 43.48%
|  |  |  | Switch Cable Installation |  | 74.08%
|  |  |  | Line Cable Installation |  | 27.53%
|  |  |  | Breakdown Testing |  | 68.53%
|  |  |  | Pre-Operation Testing |  | 44.75%
625A | 98808 | E3-4 |  | Switch Machine Installation |  | 49.65% | 48.33%
|  |  |  | Switch JB Installation |  | 60.7%
|  |  |  | Switch Cable Installation |  | 8.965%
|  |  |  | Line Cable Installation |  | 94.96%
|  |  |  | Breakdown Testing |  | 10.29%
|  |  |  | Pre-Operation Testing |  | 77.77%
625B | 99949 | E2 |  | Switch Machine Installation |  | 3.76% | 25.46%
|  |  |  | Switch JB Installation |  | 22.01%
|  |  |  | Switch Cable Installation |  | 42.16%
|  |  |  | Line Cable Installation |  | 5.064%
|  |  |  | Breakdown Testing |  | 26.23%
|  |  |  | Pre-Operation Testing |  | 50.11%
663 | 99628 | E3-4 |  | Switch Machine Installation |  | 91.41% | 50.3%
|  |  |  | Switch JB Installation |  | 19.42%
|  |  |  | Switch Cable Installation |  | 25.99%
|  |  |  | Line Cable Installation |  | 79.62%
|  |  |  | Breakdown Testing |  | 12.24%
|  |  |  | Pre-Operation Testing |  | 42.26%
673A | 99999 | E1 |  | Switch Machine Installation |  | 69.57% | 47.73%
|  |  |  | Switch JB Installation |  | 26.79%
|  |  |  | Switch Cable Installation |  | 25.53%
|  |  |  | Line Cable Installation |  | 56.87%
|  |  |  | Breakdown Testing |  | 14.35%
|  |  |  | Pre-Operation Testing |  | 72.32%
673B | 99826 | E3 |  | Switch Machine Installation |  | 34.03% | 49.18%
|  |  |  | Switch JB Installation |  | 63.42%
|  |  |  | Switch Cable Installation |  | 77.02%
|  |  |  | Line Cable Installation |  | 3.109%
|  |  |  | Breakdown Testing |  | 44.73%
|  |  |  | Pre-Operation Testing |  | 87.01%
651A | 99761 | E4 |  | Switch Machine Installation |  | 8.19% | 36.89%
|  |  |  | Switch JB Installation |  | 56.78%
|  |  |  | Switch Cable Installation |  | 76.41%
|  |  |  | Line Cable Installation |  | 47.13%
|  |  |  | Breakdown Testing |  | 48.71%
|  |  |  | Pre-Operation Testing |  | 3.984%
651B | 99949 | E2 |  | Switch Machine Installation |  | 15.99% | 42.2%
|  |  |  | Switch JB Installation |  | 19.32%
|  |  |  | Switch Cable Installation |  | 11.28%
|  |  |  | Line Cable Installation |  | 75%
|  |  |  | Breakdown Testing |  | 14.82%
|  |  |  | Pre-Operation Testing |  | 93.92%
757A | 113880 | E1 |  | Switch Machine Installation |  | 39.1% | 25.22%
|  |  |  | Switch JB Installation |  | 51.16%
|  |  |  | Switch Cable Installation |  | 14.64%
|  |  |  | Line Cable Installation |  | 2.463%
|  |  |  | Breakdown Testing |  | 1.317%
|  |  |  | Pre-Operation Testing |  | 68.58%
757B | 114010 | E2 |  | Switch Machine Installation |  | 1.08% | 45.32%
|  |  |  | Switch JB Installation |  | 23.11%
|  |  |  | Switch Cable Installation |  | 97.09%
|  |  |  | Line Cable Installation |  | 8.976%
|  |  |  | Breakdown Testing |  | 84.68%
|  |  |  | Pre-Operation Testing |  | 34.8%
753A | 114010 | E1 |  | Switch Machine Installation |  | 60.45% | 33.85%
|  |  |  | Switch JB Installation |  | 50.74%
|  |  |  | Switch Cable Installation |  | 4.491%
|  |  |  | Line Cable Installation |  | 89.16%
|  |  |  | Breakdown Testing |  | 0.481%
|  |  |  | Pre-Operation Testing |  | 14.66%
753B | 113880 | E2 |  | Switch Machine Installation |  | 29.32% | 35.81%
|  |  |  | Switch JB Installation |  | 8.764%
|  |  |  | Switch Cable Installation |  | 11.06%
|  |  |  | Line Cable Installation |  | 14.19%
|  |  |  | Breakdown Testing |  | 61.27%
|  |  |  | Pre-Operation Testing |  | 63.2%
825 |  | E1 |  | Switch Machine Installation |  | 66.93% | 48.86% | Stationing missing
|  |  |  | Switch JB Installation |  | 17.97%
|  |  |  | Switch Cable Installation |  | 34.82%
|  |  |  | Line Cable Installation |  | 22.94%
|  |  |  | Breakdown Testing |  | 20.82%
|  |  |  | Pre-Operation Testing |  | 98.8%
815A | 121995 | E5 |  | Switch Machine Installation |  | 16.46% | 50.73%
|  |  |  | Switch JB Installation |  | 94.67%
|  |  |  | Switch Cable Installation |  | 66.9%
|  |  |  | Line Cable Installation |  | 42.93%
|  |  |  | Breakdown Testing |  | 31.26%
|  |  |  | Pre-Operation Testing |  | 96.09%
815B | 121831 | E2 |  | Switch Machine Installation |  | 49.35% | 46.42%
|  |  |  | Switch JB Installation |  | 28.43%
|  |  |  | Switch Cable Installation |  | 99.02%
|  |  |  | Line Cable Installation |  | 0.1361%
|  |  |  | Breakdown Testing |  | 54.21%
|  |  |  | Pre-Operation Testing |  | 29.39%
851B | 122757 | E5 |  | Switch Machine Installation |  | 50.39% | 55.18%
|  |  |  | Switch JB Installation |  | 82.97%
|  |  |  | Switch Cable Installation |  | 47.97%
|  |  |  | Line Cable Installation |  | 40.25%
|  |  |  | Breakdown Testing |  | 56.77%
|  |  |  | Pre-Operation Testing |  | 80.5%
851A | 122923 | E1 |  | Switch Machine Installation |  | 50.9% | 56.46%
|  |  |  | Switch JB Installation |  | 78.89%
|  |  |  | Switch Cable Installation |  | 96.38%
|  |  |  | Line Cable Installation |  | 28.81%
|  |  |  | Breakdown Testing |  | 78.05%
|  |  |  | Pre-Operation Testing |  | 28.18%
841 | 122923 | E2 |  | Switch Machine Installation |  | 50.06% | 51.35%
|  |  |  | Switch JB Installation |  | 64.79%
|  |  |  | Switch Cable Installation |  | 6.79%
|  |  |  | Line Cable Installation |  | 43.58%
|  |  |  | Breakdown Testing |  | 91.6%
|  |  |  | Pre-Operation Testing |  | 64.73%
753B | 113880 | E2 |  | Switch Machine Installation |  | 99.92% | 55.22%
|  |  |  | Switch JB Installation |  | 1.524%
|  |  |  | Switch Cable Installation |  | 48.73%
|  |  |  | Line Cable Installation |  | 72.84%
|  |  |  | Breakdown Testing |  | 51.05%
|  |  |  | Pre-Operation Testing |  | 3.555%

## WRU
Stationing | Track No | Location | Activity | Date | Progress | General Progress | Notes
54000 | B1 |  | Radio Unit Installation |  | 63.6% | 60.9% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 20.02%
|  |  | Fiber Box Installation |  | 3.723%
|  |  | Antenna Installation |  | 97.14%
|  |  | Antenna Cable Installation |  | 91.12%
|  |  | Splitter Installation |  | 60.02%
|  |  | Fiber Cable Splicing |  | 99.36%
|  |  | Fiber Testing |  | 64.49%
|  |  | Power Testing |  | 48.61%
54000 | B3 |  | Radio Unit Installation |  | 89.73% | 63.72% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 69.05%
|  |  | Fiber Box Installation |  | 27.27%
|  |  | Antenna Installation |  | 94.47%
|  |  | Antenna Cable Installation |  | 99.9%
|  |  | Splitter Installation |  | 67.57%
|  |  | Fiber Cable Splicing |  | 78.21%
|  |  | Fiber Testing |  | 24.89%
|  |  | Power Testing |  | 22.39%
54000 | B4 |  | Radio Unit Installation |  | 48.36% | 47.7% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 36.41%
|  |  | Fiber Box Installation |  | 75.34%
|  |  | Antenna Installation |  | 74.67%
|  |  | Antenna Cable Installation |  | 6.148%
|  |  | Splitter Installation |  | 43.42%
|  |  | Fiber Cable Splicing |  | 5.886%
|  |  | Fiber Testing |  | 60.4%
|  |  | Power Testing |  | 78.69%
54000 | B2 |  | Radio Unit Installation |  | 27.31% | 54.68% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 61.58%
|  |  | Fiber Box Installation |  | 17.16%
|  |  | Antenna Installation |  | 96.06%
|  |  | Antenna Cable Installation |  | 52.5%
|  |  | Splitter Installation |  | 54.55%
|  |  | Fiber Cable Splicing |  | 80.38%
|  |  | Fiber Testing |  | 69.43%
|  |  | Power Testing |  | 33.11%
54000 | B5 |  | Radio Unit Installation |  | 29.61% | 40.99% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 71.82%
|  |  | Fiber Box Installation |  | 32.21%
|  |  | Antenna Installation |  | 44.14%
|  |  | Antenna Cable Installation |  | 43.14%
|  |  | Splitter Installation |  | 34.99%
|  |  | Fiber Cable Splicing |  | 18.87%
|  |  | Fiber Testing |  | 27.16%
|  |  | Power Testing |  | 66.94%
55500 | B2 |  | Radio Unit Installation |  | 82.27% | 65.76% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 45.32%
|  |  | Fiber Box Installation |  | 53.05%
|  |  | Antenna Installation |  | 63.72%
|  |  | Antenna Cable Installation |  | 65.33%
|  |  | Splitter Installation |  | 50.83%
|  |  | Fiber Cable Splicing |  | 61.15%
|  |  | Fiber Testing |  | 73.96%
|  |  | Power Testing |  | 96.24%
55500 | B1 |  | Radio Unit Installation |  | 39.69% | 48.82% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 70.16%
|  |  | Fiber Box Installation |  | 78%
|  |  | Antenna Installation |  | 2.828%
|  |  | Antenna Cable Installation |  | 17.15%
|  |  | Splitter Installation |  | 89.77%
|  |  | Fiber Cable Splicing |  | 59.21%
|  |  | Fiber Testing |  | 57.63%
|  |  | Power Testing |  | 24.91%
56300 | B1 |  | Radio Unit Installation |  | 50.96% | 57.21% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 62.87%
|  |  | Fiber Box Installation |  | 99.63%
|  |  | Antenna Installation |  | 23.96%
|  |  | Antenna Cable Installation |  | 79.99%
|  |  | Splitter Installation |  | 89.09%
|  |  | Fiber Cable Splicing |  | 8.585%
|  |  | Fiber Testing |  | 36.44%
|  |  | Power Testing |  | 63.4%
56500 | B1 |  | Radio Unit Installation |  | 55.7% | 46.94% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 84.53%
|  |  | Fiber Box Installation |  | 55.83%
|  |  | Antenna Installation |  | 53.93%
|  |  | Antenna Cable Installation |  | 40.86%
|  |  | Splitter Installation |  | 9.248%
|  |  | Fiber Cable Splicing |  | 12.91%
|  |  | Fiber Testing |  | 39.69%
|  |  | Power Testing |  | 69.74%
57200 | B1 |  | Radio Unit Installation |  | 95.83% | 58.56% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 78.39%
|  |  | Fiber Box Installation |  | 62.71%
|  |  | Antenna Installation |  | 15.33%
|  |  | Antenna Cable Installation |  | 92.15%
|  |  | Splitter Installation |  | 23.72%
|  |  | Fiber Cable Splicing |  | 63.86%
|  |  | Fiber Testing |  | 41.03%
|  |  | Power Testing |  | 54.04%
57400 | B1 |  | Radio Unit Installation |  | 63.65% | 65.09% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 29.01%
|  |  | Fiber Box Installation |  | 66.22%
|  |  | Antenna Installation |  | 15.77%
|  |  | Antenna Cable Installation |  | 89.94%
|  |  | Splitter Installation |  | 96.59%
|  |  | Fiber Cable Splicing |  | 72.7%
|  |  | Fiber Testing |  | 71.79%
|  |  | Power Testing |  | 80.11%
58300 | B1 |  | Radio Unit Installation |  | 70.26% | 61.44% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 61.63%
|  |  | Fiber Box Installation |  | 53.96%
|  |  | Antenna Installation |  | 33.88%
|  |  | Antenna Cable Installation |  | 94.38%
|  |  | Splitter Installation |  | 77.19%
|  |  | Fiber Cable Splicing |  | 41.05%
|  |  | Fiber Testing |  | 99.58%
|  |  | Power Testing |  | 20.99%
58400 | B1 |  | Radio Unit Installation |  | 7.836% | 64.44% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 95.84%
|  |  | Fiber Box Installation |  | 75.54%
|  |  | Antenna Installation |  | 55.49%
|  |  | Antenna Cable Installation |  | 70.41%
|  |  | Splitter Installation |  | 99.2%
|  |  | Fiber Cable Splicing |  | 61.67%
|  |  | Fiber Testing |  | 60.23%
|  |  | Power Testing |  | 53.74%
59400 | B1 |  | Radio Unit Installation |  | 94.21% | 51.3% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0.7091%
|  |  | Fiber Box Installation |  | 5.692%
|  |  | Antenna Installation |  | 59.53%
|  |  | Antenna Cable Installation |  | 96.38%
|  |  | Splitter Installation |  | 83.67%
|  |  | Fiber Cable Splicing |  | 38.13%
|  |  | Fiber Testing |  | 30.76%
|  |  | Power Testing |  | 52.64%
59700 | B1 |  | Radio Unit Installation |  | 19.24% | 46.61% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 67.12%
|  |  | Fiber Box Installation |  | 15.07%
|  |  | Antenna Installation |  | 79.8%
|  |  | Antenna Cable Installation |  | 86.75%
|  |  | Splitter Installation |  | 81.39%
|  |  | Fiber Cable Splicing |  | 26.52%
|  |  | Fiber Testing |  | 31.12%
|  |  | Power Testing |  | 12.47%
60500 | B1 |  | Radio Unit Installation |  | 96.85% | 51.29% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 23.61%
|  |  | Fiber Box Installation |  | 76.72%
|  |  | Antenna Installation |  | 4.146%
|  |  | Antenna Cable Installation |  | 1.956%
|  |  | Splitter Installation |  | 77.9%
|  |  | Fiber Cable Splicing |  | 62.66%
|  |  | Fiber Testing |  | 93.15%
|  |  | Power Testing |  | 24.64%
60800 | B2 |  | Radio Unit Installation |  | 41.7% | 35.14% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 15.2%
|  |  | Fiber Box Installation |  | 27.3%
|  |  | Antenna Installation |  | 9.631%
|  |  | Antenna Cable Installation |  | 28.77%
|  |  | Splitter Installation |  | 84.14%
|  |  | Fiber Cable Splicing |  | 96.34%
|  |  | Fiber Testing |  | 0.6736%
|  |  | Power Testing |  | 12.51%
60800 | B1 |  | Radio Unit Installation |  | 75.82% | 49.4% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 15.62%
|  |  | Fiber Box Installation |  | 77.01%
|  |  | Antenna Installation |  | 10.72%
|  |  | Antenna Cable Installation |  | 20.09%
|  |  | Splitter Installation |  | 13.86%
|  |  | Fiber Cable Splicing |  | 40.88%
|  |  | Fiber Testing |  | 91.17%
|  |  | Power Testing |  | 99.42%
61900 | B2 |  | Radio Unit Installation |  | 13.11% | 50.46% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 83.4%
|  |  | Fiber Box Installation |  | 0.8417%
|  |  | Antenna Installation |  | 97.95%
|  |  | Antenna Cable Installation |  | 38.98%
|  |  | Splitter Installation |  | 86.86%
|  |  | Fiber Cable Splicing |  | 77.95%
|  |  | Fiber Testing |  | 8.687%
|  |  | Power Testing |  | 46.37%
61900 | B1 |  | Radio Unit Installation |  | 29.83% | 53.37% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 31.15%
|  |  | Fiber Box Installation |  | 2.427%
|  |  | Antenna Installation |  | 77.99%
|  |  | Antenna Cable Installation |  | 83.87%
|  |  | Splitter Installation |  | 65.87%
|  |  | Fiber Cable Splicing |  | 18.9%
|  |  | Fiber Testing |  | 86.34%
|  |  | Power Testing |  | 83.92%
62300 | B1 |  | Radio Unit Installation |  | 33.3% | 51.72% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 97.57%
|  |  | Fiber Box Installation |  | 13.74%
|  |  | Antenna Installation |  | 68.07%
|  |  | Antenna Cable Installation |  | 97.27%
|  |  | Splitter Installation |  | 9.653%
|  |  | Fiber Cable Splicing |  | 50.61%
|  |  | Fiber Testing |  | 51.88%
|  |  | Power Testing |  | 43.43%
63200 | B1 |  | Radio Unit Installation |  | 64.85% | 49.97% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 90.34%
|  |  | Fiber Box Installation |  | 49.05%
|  |  | Antenna Installation |  | 19.44%
|  |  | Antenna Cable Installation |  | 61.15%
|  |  | Splitter Installation |  | 38.03%
|  |  | Fiber Cable Splicing |  | 33.15%
|  |  | Fiber Testing |  | 86.68%
|  |  | Power Testing |  | 7.002%
63300 | B1 |  | Radio Unit Installation |  | 20.54% | 36.45% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 33.39%
|  |  | Fiber Box Installation |  | 66.45%
|  |  | Antenna Installation |  | 67.85%
|  |  | Antenna Cable Installation |  | 22.12%
|  |  | Splitter Installation |  | 59.81%
|  |  | Fiber Cable Splicing |  | 17.7%
|  |  | Fiber Testing |  | 13.95%
|  |  | Power Testing |  | 26.21%
64200 | B1 |  | Radio Unit Installation |  | 68.62% | 44.24% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 55.26%
|  |  | Fiber Box Installation |  | 0.03118%
|  |  | Antenna Installation |  | 28.54%
|  |  | Antenna Cable Installation |  | 31.35%
|  |  | Splitter Installation |  | 88.88%
|  |  | Fiber Cable Splicing |  | 15.28%
|  |  | Fiber Testing |  | 64.1%
|  |  | Power Testing |  | 46.12%
64300 | B1 |  | Radio Unit Installation |  | 29.74% | 50.48% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 90.87%
|  |  | Fiber Box Installation |  | 66.76%
|  |  | Antenna Installation |  | 17.22%
|  |  | Antenna Cable Installation |  | 6.27%
|  |  | Splitter Installation |  | 87.37%
|  |  | Fiber Cable Splicing |  | 87.2%
|  |  | Fiber Testing |  | 21.15%
|  |  | Power Testing |  | 47.75%
65200 | B1 |  | Radio Unit Installation |  | 6.969% | 43.5% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 64.1%
|  |  | Fiber Box Installation |  | 71.14%
|  |  | Antenna Installation |  | 90.54%
|  |  | Antenna Cable Installation |  | 39.78%
|  |  | Splitter Installation |  | 34.17%
|  |  | Fiber Cable Splicing |  | 3.595%
|  |  | Fiber Testing |  | 23.72%
|  |  | Power Testing |  | 57.46%
65200 | B2 |  | Radio Unit Installation |  | 12.49% | 44.69% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 57.33%
|  |  | Fiber Box Installation |  | 63.16%
|  |  | Antenna Installation |  | 46.87%
|  |  | Antenna Cable Installation |  | 60.35%
|  |  | Splitter Installation |  | 40.17%
|  |  | Fiber Cable Splicing |  | 18.77%
|  |  | Fiber Testing |  | 14.37%
|  |  | Power Testing |  | 88.67%
66300 | B1 |  | Radio Unit Installation |  | 18.13% | 56.89% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 60.58%
|  |  | Fiber Box Installation |  | 78.3%
|  |  | Antenna Installation |  | 61.23%
|  |  | Antenna Cable Installation |  | 65.53%
|  |  | Splitter Installation |  | 88.82%
|  |  | Fiber Cable Splicing |  | 62.03%
|  |  | Fiber Testing |  | 19.67%
|  |  | Power Testing |  | 57.78%
66300 | B2 |  | Radio Unit Installation |  | 69.38% | 37.15% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 58.82%
|  |  | Fiber Box Installation |  | 32.78%
|  |  | Antenna Installation |  | 16%
|  |  | Antenna Cable Installation |  | 32.23%
|  |  | Splitter Installation |  | 19.71%
|  |  | Fiber Cable Splicing |  | 16.27%
|  |  | Fiber Testing |  | 53.09%
|  |  | Power Testing |  | 36.08%
67500 | B1 |  | Radio Unit Installation |  | 14.01% | 49.63% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 7.9%
|  |  | Fiber Box Installation |  | 36.07%
|  |  | Antenna Installation |  | 73.4%
|  |  | Antenna Cable Installation |  | 93.38%
|  |  | Splitter Installation |  | 30.65%
|  |  | Fiber Cable Splicing |  | 63.45%
|  |  | Fiber Testing |  | 99.24%
|  |  | Power Testing |  | 28.55%
67500 | B2 |  | Radio Unit Installation |  | 18.03% | 40.36% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 22.55%
|  |  | Fiber Box Installation |  | 70.83%
|  |  | Antenna Installation |  | 65.33%
|  |  | Antenna Cable Installation |  | 46.55%
|  |  | Splitter Installation |  | 26.02%
|  |  | Fiber Cable Splicing |  | 29.52%
|  |  | Fiber Testing |  | 46.8%
|  |  | Power Testing |  | 37.65%
68300 | B1 |  | Radio Unit Installation |  | 83.71% | 53.86% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 88.95%
|  |  | Fiber Box Installation |  | 70.25%
|  |  | Antenna Installation |  | 22.6%
|  |  | Antenna Cable Installation |  | 11.2%
|  |  | Splitter Installation |  | 27.46%
|  |  | Fiber Cable Splicing |  | 89.82%
|  |  | Fiber Testing |  | 36.9%
|  |  | Power Testing |  | 53.85%
68300 | B2 |  | Radio Unit Installation |  | 41.69% | 43.97% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 68.16%
|  |  | Fiber Box Installation |  | 17.38%
|  |  | Antenna Installation |  | 35.47%
|  |  | Antenna Cable Installation |  | 90.11%
|  |  | Splitter Installation |  | 50.37%
|  |  | Fiber Cable Splicing |  | 32.03%
|  |  | Fiber Testing |  | 35.99%
|  |  | Power Testing |  | 24.53%
69900 | B1 |  | Radio Unit Installation |  | 40.05% | 48.24% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 19.28%
|  |  | Fiber Box Installation |  | 25.14%
|  |  | Antenna Installation |  | 42.57%
|  |  | Antenna Cable Installation |  | 65.94%
|  |  | Splitter Installation |  | 8.56%
|  |  | Fiber Cable Splicing |  | 91.53%
|  |  | Fiber Testing |  | 71.82%
|  |  | Power Testing |  | 69.26%
71400 | B1 |  | Radio Unit Installation |  | 34.16% | 55.76% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 16.54%
|  |  | Fiber Box Installation |  | 45.89%
|  |  | Antenna Installation |  | 68.51%
|  |  | Antenna Cable Installation |  | 66.13%
|  |  | Splitter Installation |  | 82.47%
|  |  | Fiber Cable Splicing |  | 90.99%
|  |  | Fiber Testing |  | 8.691%
|  |  | Power Testing |  | 88.48%
73000 | B1 |  | Radio Unit Installation |  | 98.35% | 58.77% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 77.51%
|  |  | Fiber Box Installation |  | 9.056%
|  |  | Antenna Installation |  | 0.7358%
|  |  | Antenna Cable Installation |  | 81.76%
|  |  | Splitter Installation |  | 71.51%
|  |  | Fiber Cable Splicing |  | 72.41%
|  |  | Fiber Testing |  | 47.55%
|  |  | Power Testing |  | 70.03%
73000 | B2 |  | Radio Unit Installation |  | 46.56% | 57.93% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 57%
|  |  | Fiber Box Installation |  | 83.63%
|  |  | Antenna Installation |  | 88.47%
|  |  | Antenna Cable Installation |  | 24.74%
|  |  | Splitter Installation |  | 22.74%
|  |  | Fiber Cable Splicing |  | 87.71%
|  |  | Fiber Testing |  | 86.9%
|  |  | Power Testing |  | 23.61%
74100 | B1 |  | Radio Unit Installation |  | 12.48% | 47.56% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 21.49%
|  |  | Fiber Box Installation |  | 43.9%
|  |  | Antenna Installation |  | 60.51%
|  |  | Antenna Cable Installation |  | 71.81%
|  |  | Splitter Installation |  | 11.63%
|  |  | Fiber Cable Splicing |  | 26.68%
|  |  | Fiber Testing |  | 97.22%
|  |  | Power Testing |  | 82.3%
75300 | B1 |  | Radio Unit Installation |  | 65.97% | 55.41% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 45.66%
|  |  | Fiber Box Installation |  | 52.32%
|  |  | Antenna Installation |  | 26.76%
|  |  | Antenna Cable Installation |  | 59.47%
|  |  | Splitter Installation |  | 35.01%
|  |  | Fiber Cable Splicing |  | 60.68%
|  |  | Fiber Testing |  | 62.33%
|  |  | Power Testing |  | 90.46%
75300 | B2 |  | Radio Unit Installation |  | 76.88% | 47.55% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 76.36%
|  |  | Fiber Box Installation |  | 52.82%
|  |  | Antenna Installation |  | 42.46%
|  |  | Antenna Cable Installation |  | 13.09%
|  |  | Splitter Installation |  | 33.41%
|  |  | Fiber Cable Splicing |  | 8.279%
|  |  | Fiber Testing |  | 96.74%
|  |  | Power Testing |  | 27.94%
88300 | E1 |  | Radio Unit Installation |  | 82.54% | 61.37% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 16.21%
|  |  | Fiber Box Installation |  | 56.06%
|  |  | Antenna Installation |  | 38.37%
|  |  | Antenna Cable Installation |  | 45.9%
|  |  | Splitter Installation |  | 79.22%
|  |  | Fiber Cable Splicing |  | 93.45%
|  |  | Fiber Testing |  | 65.9%
|  |  | Power Testing |  | 74.69%
88600 | E1 |  | Radio Unit Installation |  | 53.01% | 56.5% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 11.29%
|  |  | Fiber Box Installation |  | 83.57%
|  |  | Antenna Installation |  | 91.63%
|  |  | Antenna Cable Installation |  | 63.92%
|  |  | Splitter Installation |  | 12.21%
|  |  | Fiber Cable Splicing |  | 83.39%
|  |  | Fiber Testing |  | 56.93%
|  |  | Power Testing |  | 52.51%
90800 | E1 |  | Radio Unit Installation |  | 50.29% | 37.69% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 5.784%
|  |  | Fiber Box Installation |  | 1.963%
|  |  | Antenna Installation |  | 11.08%
|  |  | Antenna Cable Installation |  | 86.46%
|  |  | Splitter Installation |  | 63.68%
|  |  | Fiber Cable Splicing |  | 11.39%
|  |  | Fiber Testing |  | 47.87%
|  |  | Power Testing |  | 60.65%
92400 | E1 |  | Radio Unit Installation |  | 13.65% | 54.63% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 58.51%
|  |  | Fiber Box Installation |  | 93.41%
|  |  | Antenna Installation |  | 98.62%
|  |  | Antenna Cable Installation |  | 33.19%
|  |  | Splitter Installation |  | 42.68%
|  |  | Fiber Cable Splicing |  | 66.32%
|  |  | Fiber Testing |  | 38%
|  |  | Power Testing |  | 47.32%
93600 | E1 |  | Radio Unit Installation |  | 52.04% | 47.78% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 7.333%
|  |  | Fiber Box Installation |  | 45.64%
|  |  | Antenna Installation |  | 25.11%
|  |  | Antenna Cable Installation |  | 85.66%
|  |  | Splitter Installation |  | 64.89%
|  |  | Fiber Cable Splicing |  | 13.86%
|  |  | Fiber Testing |  | 92.3%
|  |  | Power Testing |  | 43.18%
95000 | E1 |  | Radio Unit Installation |  | 24.18% | 63.21% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 82.85%
|  |  | Fiber Box Installation |  | 89.6%
|  |  | Antenna Installation |  | 99.96%
|  |  | Antenna Cable Installation |  | 81.34%
|  |  | Splitter Installation |  | 12.89%
|  |  | Fiber Cable Splicing |  | 47.95%
|  |  | Fiber Testing |  | 83.52%
|  |  | Power Testing |  | 46.57%
96500 | E1 |  | Radio Unit Installation |  | 35% | 55.58% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 78.38%
|  |  | Fiber Box Installation |  | 84.36%
|  |  | Antenna Installation |  | 7.385%
|  |  | Antenna Cable Installation |  | 99.12%
|  |  | Splitter Installation |  | 69.68%
|  |  | Fiber Cable Splicing |  | 33.26%
|  |  | Fiber Testing |  | 0.6743%
|  |  | Power Testing |  | 92.34%
98200 | E1 |  | Radio Unit Installation |  | 32.5% | 54.42% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 67.95%
|  |  | Fiber Box Installation |  | 49.95%
|  |  | Antenna Installation |  | 29.89%
|  |  | Antenna Cable Installation |  | 88.42%
|  |  | Splitter Installation |  | 92.21%
|  |  | Fiber Cable Splicing |  | 81.76%
|  |  | Fiber Testing |  | 21.97%
|  |  | Power Testing |  | 25.1%
99700 | E1 |  | Radio Unit Installation |  | 44.71% | 36.1% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 42.4%
|  |  | Fiber Box Installation |  | 1.587%
|  |  | Antenna Installation |  | 35.68%
|  |  | Antenna Cable Installation |  | 44.81%
|  |  | Splitter Installation |  | 48.12%
|  |  | Fiber Cable Splicing |  | 15.3%
|  |  | Fiber Testing |  | 87.78%
|  |  | Power Testing |  | 4.514%
99700 | E2 |  | Radio Unit Installation |  | 15.26% | 31.79% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 58.44%
|  |  | Fiber Box Installation |  | 56.54%
|  |  | Antenna Installation |  | 34.57%
|  |  | Antenna Cable Installation |  | 3.926%
|  |  | Splitter Installation |  | 3.505%
|  |  | Fiber Cable Splicing |  | 0.7619%
|  |  | Fiber Testing |  | 77.07%
|  |  | Power Testing |  | 35.99%
100400 | E1 |  | Radio Unit Installation |  | 36.38% | 37.76% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 77.76%
|  |  | Fiber Box Installation |  | 3.948%
|  |  | Antenna Installation |  | 52.24%
|  |  | Antenna Cable Installation |  | 9.36%
|  |  | Splitter Installation |  | 14.48%
|  |  | Fiber Cable Splicing |  | 30.71%
|  |  | Fiber Testing |  | 23.69%
|  |  | Power Testing |  | 91.25%
100600 | E1 |  | Radio Unit Installation |  | 75.34% | 53.62% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 2.119%
|  |  | Fiber Box Installation |  | 19.79%
|  |  | Antenna Installation |  | 68.55%
|  |  | Antenna Cable Installation |  | 23.76%
|  |  | Splitter Installation |  | 57.39%
|  |  | Fiber Cable Splicing |  | 85.11%
|  |  | Fiber Testing |  | 75.95%
|  |  | Power Testing |  | 74.55%
101500 | E1 |  | Radio Unit Installation |  | 67.94% | 49.89% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 58.76%
|  |  | Fiber Box Installation |  | 1.858%
|  |  | Antenna Installation |  | 10.93%
|  |  | Antenna Cable Installation |  | 62.4%
|  |  | Splitter Installation |  | 40%
|  |  | Fiber Cable Splicing |  | 54.17%
|  |  | Fiber Testing |  | 93.74%
|  |  | Power Testing |  | 59.26%
102600 | E1 |  | Radio Unit Installation |  | 93.24% | 59.09% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 43.11%
|  |  | Fiber Box Installation |  | 73.41%
|  |  | Antenna Installation |  | 96.76%
|  |  | Antenna Cable Installation |  | 32.15%
|  |  | Splitter Installation |  | 98.92%
|  |  | Fiber Cable Splicing |  | 47.41%
|  |  | Fiber Testing |  | 1.417%
|  |  | Power Testing |  | 45.44%
103800 | E1 |  | Radio Unit Installation |  | 44.59% | 44.25% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 79.97%
|  |  | Fiber Box Installation |  | 95.22%
|  |  | Antenna Installation |  | 15.13%
|  |  | Antenna Cable Installation |  | 31.17%
|  |  | Splitter Installation |  | 69.76%
|  |  | Fiber Cable Splicing |  | 4.424%
|  |  | Fiber Testing |  | 16.75%
|  |  | Power Testing |  | 41.25%
104700 | E1 |  | Radio Unit Installation |  | 3.099% | 63.33% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 80.59%
|  |  | Fiber Box Installation |  | 59.48%
|  |  | Antenna Installation |  | 89.83%
|  |  | Antenna Cable Installation |  | 76.15%
|  |  | Splitter Installation |  | 47.64%
|  |  | Fiber Cable Splicing |  | 42.09%
|  |  | Fiber Testing |  | 76.18%
|  |  | Power Testing |  | 94.89%
105900 | E1 |  | Radio Unit Installation |  | 32.84% | 54.45% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 52.29%
|  |  | Fiber Box Installation |  | 56.26%
|  |  | Antenna Installation |  | 94.13%
|  |  | Antenna Cable Installation |  | 76.3%
|  |  | Splitter Installation |  | 53.42%
|  |  | Fiber Cable Splicing |  | 76.1%
|  |  | Fiber Testing |  | 46.44%
|  |  | Power Testing |  | 2.228%
106900 | E1 |  | Radio Unit Installation |  | 39.23% | 52.56% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 70.61%
|  |  | Fiber Box Installation |  | 11.08%
|  |  | Antenna Installation |  | 5.124%
|  |  | Antenna Cable Installation |  | 65.23%
|  |  | Splitter Installation |  | 84.61%
|  |  | Fiber Cable Splicing |  | 62.04%
|  |  | Fiber Testing |  | 37.41%
|  |  | Power Testing |  | 97.69%
108300 | E1 |  | Radio Unit Installation |  | 16.23% | 44.31% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 70.44%
|  |  | Fiber Box Installation |  | 22.11%
|  |  | Antenna Installation |  | 86.64%
|  |  | Antenna Cable Installation |  | 23.92%
|  |  | Splitter Installation |  | 35.68%
|  |  | Fiber Cable Splicing |  | 42.65%
|  |  | Fiber Testing |  | 10.24%
|  |  | Power Testing |  | 90.86%
109900 | E1 |  | Radio Unit Installation |  | 25.96% | 68.87% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 6.672%
|  |  | Fiber Box Installation |  | 99.78%
|  |  | Antenna Installation |  | 82.32%
|  |  | Antenna Cable Installation |  | 62.45%
|  |  | Splitter Installation |  | 93.17%
|  |  | Fiber Cable Splicing |  | 99.16%
|  |  | Fiber Testing |  | 69.96%
|  |  | Power Testing |  | 80.35%
111100 | E1 |  | Radio Unit Installation |  | 40.5% | 42.76% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 74.15%
|  |  | Fiber Box Installation |  | 41.83%
|  |  | Antenna Installation |  | 34.56%
|  |  | Antenna Cable Installation |  | 50.49%
|  |  | Splitter Installation |  | 30.01%
|  |  | Fiber Cable Splicing |  | 56.93%
|  |  | Fiber Testing |  | 20.44%
|  |  | Power Testing |  | 35.89%
112200 | E1 |  | Radio Unit Installation |  | 21.17% | 46.96% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 31.87%
|  |  | Fiber Box Installation |  | 50.55%
|  |  | Antenna Installation |  | 54.22%
|  |  | Antenna Cable Installation |  | 14.9%
|  |  | Splitter Installation |  | 56.13%
|  |  | Fiber Cable Splicing |  | 52.98%
|  |  | Fiber Testing |  | 77.88%
|  |  | Power Testing |  | 62.94%
113000 | E1 |  | Radio Unit Installation |  | 36.67% | 54.79% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 89.89%
|  |  | Fiber Box Installation |  | 26.1%
|  |  | Antenna Installation |  | 53.2%
|  |  | Antenna Cable Installation |  | 91.41%
|  |  | Splitter Installation |  | 8.84%
|  |  | Fiber Cable Splicing |  | 64.63%
|  |  | Fiber Testing |  | 97.39%
|  |  | Power Testing |  | 25.02%
114300 | E1 |  | Radio Unit Installation |  | 36.71% | 35.19% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 20.99%
|  |  | Fiber Box Installation |  | 22.42%
|  |  | Antenna Installation |  | 3.476%
|  |  | Antenna Cable Installation |  | 93.23%
|  |  | Splitter Installation |  | 15.85%
|  |  | Fiber Cable Splicing |  | 15.77%
|  |  | Fiber Testing |  | 48.37%
|  |  | Power Testing |  | 59.88%
115500 | E1 |  | Radio Unit Installation |  | 28.39% | 30.08% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 44.68%
|  |  | Fiber Box Installation |  | 35.56%
|  |  | Antenna Installation |  | 0.8053%
|  |  | Antenna Cable Installation |  | 15.26%
|  |  | Splitter Installation |  | 16.67%
|  |  | Fiber Cable Splicing |  | 9.078%
|  |  | Fiber Testing |  | 52.93%
|  |  | Power Testing |  | 67.34%
116900 | E1 |  | Radio Unit Installation |  | 3.324% | 55.65% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 28.11%
|  |  | Fiber Box Installation |  | 53.67%
|  |  | Antenna Installation |  | 18.8%
|  |  | Antenna Cable Installation |  | 87.66%
|  |  | Splitter Installation |  | 95.73%
|  |  | Fiber Cable Splicing |  | 82.04%
|  |  | Fiber Testing |  | 59.61%
|  |  | Power Testing |  | 71.87%
118300 | E1 |  | Radio Unit Installation |  | 97.93% | 67.91% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 78.69%
|  |  | Fiber Box Installation |  | 24.46%
|  |  | Antenna Installation |  | 96.82%
|  |  | Antenna Cable Installation |  | 98.46%
|  |  | Splitter Installation |  | 95.76%
|  |  | Fiber Cable Splicing |  | 52.51%
|  |  | Fiber Testing |  | 43.34%
|  |  | Power Testing |  | 23.23%
118300 | E2 |  | Radio Unit Installation |  | 90.14% | 52.52% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 43.43%
|  |  | Fiber Box Installation |  | 2.853%
|  |  | Antenna Installation |  | 62.21%
|  |  | Antenna Cable Installation |  | 60.16%
|  |  | Splitter Installation |  | 76.72%
|  |  | Fiber Cable Splicing |  | 96.92%
|  |  | Fiber Testing |  | 29.77%
|  |  | Power Testing |  | 10.45%
119500 | E1 |  | Radio Unit Installation |  | 66.75% | 47.35% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 30.39%
|  |  | Fiber Box Installation |  | 49.98%
|  |  | Antenna Installation |  | 22.29%
|  |  | Antenna Cable Installation |  | 60.1%
|  |  | Splitter Installation |  | 36.98%
|  |  | Fiber Cable Splicing |  | 55.72%
|  |  | Fiber Testing |  | 11.34%
|  |  | Power Testing |  | 92.56%
119500 | E2 |  | Radio Unit Installation |  | 54.68% | 48.47% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 31.5%
|  |  | Fiber Box Installation |  | 6.957%
|  |  | Antenna Installation |  | 8.449%
|  |  | Antenna Cable Installation |  | 76.97%
|  |  | Splitter Installation |  | 49.24%
|  |  | Fiber Cable Splicing |  | 45.31%
|  |  | Fiber Testing |  | 64.23%
|  |  | Power Testing |  | 98.91%
120800 | E1 |  | Radio Unit Installation |  | 48.58% | 48.95% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 68.05%
|  |  | Fiber Box Installation |  | 25.79%
|  |  | Antenna Installation |  | 6.078%
|  |  | Antenna Cable Installation |  | 61.23%
|  |  | Splitter Installation |  | 76.91%
|  |  | Fiber Cable Splicing |  | 40.88%
|  |  | Fiber Testing |  | 60.66%
|  |  | Power Testing |  | 52.35%
120800 | E2 |  | Radio Unit Installation |  | 12.48% | 53.14% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 40.1%
|  |  | Fiber Box Installation |  | 90.85%
|  |  | Antenna Installation |  | 73.25%
|  |  | Antenna Cable Installation |  | 59.64%
|  |  | Splitter Installation |  | 18.33%
|  |  | Fiber Cable Splicing |  | 92.01%
|  |  | Fiber Testing |  | 1.794%
|  |  | Power Testing |  | 89.81%
121900 | E1 |  | Radio Unit Installation |  | 13.34% | 44.96% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 81.25%
|  |  | Fiber Box Installation |  | 70.03%
|  |  | Antenna Installation |  | 20.17%
|  |  | Antenna Cable Installation |  | 18.91%
|  |  | Splitter Installation |  | 29.74%
|  |  | Fiber Cable Splicing |  | 50.88%
|  |  | Fiber Testing |  | 49.1%
|  |  | Power Testing |  | 71.19%
122800 | E1 |  | Radio Unit Installation |  | 53.8% | 38.48% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 16.34%
|  |  | Fiber Box Installation |  | 74.82%
|  |  | Antenna Installation |  | 31.53%
|  |  | Antenna Cable Installation |  | 65.62%
|  |  | Splitter Installation |  | 89.1%
|  |  | Fiber Cable Splicing |  | 1.676%
|  |  | Fiber Testing |  | 10.27%
|  |  | Power Testing |  | 3.211%
123900 | D1 |  | Radio Unit Installation |  | 33.14% | 66.15% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 25.8%
|  |  | Fiber Box Installation |  | 54.76%
|  |  | Antenna Installation |  | 98.96%
|  |  | Antenna Cable Installation |  | 94.24%
|  |  | Splitter Installation |  | 85.02%
|  |  | Fiber Cable Splicing |  | 27.81%
|  |  | Fiber Testing |  | 96.17%
|  |  | Power Testing |  | 79.44%
124900 | D1 |  | Radio Unit Installation |  | 43.3% | 44.07% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 90.56%
|  |  | Fiber Box Installation |  | 34.63%
|  |  | Antenna Installation |  | 71.41%
|  |  | Antenna Cable Installation |  | 18.41%
|  |  | Splitter Installation |  | 68.33%
|  |  | Fiber Cable Splicing |  | 60.26%
|  |  | Fiber Testing |  | 4.964%
|  |  | Power Testing |  | 4.728%
125900 | D1 |  | Radio Unit Installation |  | 54.85% | 43.31% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 13.57%
|  |  | Fiber Box Installation |  | 63.34%
|  |  | Antenna Installation |  | 20.74%
|  |  | Antenna Cable Installation |  | 23.73%
|  |  | Splitter Installation |  | 11.59%
|  |  | Fiber Cable Splicing |  | 98.96%
|  |  | Fiber Testing |  | 19.6%
|  |  | Power Testing |  | 83.37%
123900 | D2 |  | Radio Unit Installation |  | 33.81% | 45.94% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 9.98%
|  |  | Fiber Box Installation |  | 35.02%
|  |  | Antenna Installation |  | 75.48%
|  |  | Antenna Cable Installation |  | 31.46%
|  |  | Splitter Installation |  | 3.165%
|  |  | Fiber Cable Splicing |  | 99.66%
|  |  | Fiber Testing |  | 27.64%
|  |  | Power Testing |  | 97.22%
124900 | D2 |  | Radio Unit Installation |  | 84.59% | 69.43% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 22.08%
|  |  | Fiber Box Installation |  | 83.34%
|  |  | Antenna Installation |  | 84.78%
|  |  | Antenna Cable Installation |  | 67.04%
|  |  | Splitter Installation |  | 55.89%
|  |  | Fiber Cable Splicing |  | 87.65%
|  |  | Fiber Testing |  | 50.34%
|  |  | Power Testing |  | 89.17%
125900 | D2 |  | Radio Unit Installation |  | 62.14% | 54.96% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 12.22%
|  |  | Fiber Box Installation |  | 48.24%
|  |  | Antenna Installation |  | 44.97%
|  |  | Antenna Cable Installation |  | 95.15%
|  |  | Splitter Installation |  | 36.98%
|  |  | Fiber Cable Splicing |  | 69.47%
|  |  | Fiber Testing |  | 25.7%
|  |  | Power Testing |  | 99.81%

## Z-CASE
Stationing | Track No | Location | Activity | Date | Progress | General Progress | Notes
|  |  | CASE Install |  | 80.19% |  | Z-CASE IS BY E1-986 (Z)
|  |  | Cable Connection/Termination |  | 87.45%
|  |  | Pre-Op testing |  | 8.936%
|  |  | CASE Install |  | 46.1% |  | Z-CASE IS BY E1-1006 (Z)
|  |  | Cable Connection/Termination |  | 67.2%
|  |  | Pre-Op testing |  | 30.52%
|  |  | CASE Install |  | 80.17% |  | Z-CASE IS BY E1-1030 (Z)
|  |  | Cable Connection/Termination |  | 2.272%
|  |  | Pre-Op testing |  | 85.94%
|  |  | CASE Install |  | 23.11% |  | Z-CASE IS BY E1-1068 (Z)
|  |  | Cable Connection/Termination |  | 25.23%
|  |  | Pre-Op testing |  | 41.15%
115725 | E1 |  | CASE Install |  | 70.42% |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
|  |  | Cable Connection/Termination |  | 71.11%
|  |  | Pre-Op testing |  | 65.23%
121810 | E1 |  | CASE Install |  | 20.28% |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
|  |  | Cable Connection/Termination |  | 8.442%
|  |  | Pre-Op testing |  | 60.57%
| E1 |  | CASE Install |  | 57.75% |  | Z-CASE IS BY E1-1229 (Z)
|  |  | Cable Connection/Termination |  | 16.93%
|  |  | Pre-Op testing |  | 96.89%
| E1 |  | CASE Install |  | 74% |  | Z-CASE IS BY E1-1230 (Z)
|  |  | Cable Connection/Termination |  | 27.57%
|  |  | Pre-Op testing |  | 0.06154%
98565 | E2 |  | CASE Install |  | 43.3% |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
|  |  | Cable Connection/Termination |  | 26.61%
|  |  | Pre-Op testing |  | 7.241%
114869 | E2 |  | CASE Install |  | 54.2% |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
|  |  | Cable Connection/Termination |  | 69.02%
|  |  | Pre-Op testing |  | 29.89%
| E2 |  | CASE Install |  | 21.53% |  | Z-CASE IS BY E2-1230(Z)
|  |  | Cable Connection/Termination |  | 13.24%
|  |  | Pre-Op testing |  | 1.413%
122071 | E5 |  | CASE Install |  | 62.89% |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
|  |  | Cable Connection/Termination |  | 86.74%
|  |  | Pre-Op testing |  | 89.61%
122687 | E5 |  | CASE Install |  | 91.74% |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
|  |  | Cable Connection/Termination |  | 26.81%
|  |  | Pre-Op testing |  | 65.59%

## TOPB
Stationing | Track No | Location | Activity | Date | Progress | General Progress | Notes
121810 | E1 |  | TOPB Install |  | 32.91% |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
|  |  | Cable Connection/Termination |  | 49.24%
|  |  | Pre-Op testing |  | 68.93%
122987 | E1 |  | TOPB Install |  | 6.959% |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
|  |  | Cable Connection/Termination |  | 0.6087%
|  |  | Pre-Op testing |  | 53.74%
|  |  | TOPB Install |  | 47.25% |  | TOPB @ ~D1-1239
|  |  | Cable Connection/Termination |  | 48.99%
|  |  | Pre-Op testing |  | 64.14%
121809 | E2 |  | TOPB Install |  | 26.71% |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
|  |  | Cable Connection/Termination |  | 76.93%
|  |  | Pre-Op testing |  | 51.24%
122970 | E2 |  | TOPB Install |  | 74.49% |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
|  |  | Cable Connection/Termination |  | 67.43%
|  |  | Pre-Op testing |  | 21.37%
124043 | D2 |  | TOPB Install |  | 30.13% |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
|  |  | Cable Connection/Termination |  | 5.864%
|  |  | Pre-Op testing |  | 56.9%

## Report Screenshot
Tasks | Total Quantity | Installed/Tested Quantity
Acceptance Test (Ea) | 29 | 3
Antenna Cable (ft) | 61885 | 58432
Brackets (Ea) | 12147 | 11856
Coax Cable (Ea) | 59 | 59
Insertion Loss (Segment) (ft) | 47445 | 43615
Removals (ft) | 30946 | 2380
Coupler Plates | 27 | 27
DC Resistance (Segment) | 47410 | 43580
Megger (Segment) | 47445 | 43615
VSWR (Segment) | 47445 | 43615
End-To-End | 47445 | 33565
Heat Map Test | 47445 | 29175
Coverage Test/Survey | 47445 | 3160
Megger Coax Cable (Reel) | 4000 | 4000
Megger Antenna Cable (Reel) | 80000 | 80000
Megger 1/2in Cable (Reel) | 100 | 100
DC Resistance Coax Cable (Reel) | 4000 | 4000
DC Resistance Antenna Cable (Reel) | 80000 | 80000
DC Resistance 1/2in Cable (Reel) | 100 | 100

## Dashboard
RADIO INSTALLATION DASHBOARD
OVERALL TASK COMPLETION (ALL TRACKS)
TASK PERCENT COMPLETION (PER TRACK)
OVERALL INSTALLATION PROGRESS PER TRACK SECTION
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.