## Reference
Track No. | Column Side | Activities | Bracket Type | Station | Track Stationing | Tunnel | Description | Track Stationing | Notes
B1 | W | Steel Messenger Supports | 1 | Church Avenue | 556+96 to 563+56 | CHU-FOR | Church Ave to Fort Hamilton | 563+56 to 584+88
B2 | E | Messenger Clamps | 2 | Fort Hamilton Parkway | 584+88 to 591+90 | FOR-15S | Fort Hamilton to 15th Street | 591+90 to 625+70
B3 | W | Messenger Wire Pull | 3 | 15th Street Prospect Park | 625+70 to 632+30 | 15S-7AV | 15th Street to 7th Avenue | 632+30 to 653+96
B4 | E | Messenger Wire Tension | 4 | 7th Avenue | 653+96 to 660+56 | 7AV-4TH | 7th Avenue to 4th & 9th Street | 660+56-683+83
E1 | W | Cable Pull | 4A | 4th & 9th Street | 683+83 to 690+91 | 4TH-SMI | 4th & 9th Street to Smith & 9th Street | 690+91 to 705+11
E2 | E | Messenger Straps | 5 | Smith & 9th Street | 705+11 to 712+32 | SMI-CAR | Smith & 9th Street to Carroll Street | 712+32 to 732+89
E3 |  | 15inch CMRS |  | Carroll Street | 732+39 to 738+99 | CAR-BER | Carroll Street to Bergen Street | 738+99 to 756+82
E4 |  | 24inch CMRS |  | Bergen Street | 756+82 to 763+42 | BER-HOY | Bergen Street to Hoyt Schermerhorn | 763+42 to 761+84 | track goes from 768+XX to 693+95
E5 |  | Column mount CMRS |  | Hoyt Schermerhorn | 761+84 to 768+87 | HOY-FUL | Hoyt Schermerhorn to Fulton | 768+87 to 740+30
|  | Station Brackets |  | Fulton Street | 740+30 to 733+70 | FUL-CLI | Fulton to Clinton Washington | 733+70 to 951+82 | track goes from 733+15 to 934+96
Location |  | Grounding |  | Clinton Washington Avenue | 951+82 to 958+42 | CLI-CLA | Clinton Washington to Classon | 958+42 to 970+82
Church Avenue |  | Obstruction Brackets |  | Classon Avenue | 970+82 to 977+42 | CLA-BED | Classon to Bedford Nostand | 977+42 to 989+22
CHU-FOR |  | Cable Pull |  | Bedford Nostrand Avenue | 989+22 to 995+82 | BED-MYR | Bedford Nostrand to Myrtle Willoughby | 995+82 to 1017+47
Fort Hamilton Parkway |  | Cable Tray Brackets |  | Myrtle Willoughby Ave | 1017+47 to 1024+52 | MYR-FLU | Myrtle Willoughby to Flushing Avenue | 1024+52 to 1039+42
FOR-15S |  | Installing Tray |  | Flushing Avenue Station | 1039+42 to 1046+20 | FLU-BRO | Flushing Avenue to Broadway | 1046+20 to 1060+52
15th Street Prospect Park |  | Core Drilling |  | Broadway | 1060+52 to 1067+12 | BRO-MET | Broadway to Metropolitan | 1067+12 to 1132+45
15S-7AV |  | Cable Pull |  | Metropolitan Avenue | 1132+45 to 1139+50 | MET-NAS | Metropolitan to Nassau | 1139+50 to 1131+52
7th Avenue |  | Arch Bar Installation |  | Nassau Avenue | 1131+52 to 1138+32 | NAS-GRE | Nassau to Greenpoint | 1138+32 to 1157+00
7AV-4TH |  |  |  | Greenpoint Avenue | 1157+00 to 1164+32 | GRE-21S | Greenpoint to 21 St | 1164+32 to 1211+33
4th & 9th Street |  |  |  | 21 St Station | 1211+33 to 1217+92 | 21S-COU | 21 St to Court Square | 1217+92 to 1229+23
4TH-SMI |  |  |  | Court Square | 1229+23 to 1236+66 | COU-QUE | Court Square to Queens Plaza | 1236+66 to 1250+65
Smith & 9th Street |  |  |  | Queens Plaza | 1250+65 to 1257+27
SMI-CAR
Carroll Street |  |  |  | Signal Types
CAR-BER |  |  |  | HOME
Bergen Street* |  |  |  | APPROACH
BER-HOY |  |  |  | BUMPER
Hoyt Schermerhorn |  |  |  | REV. HOME
HOY-FUL |  |  |  | REV. APPROACH
Fulton Street
FUL-CLI
Clinton Washington Avenue
CLI-CLA
Classon Avenue
CLA-BED
Bedford Nostrand Avenue
BED-MYR
Myrtle Willoughby Ave
MYR-FLU
Flushing Avenue Station
FLU-BRO
Broadway
BRO-MET
Metropolitan Avenue
MET-NAS
Nassau Avenue
NAS-GRE
Greenpoint Avenue
GRE-21S
21 St Station
21S-COU
Court Square
COU-QUE
Queens Plaza

## Work Sheet (hidden)
OVERALL INSTALLATION PER AREA
Status | Count
Not Started | #REF!
In Progress | #REF!
Completed | #REF!
Remaining | #REF!
Total Tasks | #REF!
Completed Sections | #REF!
Remaining Sections | #REF!

## Ref Activity Bar (hidden)
RADIO INSTALLATION DASHBOARD
TRACK | C3/C4
TASK | COMPLETION PROGRESS
Removals | 12.5%
Grand Total | 12.5%

## Ref Progress per Activity (hidden)
TASK | Acceptance Test
|  | Not Started | 0 | Completed Sections | 13.04%
TRACK | Average of PROGRESS | In Progress | 0 | Remaining Sections | 86.96%
C1 | 16.67% | Completed | 0
C2 | 16.67%
C3 | 0%
C3/C4 | 14.29%
C4 | 0%
C5 | 0%
C6 | 0%
Grand Total | 13.04%

## CMRS
Start | Finish | Track No | Location | Activity | Total Quantity | QTY Installed | Date | Progress | General Progress | Notes | Notes
124510 | 124500 | D1 | COU-QUE | Steel Mess Supports | 566 | 234 |  | 0.41343 | 0.57253
|  |  |  | Messenger Clamps | 12 | 12 |  | 1
|  |  |  | Messenger Wire Pull | 10 |  |  | 0
|  |  |  | Messenger Wire Tension | 1 | 1 |  | 1
|  |  |  | # Cables Pulled | 6 | 3 |  | 0.5
|  |  |  | Messenger Straps | 23 | 12 |  | 0.52174
124500 | 124320 | D1 | COU-QUE | Steel Mess Supports |  |  |  | #DIV/0! | #DIV/0!
|  |  |  | Messenger Clamps |  |  |  | #DIV/0!
|  |  |  | Messenger Wire Pull | 180 |  |  | 0
|  |  |  | Messenger Wire Tension | 1 |  |  | 0
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
|  |  |  | Messenger Straps |  |  |  | #DIV/0!
124320 | 124100 | D1 | COU-QUE | Steel Mess Supports |  |  |  | #DIV/0! | #DIV/0!
|  |  |  | Messenger Clamps |  |  |  | #DIV/0!
|  |  |  | Messenger Wire Pull | 220 |  |  | 0
|  |  |  | Messenger Wire Tension | 1 |  |  | 0
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
|  |  |  | Messenger Straps |  |  |  | #DIV/0!
124100 | 123970 | D1 | COU-QUE | Steel Mess Supports |  |  |  | #DIV/0! | #DIV/0!
|  |  |  | Messenger Clamps |  |  |  | #DIV/0!
|  |  |  | Messenger Wire Pull | 130 |  |  | 0
|  |  |  | Messenger Wire Tension | 1 |  |  | 0
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
|  |  |  | Messenger Straps |  |  |  | #DIV/0!
123970 | 123930 | D1 | COU-QUE | 15" CMRS Install | 40 | 23 |  | 0.575 | 0.56313
|  |  |  | Column Clamp | 8 | 3 |  | 0.375
|  |  |  | Station Brackets | 8 | 7 |  | 0.875
|  |  |  | Grounding | 23 | 12 |  | 0.52174
|  |  |  | Obstruction Brackets | 12 | 11 |  | 0.91667
|  |  |  | # Cables Pulled | 78 | 9 |  | 0.11538
123930 | 123715 | D1 | COU-QUE | 15" CMRS Install | 215 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 43 |  |  | 0
|  |  |  | Station Brackets | 43 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
|  | D1 | COU-QUE | Crossover (Arch Bar Installation) |  |  |  | #DIV/0!
122975 | 122827 | E1 | 21S-COU | Steel Mess Supports |  |  |  | #DIV/0! | #DIV/0!
|  |  |  | Messenger Clamps |  |  |  | #DIV/0!
|  |  |  | Messenger Wire Pull | 148 |  |  | 0
|  |  |  | Messenger Wire Tension |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
|  |  |  | Messenger Straps |  |  |  | #DIV/0!
122827 | 122250 | E1 | 21S-COU | 24" CMRS Install | 577 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 116 |  |  | 0
|  |  |  | Station Brackets | 116 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
122250 | 121833 | E1 | 21S-COU | Steel Mess Supports |  |  |  | #DIV/0! | #DIV/0!
|  |  |  | Messenger Clamps |  |  |  | #DIV/0!
|  |  |  | Messenger Wire Pull | 417 |  |  | 0
|  |  |  | Messenger Wire Tension |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled | 417 |  |  | 0
|  |  |  | Messenger Straps |  |  |  | #DIV/0!
121833 | 121030 | E1 | 21 STREET | Steel Mess Supports |  |  |  | #DIV/0! | #DIV/0!
|  |  |  | Messenger Clamps |  |  |  | #DIV/0!
|  |  |  | Messenger Wire Pull | 803 |  |  | 0
|  |  |  | Messenger Wire Tension |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled | 803 |  |  | 0
|  |  |  | Messenger Straps |  |  |  | #DIV/0!
121030 | 117010 | E1 | GRE-21S | 15" CMRS Install | 4020 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 804 |  |  | 0
|  |  |  | Station Brackets | 804 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
117010 | 116810 | E1 | GRE-21S | 15" CMRS Install | 200 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 40 |  |  | 0
|  |  |  | Station Brackets | 40 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
116810 | 116471 | E1 | GRE-21S | 15" CMRS Install | 339 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 68 |  |  | 0
|  |  |  | Station Brackets | 68 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
116471 | 115694 | E1 | GREENPOINT | 24" CMRS Install | 777 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 156 |  |  | 0
|  |  |  | Station Brackets | 156 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
115694 | 115628 | E1 | NAS-GRE | 24" CMRS Install | 66 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 14 |  |  | 0
|  |  |  | Station Brackets | 14 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
115628 | 114897 | E1 | NAS-GRE | 24" CMRS Install | 731 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 147 |  |  | 0
|  |  |  | Station Brackets | 147 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
114897 | 114719 | E1 | NAS-GRE | Steel Mess Supports |  |  |  | #DIV/0! | #DIV/0!
|  |  |  | Messenger Clamps |  |  |  | #DIV/0!
|  |  |  | Messenger Wire Pull | 178 |  |  | 0
|  |  |  | Messenger Wire Tension |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
|  |  |  | Messenger Straps |  |  |  | #DIV/0!
114719 | 114040 | E1 | NAS-GRE | 24" CMRS Install | 679 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 136 |  |  | 0
|  |  |  | Station Brackets | 136 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
114040 | 113815 | E1 | NAS-GRE | Steel Mess Supports |  |  |  | #DIV/0! | #DIV/0!
|  |  |  | Messenger Clamps |  |  |  | #DIV/0!
|  |  |  | Messenger Wire Pull | 225 |  |  | 0
|  |  |  | Messenger Wire Tension |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
|  |  |  | Messenger Straps |  |  |  | #DIV/0!
113815 | 113019 | E1 | NASSAU | 24" CMRS Install | 796 |  |  | 0 | #DIV/0! |  | weight: 6.7 lb/ft
|  |  |  | Column Clamp | 160 |  |  | 0
|  |  |  | Station Brackets | 160 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled | 15 |  |  | 0
|  | E1 | NASSAU | 24" CMRS Install | 0 |  |  | #DIV/0! | #DIV/0!
|  |  |  | Column Clamp | 0 |  |  | #DIV/0!
|  |  |  | Station Brackets | 0 |  |  | #DIV/0!
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
113019 | 112700 | E1 | MET-NAS | 24" CMRS Install | 319 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 64 |  |  | 0
|  |  |  | Station Brackets | 64 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
112700 | 110878 | E1 | MET-NAS | 15" CMRS Install | 1822 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 365 |  |  | 0
|  |  |  | Station Brackets | 365 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
110878 | 110793 | E1 | MET-NAS | 15" CMRS Install | 85 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 17 |  |  | 0
|  |  |  | Station Brackets | 17 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
110793 | 109251 | E1 | MET-NAS | 15" CMRS Install | 1542 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 309 |  |  | 0
|  |  |  | Station Brackets | 309 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled | 7 |  |  | 0
109251 | 109133 | E1 | MET-NAS | 15" CMRS Install | 118 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 24 |  |  | 0
|  |  |  | Station Brackets | 24 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled | 4 |  |  | 0
109133 | 108356 | E1 | METROPOLITAN | 15" CMRS Install | 777 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 156 |  |  | 0
|  |  |  | Station Brackets | 156 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled | 4 |  |  | 0
108356 | 107651 | E1 | BRO-MET | 15" CMRS Install | 705 | 550 |  | 0.78014 | #DIV/0!
|  |  |  | Column Clamp | 141 |  |  | 0
|  |  |  | Station Brackets | 141 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled | 2 |  |  | 0
107651 | 107611 | E1 | BRO-MET | 15" CMRS Install | 40 |  |  | 0 | #DIV/0! |  | Check endings for specific stationings (DWG 48012-17N-006.0) where cable switches from 1 to 2
|  |  |  | Column Clamp | 8 |  |  | 0
|  |  |  | Station Brackets | 8 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled | 2 |  |  | 0
107611 | 106768 | E1 | BRO-MET | 15" CMRS Install | 843 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 169 |  |  | 0
|  |  |  | Station Brackets | 169 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled | 1 |  |  | 0
106768 | 106702 | E1 | BRO-MET | 15" CMRS Install | 66 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 14 |  |  | 0
|  |  |  | Station Brackets | 14 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled | 2 |  |  | 0
106702 | 106011 | E1 | BROADWAY | 15" CMRS Install | 691 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 139 |  |  | 0
|  |  |  | Station Brackets | 139 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled | 3 |  |  | 0
|  | E1 | BROADWAY | 15" CMRS Install | 0 |  |  | #DIV/0! | #DIV/0!
|  |  |  | Column Clamp | 0 |  |  | #DIV/0!
|  |  |  | Station Brackets | 0 |  |  | #DIV/0!
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
|  | E1 | BROADWAY | 15" CMRS Install | 0 |  |  | #DIV/0! | #DIV/0!
|  |  |  | Column Clamp | 0 |  |  | #DIV/0!
|  |  |  | Station Brackets | 0 |  |  | #DIV/0!
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
106011 | 105293 | E1 | FLU-BRO | 15" CMRS Install | 718 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 144 |  |  | 0
|  |  |  | Station Brackets | 144 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled | 11 |  |  | 0
105293 | 104667 | E1 | FLU-BRO | 15" CMRS Install | 626 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 126 |  |  | 0
|  |  |  | Station Brackets | 126 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled | 10 |  |  | 0
104667 | 103784 | E1 | FLUSHING | 15" CMRS Install | 883 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 177 |  |  | 0
|  |  |  | Station Brackets | 177 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled | 11 |  |  | 0
103784 | 103231 | E1 | MYR-FLU | 15" CMRS Install | 553 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 111 |  |  | 0
|  |  |  | Station Brackets | 111 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
103231 | 103165 | E1 | MYR-FLU | 15" CMRS Install | 66 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 14 |  |  | 0
|  |  |  | Station Brackets | 14 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
103165 | 102533 | E1 | MYR-FLU | 15" CMRS Install | 632 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 127 |  |  | 0
|  |  |  | Station Brackets | 127 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled | 12 |  |  | 0
102533 | 101595 | E1 | MYRTLE | 24" CMRS Install | 938 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 188 |  |  | 0
|  |  |  | Station Brackets | 188 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled | 14 |  |  | 0
101595 | 101558 | E1 | BED-MYR | 24" CMRS Install | 37 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 8 |  |  | 0
|  |  |  | Station Brackets | 8 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
101558 | 101050 | E1 | BED-MYR | 24" CMRS Install | 508 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 102 |  |  | 0
|  |  |  | Station Brackets | 102 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
101050 | 101015 | E1 | BED-MYR | 24" CMRS Install | 35 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 7 |  |  | 0
|  |  |  | Station Brackets | 7 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
101015 | 100530 | E1 | BED-MYR | 24" CMRS Install | 485 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 97 |  |  | 0
|  |  |  | Station Brackets | 97 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
100530 | 100383 | E1 | BED-MYR | Steel Mess Supports |  |  |  | #DIV/0! | #DIV/0!
|  |  |  | Messenger Clamps |  |  |  | #DIV/0!
|  |  |  | Messenger Wire Pull | 147 |  |  | 0
|  |  |  | Messenger Wire Tension | 1 |  |  | 0
|  |  |  | # Cables Pulled | 16 |  |  | 0
|  |  |  | Messenger Straps |  |  |  | #DIV/0!
|  | E1 | BED-MYR | Crossover (Arch Bar Installation) |  |  |  | #DIV/0!
100383 | 100282 | E1 | BED-MYR | Steel Mess Supports |  |  |  | #DIV/0! | #DIV/0!
|  |  |  | Messenger Clamps |  |  |  | #DIV/0!
|  |  |  | Messenger Wire Pull | 101 |  |  | 0
|  |  |  | Messenger Wire Tension | 1 |  |  | 0
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
|  |  |  | Messenger Straps |  |  |  | #DIV/0!
100282 | 100036 | E1 | BED-MYR | Steel Mess Supports |  |  |  | #DIV/0! | #DIV/0!
|  |  |  | Messenger Clamps |  |  |  | #DIV/0!
|  |  |  | Messenger Wire Pull | 246 |  |  | 0
|  |  |  | Messenger Wire Tension | 1 |  |  | 0
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
|  |  |  | Messenger Straps |  |  |  | #DIV/0!
100036 | 99560 | E1 | BED-MYR | Steel Mess Supports |  |  |  | #DIV/0! | #DIV/0!
|  |  |  | Messenger Clamps |  |  |  | #DIV/0!
|  |  |  | Messenger Wire Pull | 476 |  |  | 0
|  |  |  | Messenger Wire Tension | 1 |  |  | 0
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
|  |  |  | Messenger Straps |  |  |  | #DIV/0!
98845 | 98555 | E1 | CLA-BED | 24" CMRS Install | 290 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 58 |  |  | 0
|  |  |  | Station Brackets | 58 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
|  | E1 | CLA-BED | Crossover (Arch Bar Installation) |  |  |  | #DIV/0!
98555 | 98220 | E1 | CLA-BED | 24" CMRS Install | 335 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 67 |  |  | 0
|  |  |  | Station Brackets | 67 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
98220 | 98140 | E1 | CLA-BED | 24" CMRS Install | 80 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 16 |  |  | 0
|  |  |  | Station Brackets | 16 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
98140 | 97920 | E1 | CLA-BED | 24" CMRS Install | 220 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 44 |  |  | 0
|  |  |  | Station Brackets | 44 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
97920 | 97670 | E1 | CLA-BED | Steel Mess Supports |  |  |  | #DIV/0! | #DIV/0!
|  |  |  | Messenger Clamps |  |  |  | #DIV/0!
|  |  |  | Messenger Wire Pull | 250 |  |  | 0
|  |  |  | Messenger Wire Tension | 1 |  |  | 0
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
|  |  |  | Messenger Straps |  |  |  | #DIV/0!
97670 | 97580 | E1 | CLASSON | 24" CMRS Install | 90 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 18 |  |  | 0
|  |  |  | Station Brackets | 18 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
97580 | 97230 | E1 | CLASSON | 24" CMRS Install | 350 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 70 |  |  | 0
|  |  |  | Station Brackets | 70 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
97230 | 96920 | E1 | CLASSON | 24" CMRS Install | 310 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 62 |  |  | 0
|  |  |  | Station Brackets | 62 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
96920 | 96685 | E1 | CLI-CLA | Steel Mess Supports |  |  |  | #DIV/0! | #DIV/0!
|  |  |  | Messenger Clamps |  |  |  | #DIV/0!
|  |  |  | Messenger Wire Pull | 235 |  |  | 0
|  |  |  | Messenger Wire Tension | 1 |  |  | 0
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
|  |  |  | Messenger Straps |  |  |  | #DIV/0!
96685 | 96460 | E1 | CLI-CLA | 24" CMRS Install | 225 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 45 |  |  | 0
|  |  |  | Station Brackets | 45 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
96460 | 96387 | E1 | CLI-CLA | 24" CMRS Install | 73 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 15 |  |  | 0
|  |  |  | Station Brackets | 15 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
96387 | 96051 | E1 | CLI-CLA | 24" CMRS Install | 336 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 68 |  |  | 0
|  |  |  | Station Brackets | 68 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
96038 | 95998 | E1 | CLI-CLA | 24" CMRS Install | 40 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 8 |  |  | 0
|  |  |  | Station Brackets | 8 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
95998 | 95873 | E1 | CLI-CLA | 24" CMRS Install | 125 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 25 |  |  | 0
|  |  |  | Station Brackets | 25 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
95873 | 95781 | E1 | CLINTON-WASHINGTON | 24" CMRS Install | 92 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 19 |  |  | 0
|  |  |  | Station Brackets | 19 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
95781 | 95695 | E1 | CLINTON-WASHINGTON | 24" CMRS Install | 86 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 18 |  |  | 0
|  |  |  | Station Brackets | 18 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
95695 | 95544 | E1 | CLINTON-WASHINGTON | 24" CMRS Install | 151 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 31 |  |  | 0
|  |  |  | Station Brackets | 31 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
95544 | 95155 | E1 | CLINTON-WASHINGTON | 24" CMRS Install | 389 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 78 |  |  | 0
|  |  |  | Station Brackets | 78 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
95155 | 95004 | E1 | CLINTON-WASHINGTON | 24" CMRS Install | 151 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 31 |  |  | 0
|  |  |  | Station Brackets | 31 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
95004 | 94266 | E1 | FUL-CLI | 24" CMRS Install | 738 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 148 |  |  | 0
|  |  |  | Station Brackets | 148 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
94266 | 94207 | E1 | FUL-CLI | 24" CMRS Install | 59 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 12 |  |  | 0
|  |  |  | Station Brackets | 12 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
94207 | 93350 | E1 | FUL-CLI | 24" CMRS Install | 857 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 172 |  |  | 0
|  |  |  | Station Brackets | 172 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
73350 | 73690 | E1 | FULTON | 15" CMRS Install | 340 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 68 |  |  | 0
|  |  |  | Station Brackets | 68 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
73690 | 74030 | E1 | FULTON | 15" CMRS Install | 340 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 68 |  |  | 0
|  |  |  | Station Brackets | 68 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
|  | E1 | FULTON | 15" CMRS Install | 0 |  |  | #DIV/0! | #DIV/0!
|  |  |  | Column Clamp | 0 |  |  | #DIV/0!
|  |  |  | Station Brackets | 0 |  |  | #DIV/0!
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
74030 | 76085 | E1 | HOY-FUL | 24" CMRS Install | 2055 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 411 |  |  | 0
|  |  |  | Station Brackets | 411 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
76085 | 76110 | E1 | HOY-FUL | 15" CMRS Install | 25 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 5 |  |  | 0
|  |  |  | Station Brackets | 5 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
76110 | 76165 | E1 | HOY-FUL | 15" CMRS Install | 55 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 11 |  |  | 0
|  |  |  | Station Brackets | 11 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
76165 | 77470 | E1 | HOYT SCHERMERHORN | 15" CMRS Install | 1305 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 261 |  |  | 0
|  |  |  | Station Brackets | 261 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
77470 | 77595 | E1 | BER-HOY | 15" CMRS Install | 125 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 25 |  |  | 0
|  |  |  | Station Brackets | 25 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
77595 | 78230 | E1 | BER-HOY | 24" CMRS Install | 635 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 127 |  |  | 0
|  |  |  | Station Brackets | 127 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
78230 | 78515 | E1 | BER-HOY | 24" CMRS Install | 285 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 57 |  |  | 0
|  |  |  | Station Brackets | 57 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
|  | E2 | BERGEN | Cable Tray Brackets |  |  |  | #DIV/0! | #DIV/0!
|  |  |  | Installing Tray |  |  |  | #DIV/0!
|  |  |  | Core Drilling | 1 |  |  | 0
|  |  |  | Cable Pull |  |  |  | #DIV/0!
78515 | 78315 | E2 | BER-HOY | Steel Mess Supports |  |  |  | #DIV/0! | #DIV/0!
|  |  |  | Messenger Clamps |  |  |  | #DIV/0!
|  |  |  | Messenger Wire Pull | 200 |  |  | 0
|  |  |  | Messenger Wire Tension | 1 |  |  | 0
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
|  |  |  | Messenger Straps |  |  |  | #DIV/0!
78315 | 77655 | E2 | BER-HOY | 24" CMRS Install | 660 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 132 |  |  | 0
|  |  |  | Station Brackets | 132 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
77655 | 77585 | E2 | BER-HOY | 24" CMRS Install | 70 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 14 |  |  | 0
|  |  |  | Station Brackets | 14 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
77585 | 76845 | E2 | BER-HOY | 24" CMRS Install | 740 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 148 |  |  | 0
|  |  |  | Station Brackets | 148 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
76845 | 76150 | E2 | HOYT SCHERMERHORN | 24" CMRS Install | 695 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 139 |  |  | 0
|  |  |  | Station Brackets | 139 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
76150 | 76090 | E2 | HOY-FUL | 24" CMRS Install | 60 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 12 |  |  | 0
|  |  |  | Station Brackets | 12 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
76090 | 75950 | E2 | HOY-FUL | 24" CMRS Install | 140 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 28 |  |  | 0
|  |  |  | Station Brackets | 28 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
75950 | 75900 | E2 | HOY-FUL | Steel Mess Supports |  |  |  | #DIV/0! | #DIV/0!
|  |  |  | Messenger Clamps |  |  |  | #DIV/0!
|  |  |  | Messenger Wire Pull | 50 |  |  | 0
|  |  |  | Messenger Wire Tension | 1 |  |  | 0
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
|  |  |  | Messenger Straps |  |  |  | #DIV/0!
75900 | 74590 | E2 | HOY-FUL | 24" CMRS Install | 1310 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 262 |  |  | 0
|  |  |  | Station Brackets | 262 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
74590 | 74450 | E2 | HOY-FUL | Steel Mess Supports |  |  |  | #DIV/0! | #DIV/0!
|  |  |  | Messenger Clamps |  |  |  | #DIV/0!
|  |  |  | Messenger Wire Pull | 140 |  |  | 0
|  |  |  | Messenger Wire Tension | 1 |  |  | 0
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
|  |  |  | Messenger Straps |  |  |  | #DIV/0!
74450 | 74070 | E2 | HOY-FUL | 24" CMRS Install | 380 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 76 |  |  | 0
|  |  |  | Station Brackets | 76 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
74070 | 74030 | E2 | HOY-FUL | 24" CMRS Install | 40 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 8 |  |  | 0
|  |  |  | Station Brackets | 8 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
74030 | 73690 | E2 | FULTON | 15" CMRS Install | 340 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 68 |  |  | 0
|  |  |  | Station Brackets | 68 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
73690 | 73250 | E2 | FULTON | 15" CMRS Install | 440 |  |  | 0 | #DIV/0! | Cable Management Takeoffs Cell F110* - 147LF instead of 440LF | Cable Management Takeoffs Cell F110* - 147LF instead of 440LF
|  |  |  | Column Clamp | 88 |  |  | 0
|  |  |  | Station Brackets | 88 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
|  | E2 | FULTON | 15" CMRS Install | 0 |  |  | #DIV/0! | #DIV/0!
|  |  |  | Column Clamp | 0 |  |  | #DIV/0!
|  |  |  | Station Brackets | 0 |  |  | #DIV/0!
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
73250 | 72315 | E2 | FUL-CLI | 24" CMRS Install | 935 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 187 |  |  | 0
|  |  |  | Station Brackets | 187 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
94400 | 94989 | E2 | FUL-CLI | 24" CMRS Install | 589 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 118 |  |  | 0
|  |  |  | Station Brackets | 118 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
94989 | 95114 | E2 | FUL-CLI | 24" CMRS Install | 125 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 25 |  |  | 0
|  |  |  | Station Brackets | 25 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
94989 | 95114 | E2 | CLINTON-WASHINGTON | 24" CMRS Install | 125 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 25 |  |  | 0
|  |  |  | Station Brackets | 25 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
95503 | 95701 | E2 | CLINTON-WASHINGTON | 24" CMRS Install | 198 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 40 |  |  | 0
|  |  |  | Station Brackets | 40 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
95767 | 95852 | E2 | CLINTON-WASHINGTON | 24" CMRS Install | 85 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 17 |  |  | 0
|  |  |  | Station Brackets | 17 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
95852 | 96366 | E2 | CLINTON-WASHINGTON | 24" CMRS Install | 514 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 103 |  |  | 0
|  |  |  | Station Brackets | 103 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
96366 | 96432 | E2 | CLINTON-WASHINGTON | 24" CMRS Install | 66 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 14 |  |  | 0
|  |  |  | Station Brackets | 14 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
96432 | 96649 | E2 | CLINTON-WASHINGTON | 24" CMRS Install | 217 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 44 |  |  | 0
|  |  |  | Station Brackets | 44 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
95767 | 95852 | E2 | CLINTON-WASHINGTON | 24" CMRS Install | 85 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 17 |  |  | 0
|  |  |  | Station Brackets | 17 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
95852 | 96366 | E2 | CLI-CLA | 24" CMRS Install | 514 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 103 |  |  | 0
|  |  |  | Station Brackets | 103 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
96366 | 96432 | E2 | CLI-CLA | 24" CMRS Install | 66 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 14 |  |  | 0
|  |  |  | Station Brackets | 14 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
96432 | 96649 | E2 | CLI-CLA | 24" CMRS Install | 217 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 44 |  |  | 0
|  |  |  | Station Brackets | 44 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
96649 | 96770 | E2 | CLI-CLA | 24" CMRS Install | 121 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 25 |  |  | 0
|  |  |  | Station Brackets | 25 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
96770 | 96990 | E2 | CLI-CLA | Steel Mess Supports |  |  |  | #DIV/0! | #DIV/0!
|  |  |  | Messenger Clamps |  |  |  | #DIV/0!
|  |  |  | Messenger Wire Pull | 220 |  |  | 0
|  |  |  | Messenger Wire Tension | 1 |  |  | 0
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
|  |  |  | Messenger Straps |  |  |  | #DIV/0!
96990 | 97230 | E2 | CLASSON | 24" CMRS Install | 240 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 48 |  |  | 0
|  |  |  | Station Brackets | 48 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
97230 | 97538 | E2 | CLASSON | 24" CMRS Install | 308 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 62 |  |  | 0
|  |  |  | Station Brackets | 62 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
97538 | 97670 | E2 | CLASSON | 24" CMRS Install | 132 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 27 |  |  | 0
|  |  |  | Station Brackets | 27 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
97670 | 98015 | E2 | CLA-BED | Steel Mess Supports |  |  |  | #DIV/0! | #DIV/0!
|  |  |  | Messenger Clamps |  |  |  | #DIV/0!
|  |  |  | Messenger Wire Pull | 345 |  |  | 0
|  |  |  | Messenger Wire Tension | 1 |  |  | 0
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
|  |  |  | Messenger Straps |  |  |  | #DIV/0!
98015 | 98125 | E2 | CLA-BED | 24" CMRS Install | 110 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 22 |  |  | 0
|  |  |  | Station Brackets | 22 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
98125 | 98185 | E2 | CLA-BED | 24" CMRS Install | 60 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 12 |  |  | 0
|  |  |  | Station Brackets | 12 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
98185 | 98440 | E2 | CLA-BED | 24" CMRS Install | 255 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 51 |  |  | 0
|  |  |  | Station Brackets | 51 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
|  | E2 | CLA-BED | Crossover (Arch Bar Installation) |  |  |  | #DIV/0!
98440 | 98586 | E2 | CLA-BED | 24" CMRS Install | 146 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 30 |  |  | 0
|  |  |  | Station Brackets | 30 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
98586 | 98836 | E2 | CLA-BED | Steel Mess Supports |  |  |  | #DIV/0! | #DIV/0!
|  |  |  | Messenger Clamps |  |  |  | #DIV/0!
|  |  |  | Messenger Wire Pull | 250 |  |  | 0
|  |  |  | Messenger Wire Tension | 1 |  |  | 0
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
|  |  |  | Messenger Straps |  |  |  | #DIV/0!
98836 | 99505 | E2 | BEDFORD NOSTRAND | Cable Tray Brackets | 134 |  |  | 0 | 0
|  |  |  | Installing Tray | 669 |  |  | 0
|  |  |  | Core Drilling | 1 |  |  | 0
|  |  |  | Cable Pull | 669 |  |  | 0
99505 | 99950 | E2 | BED-MYR | Steel Mess Supports |  |  |  | #DIV/0! | #DIV/0!
|  |  |  | Messenger Clamps |  |  |  | #DIV/0!
|  |  |  | Messenger Wire Pull | 445 |  |  | 0
|  |  |  | Messenger Wire Tension | 1 |  |  | 0
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
|  |  |  | Messenger Straps |  |  |  | #DIV/0!
|  | E2 | CLA-BED | Crossover (Arch Bar Installation) |  |  |  | #DIV/0!
99950 | 100290 | E2 | BED-MYR | 24" CMRS Install | 340 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 68 |  |  | 0
|  |  |  | Station Brackets | 68 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled | 9 |  |  | 0
100290 | 100740 | E2 | BED-MYR | 24" CMRS Install | 450 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 90 |  |  | 0
|  |  |  | Station Brackets | 90 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled | 10 |  |  | 0
100740 | 100792 | E2 | BED-MYR | 24" CMRS Install | 52 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 11 |  |  | 0
|  |  |  | Station Brackets | 11 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled | 8 |  |  | 0
100792 | 101595 | E2 | BED-MYR | 24" CMRS Install | 803 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 161 |  |  | 0
|  |  |  | Station Brackets | 161 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled | 8 |  |  | 0
101595 | 101688 | E2 | BED-MYR | 24" CMRS Install | 93 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 19 |  |  | 0
|  |  |  | Station Brackets | 19 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled | 7 |  |  | 0
101688 | 102400 | E2 | MYRTLE AVE | 15" CMRS Install | 712 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 143 |  |  | 0
|  |  |  | Station Brackets | 143 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled | 8 |  |  | 0
102400 | 102550 | E2 | MYR-FLU | Steel Mess Supports |  |  |  | #DIV/0! | #DIV/0!
|  |  |  | Messenger Clamps |  |  |  | #DIV/0!
|  |  |  | Messenger Wire Pull | 150 |  |  | 0
|  |  |  | Messenger Wire Tension | 1 |  |  | 0
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
|  |  |  | Messenger Straps |  |  |  | #DIV/0!
102550 | 103165 | E2 | MYR-FLU | 15" CMRS Install | 615 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 123 |  |  | 0
|  |  |  | Station Brackets | 123 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled | 6 |  |  | 0
103165 | 103230 | E2 | MYR-FLU | 15" CMRS Install | 65 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 13 |  |  | 0
|  |  |  | Station Brackets | 13 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled | 6 |  |  | 0
103230 | 103809 | E2 | MYR-FLU | 15" CMRS Install | 579 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 116 |  |  | 0
|  |  |  | Station Brackets | 116 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled | 5 |  |  | 0
103809 | 103902 | E2 | MYR-FLU | 15" CMRS Install | 93 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 19 |  |  | 0
|  |  |  | Station Brackets | 19 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled | 6 |  |  | 0
103902 | 104595 | E2 | FLUSHING | 15" CMRS Install | 693 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 139 |  |  | 0
|  |  |  | Station Brackets | 139 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled | 5 |  |  | 0
104595 | 104750 | E2 | FLU-BRO | Steel Mess Supports | 8 |  |  | 0 | 0
|  |  |  | Messenger Clamps | 8 |  |  | 0
|  |  |  | Messenger Wire Pull | 155 |  |  | 0
|  |  |  | Messenger Wire Tension | 1 |  |  | 0
|  |  |  | # Cables Pulled | 4 |  |  | 0
|  |  |  | Messenger Straps | 124 |  |  | 0
104750 | 105270 | E2 | FLU-BRO | 15" CMRS Install | 520 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 104 |  |  | 0
|  |  |  | Station Brackets | 104 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled | 5 |  |  | 0
105270 | 105930 | E2 | FLU-BRO | 15" CMRS Install | 660 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 132 |  |  | 0
|  |  |  | Station Brackets | 132 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled | 3 |  |  | 0
105930 | 106003 | E2 | FLU-BRO | 15" CMRS Install | 73 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 15 |  |  | 0
|  |  |  | Station Brackets | 15 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
106003 | 106648 | E2 | BROADWAY | 15" CMRS Install | 645 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 129 |  |  | 0
|  |  |  | Station Brackets | 129 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled | 5 |  |  | 0
|  | E2 | BROADWAY | 15" CMRS Install | 0 |  |  | #DIV/0! | #DIV/0!
|  |  |  | Column Clamp | 0 |  |  | #DIV/0!
|  |  |  | Station Brackets | 0 |  |  | #DIV/0!
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
|  | E2 | BROADWAY | 15" CMRS Install | 0 |  |  | #DIV/0! | #DIV/0!
|  |  |  | Column Clamp | 0 |  |  | #DIV/0!
|  |  |  | Station Brackets | 0 |  |  | #DIV/0!
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
106650 | 106920 | E2 | BRO-MET | Steel Mess Supports | 14 |  |  | 0 | 0
|  |  |  | Messenger Clamps | 14 |  |  | 0
|  |  |  | Messenger Wire Pull | 270 |  |  | 0
|  |  |  | Messenger Wire Tension | 1 |  |  | 0
|  |  |  | # Cables Pulled | 1 |  |  | 0
|  |  |  | Messenger Straps | 216 |  |  | 0
106918 | 107620 | E2 | BRO-MET | 15" CMRS Install | 702 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 141 |  |  | 0
|  |  |  | Station Brackets | 141 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled | 2 |  |  | 0
107620 | 107683 | E2 | BRO-MET | 15" CMRS Install | 63 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 13 |  |  | 0
|  |  |  | Station Brackets | 13 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled | 2 |  |  | 0
107683 | 108360 | E2 | BRO-MET | 15" CMRS Install | 677 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 136 |  |  | 0
|  |  |  | Station Brackets | 136 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled | 2 |  |  | 0
108360 | 109235 | E2 | METROPOLITAN | 15" CMRS Install | 875 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 175 |  |  | 0
|  |  |  | Station Brackets | 175 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled | 3 |  |  | 0
109235 | 110795 | E2 | MET-NAS | 24" CMRS Install | 1560 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 312 |  |  | 0
|  |  |  | Station Brackets | 312 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled | 6 |  |  | 0
110795 | 110865 | E2 | MET-NAS | 24" CMRS Install | 70 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 14 |  |  | 0
|  |  |  | Station Brackets | 14 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
110865 | 113020 | E2 | MET-NAS | 24" CMRS Install | 2155 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 431 |  |  | 0
|  |  |  | Station Brackets | 431 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
113020 | 113155 | E2 | MET-NAS | 24" CMRS Install | 135 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 27 |  |  | 0
|  |  |  | Station Brackets | 27 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled | 28 |  |  | 0
113155 | 113815 | E2 | NASSAU | 24" CMRS Install | 660 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 132 |  |  | 0
|  |  |  | Station Brackets | 132 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled | 28 |  |  | 0
113815 | 114105 | E2 | NAS-GRE | Steel Mess Supports |  |  |  | #DIV/0! | #DIV/0!
|  |  |  | Messenger Clamps |  |  |  | #DIV/0!
|  |  |  | Messenger Wire Pull | 290 |  |  | 0
|  |  |  | Messenger Wire Tension | 1 |  |  | 0
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
|  |  |  | Messenger Straps |  |  |  | #DIV/0!
114105 | 114730 | E2 | NAS-GRE | 24" CMRS Install | 625 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 125 |  |  | 0
|  |  |  | Station Brackets | 125 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
114730 | 114910 | E2 | NAS-GRE | Steel Mess Supports |  |  |  | #DIV/0! | #DIV/0!
|  |  |  | Messenger Clamps |  |  |  | #DIV/0!
|  |  |  | Messenger Wire Pull | 180 |  |  | 0
|  |  |  | Messenger Wire Tension |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
|  |  |  | Messenger Straps |  |  |  | #DIV/0!
114910 | 115625 | E2 | NAS-GRE | 24" CMRS Install | 715 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 143 |  |  | 0
|  |  |  | Station Brackets | 143 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
115625 | 116435 | E2 | GREENPOINT | 24" CMRS Install | 810 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 162 |  |  | 0
|  |  |  | Station Brackets | 162 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
116435 | 117130 | E2 | GRE-21S | 24" CMRS Install | 695 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 139 |  |  | 0
|  |  |  | Station Brackets | 139 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
|  | E2 | GRE-21S | Crossover (Arch Bar Installation) |  |  |  | #DIV/0!
117130 | 121035 | E2 | GRE-21S | 24" CMRS Install | 3905 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 781 |  |  | 0
|  |  |  | Station Brackets | 781 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
121035 | 122030 | E2 | 21ST STATION | Steel Mess Supports |  |  |  | #DIV/0! | #DIV/0!
|  |  |  | Messenger Clamps |  |  |  | #DIV/0!
|  |  |  | Messenger Wire Pull | 995 |  |  | 0
|  |  |  | Messenger Wire Tension | 1 |  |  | 0
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
|  |  |  | Messenger Straps |  |  |  | #DIV/0!
122030 | 122430 | E2 | 21S-COU | 24" CMRS Install | 400 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 80 |  |  | 0
|  |  |  | Station Brackets | 80 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
122430 | 122660 | E2 | 21S-COU | Steel Mess Supports |  |  |  | #DIV/0! | #DIV/0!
|  |  |  | Messenger Clamps |  |  |  | #DIV/0!
|  |  |  | Messenger Wire Pull | 230 |  |  | 0
|  |  |  | Messenger Wire Tension | 1 |  |  | 0
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
|  |  |  | Messenger Straps |  |  |  | #DIV/0!
122660 | 122827 | E2 | 21S-COU | 24" CMRS Install | 167 |  |  | 0 | #DIV/0!
|  |  |  | Column Clamp | 34 |  |  | 0
|  |  |  | Station Brackets | 34 |  |  | 0
|  |  |  | Grounding |  |  |  | #DIV/0!
|  |  |  | Obstruction Brackets |  |  |  | #DIV/0!
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
122827 | 123085 | E2 | 21S-COU | Steel Mess Supports |  |  |  | #DIV/0! | #DIV/0!
|  |  |  | Messenger Clamps |  |  |  | #DIV/0!
|  |  |  | Messenger Wire Pull | 258 |  |  | 0
|  |  |  | Messenger Wire Tension | 1 |  |  | 0
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
|  |  |  | Messenger Straps |  |  |  | #DIV/0!
123085 | 123690 | E2 | COURT SQ | Cable Tray Brackets | 134 |  |  | 0 | 0
|  |  |  | Installing Tray | 605 |  |  | 0
|  |  |  | Core Drilling | 1 |  |  | 0
|  |  |  | Cable Pull | 605 |  |  | 0
123690 | 123750 | E2 | COU-QUE | Steel Mess Supports |  |  |  | #DIV/0! | #DIV/0!
|  |  |  | Messenger Clamps |  |  |  | #DIV/0!
|  |  |  | Messenger Wire Pull | 60 |  |  | 0
|  |  |  | Messenger Wire Tension | 1 |  |  | 0
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
|  |  |  | Messenger Straps |  |  |  | #DIV/0!
123750 | 123950 | E2 | COU-QUE | Steel Mess Supports |  |  |  | #DIV/0! | #DIV/0!
|  |  |  | Messenger Clamps |  |  |  | #DIV/0!
|  |  |  | Messenger Wire Pull | 200 |  |  | 0
|  |  |  | Messenger Wire Tension | 1 |  |  | 0
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
|  |  |  | Messenger Straps |  |  |  | #DIV/0!
123950 | 124050 | E2 | COU-QUE | Steel Mess Supports |  |  |  | #DIV/0! | #DIV/0!
|  |  |  | Messenger Clamps |  |  |  | #DIV/0!
|  |  |  | Messenger Wire Pull | 100 |  |  | 0
|  |  |  | Messenger Wire Tension | 1 |  |  | 0
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
|  |  |  | Messenger Straps |  |  |  | #DIV/0!
124050 | 124190 | E2 | COU-QUE | Steel Mess Supports |  |  |  | #DIV/0! | #DIV/0!
|  |  |  | Messenger Clamps |  |  |  | #DIV/0!
|  |  |  | Messenger Wire Pull | 140 |  |  | 0
|  |  |  | Messenger Wire Tension | 1 |  |  | 0
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
|  |  |  | Messenger Straps |  |  |  | #DIV/0!
124190 | 124490 | E2 | COU-QUE | Steel Mess Supports |  |  |  | #DIV/0! | #DIV/0!
|  |  |  | Messenger Clamps |  |  |  | #DIV/0!
|  |  |  | Messenger Wire Pull | 300 |  |  | 0
|  |  |  | Messenger Wire Tension | 1 |  |  | 0
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
|  |  |  | Messenger Straps |  |  |  | #DIV/0!
124490 | 124700 | E2 | COU-QUE | Steel Mess Supports |  |  |  | #DIV/0! | #DIV/0!
|  |  |  | Messenger Clamps |  |  |  | #DIV/0!
|  |  |  | Messenger Wire Pull | 210 |  |  | 0
|  |  |  | Messenger Wire Tension | 1 |  |  | 0
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
|  |  |  | Messenger Straps |  |  |  | #DIV/0!
124700 | 125010 | E2 | COU-QUE | Steel Mess Supports |  |  |  | #DIV/0! | #DIV/0!
|  |  |  | Messenger Clamps |  |  |  | #DIV/0!
|  |  |  | Messenger Wire Pull | 310 |  |  | 0
|  |  |  | Messenger Wire Tension | 1 |  |  | 0
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
|  |  |  | Messenger Straps |  |  |  | #DIV/0!
|  | E2 | COU-QUE | Crossover (Arch Bar Installation) |  |  |  | #DIV/0!
75650 | 78244 | B3 | BERGEN ST | Steel Mess Supports |  |  |  | #DIV/0! | #DIV/0!
|  |  |  | Messenger Clamps |  |  |  | #DIV/0!
|  |  |  | Messenger Wire Pull | 2594 |  |  | 0
|  |  |  | Messenger Wire Tension | 1 |  |  | 0
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
|  |  |  | Messenger Straps |  |  |  | #DIV/0!
|  | B3 | BER-JAY | Steel Mess Supports |  |  |  | #DIV/0! | #DIV/0!
|  |  |  | Messenger Clamps |  |  |  | #DIV/0!
|  |  |  | Messenger Wire Pull | 0 |  |  | #DIV/0!
|  |  |  | Messenger Wire Tension | 1 |  |  | 0
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
|  |  |  | Messenger Straps |  |  |  | #DIV/0!
|  | B4 | BER-JAY | Steel Mess Supports |  |  |  | #DIV/0! | #DIV/0!
|  |  |  | Messenger Clamps |  |  |  | #DIV/0!
|  |  |  | Messenger Wire Pull | 0 |  |  | #DIV/0!
|  |  |  | Messenger Wire Tension | 1 |  |  | 0
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
|  |  |  | Messenger Straps |  |  |  | #DIV/0!
|  | E3/E4 | COURT SQ | Steel Mess Supports |  |  |  | #DIV/0! | #DIV/0!
|  |  |  | Messenger Clamps |  |  |  | #DIV/0!
|  |  |  | Messenger Wire Pull | 0 |  |  | #DIV/0!
|  |  |  | Messenger Wire Tension | 1 |  |  | 0
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
|  |  |  | Messenger Straps |  |  |  | #DIV/0!
75640 | 75300 | B1 | BER-CAR | Steel Mess Supports |  |  |  | #DIV/0! | #DIV/0!
|  |  |  | Messenger Clamps |  |  |  | #DIV/0!
|  |  |  | Messenger Wire Pull | 340 |  |  | 0
|  |  |  | Messenger Wire Tension | 1 |  |  | 0
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
|  |  |  | Messenger Straps |  |  |  | #DIV/0!
68570 | 68330 | B3 | 4TH AVE | Steel Mess Supports |  |  |  | #DIV/0! | #DIV/0!
|  |  |  | Messenger Clamps |  |  |  | #DIV/0!
|  |  |  | Messenger Wire Pull | 240 |  |  | 0
|  |  |  | Messenger Wire Tension | 1 |  |  | 0
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
|  |  |  | Messenger Straps |  |  |  | #DIV/0!
68330 | 68030 | B3 | 4AV-7AV | Steel Mess Supports |  |  |  | #DIV/0! | #DIV/0!
|  |  |  | Messenger Clamps |  |  |  | #DIV/0!
|  |  |  | Messenger Wire Pull | 300 |  |  | 0
|  |  |  | Messenger Wire Tension | 1 |  |  | 0
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
|  |  |  | Messenger Straps |  |  |  | #DIV/0!
66070 | 66000 | B3 | 4AV-7AV | Steel Mess Supports |  |  |  | #DIV/0! | #DIV/0!
|  |  |  | Messenger Clamps |  |  |  | #DIV/0!
|  |  |  | Messenger Wire Pull | 70 |  |  | 0
|  |  |  | Messenger Wire Tension | 1 |  |  | 0
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
|  |  |  | Messenger Straps |  |  |  | #DIV/0!
60350 | 60000 | B1 | 15S-FOR | Steel Mess Supports |  |  |  | #DIV/0! | #DIV/0!
|  |  |  | Messenger Clamps |  |  |  | #DIV/0!
|  |  |  | Messenger Wire Pull | 350 |  |  | 0
|  |  |  | Messenger Wire Tension | 1 |  |  | 0
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
|  |  |  | Messenger Straps |  |  |  | #DIV/0!
56440 | 56350 | B1 | FOR-CHU | Steel Mess Supports |  |  |  | #DIV/0! | #DIV/0!
|  |  |  | Messenger Clamps |  |  |  | #DIV/0!
|  |  |  | Messenger Wire Pull | 90 |  |  | 0
|  |  |  | Messenger Wire Tension | 1 |  |  | 0
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
|  |  |  | Messenger Straps |  |  |  | #DIV/0!
55580 | 54500 | B2 | CHU-DIT | Steel Mess Supports |  |  |  | #DIV/0! | #DIV/0!
|  |  |  | Messenger Clamps |  |  |  | #DIV/0!
|  |  |  | Messenger Wire Pull | 1080 |  |  | 0
|  |  |  | Messenger Wire Tension | 1 |  |  | 0
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
|  |  |  | Messenger Straps |  |  |  | #DIV/0!
54730 | 55000 | B2 | CHU-DIT | Steel Mess Supports |  |  |  | #DIV/0! | #DIV/0!
|  |  |  | Messenger Clamps |  |  |  | #DIV/0!
|  |  |  | Messenger Wire Pull | 270 |  |  | 0
|  |  |  | Messenger Wire Tension | 1 |  |  | 0
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
|  |  |  | Messenger Straps |  |  |  | #DIV/0!
55485 | 55725 | B2 | CHU-DIT | Steel Mess Supports |  |  |  | #DIV/0! | #DIV/0!
|  |  |  | Messenger Clamps |  |  |  | #DIV/0!
|  |  |  | Messenger Wire Pull | 240 |  |  | 0
|  |  |  | Messenger Wire Tension | 1 |  |  | 0
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
|  |  |  | Messenger Straps |  |  |  | #DIV/0!
55725 | 56635 | B2 | CHURCH AVE | Steel Mess Supports |  |  |  | #DIV/0! | #DIV/0!
|  |  |  | Messenger Clamps |  |  |  | #DIV/0!
|  |  |  | Messenger Wire Pull | 910 |  |  | 0
|  |  |  | Messenger Wire Tension | 1 |  |  | 0
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
|  |  |  | Messenger Straps |  |  |  | #DIV/0!
57320 | 57445 | B2 | CHU-FOR | Steel Mess Supports |  |  |  | #DIV/0! | #DIV/0!
|  |  |  | Messenger Clamps |  |  |  | #DIV/0!
|  |  |  | Messenger Wire Pull | 125 |  |  | 0
|  |  |  | Messenger Wire Tension | 1 |  |  | 0
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
|  |  |  | Messenger Straps |  |  |  | #DIV/0!
60165 | 60620 | B2 | 15S-FOR | Steel Mess Supports |  |  |  | #DIV/0! | #DIV/0!
|  |  |  | Messenger Clamps |  |  |  | #DIV/0!
|  |  |  | Messenger Wire Pull | 455 |  |  | 0
|  |  |  | Messenger Wire Tension | 1 |  |  | 0
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
|  |  |  | Messenger Straps |  |  |  | #DIV/0!
62560 | 63425 | B2 | 15TH STREET PROSPECT PARK | Steel Mess Supports |  |  |  | #DIV/0! | #DIV/0!
|  |  |  | Messenger Clamps |  |  |  | #DIV/0!
|  |  |  | Messenger Wire Pull | 865 |  |  | 0
|  |  |  | Messenger Wire Tension | 1 |  |  | 0
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
|  |  |  | Messenger Straps |  |  |  | #DIV/0!
67950 | 68330 | B4/B2 | 4AV-7AV | Steel Mess Supports |  |  |  | #DIV/0! | #DIV/0!
|  |  |  | Messenger Clamps |  |  |  | #DIV/0!
|  |  |  | Messenger Wire Pull | 380 |  |  | 0
|  |  |  | Messenger Wire Tension | 1 |  |  | 0
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
|  |  |  | Messenger Straps |  |  |  | #DIV/0!
74740 | 74840 | B2 | CAR-BER | Steel Mess Supports |  |  |  | #DIV/0! | #DIV/0!
|  |  |  | Messenger Clamps |  |  |  | #DIV/0!
|  |  |  | Messenger Wire Pull | 100 |  |  | 0
|  |  |  | Messenger Wire Tension | 1 |  |  | 0
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
|  |  |  | Messenger Straps |  |  |  | #DIV/0!
75395 | 75650 | B2 | CAR-BER | Steel Mess Supports |  |  |  | #DIV/0! | #DIV/0!
|  |  |  | Messenger Clamps |  |  |  | #DIV/0!
|  |  |  | Messenger Wire Pull | 255 |  |  | 0
|  |  |  | Messenger Wire Tension | 1 |  |  | 0
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
|  |  |  | Messenger Straps |  |  |  | #DIV/0!
78905 | 75950 | B3 | JAY-BER | Steel Mess Supports |  |  |  | #DIV/0! | #DIV/0!
|  |  |  | Messenger Clamps |  |  |  | #DIV/0!
|  |  |  | Messenger Wire Pull | 2955 |  |  | 0
|  |  |  | Messenger Wire Tension | 1 |  |  | 0
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
|  |  |  | Messenger Straps |  |  |  | #DIV/0!
75950 | 75650 | B3 | BERGEN ST | Steel Mess Supports |  |  |  | #DIV/0! | #DIV/0!
|  |  |  | Messenger Clamps |  |  |  | #DIV/0!
|  |  |  | Messenger Wire Pull | 300 |  |  | 0
|  |  |  | Messenger Wire Tension | 1 |  |  | 0
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
|  |  |  | Messenger Straps |  |  |  | #DIV/0!
75650 | 75420 | B3 | BER-CAR | Steel Mess Supports |  |  |  | #DIV/0! | #DIV/0!
|  |  |  | Messenger Clamps |  |  |  | #DIV/0!
|  |  |  | Messenger Wire Pull | 230 |  |  | 0
|  |  |  | Messenger Wire Tension | 1 |  |  | 0
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
|  |  |  | Messenger Straps |  |  |  | #DIV/0!
73285 | 72960 | B3 | BER-CAR | Steel Mess Supports |  |  |  | #DIV/0! | #DIV/0!
|  |  |  | Messenger Clamps |  |  |  | #DIV/0!
|  |  |  | Messenger Wire Pull | 325 |  |  | 0
|  |  |  | Messenger Wire Tension | 1 |  |  | 0
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
|  |  |  | Messenger Straps |  |  |  | #DIV/0!
72960 | 72035 | B3/B4 | CAR-4TH | Steel Mess Supports |  |  |  | #DIV/0! | #DIV/0!
|  |  |  | Messenger Clamps |  |  |  | #DIV/0!
|  |  |  | Messenger Wire Pull | 925 |  |  | 0
|  |  |  | Messenger Wire Tension | 1 |  |  | 0
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
|  |  |  | Messenger Straps |  |  |  | #DIV/0!
71150 | 70965 | B3/B4 | CAR-4TH | Steel Mess Supports |  |  |  | #DIV/0! | #DIV/0!
|  |  |  | Messenger Clamps |  |  |  | #DIV/0!
|  |  |  | Messenger Wire Pull | 185 |  |  | 0
|  |  |  | Messenger Wire Tension | 1 |  |  | 0
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
|  |  |  | Messenger Straps |  |  |  | #DIV/0!
70965 | 70445 | B3/B6 | CAR-4TH | Steel Mess Supports |  |  |  | #DIV/0! | #DIV/0!
|  |  |  | Messenger Clamps |  |  |  | #DIV/0!
|  |  |  | Messenger Wire Pull | 520 |  |  | 0
|  |  |  | Messenger Wire Tension | 1 |  |  | 0
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
|  |  |  | Messenger Straps |  |  |  | #DIV/0!
70445 | 70045 | B3/B7 | CAR-4TH | Steel Mess Supports |  |  |  | #DIV/0! | #DIV/0!
|  |  |  | Messenger Clamps |  |  |  | #DIV/0!
|  |  |  | Messenger Wire Pull | 400 |  |  | 0
|  |  |  | Messenger Wire Tension | 1 |  |  | 0
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
|  |  |  | Messenger Straps |  |  |  | #DIV/0!
68625 | 68400 | B3/B8 | CAR-4TH | Steel Mess Supports |  |  |  | #DIV/0! | #DIV/0!
|  |  |  | Messenger Clamps |  |  |  | #DIV/0!
|  |  |  | Messenger Wire Pull | 225 |  |  | 0
|  |  |  | Messenger Wire Tension | 1 |  |  | 0
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
|  |  |  | Messenger Straps |  |  |  | #DIV/0!
68400 | 68330 | B3/B9 | CAR-4TH | Steel Mess Supports |  |  |  | #DIV/0! | #DIV/0!
|  |  |  | Messenger Clamps |  |  |  | #DIV/0!
|  |  |  | Messenger Wire Pull | 70 |  |  | 0
|  |  |  | Messenger Wire Tension | 1 |  |  | 0
|  |  |  | # Cables Pulled |  |  |  | #DIV/0!
|  |  |  | Messenger Straps |  |  |  | #DIV/0!

## AXLE COUNTER
Stationing | Track No | Location | Activity | Date | Progress | General Progress | Notes | DWG REF.
54600 | B1 | DIT-CHU | Axle Counter Installation |  | 0% | 0% | STATIONING SHOWN IS THAT OF THE NEAREST IJ, AXC STATIONING DOES NOT EXIST | B1-546
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B1 |  | Axle Counter Installation |  | 0% | 0% | NO INFO | B1-547
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
59297 | B1 | FOR-15S | Axle Counter Installation |  | 0% | 0% |  | B1-553
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B1 |  | Axle Counter Installation |  | 0% | 0% | NO INFO | B1-554
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
55687 | B1 | DIT-CHU | Axle Counter Installation |  | 0% | 0% |  | B1-557
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
56367 | B1 | CHU-FOR | Axle Counter Installation |  | 0% | 0% |  | B1-564
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
58524.6 | B1 | FORT HAMILTON PARKWAY | Axle Counter Installation |  | 0% | 0% |  | B1-585
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
59210.25 | B1 | FOR-15S | Axle Counter Installation |  | 0% | 0% |  | B1-592
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
62572.5 | B1 | FOR-15S | Axle Counter Installation |  | 0% | 0% |  | B1-626
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
63251.4 | B1 | 15S-7AV | Axle Counter Installation |  | 0% | 0% |  | B1-632
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
65387.3 | B1 | 15S-7AV | Axle Counter Installation |  | 0% | 0% |  | B1-654
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
66076 | B1 | 7AV-4TH | Axle Counter Installation |  | 0% | 0% |  | B1-661
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
73206.7 | B1 | SMI-CAR | Axle Counter Installation |  | 0% | 0% |  | B1-732
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
73932 | B1 | CAR-BER | Axle Counter Installation |  | 0% | 0% |  | B1-739
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
75408 | B1 | CAR-BER | Axle Counter Installation |  | 0% | 0% |  | B1-755
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
75669 | B1 | CAR-BER | Axle Counter Installation |  | 0% | 0% |  | B1-756
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
76352 | B1 | BER-HOY | Axle Counter Installation |  | 0% | 0% |  | B1-763, B1-764
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
76589 | B1 | HOYT-SCHERMERHORN | Axle Counter Installation |  | 0% | 0% |  | B1-766
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
76901.5 | B1 | HOY-FUL | Axle Counter Installation |  | 0% | 0% |  | B1-770
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
77088 | B1 | FUL-CLI | Axle Counter Installation |  | 0% | 0% |  | B1-771
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
54737 | B2 | DIT-CHU | Axle Counter Installation |  | 0% | 0% |  | B2-546
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
54731 | B2 |  | Axle Counter Installation |  | 0% | 0% |  | B2-547
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
55000 | B2 | DIT-CHU | Axle Counter Installation |  | 0% | 0% |  | B2-549
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
55498 | B2 | DIT-CHU | Axle Counter Installation |  | 0% | 0% |  | B2-554
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B2 |  | Axle Counter Installation |  | 0% | 0% | NO REF DWG EXISTS | B2-555
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B2 |  | Axle Counter Installation |  | 0% | 0% | NO REF DWG EXISTS | B2-556
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
55857 | B2 | CHURCH AVE | Axle Counter Installation |  | 0% | 0% |  | B2-558
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
58500 | B2 | FORT HAMILTON PARKWAY | Axle Counter Installation |  | 0% | 0% |  | B2-585
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
59203.8 | B2 | FOR-15S | Axle Counter Installation |  | 0% | 0% |  | B2-592
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
62550.6 | B2 |  | Axle Counter Installation |  | 0% | 0% |  | B2-625
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
65375.3 | B2 | 15S-7AV | Axle Counter Installation |  | 0% | 0% |  | B2-654
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
66062.3 | B2 | 7AV-4TH | Axle Counter Installation |  | 0% | 0% |  | B2-661
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B2 |  | Axle Counter Installation |  | 0% | 0% | NO REF DWG EXISTS | B2-665
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B2 |  | Axle Counter Installation |  | 0% | 0% | NO REF DWG EXISTS | B2-684
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B2 |  | Axle Counter Installation |  | 0% | 0% | NO REF DWG EXISTS | B2-691
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B2 |  | Axle Counter Installation |  | 0% | 0% | NO REF DWG EXISTS | B2-692
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B2 |  | Axle Counter Installation |  | 0% | 0% | NO REF DWG EXISTS | B2-692A
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B2 |  | Axle Counter Installation |  | 0% | 0% | NO REF DWG EXISTS | B2-693
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B2 |  | Axle Counter Installation |  | 0% | 0% | NO REF DWG EXISTS | B2-705
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B2 |  | Axle Counter Installation |  | 0% | 0% | NO REF DWG EXISTS | B2-712
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B2 |  | Axle Counter Installation |  | 0% | 0% | DWG EXISTS, BUT EMPTY | B2-732
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
73926.3 | B2 | CARROLL STREET | Axle Counter Installation |  | 0% | 0% |  | B2-739
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
75267 | B2 | CAR-BER | Axle Counter Installation |  | 0% | 0% |  | B2-753
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B2 |  | Axle Counter Installation |  | 0% | 0% | NO REF DWG EXISTS | B2-755
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
75646 | B2 | CAR-BER | Axle Counter Installation |  | 0% | 0% |  | B2-756
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
76352 | B2 |  | Axle Counter Installation |  | 0% | 0% |  | B2-763, B2-764
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
76536 | B2 |  | Axle Counter Installation |  | 0% | 0% |  | B2-765
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
76797 | B2 |  | Axle Counter Installation |  | 0% | 0% |  | B2-768
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
77116 | B2 |  | Axle Counter Installation |  | 0% | 0% |  | B2-770
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B3 |  | Axle Counter Installation |  | 0% | 0% | REF DWG EXISTS, NO STATIONINGS SHOWN | B3-546
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B3 |  | Axle Counter Installation |  | 0% | 0% | REF DWG EXISTS, NO STATIONINGS SHOWN | B3-548
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
53361 | B3 |  | Axle Counter Installation |  | 0% | 0% |  | B3-554
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
55626 | B3 |  | Axle Counter Installation |  | 0% | 0% |  | B3-555
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B3 |  | Axle Counter Installation |  | 0% | 0% | REF DWG EXISTS, NO STATIONINGS SHOWN | B3-556
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B3 |  | Axle Counter Installation |  | 0% | 0% | REF DWG EXISTS, NO STATIONINGS SHOWN | B3-557
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B3 |  | Axle Counter Installation |  | 0% | 0% | NO REF DWG EXISTS | B3-565
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
65384.6 | B3 |  | Axle Counter Installation |  | 0% | 0% |  | B3-654
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
66073.4 | B3 |  | Axle Counter Installation |  | 0% | 0% |  | B3-661
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B3 |  | Axle Counter Installation |  | 0% | 0% | NO REF DWG EXISTS | B3-689
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B3 |  | Axle Counter Installation |  | 0% | 0% | NO REF DWG EXISTS | B3-690
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B3 |  | Axle Counter Installation |  | 0% | 0% | NO REF DWG EXISTS | B3-691
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B3 |  | Axle Counter Installation |  | 0% | 0% | NO REF DWG EXISTS | B3-692
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B3 |  | Axle Counter Installation |  | 0% | 0% | NO REF DWG EXISTS | B3-693
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B3 |  | Axle Counter Installation |  | 0% | 0% | NO REF DWG EXISTS | B3-694
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B3 |  | Axle Counter Installation |  | 0% | 0% | NO REF DWG EXISTS | B3-695
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B3 |  | Axle Counter Installation |  | 0% | 0% | NO REF DWG EXISTS | B3-696
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
75405 | B3 |  | Axle Counter Installation |  | 0% | 0% |  | B3-754
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B3 |  | Axle Counter Installation |  | 0% | 0% | NO REF DWG EXISTS | B3-755
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
75405 | B3 |  | Axle Counter Installation |  | 0% | 0% |  | B3-756
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
76383 | B3 |  | Axle Counter Installation |  | 0% | 0% |  | B3-764
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
76920 | B3 |  | Axle Counter Installation |  | 0% | 0% |  | B3-769
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B4 |  | Axle Counter Installation |  | 0% | 0% | REF DWG EXISTS, NO STATIONINGS SHOWN | B4-547
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B4 |  | Axle Counter Installation |  | 0% | 0% | REF DWG EXISTS, NO STATIONINGS SHOWN | B4-551
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B4 |  | Axle Counter Installation |  | 0% | 0% | NO REF DWG EXISTS, AWAITING RESPONSE FROM THALES ON WHETHER THIS AXC WILL BE INSTALLED | B4-554A, B4-554B
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
55533 | B4 |  | Axle Counter Installation |  | 0% | 0% |  | B4-555
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
55685 | B4 |  | Axle Counter Installation |  | 0% | 0% |  | B4-556
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
56396.5 | B4 |  | Axle Counter Installation |  | 0% | 0% |  | B4-564
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%

## SIGNALS
Stationing | Track No | Signal Type | Location | Activity | Date | Progress | General Progress | Notes
74076 | E1 | APPROACH |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
98643 | E1 | HOME |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
98903 | E1 | HOME |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
100068 | E1 | HOME |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
106031 | E1 | APPROACH |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
113852 | E1 | HOME |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
114110 | E1 | HOME |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
114869 | E1 | HOME |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
119024 | E1 | APPROACH |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
119485 | E1 | APPROACH |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
| E1 | APPROACH |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
121810 | E1 | HOME |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
122198 | E1 | HOME |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
122570 | E1 | HOME |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
122987 | E1 | HOME |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
123669 | D1 | HOME |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
73318 | E2 | APPROACH |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
98565 | E2 | HOME |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
99593 | E2 | HOME |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
99970 | E2 | HOME |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
106749 | E2 | APPROACH |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
112529 | E2 | HOME |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
113850 | E2 | HOME |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
118065 | E2 | APPROACH |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
119215 | E2 | APPROACH |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
123687 | D2 | HOME |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
124043 | D2 | HOME |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
99806 | E3 | HOME |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
100019 | E3 | HOME |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
99592 | E4 | HOME |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
122071 | E5 | HOME |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
122687 | E5 | HOME |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0

## SWITCH
Name | Stationing | Track No | Location | Activity | Date | Progress | General Progress | Notes
B331 | 76395 | B1 |  | Switch Machine Installation |  | 0 | 0
|  |  |  | Switch JB Installation |  | 0
|  |  |  | Switch Cable Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
B325 | 76395 | E2 |  | Switch Machine Installation |  | 0 | 0
|  |  |  | Switch JB Installation |  | 0
|  |  |  | Switch Cable Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
633A | 99999 | E1 |  | Switch Machine Installation |  | 0 | 0
|  |  |  | Switch JB Installation |  | 0
|  |  |  | Switch Cable Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
633B | 98900 | E3-4 |  | Switch Machine Installation |  | 0 | 0
|  |  |  | Switch JB Installation |  | 0
|  |  |  | Switch Cable Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
625A | 98808 | E3-4 |  | Switch Machine Installation |  | 0 | 0
|  |  |  | Switch JB Installation |  | 0
|  |  |  | Switch Cable Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
625B | 99949 | E2 |  | Switch Machine Installation |  | 0 | 0
|  |  |  | Switch JB Installation |  | 0
|  |  |  | Switch Cable Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
663 | 99628 | E3-4 |  | Switch Machine Installation |  | 0 | 0
|  |  |  | Switch JB Installation |  | 0
|  |  |  | Switch Cable Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
673A | 99999 | E1 |  | Switch Machine Installation |  | 0 | 0
|  |  |  | Switch JB Installation |  | 0
|  |  |  | Switch Cable Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
673B | 99826 | E3 |  | Switch Machine Installation |  | 0 | 0
|  |  |  | Switch JB Installation |  | 0
|  |  |  | Switch Cable Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
651A | 99761 | E4 |  | Switch Machine Installation |  | 0 | 0
|  |  |  | Switch JB Installation |  | 0
|  |  |  | Switch Cable Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
651B | 99949 | E2 |  | Switch Machine Installation |  | 0 | 0
|  |  |  | Switch JB Installation |  | 0
|  |  |  | Switch Cable Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
757A | 113880 | E1 |  | Switch Machine Installation |  | 0 | 0
|  |  |  | Switch JB Installation |  | 0
|  |  |  | Switch Cable Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
757B | 114010 | E2 |  | Switch Machine Installation |  | 0 | 0
|  |  |  | Switch JB Installation |  | 0
|  |  |  | Switch Cable Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
753A | 114010 | E1 |  | Switch Machine Installation |  | 0 | 0
|  |  |  | Switch JB Installation |  | 0
|  |  |  | Switch Cable Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
753B | 113880 | E2 |  | Switch Machine Installation |  | 0 | 0
|  |  |  | Switch JB Installation |  | 0
|  |  |  | Switch Cable Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
825 |  | E1 |  | Switch Machine Installation |  | 0 | 0 | Stationing missing
|  |  |  | Switch JB Installation |  | 0
|  |  |  | Switch Cable Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
815A | 121995 | E5 |  | Switch Machine Installation |  | 0 | 0
|  |  |  | Switch JB Installation |  | 0
|  |  |  | Switch Cable Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
815B | 121831 | E2 |  | Switch Machine Installation |  | 0 | 0
|  |  |  | Switch JB Installation |  | 0
|  |  |  | Switch Cable Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
851B | 122757 | E5 |  | Switch Machine Installation |  | 0 | 0
|  |  |  | Switch JB Installation |  | 0
|  |  |  | Switch Cable Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
851A | 122923 | E1 |  | Switch Machine Installation |  | 0 | 0
|  |  |  | Switch JB Installation |  | 0
|  |  |  | Switch Cable Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
841 | 122923 | E2 |  | Switch Machine Installation |  | 0 | 0
|  |  |  | Switch JB Installation |  | 0
|  |  |  | Switch Cable Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
753B | 113880 | E2 |  | Switch Machine Installation |  | 0 | 0
|  |  |  | Switch JB Installation |  | 0
|  |  |  | Switch Cable Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0

## WRU
Stationing | Track No | Location | Activity | Date | Progress | General Progress | Notes
54000 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
54000 | B3 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
54000 | B4 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
54000 | B2 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
54000 | B5 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
55500 | B2 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
55500 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
56300 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
56500 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
57200 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
57400 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
58300 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
58400 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
59400 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
59700 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
60500 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
60800 | B2 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
60800 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
61900 | B2 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
61900 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
62300 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
63200 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
63300 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
64200 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
64300 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
65200 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
65200 | B2 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
66300 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
66300 | B2 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
67500 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
67500 | B2 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
68300 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
68300 | B2 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
69900 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
71400 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
73000 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
73000 | B2 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
74100 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
75300 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
75300 | B2 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
88300 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
88600 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
90800 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
92400 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
93600 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
95000 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
96500 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
98200 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
99700 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
99700 | E2 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
100400 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
100600 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
101500 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
102600 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
103800 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
104700 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
105900 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
106900 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
108300 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
109900 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
111100 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
112200 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
113000 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
114300 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
115500 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
116900 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
118300 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
118300 | E2 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
119500 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
119500 | E2 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
120800 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
120800 | E2 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
121900 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
122800 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
123900 | D1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
124900 | D1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
125900 | D1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
123900 | D2 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
124900 | D2 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
125900 | D2 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0

## Z-CASE
Stationing | Track No | Location | Activity | Date | Progress | General Progress | Notes
|  |  | CASE Install |  |  |  | Z-CASE IS BY E1-986 (Z)
Cable Connection/Termination
Pre-Op testing
|  |  | CASE Install |  |  |  | Z-CASE IS BY E1-1006 (Z)
Cable Connection/Termination
Pre-Op testing
|  |  | CASE Install |  |  |  | Z-CASE IS BY E1-1030 (Z)
Cable Connection/Termination
Pre-Op testing
|  |  | CASE Install |  |  |  | Z-CASE IS BY E1-1068 (Z)
Cable Connection/Termination
Pre-Op testing
115725 | E1 |  | CASE Install |  |  |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
Cable Connection/Termination
Pre-Op testing
121810 | E1 |  | CASE Install |  |  |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
Cable Connection/Termination
Pre-Op testing
| E1 |  | CASE Install |  |  |  | Z-CASE IS BY E1-1229 (Z)
Cable Connection/Termination
Pre-Op testing
| E1 |  | CASE Install |  |  |  | Z-CASE IS BY E1-1230 (Z)
Cable Connection/Termination
Pre-Op testing
98565 | E2 |  | CASE Install |  |  |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
Cable Connection/Termination
Pre-Op testing
114869 | E2 |  | CASE Install |  |  |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
Cable Connection/Termination
Pre-Op testing
| E2 |  | CASE Install |  |  |  | Z-CASE IS BY E2-1230(Z)
Cable Connection/Termination
Pre-Op testing
122071 | E5 |  | CASE Install |  |  |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
Cable Connection/Termination
Pre-Op testing
122687 | E5 |  | CASE Install |  |  |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
Cable Connection/Termination
Pre-Op testing

## TOPB
Stationing | Track No | Location | Activity | Date | Progress | General Progress | Notes
121810 | E1 |  | TOPB Install |  |  |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
Cable Connection/Termination
Pre-Op testing
122987 | E1 |  | TOPB Install |  |  |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
Cable Connection/Termination
Pre-Op testing
|  |  | TOPB Install |  |  |  | TOPB @ ~D1-1239
Cable Connection/Termination
Pre-Op testing
121809 | E2 |  | TOPB Install |  |  |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
Cable Connection/Termination
Pre-Op testing
122970 | E2 |  | TOPB Install |  |  |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
Cable Connection/Termination
Pre-Op testing
124043 | D2 |  | TOPB Install |  |  |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
Cable Connection/Termination
Pre-Op testing

## Report Screenshot
Tasks | Total Quantity | Installed/Tested Quantity
Acceptance Test (Ea) | 29 | 3
Antenna Cable (ft) | 61885 | 58432
Brackets (Ea) | 12147 | 11856
Coax Cable (Ea) | 59 | 59
Insertion Loss (Segment) (ft) | 47445 | 43615
Removals (ft) | 30946 | 2380
Coupler Plates | 27 | 27
DC Resistance (Segment) | 47410 | 43580
Megger (Segment) | 47445 | 43615
VSWR (Segment) | 47445 | 43615
End-To-End | 47445 | 33565
Heat Map Test | 47445 | 29175
Coverage Test/Survey | 47445 | 3160
Megger Coax Cable (Reel) | 4000 | 4000
Megger Antenna Cable (Reel) | 80000 | 80000
Megger 1/2in Cable (Reel) | 100 | 100
DC Resistance Coax Cable (Reel) | 4000 | 4000
DC Resistance Antenna Cable (Reel) | 80000 | 80000
DC Resistance 1/2in Cable (Reel) | 100 | 100

## Dashboard
RADIO INSTALLATION DASHBOARD
OVERALL TASK COMPLETION (ALL TRACKS)
TASK PERCENT COMPLETION (PER TRACK)
OVERALL INSTALLATION PROGRESS PER TRACK SECTION
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.