## Reference
Track No. | Column Side | Activities | Bracket Type | Station | Track Stationing | Tunnel | Description | Track Stationing | Notes
B1 | W | Steel Messenger Supports | 1 | Church Avenue | 556+96 to 563+56 | CHU-FOR | Church Ave to Fort Hamilton | 563+56 to 584+88
B2 | E | Messenger Clamps | 2 | Fort Hamilton Parkway | 584+88 to 591+90 | FOR-15S | Fort Hamilton to 15th Street | 591+90 to 625+70
B3 | W | Messenger Wire Pull | 3 | 15th Street Prospect Park | 625+70 to 632+30 | 15S-7AV | 15th Street to 7th Avenue | 632+30 to 653+96
B4 | E | Messenger Wire Tension | 4 | 7th Avenue | 653+96 to 660+56 | 7AV-4TH | 7th Avenue to 4th & 9th Street | 660+56-683+83
E1 | W | Cable Pull | 4A | 4th & 9th Street | 683+83 to 690+91 | 4TH-SMI | 4th & 9th Street to Smith & 9th Street | 690+91 to 705+11
E2 | E | Messenger Straps | 5 | Smith & 9th Street | 705+11 to 712+32 | SMI-CAR | Smith & 9th Street to Carroll Street | 712+32 to 732+89
E3 |  | 15inch CMRS |  | Carroll Street | 732+39 to 738+99 | CAR-BER | Carroll Street to Bergen Street | 738+99 to 756+82
E4 |  | 24inch CMRS |  | Bergen Street | 756+82 to 763+42 | BER-HOY | Bergen Street to Hoyt Schermerhorn | 763+42 to 761+84 | track goes from 768+XX to 693+95
E5 |  | Column mount CMRS |  | Hoyt Schermerhorn | 761+84 to 768+87 | HOY-FUL | Hoyt Schermerhorn to Fulton | 768+87 to 740+30
|  | Station Brackets |  | Fulton Street | 740+30 to 733+70 | FUL-CLI | Fulton to Clinton Washington | 733+70 to 951+82 | track goes from 733+15 to 934+96
Location |  | Grounding |  | Clinton Washington Avenue | 951+82 to 958+42 | CLI-CLA | Clinton Washington to Classon | 958+42 to 970+82
Church Avenue |  | Obstruction Brackets |  | Classon Avenue | 970+82 to 977+42 | CLA-BED | Classon to Bedford Nostand | 977+42 to 989+22
CHU-FOR |  | Cable Pull |  | Bedford Nostrand Avenue | 989+22 to 995+82 | BED-MYR | Bedford Nostrand to Myrtle Willoughby | 995+82 to 1017+47
Fort Hamilton Parkway |  | Cable Tray Brackets |  | Myrtle Willoughby Ave | 1017+47 to 1024+52 | MYR-FLU | Myrtle Willoughby to Flushing Avenue | 1024+52 to 1039+42
FOR-15S |  | Installing Tray |  | Flushing Avenue Station | 1039+42 to 1046+20 | FLU-BRO | Flushing Avenue to Broadway | 1046+20 to 1060+52
15th Street Prospect Park |  | Core Drilling |  | Broadway | 1060+52 to 1067+12 | BRO-MET | Broadway to Metropolitan | 1067+12 to 1132+45
15S-7AV |  | Cable Pull |  | Metropolitan Avenue | 1132+45 to 1139+50 | MET-NAS | Metropolitan to Nassau | 1139+50 to 1131+52
7th Avenue |  | Arch Bar Installation |  | Nassau Avenue | 1131+52 to 1138+32 | NAS-GRE | Nassau to Greenpoint | 1138+32 to 1157+00
7AV-4TH |  |  |  | Greenpoint Avenue | 1157+00 to 1164+32 | GRE-21S | Greenpoint to 21 St | 1164+32 to 1211+33
4th & 9th Street |  |  |  | 21 St Station | 1211+33 to 1217+92 | 21S-COU | 21 St to Court Square | 1217+92 to 1229+23
4TH-SMI |  |  |  | Court Square | 1229+23 to 1236+66 | COU-QUE | Court Square to Queens Plaza | 1236+66 to 1250+65
Smith & 9th Street |  |  |  | Queens Plaza | 1250+65 to 1257+27
SMI-CAR
Carroll Street |  |  |  | Signal Types
CAR-BER |  |  |  | HOME
Bergen Street* |  |  |  | APPROACH
BER-HOY |  |  |  | BUMPER
Hoyt Schermerhorn |  |  |  | REV. HOME
HOY-FUL |  |  |  | REV. APPROACH
Fulton Street
FUL-CLI
Clinton Washington Avenue
CLI-CLA
Classon Avenue
CLA-BED
Bedford Nostrand Avenue
BED-MYR
Myrtle Willoughby Ave
MYR-FLU
Flushing Avenue Station
FLU-BRO
Broadway
BRO-MET
Metropolitan Avenue
MET-NAS
Nassau Avenue
NAS-GRE
Greenpoint Avenue
GRE-21S
21 St Station
21S-COU
Court Square
COU-QUE
Queens Plaza

## Work Sheet (hidden)
OVERALL INSTALLATION PER AREA
Status | Count
Not Started | #REF!
In Progress | #REF!
Completed | #REF!
Remaining | #REF!
Total Tasks | #REF!
Completed Sections | #REF!
Remaining Sections | #REF!

## Ref Activity Bar (hidden)
RADIO INSTALLATION DASHBOARD
TRACK | C3/C4
TASK | COMPLETION PROGRESS
Removals | 12.5%
Grand Total | 12.5%

## Ref Progress per Activity (hidden)
TASK | Acceptance Test
|  | Not Started | 0 | Completed Sections | 13.04%
TRACK | Average of PROGRESS | In Progress | 0 | Remaining Sections | 86.96%
C1 | 16.67% | Completed | 0
C2 | 16.67%
C3 | 0%
C3/C4 | 14.29%
C4 | 0%
C5 | 0%
C6 | 0%
Grand Total | 13.04%

## CMRS
Start | Finish | Track No | Location | Activity | Total Quantity | QTY Installed | Date | Progress | General Progress | Notes | Notes
124510 | 124500 | D1 | COU-QUE | Steel Mess Supports | 795 | 630 |  | 0.79245 | 0.54196
|  |  |  | Messenger Clamps | 713 | 128 |  | 0.17952
|  |  |  | Messenger Wire Pull | 814 | 699 |  | 0.85872
|  |  |  | Messenger Wire Tension | 511 | 397 |  | 0.77691
|  |  |  | # Cables Pulled | 747 | 141 |  | 0.18876
|  |  |  | Messenger Straps | 762 | 347 |  | 0.45538
124500 | 124320 | D1 | COU-QUE | Steel Mess Supports | 235 | 170 |  | 0.7234 | 0.52398
|  |  |  | Messenger Clamps | 122 | 114 |  | 0.93443
|  |  |  | Messenger Wire Pull | 444 | 113 |  | 0.2545
|  |  |  | Messenger Wire Tension | 558 | 175 |  | 0.31362
|  |  |  | # Cables Pulled | 673 | 364 |  | 0.54086
|  |  |  | Messenger Straps | 61 | 23 |  | 0.37705
124320 | 124100 | D1 | COU-QUE | Steel Mess Supports | 966 | 778 |  | 0.80538 | 0.5267
|  |  |  | Messenger Clamps | 45 | 9 |  | 0.2
|  |  |  | Messenger Wire Pull | 212 | 177 |  | 0.83491
|  |  |  | Messenger Wire Tension | 254 | 185 |  | 0.72835
|  |  |  | # Cables Pulled | 647 | 175 |  | 0.27048
|  |  |  | Messenger Straps | 436 | 140 |  | 0.3211
124100 | 123970 | D1 | COU-QUE | Steel Mess Supports | 98 | 55 |  | 0.56122 | 0.63351
|  |  |  | Messenger Clamps | 699 | 438 |  | 0.62661
|  |  |  | Messenger Wire Pull | 963 | 669 |  | 0.6947
|  |  |  | Messenger Wire Tension | 764 | 228 |  | 0.29843
|  |  |  | # Cables Pulled | 628 | 592 |  | 0.94268
|  |  |  | Messenger Straps | 31 | 21 |  | 0.67742
123970 | 123930 | D1 | COU-QUE | 15" CMRS Install | 402 | 295 |  | 0.73383 | 0.616
|  |  |  | Column Clamp | 388 | 280 |  | 0.72165
|  |  |  | Station Brackets | 997 | 166 |  | 0.1665
|  |  |  | Grounding | 676 | 137 |  | 0.20266
|  |  |  | Obstruction Brackets | 705 | 649 |  | 0.92057
|  |  |  | # Cables Pulled | 183 | 174 |  | 0.95082
123930 | 123715 | D1 | COU-QUE | 15" CMRS Install | 799 | 648 |  | 0.81101 | 0.39006
|  |  |  | Column Clamp | 741 | 133 |  | 0.17949
|  |  |  | Station Brackets | 183 | 22 |  | 0.12022
|  |  |  | Grounding | 562 | 77 |  | 0.13701
|  |  |  | Obstruction Brackets | 736 | 177 |  | 0.24049
|  |  |  | # Cables Pulled | 744 | 634 |  | 0.85215
|  | D1 | COU-QUE | Crossover (Arch Bar Installation) | 478 | 304 |  | 0.63598
122975 | 122827 | E1 | 21S-COU | Steel Mess Supports | 686 | 537 |  | 0.7828 | 0.61713
|  |  |  | Messenger Clamps | 539 | 421 |  | 0.78108
|  |  |  | Messenger Wire Pull | 272 | 149 |  | 0.54779
|  |  |  | Messenger Wire Tension | 234 | 194 |  | 0.82906
|  |  |  | # Cables Pulled | 885 | 90 |  | 0.10169
|  |  |  | Messenger Straps | 212 | 140 |  | 0.66038
122827 | 122250 | E1 | 21S-COU | 24" CMRS Install | 623 | 496 |  | 0.79615 | 0.47638
|  |  |  | Column Clamp | 909 | 740 |  | 0.81408
|  |  |  | Station Brackets | 766 | 24 |  | 0.031332
|  |  |  | Grounding | 15 | 5 |  | 0.33333
|  |  |  | Obstruction Brackets | 807 | 548 |  | 0.67906
|  |  |  | # Cables Pulled | 93 | 19 |  | 0.2043
122250 | 121833 | E1 | 21S-COU | Steel Mess Supports | 538 | 66 |  | 0.12268 | 0.43246
|  |  |  | Messenger Clamps | 854 | 267 |  | 0.31265
|  |  |  | Messenger Wire Pull | 31 | 13 |  | 0.41935
|  |  |  | Messenger Wire Tension | 149 | 128 |  | 0.85906
|  |  |  | # Cables Pulled | 969 | 345 |  | 0.35604
|  |  |  | Messenger Straps | 920 | 483 |  | 0.525
121833 | 121030 | E1 | 21 STREET | Steel Mess Supports | 118 | 17 |  | 0.14407 | 0.61415
|  |  |  | Messenger Clamps | 399 | 222 |  | 0.55639
|  |  |  | Messenger Wire Pull | 600 | 595 |  | 0.99167
|  |  |  | Messenger Wire Tension | 81 | 63 |  | 0.77778
|  |  |  | # Cables Pulled | 716 | 188 |  | 0.26257
|  |  |  | Messenger Straps | 883 | 841 |  | 0.95243
121030 | 117010 | E1 | GRE-21S | 15" CMRS Install | 741 | 156 |  | 0.21053 | 0.37137
|  |  |  | Column Clamp | 676 | 147 |  | 0.21746
|  |  |  | Station Brackets | 364 | 121 |  | 0.33242
|  |  |  | Grounding | 604 | 23 |  | 0.038079
|  |  |  | Obstruction Brackets | 741 | 324 |  | 0.43725
|  |  |  | # Cables Pulled | 266 | 264 |  | 0.99248
117010 | 116810 | E1 | GRE-21S | 15" CMRS Install | 259 | 39 |  | 0.15058 | 0.54768
|  |  |  | Column Clamp | 800 | 373 |  | 0.46625
|  |  |  | Station Brackets | 417 | 292 |  | 0.70024
|  |  |  | Grounding | 641 | 549 |  | 0.85647
|  |  |  | Obstruction Brackets | 860 | 206 |  | 0.23953
|  |  |  | # Cables Pulled | 126 | 110 |  | 0.87302
116810 | 116471 | E1 | GRE-21S | 15" CMRS Install | 719 | 36 |  | 0.05007 | 0.43956
|  |  |  | Column Clamp | 133 | 113 |  | 0.84962
|  |  |  | Station Brackets | 356 | 16 |  | 0.044944
|  |  |  | Grounding | 996 | 593 |  | 0.59538
|  |  |  | Obstruction Brackets | 100 | 65 |  | 0.65
|  |  |  | # Cables Pulled | 968 | 433 |  | 0.44731
116471 | 115694 | E1 | GREENPOINT | 24" CMRS Install | 631 | 516 |  | 0.81775 | 0.55253
|  |  |  | Column Clamp | 746 | 411 |  | 0.55094
|  |  |  | Station Brackets | 303 | 68 |  | 0.22442
|  |  |  | Grounding | 195 | 53 |  | 0.27179
|  |  |  | Obstruction Brackets | 437 | 407 |  | 0.93135
|  |  |  | # Cables Pulled | 686 | 356 |  | 0.51895
115694 | 115628 | E1 | NAS-GRE | 24" CMRS Install | 915 | 266 |  | 0.29071 | 0.47699
|  |  |  | Column Clamp | 44 | 5 |  | 0.11364
|  |  |  | Station Brackets | 164 | 116 |  | 0.70732
|  |  |  | Grounding | 615 | 527 |  | 0.85691
|  |  |  | Obstruction Brackets | 892 | 788 |  | 0.88341
|  |  |  | # Cables Pulled | 402 | 4 |  | 0.0099502
115628 | 114897 | E1 | NAS-GRE | 24" CMRS Install | 703 | 672 |  | 0.9559 | 0.39008
|  |  |  | Column Clamp | 293 | 88 |  | 0.30034
|  |  |  | Station Brackets | 493 | 149 |  | 0.30223
|  |  |  | Grounding | 607 | 106 |  | 0.17463
|  |  |  | Obstruction Brackets | 820 | 475 |  | 0.57927
|  |  |  | # Cables Pulled | 463 | 13 |  | 0.028078
114897 | 114719 | E1 | NAS-GRE | Steel Mess Supports | 275 | 269 |  | 0.97818 | 0.52193
|  |  |  | Messenger Clamps | 914 | 254 |  | 0.2779
|  |  |  | Messenger Wire Pull | 818 | 161 |  | 0.19682
|  |  |  | Messenger Wire Tension | 566 | 340 |  | 0.60071
|  |  |  | # Cables Pulled | 916 | 624 |  | 0.68122
|  |  |  | Messenger Straps | 552 | 219 |  | 0.39674
114719 | 114040 | E1 | NAS-GRE | 24" CMRS Install | 176 | 92 |  | 0.52273 | 0.54648
|  |  |  | Column Clamp | 262 | 183 |  | 0.69847
|  |  |  | Station Brackets | 229 | 98 |  | 0.42795
|  |  |  | Grounding | 771 | 314 |  | 0.40726
|  |  |  | Obstruction Brackets | 31 | 19 |  | 0.6129
|  |  |  | # Cables Pulled | 858 | 523 |  | 0.60956
114040 | 113815 | E1 | NAS-GRE | Steel Mess Supports | 681 | 271 |  | 0.39794 | 0.30458
|  |  |  | Messenger Clamps | 615 | 528 |  | 0.85854
|  |  |  | Messenger Wire Pull | 701 | 14 |  | 0.019971
|  |  |  | Messenger Wire Tension | 896 | 179 |  | 0.19978
|  |  |  | # Cables Pulled | 525 | 181 |  | 0.34476
|  |  |  | Messenger Straps | 154 | 1 |  | 0.0064935
113815 | 113019 | E1 | NASSAU | 24" CMRS Install | 830 | 762 |  | 0.91807 | 0.58614 |  | weight: 6.7 lb/ft
|  |  |  | Column Clamp | 173 | 52 |  | 0.30058
|  |  |  | Station Brackets | 502 | 477 |  | 0.9502
|  |  |  | Grounding | 423 | 123 |  | 0.29078
|  |  |  | Obstruction Brackets | 199 | 190 |  | 0.95477
|  |  |  | # Cables Pulled | 205 | 21 |  | 0.10244
|  | E1 | NASSAU | 24" CMRS Install | 306 | 214 |  | 0.69935 | 0.34622
|  |  |  | Column Clamp | 856 | 484 |  | 0.56542
|  |  |  | Station Brackets | 911 | 15 |  | 0.016465
|  |  |  | Grounding | 591 | 238 |  | 0.40271
|  |  |  | Obstruction Brackets | 337 | 95 |  | 0.2819
|  |  |  | # Cables Pulled | 637 | 71 |  | 0.11146
113019 | 112700 | E1 | MET-NAS | 24" CMRS Install | 471 | 440 |  | 0.93418 | 0.6888
|  |  |  | Column Clamp | 332 | 223 |  | 0.67169
|  |  |  | Station Brackets | 646 | 406 |  | 0.62848
|  |  |  | Grounding | 156 | 133 |  | 0.85256
|  |  |  | Obstruction Brackets | 525 | 163 |  | 0.31048
|  |  |  | # Cables Pulled | 480 | 353 |  | 0.73542
112700 | 110878 | E1 | MET-NAS | 15" CMRS Install | 71 | 62 |  | 0.87324 | 0.62912
|  |  |  | Column Clamp | 335 | 37 |  | 0.11045
|  |  |  | Station Brackets | 243 | 150 |  | 0.61728
|  |  |  | Grounding | 535 | 381 |  | 0.71215
|  |  |  | Obstruction Brackets | 914 | 643 |  | 0.7035
|  |  |  | # Cables Pulled | 277 | 210 |  | 0.75812
110878 | 110793 | E1 | MET-NAS | 15" CMRS Install | 981 | 44 |  | 0.044852 | 0.40282
|  |  |  | Column Clamp | 519 | 176 |  | 0.33911
|  |  |  | Station Brackets | 474 | 223 |  | 0.47046
|  |  |  | Grounding | 650 | 190 |  | 0.29231
|  |  |  | Obstruction Brackets | 734 | 548 |  | 0.74659
|  |  |  | # Cables Pulled | 382 | 200 |  | 0.52356
110793 | 109251 | E1 | MET-NAS | 15" CMRS Install | 279 | 96 |  | 0.34409 | 0.46236
|  |  |  | Column Clamp | 74 | 40 |  | 0.54054
|  |  |  | Station Brackets | 945 | 277 |  | 0.29312
|  |  |  | Grounding | 892 | 124 |  | 0.13901
|  |  |  | Obstruction Brackets | 212 | 207 |  | 0.97642
|  |  |  | # Cables Pulled | 237 | 114 |  | 0.48101
109251 | 109133 | E1 | MET-NAS | 15" CMRS Install | 274 | 22 |  | 0.080292 | 0.50911
|  |  |  | Column Clamp | 204 | 11 |  | 0.053922
|  |  |  | Station Brackets | 67 | 48 |  | 0.71642
|  |  |  | Grounding | 52 | 23 |  | 0.44231
|  |  |  | Obstruction Brackets | 705 | 660 |  | 0.93617
|  |  |  | # Cables Pulled | 923 | 762 |  | 0.82557
109133 | 108356 | E1 | METROPOLITAN | 15" CMRS Install | 713 | 451 |  | 0.63254 | 0.53457
|  |  |  | Column Clamp | 167 | 76 |  | 0.45509
|  |  |  | Station Brackets | 248 | 55 |  | 0.22177
|  |  |  | Grounding | 660 | 102 |  | 0.15455
|  |  |  | Obstruction Brackets | 735 | 592 |  | 0.80544
|  |  |  | # Cables Pulled | 226 | 212 |  | 0.93805
108356 | 107651 | E1 | BRO-MET | 15" CMRS Install | 160 | 36 |  | 0.225 | 0.58613
|  |  |  | Column Clamp | 794 | 634 |  | 0.79849
|  |  |  | Station Brackets | 960 | 554 |  | 0.57708
|  |  |  | Grounding | 857 | 794 |  | 0.92649
|  |  |  | Obstruction Brackets | 318 | 290 |  | 0.91195
|  |  |  | # Cables Pulled | 720 | 56 |  | 0.077778
107651 | 107611 | E1 | BRO-MET | 15" CMRS Install | 557 | 453 |  | 0.81329 | 0.59044 |  | Check endings for specific stationings (DWG 48012-17N-006.0) where cable switches from 1 to 2
|  |  |  | Column Clamp | 918 | 728 |  | 0.79303
|  |  |  | Station Brackets | 304 | 72 |  | 0.23684
|  |  |  | Grounding | 259 | 44 |  | 0.16988
|  |  |  | Obstruction Brackets | 916 | 884 |  | 0.96507
|  |  |  | # Cables Pulled | 395 | 223 |  | 0.56456
107611 | 106768 | E1 | BRO-MET | 15" CMRS Install | 213 | 144 |  | 0.67606 | 0.64716
|  |  |  | Column Clamp | 587 | 234 |  | 0.39864
|  |  |  | Station Brackets | 20 | 10 |  | 0.5
|  |  |  | Grounding | 533 | 377 |  | 0.70732
|  |  |  | Obstruction Brackets | 921 | 575 |  | 0.62432
|  |  |  | # Cables Pulled | 899 | 878 |  | 0.97664
106768 | 106702 | E1 | BRO-MET | 15" CMRS Install | 94 | 44 |  | 0.46809 | 0.67351
|  |  |  | Column Clamp | 657 | 424 |  | 0.64536
|  |  |  | Station Brackets | 622 | 274 |  | 0.44051
|  |  |  | Grounding | 688 | 599 |  | 0.87064
|  |  |  | Obstruction Brackets | 698 | 500 |  | 0.71633
|  |  |  | # Cables Pulled | 951 | 856 |  | 0.90011
106702 | 106011 | E1 | BROADWAY | 15" CMRS Install | 376 | 366 |  | 0.9734 | 0.619
|  |  |  | Column Clamp | 689 | 118 |  | 0.17126
|  |  |  | Station Brackets | 531 | 291 |  | 0.54802
|  |  |  | Grounding | 482 | 231 |  | 0.47925
|  |  |  | Obstruction Brackets | 894 | 814 |  | 0.91051
|  |  |  | # Cables Pulled | 825 | 521 |  | 0.63152
|  | E1 | BROADWAY | 15" CMRS Install | 192 | 106 |  | 0.55208 | 0.38972
|  |  |  | Column Clamp | 713 | 7 |  | 0.0098177
|  |  |  | Station Brackets | 255 | 8 |  | 0.031373
|  |  |  | Grounding | 203 | 13 |  | 0.064039
|  |  |  | Obstruction Brackets | 977 | 843 |  | 0.86285
|  |  |  | # Cables Pulled | 55 | 45 |  | 0.81818
|  | E1 | BROADWAY | 15" CMRS Install | 418 | 216 |  | 0.51675 | 0.54874
|  |  |  | Column Clamp | 240 | 55 |  | 0.22917
|  |  |  | Station Brackets | 676 | 628 |  | 0.92899
|  |  |  | Grounding | 83 | 48 |  | 0.57831
|  |  |  | Obstruction Brackets | 727 | 246 |  | 0.33838
|  |  |  | # Cables Pulled | 488 | 342 |  | 0.70082
106011 | 105293 | E1 | FLU-BRO | 15" CMRS Install | 408 | 121 |  | 0.29657 | 0.52759
|  |  |  | Column Clamp | 857 | 46 |  | 0.053676
|  |  |  | Station Brackets | 529 | 229 |  | 0.43289
|  |  |  | Grounding | 910 | 864 |  | 0.94945
|  |  |  | Obstruction Brackets | 484 | 406 |  | 0.83884
|  |  |  | # Cables Pulled | 340 | 202 |  | 0.59412
105293 | 104667 | E1 | FLU-BRO | 15" CMRS Install | 697 | 184 |  | 0.26399 | 0.40762
|  |  |  | Column Clamp | 811 | 447 |  | 0.55117
|  |  |  | Station Brackets | 995 | 488 |  | 0.49045
|  |  |  | Grounding | 830 | 522 |  | 0.62892
|  |  |  | Obstruction Brackets | 366 | 158 |  | 0.43169
|  |  |  | # Cables Pulled | 453 | 36 |  | 0.07947
104667 | 103784 | E1 | FLUSHING | 15" CMRS Install | 14 | 10 |  | 0.71429 | 0.40071
|  |  |  | Column Clamp | 559 | 91 |  | 0.16279
|  |  |  | Station Brackets | 161 | 44 |  | 0.27329
|  |  |  | Grounding | 423 | 22 |  | 0.052009
|  |  |  | Obstruction Brackets | 965 | 617 |  | 0.63938
|  |  |  | # Cables Pulled | 464 | 261 |  | 0.5625
103784 | 103231 | E1 | MYR-FLU | 15" CMRS Install | 212 | 174 |  | 0.82075 | 0.4754
|  |  |  | Column Clamp | 809 | 141 |  | 0.17429
|  |  |  | Station Brackets | 446 | 28 |  | 0.06278
|  |  |  | Grounding | 502 | 264 |  | 0.5259
|  |  |  | Obstruction Brackets | 144 | 74 |  | 0.51389
|  |  |  | # Cables Pulled | 628 | 474 |  | 0.75478
103231 | 103165 | E1 | MYR-FLU | 15" CMRS Install | 351 | 243 |  | 0.69231 | 0.44804
|  |  |  | Column Clamp | 31 | 12 |  | 0.3871
|  |  |  | Station Brackets | 20 | 12 |  | 0.6
|  |  |  | Grounding | 158 | 5 |  | 0.031646
|  |  |  | Obstruction Brackets | 947 | 475 |  | 0.50158
|  |  |  | # Cables Pulled | 471 | 224 |  | 0.47558
103165 | 102533 | E1 | MYR-FLU | 15" CMRS Install | 94 | 1 |  | 0.010638 | 0.40263
|  |  |  | Column Clamp | 788 | 731 |  | 0.92766
|  |  |  | Station Brackets | 279 | 120 |  | 0.43011
|  |  |  | Grounding | 885 | 136 |  | 0.15367
|  |  |  | Obstruction Brackets | 819 | 692 |  | 0.84493
|  |  |  | # Cables Pulled | 861 | 42 |  | 0.04878
102533 | 101595 | E1 | MYRTLE | 24" CMRS Install | 303 | 84 |  | 0.27723 | 0.54061
|  |  |  | Column Clamp | 289 | 92 |  | 0.31834
|  |  |  | Station Brackets | 601 | 346 |  | 0.57571
|  |  |  | Grounding | 760 | 401 |  | 0.52763
|  |  |  | Obstruction Brackets | 808 | 470 |  | 0.58168
|  |  |  | # Cables Pulled | 325 | 313 |  | 0.96308
101595 | 101558 | E1 | BED-MYR | 24" CMRS Install | 834 | 532 |  | 0.63789 | 0.5857
|  |  |  | Column Clamp | 841 | 817 |  | 0.97146
|  |  |  | Station Brackets | 407 | 54 |  | 0.13268
|  |  |  | Grounding | 509 | 341 |  | 0.66994
|  |  |  | Obstruction Brackets | 853 | 831 |  | 0.97421
|  |  |  | # Cables Pulled | 453 | 58 |  | 0.12804
101558 | 101050 | E1 | BED-MYR | 24" CMRS Install | 947 | 896 |  | 0.94615 | 0.68429
|  |  |  | Column Clamp | 996 | 550 |  | 0.55221
|  |  |  | Station Brackets | 320 | 260 |  | 0.8125
|  |  |  | Grounding | 17 | 15 |  | 0.88235
|  |  |  | Obstruction Brackets | 584 | 332 |  | 0.56849
|  |  |  | # Cables Pulled | 404 | 139 |  | 0.34406
101050 | 101015 | E1 | BED-MYR | 24" CMRS Install | 323 | 47 |  | 0.14551 | 0.43183
|  |  |  | Column Clamp | 662 | 554 |  | 0.83686
|  |  |  | Station Brackets | 471 | 447 |  | 0.94904
|  |  |  | Grounding | 638 | 135 |  | 0.2116
|  |  |  | Obstruction Brackets | 634 | 66 |  | 0.1041
|  |  |  | # Cables Pulled | 948 | 326 |  | 0.34388
101015 | 100530 | E1 | BED-MYR | 24" CMRS Install | 560 | 59 |  | 0.10536 | 0.42773
|  |  |  | Column Clamp | 572 | 316 |  | 0.55245
|  |  |  | Station Brackets | 656 | 23 |  | 0.035061
|  |  |  | Grounding | 934 | 396 |  | 0.42398
|  |  |  | Obstruction Brackets | 236 | 153 |  | 0.64831
|  |  |  | # Cables Pulled | 976 | 782 |  | 0.80123
100530 | 100383 | E1 | BED-MYR | Steel Mess Supports | 760 | 552 |  | 0.72632 | 0.66738
|  |  |  | Messenger Clamps | 989 | 422 |  | 0.42669
|  |  |  | Messenger Wire Pull | 203 | 188 |  | 0.92611
|  |  |  | Messenger Wire Tension | 22 | 8 |  | 0.36364
|  |  |  | # Cables Pulled | 521 | 363 |  | 0.69674
|  |  |  | Messenger Straps | 636 | 550 |  | 0.86478
|  | E1 | BED-MYR | Crossover (Arch Bar Installation) | 487 | 200 |  | 0.41068
100383 | 100282 | E1 | BED-MYR | Steel Mess Supports | 580 | 228 |  | 0.3931 | 0.46215
|  |  |  | Messenger Clamps | 120 | 83 |  | 0.69167
|  |  |  | Messenger Wire Pull | 845 | 192 |  | 0.22722
|  |  |  | Messenger Wire Tension | 408 | 7 |  | 0.017157
|  |  |  | # Cables Pulled | 798 | 527 |  | 0.6604
|  |  |  | Messenger Straps | 60 | 47 |  | 0.78333
100282 | 100036 | E1 | BED-MYR | Steel Mess Supports | 379 | 24 |  | 0.063325 | 0.42236
|  |  |  | Messenger Clamps | 514 | 81 |  | 0.15759
|  |  |  | Messenger Wire Pull | 557 | 331 |  | 0.59425
|  |  |  | Messenger Wire Tension | 58 | 47 |  | 0.81034
|  |  |  | # Cables Pulled | 792 | 116 |  | 0.14646
|  |  |  | Messenger Straps | 370 | 282 |  | 0.76216
100036 | 99560 | E1 | BED-MYR | Steel Mess Supports | 801 | 449 |  | 0.56055 | 0.52537
|  |  |  | Messenger Clamps | 601 | 541 |  | 0.90017
|  |  |  | Messenger Wire Pull | 68 | 63 |  | 0.92647
|  |  |  | Messenger Wire Tension | 391 | 36 |  | 0.092072
|  |  |  | # Cables Pulled | 864 | 129 |  | 0.14931
|  |  |  | Messenger Straps | 867 | 454 |  | 0.52364
98845 | 98555 | E1 | CLA-BED | 24" CMRS Install | 659 | 161 |  | 0.24431 | 0.45998
|  |  |  | Column Clamp | 210 | 24 |  | 0.11429
|  |  |  | Station Brackets | 816 | 355 |  | 0.43505
|  |  |  | Grounding | 579 | 360 |  | 0.62176
|  |  |  | Obstruction Brackets | 892 | 583 |  | 0.65359
|  |  |  | # Cables Pulled | 55 | 38 |  | 0.69091
|  | E1 | CLA-BED | Crossover (Arch Bar Installation) | 567 | 438 |  | 0.77249
98555 | 98220 | E1 | CLA-BED | 24" CMRS Install | 462 | 167 |  | 0.36147 | 0.39343
|  |  |  | Column Clamp | 762 | 86 |  | 0.11286
|  |  |  | Station Brackets | 945 | 210 |  | 0.22222
|  |  |  | Grounding | 623 | 544 |  | 0.87319
|  |  |  | Obstruction Brackets | 777 | 345 |  | 0.44402
|  |  |  | # Cables Pulled | 914 | 317 |  | 0.34683
98220 | 98140 | E1 | CLA-BED | 24" CMRS Install | 199 | 39 |  | 0.19598 | 0.35477
|  |  |  | Column Clamp | 420 | 174 |  | 0.41429
|  |  |  | Station Brackets | 440 | 47 |  | 0.10682
|  |  |  | Grounding | 482 | 230 |  | 0.47718
|  |  |  | Obstruction Brackets | 907 | 277 |  | 0.3054
|  |  |  | # Cables Pulled | 504 | 317 |  | 0.62897
98140 | 97920 | E1 | CLA-BED | 24" CMRS Install | 257 | 255 |  | 0.99222 | 0.82933
|  |  |  | Column Clamp | 702 | 693 |  | 0.98718
|  |  |  | Station Brackets | 184 | 57 |  | 0.30978
|  |  |  | Grounding | 281 | 246 |  | 0.87544
|  |  |  | Obstruction Brackets | 55 | 45 |  | 0.81818
|  |  |  | # Cables Pulled | 734 | 729 |  | 0.99319
97920 | 97670 | E1 | CLA-BED | Steel Mess Supports | 317 | 254 |  | 0.80126 | 0.48881
|  |  |  | Messenger Clamps | 342 | 302 |  | 0.88304
|  |  |  | Messenger Wire Pull | 43 | 1 |  | 0.023256
|  |  |  | Messenger Wire Tension | 614 | 414 |  | 0.67427
|  |  |  | # Cables Pulled | 436 | 92 |  | 0.21101
|  |  |  | Messenger Straps | 200 | 68 |  | 0.34
97670 | 97580 | E1 | CLASSON | 24" CMRS Install | 446 | 277 |  | 0.62108 | 0.53323
|  |  |  | Column Clamp | 234 | 160 |  | 0.68376
|  |  |  | Station Brackets | 980 | 423 |  | 0.43163
|  |  |  | Grounding | 443 | 391 |  | 0.88262
|  |  |  | Obstruction Brackets | 659 | 343 |  | 0.52049
|  |  |  | # Cables Pulled | 987 | 59 |  | 0.059777
97580 | 97230 | E1 | CLASSON | 24" CMRS Install | 868 | 590 |  | 0.67972 | 0.53646
|  |  |  | Column Clamp | 438 | 329 |  | 0.75114
|  |  |  | Station Brackets | 847 | 132 |  | 0.15584
|  |  |  | Grounding | 787 | 509 |  | 0.64676
|  |  |  | Obstruction Brackets | 113 | 90 |  | 0.79646
|  |  |  | # Cables Pulled | 233 | 44 |  | 0.18884
97230 | 96920 | E1 | CLASSON | 24" CMRS Install | 446 | 300 |  | 0.67265 | 0.61396
|  |  |  | Column Clamp | 342 | 183 |  | 0.53509
|  |  |  | Station Brackets | 405 | 159 |  | 0.39259
|  |  |  | Grounding | 699 | 359 |  | 0.51359
|  |  |  | Obstruction Brackets | 34 | 26 |  | 0.76471
|  |  |  | # Cables Pulled | 626 | 504 |  | 0.80511
96920 | 96685 | E1 | CLI-CLA | Steel Mess Supports | 228 | 101 |  | 0.44298 | 0.69764
|  |  |  | Messenger Clamps | 938 | 551 |  | 0.58742
|  |  |  | Messenger Wire Pull | 866 | 855 |  | 0.9873
|  |  |  | Messenger Wire Tension | 765 | 575 |  | 0.75163
|  |  |  | # Cables Pulled | 669 | 633 |  | 0.94619
|  |  |  | Messenger Straps | 421 | 198 |  | 0.47031
96685 | 96460 | E1 | CLI-CLA | 24" CMRS Install | 496 | 133 |  | 0.26815 | 0.54751
|  |  |  | Column Clamp | 171 | 171 |  | 1
|  |  |  | Station Brackets | 916 | 654 |  | 0.71397
|  |  |  | Grounding | 942 | 110 |  | 0.11677
|  |  |  | Obstruction Brackets | 48 | 11 |  | 0.22917
|  |  |  | # Cables Pulled | 349 | 334 |  | 0.95702
96460 | 96387 | E1 | CLI-CLA | 24" CMRS Install | 590 | 163 |  | 0.27627 | 0.30277
|  |  |  | Column Clamp | 912 | 142 |  | 0.1557
|  |  |  | Station Brackets | 383 | 232 |  | 0.60574
|  |  |  | Grounding | 46 | 31 |  | 0.67391
|  |  |  | Obstruction Brackets | 585 | 27 |  | 0.046154
|  |  |  | # Cables Pulled | 17 | 1 |  | 0.058824
96387 | 96051 | E1 | CLI-CLA | 24" CMRS Install | 329 | 244 |  | 0.74164 | 0.7189
|  |  |  | Column Clamp | 201 | 88 |  | 0.43781
|  |  |  | Station Brackets | 260 | 67 |  | 0.25769
|  |  |  | Grounding | 749 | 736 |  | 0.98264
|  |  |  | Obstruction Brackets | 629 | 625 |  | 0.99364
|  |  |  | # Cables Pulled | 10 | 9 |  | 0.9
96038 | 95998 | E1 | CLI-CLA | 24" CMRS Install | 877 | 95 |  | 0.10832 | 0.47515
|  |  |  | Column Clamp | 416 | 146 |  | 0.35096
|  |  |  | Station Brackets | 255 | 254 |  | 0.99608
|  |  |  | Grounding | 918 | 896 |  | 0.97603
|  |  |  | Obstruction Brackets | 399 | 13 |  | 0.032581
|  |  |  | # Cables Pulled | 398 | 154 |  | 0.38693
95998 | 95873 | E1 | CLI-CLA | 24" CMRS Install | 493 | 424 |  | 0.86004 | 0.39736
|  |  |  | Column Clamp | 202 | 25 |  | 0.12376
|  |  |  | Station Brackets | 625 | 146 |  | 0.2336
|  |  |  | Grounding | 476 | 207 |  | 0.43487
|  |  |  | Obstruction Brackets | 685 | 367 |  | 0.53577
|  |  |  | # Cables Pulled | 617 | 121 |  | 0.19611
95873 | 95781 | E1 | CLINTON-WASHINGTON | 24" CMRS Install | 66 | 13 |  | 0.19697 | 0.40958
|  |  |  | Column Clamp | 691 | 129 |  | 0.18669
|  |  |  | Station Brackets | 434 | 430 |  | 0.99078
|  |  |  | Grounding | 959 | 28 |  | 0.029197
|  |  |  | Obstruction Brackets | 547 | 50 |  | 0.091408
|  |  |  | # Cables Pulled | 293 | 282 |  | 0.96246
95781 | 95695 | E1 | CLINTON-WASHINGTON | 24" CMRS Install | 846 | 563 |  | 0.66548 | 0.6207
|  |  |  | Column Clamp | 450 | 400 |  | 0.88889
|  |  |  | Station Brackets | 192 | 3 |  | 0.015625
|  |  |  | Grounding | 612 | 467 |  | 0.76307
|  |  |  | Obstruction Brackets | 12 | 7 |  | 0.58333
|  |  |  | # Cables Pulled | 947 | 765 |  | 0.80781
95695 | 95544 | E1 | CLINTON-WASHINGTON | 24" CMRS Install | 628 | 19 |  | 0.030255 | 0.67283
|  |  |  | Column Clamp | 168 | 132 |  | 0.78571
|  |  |  | Station Brackets | 506 | 299 |  | 0.59091
|  |  |  | Grounding | 973 | 935 |  | 0.96095
|  |  |  | Obstruction Brackets | 193 | 151 |  | 0.78238
|  |  |  | # Cables Pulled | 839 | 744 |  | 0.88677
95544 | 95155 | E1 | CLINTON-WASHINGTON | 24" CMRS Install | 80 | 13 |  | 0.1625 | 0.72573
|  |  |  | Column Clamp | 319 | 308 |  | 0.96552
|  |  |  | Station Brackets | 324 | 307 |  | 0.94753
|  |  |  | Grounding | 39 | 33 |  | 0.84615
|  |  |  | Obstruction Brackets | 452 | 314 |  | 0.69469
|  |  |  | # Cables Pulled | 229 | 169 |  | 0.73799
95155 | 95004 | E1 | CLINTON-WASHINGTON | 24" CMRS Install | 757 | 527 |  | 0.69617 | 0.61682
|  |  |  | Column Clamp | 122 | 100 |  | 0.81967
|  |  |  | Station Brackets | 298 | 68 |  | 0.22819
|  |  |  | Grounding | 576 | 349 |  | 0.6059
|  |  |  | Obstruction Brackets | 389 | 240 |  | 0.61697
|  |  |  | # Cables Pulled | 94 | 69 |  | 0.73404
95004 | 94266 | E1 | FUL-CLI | 24" CMRS Install | 680 | 455 |  | 0.66912 | 0.54611
|  |  |  | Column Clamp | 294 | 96 |  | 0.32653
|  |  |  | Station Brackets | 20 | 17 |  | 0.85
|  |  |  | Grounding | 482 | 146 |  | 0.3029
|  |  |  | Obstruction Brackets | 439 | 166 |  | 0.37813
|  |  |  | # Cables Pulled | 404 | 303 |  | 0.75
94266 | 94207 | E1 | FUL-CLI | 24" CMRS Install | 314 | 20 |  | 0.063694 | 0.3454
|  |  |  | Column Clamp | 731 | 299 |  | 0.40903
|  |  |  | Station Brackets | 620 | 28 |  | 0.045161
|  |  |  | Grounding | 197 | 161 |  | 0.81726
|  |  |  | Obstruction Brackets | 683 | 321 |  | 0.46999
|  |  |  | # Cables Pulled | 333 | 89 |  | 0.26727
94207 | 93350 | E1 | FUL-CLI | 24" CMRS Install | 493 | 344 |  | 0.69777 | 0.43509
|  |  |  | Column Clamp | 398 | 111 |  | 0.27889
|  |  |  | Station Brackets | 149 | 41 |  | 0.27517
|  |  |  | Grounding | 430 | 50 |  | 0.11628
|  |  |  | Obstruction Brackets | 900 | 743 |  | 0.82556
|  |  |  | # Cables Pulled | 367 | 153 |  | 0.41689
73350 | 73690 | E1 | FULTON | 15" CMRS Install | 652 | 517 |  | 0.79294 | 0.55043
|  |  |  | Column Clamp | 260 | 209 |  | 0.80385
|  |  |  | Station Brackets | 592 | 123 |  | 0.20777
|  |  |  | Grounding | 299 | 28 |  | 0.093645
|  |  |  | Obstruction Brackets | 173 | 154 |  | 0.89017
|  |  |  | # Cables Pulled | 422 | 217 |  | 0.51422
73690 | 74030 | E1 | FULTON | 15" CMRS Install | 230 | 70 |  | 0.30435 | 0.30382
|  |  |  | Column Clamp | 735 | 419 |  | 0.57007
|  |  |  | Station Brackets | 13 | 2 |  | 0.15385
|  |  |  | Grounding | 813 | 183 |  | 0.22509
|  |  |  | Obstruction Brackets | 609 | 119 |  | 0.1954
|  |  |  | # Cables Pulled | 612 | 229 |  | 0.37418
|  | E1 | FULTON | 15" CMRS Install | 72 | 31 |  | 0.43056 | 0.48149
|  |  |  | Column Clamp | 642 | 376 |  | 0.58567
|  |  |  | Station Brackets | 416 | 101 |  | 0.24279
|  |  |  | Grounding | 975 | 719 |  | 0.73744
|  |  |  | Obstruction Brackets | 454 | 246 |  | 0.54185
|  |  |  | # Cables Pulled | 231 | 81 |  | 0.35065
74030 | 76085 | E1 | HOY-FUL | 24" CMRS Install | 147 | 137 |  | 0.93197 | 0.50292
|  |  |  | Column Clamp | 369 | 275 |  | 0.74526
|  |  |  | Station Brackets | 983 | 840 |  | 0.85453
|  |  |  | Grounding | 776 | 10 |  | 0.012887
|  |  |  | Obstruction Brackets | 884 | 142 |  | 0.16063
|  |  |  | # Cables Pulled | 964 | 301 |  | 0.31224
76085 | 76110 | E1 | HOY-FUL | 15" CMRS Install | 368 | 51 |  | 0.13859 | 0.66148
|  |  |  | Column Clamp | 613 | 486 |  | 0.79282
|  |  |  | Station Brackets | 100 | 78 |  | 0.78
|  |  |  | Grounding | 516 | 366 |  | 0.7093
|  |  |  | Obstruction Brackets | 565 | 434 |  | 0.76814
|  |  |  | # Cables Pulled | 50 | 39 |  | 0.78
76110 | 76165 | E1 | HOY-FUL | 15" CMRS Install | 307 | 212 |  | 0.69055 | 0.42105
|  |  |  | Column Clamp | 483 | 286 |  | 0.59213
|  |  |  | Station Brackets | 235 | 100 |  | 0.42553
|  |  |  | Grounding | 29 | 16 |  | 0.55172
|  |  |  | Obstruction Brackets | 623 | 60 |  | 0.096308
|  |  |  | # Cables Pulled | 788 | 134 |  | 0.17005
76165 | 77470 | E1 | HOYT SCHERMERHORN | 15" CMRS Install | 578 | 339 |  | 0.58651 | 0.15925
|  |  |  | Column Clamp | 510 | 25 |  | 0.04902
|  |  |  | Station Brackets | 828 | 79 |  | 0.095411
|  |  |  | Grounding | 13 | 2 |  | 0.15385
|  |  |  | Obstruction Brackets | 690 | 23 |  | 0.033333
|  |  |  | # Cables Pulled | 588 | 22 |  | 0.037415
77470 | 77595 | E1 | BER-HOY | 15" CMRS Install | 543 | 176 |  | 0.32413 | 0.52617
|  |  |  | Column Clamp | 57 | 49 |  | 0.85965
|  |  |  | Station Brackets | 827 | 247 |  | 0.29867
|  |  |  | Grounding | 388 | 299 |  | 0.77062
|  |  |  | Obstruction Brackets | 148 | 52 |  | 0.35135
|  |  |  | # Cables Pulled | 523 | 289 |  | 0.55258
77595 | 78230 | E1 | BER-HOY | 24" CMRS Install | 103 | 6 |  | 0.058252 | 0.27363
|  |  |  | Column Clamp | 431 | 155 |  | 0.35963
|  |  |  | Station Brackets | 146 | 29 |  | 0.19863
|  |  |  | Grounding | 889 | 32 |  | 0.035996
|  |  |  | Obstruction Brackets | 847 | 390 |  | 0.46045
|  |  |  | # Cables Pulled | 191 | 101 |  | 0.5288
78230 | 78515 | E1 | BER-HOY | 24" CMRS Install | 364 | 344 |  | 0.94505 | 0.41601
|  |  |  | Column Clamp | 972 | 351 |  | 0.36111
|  |  |  | Station Brackets | 298 | 202 |  | 0.67785
|  |  |  | Grounding | 171 | 15 |  | 0.087719
|  |  |  | Obstruction Brackets | 219 | 39 |  | 0.17808
|  |  |  | # Cables Pulled | 597 | 147 |  | 0.24623
|  | E2 | BERGEN | Cable Tray Brackets | 31 | 2 |  | 0.064516 | 0.42013
|  |  |  | Installing Tray | 580 | 122 |  | 0.21034
|  |  |  | Core Drilling | 106 | 105 |  | 0.99057
|  |  |  | Cable Pull | 424 | 176 |  | 0.41509
78515 | 78315 | E2 | BER-HOY | Steel Mess Supports | 500 | 266 |  | 0.532 | 0.54377
|  |  |  | Messenger Clamps | 496 | 399 |  | 0.80444
|  |  |  | Messenger Wire Pull | 738 | 652 |  | 0.88347
|  |  |  | Messenger Wire Tension | 786 | 276 |  | 0.35115
|  |  |  | # Cables Pulled | 180 | 52 |  | 0.28889
|  |  |  | Messenger Straps | 812 | 327 |  | 0.40271
78315 | 77655 | E2 | BER-HOY | 24" CMRS Install | 670 | 580 |  | 0.86567 | 0.58557
|  |  |  | Column Clamp | 264 | 164 |  | 0.62121
|  |  |  | Station Brackets | 209 | 103 |  | 0.49282
|  |  |  | Grounding | 888 | 724 |  | 0.81532
|  |  |  | Obstruction Brackets | 780 | 527 |  | 0.67564
|  |  |  | # Cables Pulled | 561 | 24 |  | 0.042781
77655 | 77585 | E2 | BER-HOY | 24" CMRS Install | 16 | 6 |  | 0.375 | 0.60105
|  |  |  | Column Clamp | 406 | 260 |  | 0.64039
|  |  |  | Station Brackets | 570 | 417 |  | 0.73158
|  |  |  | Grounding | 283 | 218 |  | 0.77032
|  |  |  | Obstruction Brackets | 989 | 758 |  | 0.76643
|  |  |  | # Cables Pulled | 279 | 90 |  | 0.32258
77585 | 76845 | E2 | BER-HOY | 24" CMRS Install | 456 | 122 |  | 0.26754 | 0.73036
|  |  |  | Column Clamp | 619 | 535 |  | 0.8643
|  |  |  | Station Brackets | 956 | 903 |  | 0.94456
|  |  |  | Grounding | 661 | 637 |  | 0.96369
|  |  |  | Obstruction Brackets | 430 | 201 |  | 0.46744
|  |  |  | # Cables Pulled | 343 | 300 |  | 0.87464
76845 | 76150 | E2 | HOYT SCHERMERHORN | 24" CMRS Install | 111 | 75 |  | 0.67568 | 0.68014
|  |  |  | Column Clamp | 458 | 151 |  | 0.32969
|  |  |  | Station Brackets | 891 | 458 |  | 0.51403
|  |  |  | Grounding | 200 | 176 |  | 0.88
|  |  |  | Obstruction Brackets | 463 | 460 |  | 0.99352
|  |  |  | # Cables Pulled | 439 | 302 |  | 0.68793
76150 | 76090 | E2 | HOY-FUL | 24" CMRS Install | 71 | 42 |  | 0.59155 | 0.48303
|  |  |  | Column Clamp | 950 | 651 |  | 0.68526
|  |  |  | Station Brackets | 460 | 168 |  | 0.36522
|  |  |  | Grounding | 742 | 388 |  | 0.52291
|  |  |  | Obstruction Brackets | 362 | 141 |  | 0.3895
|  |  |  | # Cables Pulled | 544 | 187 |  | 0.34375
76090 | 75950 | E2 | HOY-FUL | 24" CMRS Install | 55 | 40 |  | 0.72727 | 0.62805
|  |  |  | Column Clamp | 573 | 544 |  | 0.94939
|  |  |  | Station Brackets | 375 | 260 |  | 0.69333
|  |  |  | Grounding | 391 | 48 |  | 0.12276
|  |  |  | Obstruction Brackets | 381 | 233 |  | 0.61155
|  |  |  | # Cables Pulled | 247 | 164 |  | 0.66397
75950 | 75900 | E2 | HOY-FUL | Steel Mess Supports | 833 | 397 |  | 0.47659 | 0.53783
|  |  |  | Messenger Clamps | 645 | 402 |  | 0.62326
|  |  |  | Messenger Wire Pull | 274 | 197 |  | 0.71898
|  |  |  | Messenger Wire Tension | 948 | 809 |  | 0.85338
|  |  |  | # Cables Pulled | 607 | 90 |  | 0.14827
|  |  |  | Messenger Straps | 524 | 213 |  | 0.40649
75900 | 74590 | E2 | HOY-FUL | 24" CMRS Install | 551 | 444 |  | 0.80581 | 0.52753
|  |  |  | Column Clamp | 579 | 284 |  | 0.4905
|  |  |  | Station Brackets | 595 | 50 |  | 0.084034
|  |  |  | Grounding | 451 | 174 |  | 0.38581
|  |  |  | Obstruction Brackets | 750 | 654 |  | 0.872
|  |  |  | # Cables Pulled | 370 | 195 |  | 0.52703
74590 | 74450 | E2 | HOY-FUL | Steel Mess Supports | 392 | 143 |  | 0.3648 | 0.68974
|  |  |  | Messenger Clamps | 642 | 444 |  | 0.69159
|  |  |  | Messenger Wire Pull | 348 | 320 |  | 0.91954
|  |  |  | Messenger Wire Tension | 618 | 482 |  | 0.77994
|  |  |  | # Cables Pulled | 942 | 650 |  | 0.69002
|  |  |  | Messenger Straps | 888 | 615 |  | 0.69257
74450 | 74070 | E2 | HOY-FUL | 24" CMRS Install | 132 | 100 |  | 0.75758 | 0.44326
|  |  |  | Column Clamp | 777 | 233 |  | 0.29987
|  |  |  | Station Brackets | 580 | 333 |  | 0.57414
|  |  |  | Grounding | 21 | 4 |  | 0.19048
|  |  |  | Obstruction Brackets | 869 | 690 |  | 0.79402
|  |  |  | # Cables Pulled | 322 | 14 |  | 0.043478
74070 | 74030 | E2 | HOY-FUL | 24" CMRS Install | 888 | 677 |  | 0.76239 | 0.6723
|  |  |  | Column Clamp | 821 | 572 |  | 0.69671
|  |  |  | Station Brackets | 370 | 358 |  | 0.96757
|  |  |  | Grounding | 839 | 746 |  | 0.88915
|  |  |  | Obstruction Brackets | 226 | 102 |  | 0.45133
|  |  |  | # Cables Pulled | 105 | 28 |  | 0.26667
74030 | 73690 | E2 | FULTON | 15" CMRS Install | 797 | 278 |  | 0.34881 | 0.57782
|  |  |  | Column Clamp | 400 | 305 |  | 0.7625
|  |  |  | Station Brackets | 122 | 106 |  | 0.86885
|  |  |  | Grounding | 671 | 169 |  | 0.25186
|  |  |  | Obstruction Brackets | 823 | 672 |  | 0.81652
|  |  |  | # Cables Pulled | 196 | 82 |  | 0.41837
73690 | 73250 | E2 | FULTON | 15" CMRS Install | 539 | 43 |  | 0.079777 | 0.41334 | Cable Management Takeoffs Cell F110* - 147LF instead of 440LF | Cable Management Takeoffs Cell F110* - 147LF instead of 440LF
|  |  |  | Column Clamp | 48 | 24 |  | 0.5
|  |  |  | Station Brackets | 612 | 35 |  | 0.05719
|  |  |  | Grounding | 662 | 495 |  | 0.74773
|  |  |  | Obstruction Brackets | 837 | 156 |  | 0.18638
|  |  |  | # Cables Pulled | 890 | 809 |  | 0.90899
|  | E2 | FULTON | 15" CMRS Install | 789 | 662 |  | 0.83904 | 0.33843
|  |  |  | Column Clamp | 679 | 28 |  | 0.041237
|  |  |  | Station Brackets | 342 | 199 |  | 0.58187
|  |  |  | Grounding | 687 | 142 |  | 0.2067
|  |  |  | Obstruction Brackets | 208 | 46 |  | 0.22115
|  |  |  | # Cables Pulled | 313 | 44 |  | 0.14058
73250 | 72315 | E2 | FUL-CLI | 24" CMRS Install | 836 | 466 |  | 0.55742 | 0.45578
|  |  |  | Column Clamp | 199 | 161 |  | 0.80905
|  |  |  | Station Brackets | 502 | 228 |  | 0.45418
|  |  |  | Grounding | 443 | 100 |  | 0.22573
|  |  |  | Obstruction Brackets | 699 | 206 |  | 0.29471
|  |  |  | # Cables Pulled | 658 | 259 |  | 0.39362
94400 | 94989 | E2 | FUL-CLI | 24" CMRS Install | 698 | 439 |  | 0.62894 | 0.48219
|  |  |  | Column Clamp | 974 | 635 |  | 0.65195
|  |  |  | Station Brackets | 878 | 769 |  | 0.87585
|  |  |  | Grounding | 450 | 14 |  | 0.031111
|  |  |  | Obstruction Brackets | 539 | 359 |  | 0.66605
|  |  |  | # Cables Pulled | 586 | 23 |  | 0.039249
94989 | 95114 | E2 | FUL-CLI | 24" CMRS Install | 892 | 377 |  | 0.42265 | 0.60327
|  |  |  | Column Clamp | 404 | 364 |  | 0.90099
|  |  |  | Station Brackets | 414 | 51 |  | 0.12319
|  |  |  | Grounding | 469 | 444 |  | 0.9467
|  |  |  | Obstruction Brackets | 964 | 593 |  | 0.61515
|  |  |  | # Cables Pulled | 676 | 413 |  | 0.61095
94989 | 95114 | E2 | CLINTON-WASHINGTON | 24" CMRS Install | 979 | 651 |  | 0.66496 | 0.46902
|  |  |  | Column Clamp | 507 | 117 |  | 0.23077
|  |  |  | Station Brackets | 977 | 860 |  | 0.88025
|  |  |  | Grounding | 952 | 87 |  | 0.091387
|  |  |  | Obstruction Brackets | 588 | 109 |  | 0.18537
|  |  |  | # Cables Pulled | 176 | 134 |  | 0.76136
95503 | 95701 | E2 | CLINTON-WASHINGTON | 24" CMRS Install | 598 | 263 |  | 0.4398 | 0.55875
|  |  |  | Column Clamp | 417 | 204 |  | 0.48921
|  |  |  | Station Brackets | 97 | 56 |  | 0.57732
|  |  |  | Grounding | 344 | 140 |  | 0.40698
|  |  |  | Obstruction Brackets | 232 | 224 |  | 0.96552
|  |  |  | # Cables Pulled | 19 | 9 |  | 0.47368
95767 | 95852 | E2 | CLINTON-WASHINGTON | 24" CMRS Install | 296 | 56 |  | 0.18919 | 0.51432
|  |  |  | Column Clamp | 610 | 315 |  | 0.51639
|  |  |  | Station Brackets | 272 | 154 |  | 0.56618
|  |  |  | Grounding | 828 | 440 |  | 0.5314
|  |  |  | Obstruction Brackets | 599 | 251 |  | 0.41903
|  |  |  | # Cables Pulled | 800 | 691 |  | 0.86375
95852 | 96366 | E2 | CLINTON-WASHINGTON | 24" CMRS Install | 317 | 285 |  | 0.89905 | 0.51052
|  |  |  | Column Clamp | 125 | 52 |  | 0.416
|  |  |  | Station Brackets | 429 | 114 |  | 0.26573
|  |  |  | Grounding | 147 | 120 |  | 0.81633
|  |  |  | Obstruction Brackets | 982 | 251 |  | 0.2556
|  |  |  | # Cables Pulled | 558 | 229 |  | 0.41039
96366 | 96432 | E2 | CLINTON-WASHINGTON | 24" CMRS Install | 897 | 387 |  | 0.43144 | 0.51428
|  |  |  | Column Clamp | 790 | 639 |  | 0.80886
|  |  |  | Station Brackets | 288 | 143 |  | 0.49653
|  |  |  | Grounding | 823 | 735 |  | 0.89307
|  |  |  | Obstruction Brackets | 876 | 50 |  | 0.057078
|  |  |  | # Cables Pulled | 153 | 61 |  | 0.39869
96432 | 96649 | E2 | CLINTON-WASHINGTON | 24" CMRS Install | 467 | 454 |  | 0.97216 | 0.64804
|  |  |  | Column Clamp | 64 | 4 |  | 0.0625
|  |  |  | Station Brackets | 989 | 950 |  | 0.96057
|  |  |  | Grounding | 501 | 397 |  | 0.79242
|  |  |  | Obstruction Brackets | 172 | 67 |  | 0.38953
|  |  |  | # Cables Pulled | 398 | 283 |  | 0.71106
95767 | 95852 | E2 | CLINTON-WASHINGTON | 24" CMRS Install | 18 | 3 |  | 0.16667 | 0.40701
|  |  |  | Column Clamp | 457 | 21 |  | 0.045952
|  |  |  | Station Brackets | 930 | 856 |  | 0.92043
|  |  |  | Grounding | 787 | 696 |  | 0.88437
|  |  |  | Obstruction Brackets | 362 | 124 |  | 0.34254
|  |  |  | # Cables Pulled | 609 | 50 |  | 0.082102
95852 | 96366 | E2 | CLI-CLA | 24" CMRS Install | 191 | 155 |  | 0.81152 | 0.52671
|  |  |  | Column Clamp | 759 | 708 |  | 0.93281
|  |  |  | Station Brackets | 22 | 9 |  | 0.40909
|  |  |  | Grounding | 121 | 86 |  | 0.71074
|  |  |  | Obstruction Brackets | 376 | 41 |  | 0.10904
|  |  |  | # Cables Pulled | 139 | 26 |  | 0.18705
96366 | 96432 | E2 | CLI-CLA | 24" CMRS Install | 788 | 656 |  | 0.83249 | 0.47104
|  |  |  | Column Clamp | 367 | 80 |  | 0.21798
|  |  |  | Station Brackets | 371 | 135 |  | 0.36388
|  |  |  | Grounding | 830 | 159 |  | 0.19157
|  |  |  | Obstruction Brackets | 94 | 41 |  | 0.43617
|  |  |  | # Cables Pulled | 973 | 763 |  | 0.78417
96432 | 96649 | E2 | CLI-CLA | 24" CMRS Install | 590 | 365 |  | 0.61864 | 0.76588
|  |  |  | Column Clamp | 121 | 99 |  | 0.81818
|  |  |  | Station Brackets | 610 | 579 |  | 0.94918
|  |  |  | Grounding | 741 | 228 |  | 0.30769
|  |  |  | Obstruction Brackets | 555 | 510 |  | 0.91892
|  |  |  | # Cables Pulled | 922 | 906 |  | 0.98265
96649 | 96770 | E2 | CLI-CLA | 24" CMRS Install | 311 | 137 |  | 0.44051 | 0.49437
|  |  |  | Column Clamp | 921 | 390 |  | 0.42345
|  |  |  | Station Brackets | 994 | 494 |  | 0.49698
|  |  |  | Grounding | 38 | 24 |  | 0.63158
|  |  |  | Obstruction Brackets | 378 | 80 |  | 0.21164
|  |  |  | # Cables Pulled | 290 | 221 |  | 0.76207
96770 | 96990 | E2 | CLI-CLA | Steel Mess Supports | 831 | 160 |  | 0.19254 | 0.32652
|  |  |  | Messenger Clamps | 590 | 4 |  | 0.0067797
|  |  |  | Messenger Wire Pull | 629 | 559 |  | 0.88871
|  |  |  | Messenger Wire Tension | 255 | 133 |  | 0.52157
|  |  |  | # Cables Pulled | 373 | 7 |  | 0.018767
|  |  |  | Messenger Straps | 768 | 254 |  | 0.33073
96990 | 97230 | E2 | CLASSON | 24" CMRS Install | 275 | 200 |  | 0.72727 | 0.48119
|  |  |  | Column Clamp | 999 | 624 |  | 0.62462
|  |  |  | Station Brackets | 204 | 146 |  | 0.71569
|  |  |  | Grounding | 564 | 194 |  | 0.34397
|  |  |  | Obstruction Brackets | 499 | 109 |  | 0.21844
|  |  |  | # Cables Pulled | 871 | 224 |  | 0.25718
97230 | 97538 | E2 | CLASSON | 24" CMRS Install | 198 | 158 |  | 0.79798 | 0.56391
|  |  |  | Column Clamp | 894 | 130 |  | 0.14541
|  |  |  | Station Brackets | 459 | 165 |  | 0.35948
|  |  |  | Grounding | 475 | 413 |  | 0.86947
|  |  |  | Obstruction Brackets | 902 | 636 |  | 0.7051
|  |  |  | # Cables Pulled | 662 | 335 |  | 0.50604
97538 | 97670 | E2 | CLASSON | 24" CMRS Install | 290 | 85 |  | 0.2931 | 0.54956
|  |  |  | Column Clamp | 829 | 570 |  | 0.68758
|  |  |  | Station Brackets | 632 | 279 |  | 0.44146
|  |  |  | Grounding | 192 | 82 |  | 0.42708
|  |  |  | Obstruction Brackets | 625 | 507 |  | 0.8112
|  |  |  | # Cables Pulled | 314 | 200 |  | 0.63694
97670 | 98015 | E2 | CLA-BED | Steel Mess Supports | 406 | 314 |  | 0.7734 | 0.55633
|  |  |  | Messenger Clamps | 642 | 520 |  | 0.80997
|  |  |  | Messenger Wire Pull | 197 | 41 |  | 0.20812
|  |  |  | Messenger Wire Tension | 147 | 4 |  | 0.027211
|  |  |  | # Cables Pulled | 493 | 317 |  | 0.643
|  |  |  | Messenger Straps | 299 | 262 |  | 0.87625
98015 | 98125 | E2 | CLA-BED | 24" CMRS Install | 666 | 230 |  | 0.34535 | 0.56329
|  |  |  | Column Clamp | 460 | 193 |  | 0.41957
|  |  |  | Station Brackets | 563 | 483 |  | 0.8579
|  |  |  | Grounding | 30 | 16 |  | 0.53333
|  |  |  | Obstruction Brackets | 264 | 250 |  | 0.94697
|  |  |  | # Cables Pulled | 235 | 65 |  | 0.2766
98125 | 98185 | E2 | CLA-BED | 24" CMRS Install | 833 | 715 |  | 0.85834 | 0.53452
|  |  |  | Column Clamp | 224 | 142 |  | 0.63393
|  |  |  | Station Brackets | 867 | 63 |  | 0.072664
|  |  |  | Grounding | 45 | 7 |  | 0.15556
|  |  |  | Obstruction Brackets | 768 | 653 |  | 0.85026
|  |  |  | # Cables Pulled | 880 | 560 |  | 0.63636
98185 | 98440 | E2 | CLA-BED | 24" CMRS Install | 187 | 40 |  | 0.2139 | 0.27033
|  |  |  | Column Clamp | 320 | 1 |  | 0.003125
|  |  |  | Station Brackets | 11 | 0 |  | 0
|  |  |  | Grounding | 71 | 22 |  | 0.30986
|  |  |  | Obstruction Brackets | 622 | 272 |  | 0.4373
|  |  |  | # Cables Pulled | 713 | 469 |  | 0.65778
|  | E2 | CLA-BED | Crossover (Arch Bar Installation) | 761 | 579 |  | 0.76084
98440 | 98586 | E2 | CLA-BED | 24" CMRS Install | 584 | 416 |  | 0.71233 | 0.36565
|  |  |  | Column Clamp | 702 | 28 |  | 0.039886
|  |  |  | Station Brackets | 342 | 332 |  | 0.97076
|  |  |  | Grounding | 601 | 186 |  | 0.30948
|  |  |  | Obstruction Brackets | 233 | 25 |  | 0.1073
|  |  |  | # Cables Pulled | 794 | 43 |  | 0.054156
98586 | 98836 | E2 | CLA-BED | Steel Mess Supports | 729 | 723 |  | 0.99177 | 0.56136
|  |  |  | Messenger Clamps | 29 | 22 |  | 0.75862
|  |  |  | Messenger Wire Pull | 419 | 87 |  | 0.20764
|  |  |  | Messenger Wire Tension | 744 | 593 |  | 0.79704
|  |  |  | # Cables Pulled | 736 | 93 |  | 0.12636
|  |  |  | Messenger Straps | 339 | 165 |  | 0.48673
98836 | 99505 | E2 | BEDFORD NOSTRAND | Cable Tray Brackets | 442 | 240 |  | 0.54299 | 0.60722
|  |  |  | Installing Tray | 834 | 699 |  | 0.83813
|  |  |  | Core Drilling | 55 | 16 |  | 0.29091
|  |  |  | Cable Pull | 255 | 193 |  | 0.75686
99505 | 99950 | E2 | BED-MYR | Steel Mess Supports | 340 | 309 |  | 0.90882 | 0.55128
|  |  |  | Messenger Clamps | 758 | 457 |  | 0.6029
|  |  |  | Messenger Wire Pull | 133 | 128 |  | 0.96241
|  |  |  | Messenger Wire Tension | 607 | 304 |  | 0.50082
|  |  |  | # Cables Pulled | 374 | 18 |  | 0.048128
|  |  |  | Messenger Straps | 130 | 37 |  | 0.28462
|  | E2 | CLA-BED | Crossover (Arch Bar Installation) | 718 | 160 |  | 0.22284
99950 | 100290 | E2 | BED-MYR | 24" CMRS Install | 911 | 575 |  | 0.63117 | 0.53802
|  |  |  | Column Clamp | 22 | 4 |  | 0.18182
|  |  |  | Station Brackets | 923 | 897 |  | 0.97183
|  |  |  | Grounding | 552 | 410 |  | 0.74275
|  |  |  | Obstruction Brackets | 843 | 428 |  | 0.50771
|  |  |  | # Cables Pulled | 223 | 43 |  | 0.19283
100290 | 100740 | E2 | BED-MYR | 24" CMRS Install | 461 | 8 |  | 0.017354 | 0.049445
|  |  |  | Column Clamp | 222 | 8 |  | 0.036036
|  |  |  | Station Brackets | 138 | 7 |  | 0.050725
|  |  |  | Grounding | 609 | 73 |  | 0.11987
|  |  |  | Obstruction Brackets | 72 | 2 |  | 0.027778
|  |  |  | # Cables Pulled | 668 | 30 |  | 0.04491
100740 | 100792 | E2 | BED-MYR | 24" CMRS Install | 33 | 33 |  | 1 | 0.72747
|  |  |  | Column Clamp | 631 | 287 |  | 0.45483
|  |  |  | Station Brackets | 42 | 11 |  | 0.2619
|  |  |  | Grounding | 29 | 23 |  | 0.7931
|  |  |  | Obstruction Brackets | 656 | 572 |  | 0.87195
|  |  |  | # Cables Pulled | 590 | 580 |  | 0.98305
100792 | 101595 | E2 | BED-MYR | 24" CMRS Install | 880 | 376 |  | 0.42727 | 0.51162
|  |  |  | Column Clamp | 182 | 106 |  | 0.58242
|  |  |  | Station Brackets | 364 | 275 |  | 0.75549
|  |  |  | Grounding | 766 | 129 |  | 0.16841
|  |  |  | Obstruction Brackets | 209 | 181 |  | 0.86603
|  |  |  | # Cables Pulled | 685 | 185 |  | 0.27007
101595 | 101688 | E2 | BED-MYR | 24" CMRS Install | 472 | 139 |  | 0.29449 | 0.58378
|  |  |  | Column Clamp | 562 | 293 |  | 0.52135
|  |  |  | Station Brackets | 812 | 322 |  | 0.39655
|  |  |  | Grounding | 902 | 648 |  | 0.7184
|  |  |  | Obstruction Brackets | 410 | 357 |  | 0.87073
|  |  |  | # Cables Pulled | 87 | 61 |  | 0.70115
101688 | 102400 | E2 | MYRTLE AVE | 15" CMRS Install | 129 | 43 |  | 0.33333 | 0.30596
|  |  |  | Column Clamp | 424 | 13 |  | 0.03066
|  |  |  | Station Brackets | 219 | 156 |  | 0.71233
|  |  |  | Grounding | 431 | 23 |  | 0.053364
|  |  |  | Obstruction Brackets | 854 | 86 |  | 0.1007
|  |  |  | # Cables Pulled | 261 | 158 |  | 0.60536
102400 | 102550 | E2 | MYR-FLU | Steel Mess Supports | 12 | 2 |  | 0.16667 | 0.46345
|  |  |  | Messenger Clamps | 547 | 459 |  | 0.83912
|  |  |  | Messenger Wire Pull | 225 | 89 |  | 0.39556
|  |  |  | Messenger Wire Tension | 982 | 219 |  | 0.22301
|  |  |  | # Cables Pulled | 426 | 131 |  | 0.30751
|  |  |  | Messenger Straps | 569 | 483 |  | 0.84886
102550 | 103165 | E2 | MYR-FLU | 15" CMRS Install | 97 | 43 |  | 0.4433 | 0.31276
|  |  |  | Column Clamp | 526 | 4 |  | 0.0076046
|  |  |  | Station Brackets | 459 | 252 |  | 0.54902
|  |  |  | Grounding | 893 | 307 |  | 0.34378
|  |  |  | Obstruction Brackets | 893 | 331 |  | 0.37066
|  |  |  | # Cables Pulled | 37 | 6 |  | 0.16216
103165 | 103230 | E2 | MYR-FLU | 15" CMRS Install | 970 | 747 |  | 0.7701 | 0.65425
|  |  |  | Column Clamp | 745 | 607 |  | 0.81477
|  |  |  | Station Brackets | 557 | 496 |  | 0.89048
|  |  |  | Grounding | 189 | 185 |  | 0.97884
|  |  |  | Obstruction Brackets | 792 | 193 |  | 0.24369
|  |  |  | # Cables Pulled | 826 | 188 |  | 0.2276
103230 | 103809 | E2 | MYR-FLU | 15" CMRS Install | 128 | 49 |  | 0.38281 | 0.59737
|  |  |  | Column Clamp | 304 | 263 |  | 0.86513
|  |  |  | Station Brackets | 910 | 187 |  | 0.20549
|  |  |  | Grounding | 419 | 371 |  | 0.88544
|  |  |  | Obstruction Brackets | 566 | 347 |  | 0.61307
|  |  |  | # Cables Pulled | 223 | 141 |  | 0.63229
103809 | 103902 | E2 | MYR-FLU | 15" CMRS Install | 892 | 12 |  | 0.013453 | 0.28593
|  |  |  | Column Clamp | 133 | 26 |  | 0.19549
|  |  |  | Station Brackets | 16 | 1 |  | 0.0625
|  |  |  | Grounding | 304 | 170 |  | 0.55921
|  |  |  | Obstruction Brackets | 975 | 254 |  | 0.26051
|  |  |  | # Cables Pulled | 900 | 562 |  | 0.62444
103902 | 104595 | E2 | FLUSHING | 15" CMRS Install | 364 | 50 |  | 0.13736 | 0.39803
|  |  |  | Column Clamp | 94 | 61 |  | 0.64894
|  |  |  | Station Brackets | 198 | 53 |  | 0.26768
|  |  |  | Grounding | 204 | 202 |  | 0.9902
|  |  |  | Obstruction Brackets | 944 | 76 |  | 0.080508
|  |  |  | # Cables Pulled | 482 | 127 |  | 0.26349
104595 | 104750 | E2 | FLU-BRO | Steel Mess Supports | 95 | 93 |  | 0.97895 | 0.38274
|  |  |  | Messenger Clamps | 511 | 346 |  | 0.6771
|  |  |  | Messenger Wire Pull | 541 | 68 |  | 0.12569
|  |  |  | Messenger Wire Tension | 707 | 33 |  | 0.046676
|  |  |  | # Cables Pulled | 809 | 310 |  | 0.38319
|  |  |  | Messenger Straps | 719 | 61 |  | 0.08484
104750 | 105270 | E2 | FLU-BRO | 15" CMRS Install | 247 | 1 |  | 0.0040486 | 0.55398
|  |  |  | Column Clamp | 93 | 57 |  | 0.6129
|  |  |  | Station Brackets | 150 | 141 |  | 0.94
|  |  |  | Grounding | 503 | 145 |  | 0.28827
|  |  |  | Obstruction Brackets | 877 | 793 |  | 0.90422
|  |  |  | # Cables Pulled | 907 | 521 |  | 0.57442
105270 | 105930 | E2 | FLU-BRO | 15" CMRS Install | 110 | 64 |  | 0.58182 | 0.55174
|  |  |  | Column Clamp | 684 | 504 |  | 0.73684
|  |  |  | Station Brackets | 953 | 502 |  | 0.52676
|  |  |  | Grounding | 459 | 410 |  | 0.89325
|  |  |  | Obstruction Brackets | 343 | 76 |  | 0.22157
|  |  |  | # Cables Pulled | 454 | 159 |  | 0.35022
105930 | 106003 | E2 | FLU-BRO | 15" CMRS Install | 599 | 66 |  | 0.11018 | 0.4061
|  |  |  | Column Clamp | 112 | 0 |  | 0
|  |  |  | Station Brackets | 758 | 474 |  | 0.62533
|  |  |  | Grounding | 739 | 26 |  | 0.035183
|  |  |  | Obstruction Brackets | 843 | 831 |  | 0.98577
|  |  |  | # Cables Pulled | 494 | 336 |  | 0.68016
106003 | 106648 | E2 | BROADWAY | 15" CMRS Install | 892 | 514 |  | 0.57623 | 0.43159
|  |  |  | Column Clamp | 52 | 23 |  | 0.44231
|  |  |  | Station Brackets | 12 | 1 |  | 0.083333
|  |  |  | Grounding | 821 | 817 |  | 0.99513
|  |  |  | Obstruction Brackets | 63 | 26 |  | 0.4127
|  |  |  | # Cables Pulled | 451 | 36 |  | 0.079823
|  | E2 | BROADWAY | 15" CMRS Install | 83 | 29 |  | 0.3494 | 0.6073
|  |  |  | Column Clamp | 931 | 442 |  | 0.47476
|  |  |  | Station Brackets | 255 | 174 |  | 0.68235
|  |  |  | Grounding | 83 | 72 |  | 0.86747
|  |  |  | Obstruction Brackets | 268 | 142 |  | 0.52985
|  |  |  | # Cables Pulled | 50 | 37 |  | 0.74
|  | E2 | BROADWAY | 15" CMRS Install | 473 | 13 |  | 0.027484 | 0.39629
|  |  |  | Column Clamp | 567 | 16 |  | 0.028219
|  |  |  | Station Brackets | 135 | 4 |  | 0.02963
|  |  |  | Grounding | 285 | 160 |  | 0.5614
|  |  |  | Obstruction Brackets | 805 | 710 |  | 0.88199
|  |  |  | # Cables Pulled | 563 | 478 |  | 0.84902
106650 | 106920 | E2 | BRO-MET | Steel Mess Supports | 54 | 33 |  | 0.61111 | 0.55944
|  |  |  | Messenger Clamps | 446 | 351 |  | 0.787
|  |  |  | Messenger Wire Pull | 741 | 71 |  | 0.095816
|  |  |  | Messenger Wire Tension | 929 | 747 |  | 0.80409
|  |  |  | # Cables Pulled | 570 | 465 |  | 0.81579
|  |  |  | Messenger Straps | 70 | 17 |  | 0.24286
106918 | 107620 | E2 | BRO-MET | 15" CMRS Install | 133 | 37 |  | 0.2782 | 0.38558
|  |  |  | Column Clamp | 188 | 2 |  | 0.010638
|  |  |  | Station Brackets | 539 | 259 |  | 0.48052
|  |  |  | Grounding | 889 | 351 |  | 0.39483
|  |  |  | Obstruction Brackets | 256 | 199 |  | 0.77734
|  |  |  | # Cables Pulled | 621 | 231 |  | 0.37198
107620 | 107683 | E2 | BRO-MET | 15" CMRS Install | 565 | 185 |  | 0.32743 | 0.60264
|  |  |  | Column Clamp | 810 | 764 |  | 0.94321
|  |  |  | Station Brackets | 722 | 425 |  | 0.58864
|  |  |  | Grounding | 485 | 482 |  | 0.99381
|  |  |  | Obstruction Brackets | 837 | 181 |  | 0.21625
|  |  |  | # Cables Pulled | 774 | 423 |  | 0.54651
107683 | 108360 | E2 | BRO-MET | 15" CMRS Install | 13 | 7 |  | 0.53846 | 0.33802
|  |  |  | Column Clamp | 287 | 61 |  | 0.21254
|  |  |  | Station Brackets | 371 | 227 |  | 0.61186
|  |  |  | Grounding | 688 | 352 |  | 0.51163
|  |  |  | Obstruction Brackets | 57 | 0 |  | 0
|  |  |  | # Cables Pulled | 729 | 112 |  | 0.15364
108360 | 109235 | E2 | METROPOLITAN | 15" CMRS Install | 136 | 29 |  | 0.21324 | 0.44569
|  |  |  | Column Clamp | 846 | 108 |  | 0.12766
|  |  |  | Station Brackets | 124 | 51 |  | 0.41129
|  |  |  | Grounding | 583 | 422 |  | 0.72384
|  |  |  | Obstruction Brackets | 413 | 231 |  | 0.55932
|  |  |  | # Cables Pulled | 742 | 474 |  | 0.63881
109235 | 110795 | E2 | MET-NAS | 24" CMRS Install | 265 | 250 |  | 0.9434 | 0.63662
|  |  |  | Column Clamp | 863 | 257 |  | 0.2978
|  |  |  | Station Brackets | 339 | 307 |  | 0.9056
|  |  |  | Grounding | 796 | 414 |  | 0.5201
|  |  |  | Obstruction Brackets | 347 | 281 |  | 0.8098
|  |  |  | # Cables Pulled | 516 | 177 |  | 0.34302
110795 | 110865 | E2 | MET-NAS | 24" CMRS Install | 640 | 560 |  | 0.875 | 0.41649
|  |  |  | Column Clamp | 408 | 113 |  | 0.27696
|  |  |  | Station Brackets | 960 | 377 |  | 0.39271
|  |  |  | Grounding | 794 | 343 |  | 0.43199
|  |  |  | Obstruction Brackets | 175 | 84 |  | 0.48
|  |  |  | # Cables Pulled | 71 | 3 |  | 0.042254
110865 | 113020 | E2 | MET-NAS | 24" CMRS Install | 312 | 158 |  | 0.50641 | 0.59966
|  |  |  | Column Clamp | 75 | 74 |  | 0.98667
|  |  |  | Station Brackets | 754 | 538 |  | 0.71353
|  |  |  | Grounding | 242 | 188 |  | 0.77686
|  |  |  | Obstruction Brackets | 632 | 206 |  | 0.32595
|  |  |  | # Cables Pulled | 662 | 191 |  | 0.28852
113020 | 113155 | E2 | MET-NAS | 24" CMRS Install | 520 | 332 |  | 0.63846 | 0.62925
|  |  |  | Column Clamp | 433 | 207 |  | 0.47806
|  |  |  | Station Brackets | 799 | 641 |  | 0.80225
|  |  |  | Grounding | 360 | 326 |  | 0.90556
|  |  |  | Obstruction Brackets | 920 | 324 |  | 0.35217
|  |  |  | # Cables Pulled | 197 | 118 |  | 0.59898
113155 | 113815 | E2 | NASSAU | 24" CMRS Install | 679 | 5 |  | 0.0073638 | 0.47647
|  |  |  | Column Clamp | 254 | 205 |  | 0.80709
|  |  |  | Station Brackets | 227 | 85 |  | 0.37445
|  |  |  | Grounding | 573 | 419 |  | 0.73124
|  |  |  | Obstruction Brackets | 261 | 223 |  | 0.85441
|  |  |  | # Cables Pulled | 273 | 23 |  | 0.084249
113815 | 114105 | E2 | NAS-GRE | Steel Mess Supports | 395 | 336 |  | 0.85063 | 0.59192
|  |  |  | Messenger Clamps | 326 | 290 |  | 0.88957
|  |  |  | Messenger Wire Pull | 96 | 89 |  | 0.92708
|  |  |  | Messenger Wire Tension | 971 | 7 |  | 0.0072091
|  |  |  | # Cables Pulled | 273 | 52 |  | 0.19048
|  |  |  | Messenger Straps | 67 | 46 |  | 0.68657
114105 | 114730 | E2 | NAS-GRE | 24" CMRS Install | 115 | 17 |  | 0.14783 | 0.36812
|  |  |  | Column Clamp | 593 | 254 |  | 0.42833
|  |  |  | Station Brackets | 918 | 543 |  | 0.5915
|  |  |  | Grounding | 785 | 126 |  | 0.16051
|  |  |  | Obstruction Brackets | 100 | 64 |  | 0.64
|  |  |  | # Cables Pulled | 715 | 172 |  | 0.24056
114730 | 114910 | E2 | NAS-GRE | Steel Mess Supports | 299 | 132 |  | 0.44147 | 0.55769
|  |  |  | Messenger Clamps | 512 | 402 |  | 0.78516
|  |  |  | Messenger Wire Pull | 813 | 400 |  | 0.492
|  |  |  | Messenger Wire Tension | 193 | 179 |  | 0.92746
|  |  |  | # Cables Pulled | 619 | 405 |  | 0.65428
|  |  |  | Messenger Straps | 743 | 34 |  | 0.04576
114910 | 115625 | E2 | NAS-GRE | 24" CMRS Install | 195 | 16 |  | 0.082051 | 0.42144
|  |  |  | Column Clamp | 809 | 314 |  | 0.38813
|  |  |  | Station Brackets | 623 | 23 |  | 0.036918
|  |  |  | Grounding | 612 | 283 |  | 0.46242
|  |  |  | Obstruction Brackets | 845 | 818 |  | 0.96805
|  |  |  | # Cables Pulled | 335 | 198 |  | 0.59104
115625 | 116435 | E2 | GREENPOINT | 24" CMRS Install | 211 | 82 |  | 0.38863 | 0.54585
|  |  |  | Column Clamp | 383 | 139 |  | 0.36292
|  |  |  | Station Brackets | 228 | 187 |  | 0.82018
|  |  |  | Grounding | 348 | 74 |  | 0.21264
|  |  |  | Obstruction Brackets | 619 | 371 |  | 0.59935
|  |  |  | # Cables Pulled | 313 | 279 |  | 0.89137
116435 | 117130 | E2 | GRE-21S | 24" CMRS Install | 242 | 220 |  | 0.90909 | 0.64109
|  |  |  | Column Clamp | 989 | 412 |  | 0.41658
|  |  |  | Station Brackets | 460 | 271 |  | 0.58913
|  |  |  | Grounding | 742 | 495 |  | 0.66712
|  |  |  | Obstruction Brackets | 844 | 582 |  | 0.68957
|  |  |  | # Cables Pulled | 913 | 525 |  | 0.57503
|  | E2 | GRE-21S | Crossover (Arch Bar Installation) | 863 | 666 |  | 0.77173
117130 | 121035 | E2 | GRE-21S | 24" CMRS Install | 790 | 92 |  | 0.11646 | 0.42368
|  |  |  | Column Clamp | 812 | 674 |  | 0.83005
|  |  |  | Station Brackets | 989 | 453 |  | 0.45804
|  |  |  | Grounding | 170 | 70 |  | 0.41176
|  |  |  | Obstruction Brackets | 461 | 166 |  | 0.36009
|  |  |  | # Cables Pulled | 268 | 98 |  | 0.36567
121035 | 122030 | E2 | 21ST STATION | Steel Mess Supports | 837 | 606 |  | 0.72401 | 0.57037
|  |  |  | Messenger Clamps | 936 | 854 |  | 0.91239
|  |  |  | Messenger Wire Pull | 228 | 217 |  | 0.95175
|  |  |  | Messenger Wire Tension | 866 | 1 |  | 0.0011547
|  |  |  | # Cables Pulled | 865 | 464 |  | 0.53642
|  |  |  | Messenger Straps | 914 | 271 |  | 0.2965
122030 | 122430 | E2 | 21S-COU | 24" CMRS Install | 231 | 140 |  | 0.60606 | 0.59161
|  |  |  | Column Clamp | 623 | 71 |  | 0.11396
|  |  |  | Station Brackets | 895 | 636 |  | 0.71061
|  |  |  | Grounding | 817 | 695 |  | 0.85067
|  |  |  | Obstruction Brackets | 806 | 277 |  | 0.34367
|  |  |  | # Cables Pulled | 730 | 675 |  | 0.92466
122430 | 122660 | E2 | 21S-COU | Steel Mess Supports | 147 | 97 |  | 0.65986 | 0.64813
|  |  |  | Messenger Clamps | 968 | 532 |  | 0.54959
|  |  |  | Messenger Wire Pull | 251 | 206 |  | 0.82072
|  |  |  | Messenger Wire Tension | 199 | 105 |  | 0.52764
|  |  |  | # Cables Pulled | 962 | 586 |  | 0.60915
|  |  |  | Messenger Straps | 888 | 641 |  | 0.72185
122660 | 122827 | E2 | 21S-COU | 24" CMRS Install | 477 | 211 |  | 0.44235 | 0.5313
|  |  |  | Column Clamp | 821 | 208 |  | 0.25335
|  |  |  | Station Brackets | 432 | 328 |  | 0.75926
|  |  |  | Grounding | 272 | 269 |  | 0.98897
|  |  |  | Obstruction Brackets | 1000 | 67 |  | 0.067
|  |  |  | # Cables Pulled | 783 | 530 |  | 0.67688
122827 | 123085 | E2 | 21S-COU | Steel Mess Supports | 323 | 202 |  | 0.62539 | 0.42786
|  |  |  | Messenger Clamps | 959 | 294 |  | 0.30657
|  |  |  | Messenger Wire Pull | 364 | 248 |  | 0.68132
|  |  |  | Messenger Wire Tension | 294 | 7 |  | 0.02381
|  |  |  | # Cables Pulled | 151 | 80 |  | 0.5298
|  |  |  | Messenger Straps | 792 | 317 |  | 0.40025
123085 | 123690 | E2 | COURT SQ | Cable Tray Brackets | 816 | 550 |  | 0.67402 | 0.74713
|  |  |  | Installing Tray | 340 | 312 |  | 0.91765
|  |  |  | Core Drilling | 823 | 545 |  | 0.66221
|  |  |  | Cable Pull | 407 | 299 |  | 0.73464
123690 | 123750 | E2 | COU-QUE | Steel Mess Supports | 815 | 426 |  | 0.5227 | 0.47686
|  |  |  | Messenger Clamps | 903 | 794 |  | 0.87929
|  |  |  | Messenger Wire Pull | 819 | 163 |  | 0.19902
|  |  |  | Messenger Wire Tension | 632 | 168 |  | 0.26582
|  |  |  | # Cables Pulled | 949 | 340 |  | 0.35827
|  |  |  | Messenger Straps | 904 | 575 |  | 0.63606
123750 | 123950 | E2 | COU-QUE | Steel Mess Supports | 288 | 262 |  | 0.90972 | 0.55995
|  |  |  | Messenger Clamps | 241 | 192 |  | 0.79668
|  |  |  | Messenger Wire Pull | 273 | 256 |  | 0.93773
|  |  |  | Messenger Wire Tension | 482 | 85 |  | 0.17635
|  |  |  | # Cables Pulled | 291 | 153 |  | 0.52577
|  |  |  | Messenger Straps | 521 | 7 |  | 0.013436
123950 | 124050 | E2 | COU-QUE | Steel Mess Supports | 246 | 164 |  | 0.66667 | 0.62733
|  |  |  | Messenger Clamps | 402 | 314 |  | 0.78109
|  |  |  | Messenger Wire Pull | 805 | 716 |  | 0.88944
|  |  |  | Messenger Wire Tension | 712 | 675 |  | 0.94803
|  |  |  | # Cables Pulled | 669 | 221 |  | 0.33034
|  |  |  | Messenger Straps | 492 | 73 |  | 0.14837
124050 | 124190 | E2 | COU-QUE | Steel Mess Supports | 891 | 129 |  | 0.14478 | 0.48163
|  |  |  | Messenger Clamps | 468 | 83 |  | 0.17735
|  |  |  | Messenger Wire Pull | 315 | 315 |  | 1
|  |  |  | Messenger Wire Tension | 198 | 96 |  | 0.48485
|  |  |  | # Cables Pulled | 222 | 115 |  | 0.51802
|  |  |  | Messenger Straps | 949 | 536 |  | 0.56481
124190 | 124490 | E2 | COU-QUE | Steel Mess Supports | 754 | 631 |  | 0.83687 | 0.61718
|  |  |  | Messenger Clamps | 375 | 229 |  | 0.61067
|  |  |  | Messenger Wire Pull | 477 | 270 |  | 0.56604
|  |  |  | Messenger Wire Tension | 424 | 164 |  | 0.38679
|  |  |  | # Cables Pulled | 675 | 624 |  | 0.92444
|  |  |  | Messenger Straps | 497 | 188 |  | 0.37827
124490 | 124700 | E2 | COU-QUE | Steel Mess Supports | 23 | 11 |  | 0.47826 | 0.56788
|  |  |  | Messenger Clamps | 71 | 24 |  | 0.33803
|  |  |  | Messenger Wire Pull | 701 | 673 |  | 0.96006
|  |  |  | Messenger Wire Tension | 75 | 61 |  | 0.81333
|  |  |  | # Cables Pulled | 825 | 440 |  | 0.53333
|  |  |  | Messenger Straps | 598 | 170 |  | 0.28428
124700 | 125010 | E2 | COU-QUE | Steel Mess Supports | 470 | 437 |  | 0.92979 | 0.57592
|  |  |  | Messenger Clamps | 227 | 86 |  | 0.37885
|  |  |  | Messenger Wire Pull | 26 | 5 |  | 0.19231
|  |  |  | Messenger Wire Tension | 300 | 136 |  | 0.45333
|  |  |  | # Cables Pulled | 403 | 384 |  | 0.95285
|  |  |  | Messenger Straps | 403 | 221 |  | 0.54839
|  | E2 | COU-QUE | Crossover (Arch Bar Installation) | 76 | 63 |  | 0.82895
75650 | 78244 | B3 | BERGEN ST | Steel Mess Supports | 558 | 169 |  | 0.30287 | 0.62466
|  |  |  | Messenger Clamps | 414 | 317 |  | 0.7657
|  |  |  | Messenger Wire Pull | 30 | 28 |  | 0.93333
|  |  |  | Messenger Wire Tension | 990 | 715 |  | 0.72222
|  |  |  | # Cables Pulled | 261 | 43 |  | 0.16475
|  |  |  | Messenger Straps | 511 | 439 |  | 0.8591
|  | B3 | BER-JAY | Steel Mess Supports | 741 | 589 |  | 0.79487 | 0.42072
|  |  |  | Messenger Clamps | 516 | 42 |  | 0.081395
|  |  |  | Messenger Wire Pull | 204 | 93 |  | 0.45588
|  |  |  | Messenger Wire Tension | 478 | 317 |  | 0.66318
|  |  |  | # Cables Pulled | 982 | 505 |  | 0.51426
|  |  |  | Messenger Straps | 272 | 4 |  | 0.014706
|  | B4 | BER-JAY | Steel Mess Supports | 885 | 593 |  | 0.67006 | 0.64382
|  |  |  | Messenger Clamps | 985 | 419 |  | 0.42538
|  |  |  | Messenger Wire Pull | 682 | 286 |  | 0.41935
|  |  |  | Messenger Wire Tension | 573 | 417 |  | 0.72775
|  |  |  | # Cables Pulled | 563 | 498 |  | 0.88455
|  |  |  | Messenger Straps | 863 | 635 |  | 0.73581
|  | E3/E4 | COURT SQ | Steel Mess Supports | 506 | 454 |  | 0.89723 | 0.5715
|  |  |  | Messenger Clamps | 1000 | 592 |  | 0.592
|  |  |  | Messenger Wire Pull | 89 | 82 |  | 0.92135
|  |  |  | Messenger Wire Tension | 970 | 436 |  | 0.44948
|  |  |  | # Cables Pulled | 184 | 24 |  | 0.13043
|  |  |  | Messenger Straps | 561 | 246 |  | 0.4385
75640 | 75300 | B1 | BER-CAR | Steel Mess Supports | 696 | 566 |  | 0.81322 | 0.55075
|  |  |  | Messenger Clamps | 100 | 36 |  | 0.36
|  |  |  | Messenger Wire Pull | 951 | 734 |  | 0.77182
|  |  |  | Messenger Wire Tension | 483 | 413 |  | 0.85507
|  |  |  | # Cables Pulled | 617 | 2 |  | 0.0032415
|  |  |  | Messenger Straps | 852 | 427 |  | 0.50117
68570 | 68330 | B3 | 4TH AVE | Steel Mess Supports | 101 | 30 |  | 0.29703 | 0.58714
|  |  |  | Messenger Clamps | 743 | 664 |  | 0.89367
|  |  |  | Messenger Wire Pull | 566 | 502 |  | 0.88693
|  |  |  | Messenger Wire Tension | 430 | 134 |  | 0.31163
|  |  |  | # Cables Pulled | 342 | 193 |  | 0.56433
|  |  |  | Messenger Straps | 599 | 341 |  | 0.56928
68330 | 68030 | B3 | 4AV-7AV | Steel Mess Supports | 502 | 498 |  | 0.99203 | 0.45385
|  |  |  | Messenger Clamps | 428 | 15 |  | 0.035047
|  |  |  | Messenger Wire Pull | 933 | 875 |  | 0.93783
|  |  |  | Messenger Wire Tension | 47 | 10 |  | 0.21277
|  |  |  | # Cables Pulled | 252 | 88 |  | 0.34921
|  |  |  | Messenger Straps | 688 | 135 |  | 0.19622
66070 | 66000 | B3 | 4AV-7AV | Steel Mess Supports | 531 | 107 |  | 0.20151 | 0.52891
|  |  |  | Messenger Clamps | 940 | 538 |  | 0.57234
|  |  |  | Messenger Wire Pull | 26 | 4 |  | 0.15385
|  |  |  | Messenger Wire Tension | 868 | 456 |  | 0.52535
|  |  |  | # Cables Pulled | 458 | 342 |  | 0.74672
|  |  |  | Messenger Straps | 647 | 630 |  | 0.97372
60350 | 60000 | B1 | 15S-FOR | Steel Mess Supports | 380 | 329 |  | 0.86579 | 0.58177
|  |  |  | Messenger Clamps | 144 | 51 |  | 0.35417
|  |  |  | Messenger Wire Pull | 217 | 170 |  | 0.78341
|  |  |  | Messenger Wire Tension | 758 | 13 |  | 0.01715
|  |  |  | # Cables Pulled | 873 | 444 |  | 0.50859
|  |  |  | Messenger Straps | 26 | 25 |  | 0.96154
56440 | 56350 | B1 | FOR-CHU | Steel Mess Supports | 486 | 339 |  | 0.69753 | 0.50092
|  |  |  | Messenger Clamps | 495 | 176 |  | 0.35556
|  |  |  | Messenger Wire Pull | 270 | 24 |  | 0.088889
|  |  |  | Messenger Wire Tension | 204 | 138 |  | 0.67647
|  |  |  | # Cables Pulled | 499 | 487 |  | 0.97595
|  |  |  | Messenger Straps | 90 | 19 |  | 0.21111
55580 | 54500 | B2 | CHU-DIT | Steel Mess Supports | 814 | 20 |  | 0.02457 | 0.39649
|  |  |  | Messenger Clamps | 149 | 127 |  | 0.85235
|  |  |  | Messenger Wire Pull | 953 | 27 |  | 0.028332
|  |  |  | Messenger Wire Tension | 802 | 393 |  | 0.49002
|  |  |  | # Cables Pulled | 439 | 29 |  | 0.066059
|  |  |  | Messenger Straps | 631 | 579 |  | 0.91759
54730 | 55000 | B2 | CHU-DIT | Steel Mess Supports | 32 | 17 |  | 0.53125 | 0.41035
|  |  |  | Messenger Clamps | 139 | 66 |  | 0.47482
|  |  |  | Messenger Wire Pull | 623 | 501 |  | 0.80417
|  |  |  | Messenger Wire Tension | 483 | 209 |  | 0.43271
|  |  |  | # Cables Pulled | 526 | 67 |  | 0.12738
|  |  |  | Messenger Straps | 948 | 87 |  | 0.091772
55485 | 55725 | B2 | CHU-DIT | Steel Mess Supports | 824 | 548 |  | 0.66505 | 0.85791
|  |  |  | Messenger Clamps | 484 | 476 |  | 0.98347
|  |  |  | Messenger Wire Pull | 141 | 123 |  | 0.87234
|  |  |  | Messenger Wire Tension | 739 | 695 |  | 0.94046
|  |  |  | # Cables Pulled | 311 | 275 |  | 0.88424
|  |  |  | Messenger Straps | 535 | 429 |  | 0.80187
55725 | 56635 | B2 | CHURCH AVE | Steel Mess Supports | 651 | 615 |  | 0.9447 | 0.60915
|  |  |  | Messenger Clamps | 468 | 216 |  | 0.46154
|  |  |  | Messenger Wire Pull | 55 | 14 |  | 0.25455
|  |  |  | Messenger Wire Tension | 69 | 65 |  | 0.94203
|  |  |  | # Cables Pulled | 573 | 211 |  | 0.36824
|  |  |  | Messenger Straps | 465 | 318 |  | 0.68387
57320 | 57445 | B2 | CHU-FOR | Steel Mess Supports | 926 | 590 |  | 0.63715 | 0.5596
|  |  |  | Messenger Clamps | 469 | 197 |  | 0.42004
|  |  |  | Messenger Wire Pull | 426 | 338 |  | 0.79343
|  |  |  | Messenger Wire Tension | 935 | 391 |  | 0.41818
|  |  |  | # Cables Pulled | 311 | 85 |  | 0.27331
|  |  |  | Messenger Straps | 168 | 137 |  | 0.81548
60165 | 60620 | B2 | 15S-FOR | Steel Mess Supports | 395 | 197 |  | 0.49873 | 0.30475
|  |  |  | Messenger Clamps | 390 | 97 |  | 0.24872
|  |  |  | Messenger Wire Pull | 266 | 76 |  | 0.28571
|  |  |  | Messenger Wire Tension | 999 | 303 |  | 0.3033
|  |  |  | # Cables Pulled | 66 | 25 |  | 0.37879
|  |  |  | Messenger Straps | 927 | 105 |  | 0.11327
62560 | 63425 | B2 | 15TH STREET PROSPECT PARK | Steel Mess Supports | 450 | 383 |  | 0.85111 | 0.58615
|  |  |  | Messenger Clamps | 485 | 417 |  | 0.85979
|  |  |  | Messenger Wire Pull | 252 | 58 |  | 0.23016
|  |  |  | Messenger Wire Tension | 965 | 106 |  | 0.10984
|  |  |  | # Cables Pulled | 966 | 688 |  | 0.71222
|  |  |  | Messenger Straps | 398 | 300 |  | 0.75377
67950 | 68330 | B4/B2 | 4AV-7AV | Steel Mess Supports | 461 | 379 |  | 0.82213 | 0.59411
|  |  |  | Messenger Clamps | 576 | 24 |  | 0.041667
|  |  |  | Messenger Wire Pull | 899 | 811 |  | 0.90211
|  |  |  | Messenger Wire Tension | 423 | 389 |  | 0.91962
|  |  |  | # Cables Pulled | 533 | 17 |  | 0.031895
|  |  |  | Messenger Straps | 144 | 122 |  | 0.84722
74740 | 74840 | B2 | CAR-BER | Steel Mess Supports | 529 | 13 |  | 0.024575 | 0.46414
|  |  |  | Messenger Clamps | 893 | 761 |  | 0.85218
|  |  |  | Messenger Wire Pull | 765 | 748 |  | 0.97778
|  |  |  | Messenger Wire Tension | 446 | 143 |  | 0.32063
|  |  |  | # Cables Pulled | 481 | 40 |  | 0.08316
|  |  |  | Messenger Straps | 887 | 467 |  | 0.52649
75395 | 75650 | B2 | CAR-BER | Steel Mess Supports | 995 | 51 |  | 0.051256 | 0.30304
|  |  |  | Messenger Clamps | 574 | 226 |  | 0.39373
|  |  |  | Messenger Wire Pull | 395 | 129 |  | 0.32658
|  |  |  | Messenger Wire Tension | 792 | 461 |  | 0.58207
|  |  |  | # Cables Pulled | 852 | 333 |  | 0.39085
|  |  |  | Messenger Straps | 488 | 36 |  | 0.07377
78905 | 75950 | B3 | JAY-BER | Steel Mess Supports | 893 | 780 |  | 0.87346 | 0.53339
|  |  |  | Messenger Clamps | 899 | 161 |  | 0.17909
|  |  |  | Messenger Wire Pull | 526 | 289 |  | 0.54943
|  |  |  | Messenger Wire Tension | 424 | 257 |  | 0.60613
|  |  |  | # Cables Pulled | 583 | 533 |  | 0.91424
|  |  |  | Messenger Straps | 936 | 73 |  | 0.077991
75950 | 75650 | B3 | BERGEN ST | Steel Mess Supports | 600 | 330 |  | 0.55 | 0.60131
|  |  |  | Messenger Clamps | 137 | 104 |  | 0.75912
|  |  |  | Messenger Wire Pull | 88 | 81 |  | 0.92045
|  |  |  | Messenger Wire Tension | 905 | 597 |  | 0.65967
|  |  |  | # Cables Pulled | 655 | 268 |  | 0.40916
|  |  |  | Messenger Straps | 530 | 164 |  | 0.30943
75650 | 75420 | B3 | BER-CAR | Steel Mess Supports | 444 | 185 |  | 0.41667 | 0.53681
|  |  |  | Messenger Clamps | 149 | 110 |  | 0.73826
|  |  |  | Messenger Wire Pull | 422 | 249 |  | 0.59005
|  |  |  | Messenger Wire Tension | 845 | 430 |  | 0.50888
|  |  |  | # Cables Pulled | 280 | 23 |  | 0.082143
|  |  |  | Messenger Straps | 139 | 123 |  | 0.88489
73285 | 72960 | B3 | BER-CAR | Steel Mess Supports | 670 | 93 |  | 0.13881 | 0.38379
|  |  |  | Messenger Clamps | 24 | 18 |  | 0.75
|  |  |  | Messenger Wire Pull | 188 | 31 |  | 0.16489
|  |  |  | Messenger Wire Tension | 897 | 34 |  | 0.037904
|  |  |  | # Cables Pulled | 859 | 268 |  | 0.31199
|  |  |  | Messenger Straps | 347 | 312 |  | 0.89914
72960 | 72035 | B3/B4 | CAR-4TH | Steel Mess Supports | 228 | 96 |  | 0.42105 | 0.40879
|  |  |  | Messenger Clamps | 445 | 340 |  | 0.76404
|  |  |  | Messenger Wire Pull | 397 | 46 |  | 0.11587
|  |  |  | Messenger Wire Tension | 940 | 779 |  | 0.82872
|  |  |  | # Cables Pulled | 146 | 26 |  | 0.17808
|  |  |  | Messenger Straps | 683 | 99 |  | 0.14495
71150 | 70965 | B3/B4 | CAR-4TH | Steel Mess Supports | 183 | 171 |  | 0.93443 | 0.66668
|  |  |  | Messenger Clamps | 520 | 227 |  | 0.43654
|  |  |  | Messenger Wire Pull | 538 | 259 |  | 0.48141
|  |  |  | Messenger Wire Tension | 930 | 388 |  | 0.4172
|  |  |  | # Cables Pulled | 847 | 671 |  | 0.79221
|  |  |  | Messenger Straps | 778 | 730 |  | 0.9383
70965 | 70445 | B3/B6 | CAR-4TH | Steel Mess Supports | 465 | 334 |  | 0.71828 | 0.47416
|  |  |  | Messenger Clamps | 287 | 167 |  | 0.58188
|  |  |  | Messenger Wire Pull | 575 | 292 |  | 0.50783
|  |  |  | Messenger Wire Tension | 740 | 523 |  | 0.70676
|  |  |  | # Cables Pulled | 349 | 84 |  | 0.24069
|  |  |  | Messenger Straps | 402 | 36 |  | 0.089552
70445 | 70045 | B3/B7 | CAR-4TH | Steel Mess Supports | 268 | 131 |  | 0.48881 | 0.65881
|  |  |  | Messenger Clamps | 794 | 353 |  | 0.44458
|  |  |  | Messenger Wire Pull | 499 | 355 |  | 0.71142
|  |  |  | Messenger Wire Tension | 14 | 14 |  | 1
|  |  |  | # Cables Pulled | 478 | 409 |  | 0.85565
|  |  |  | Messenger Straps | 84 | 38 |  | 0.45238
68625 | 68400 | B3/B8 | CAR-4TH | Steel Mess Supports | 890 | 49 |  | 0.055056 | 0.39825
|  |  |  | Messenger Clamps | 612 | 412 |  | 0.6732
|  |  |  | Messenger Wire Pull | 259 | 145 |  | 0.55985
|  |  |  | Messenger Wire Tension | 259 | 124 |  | 0.47876
|  |  |  | # Cables Pulled | 480 | 63 |  | 0.13125
|  |  |  | Messenger Straps | 696 | 342 |  | 0.49138
68400 | 68330 | B3/B9 | CAR-4TH | Steel Mess Supports | 73 | 15 |  | 0.20548 | 0.56015
|  |  |  | Messenger Clamps | 59 | 42 |  | 0.71186
|  |  |  | Messenger Wire Pull | 900 | 329 |  | 0.36556
|  |  |  | Messenger Wire Tension | 250 | 75 |  | 0.3
|  |  |  | # Cables Pulled | 81 | 65 |  | 0.80247
|  |  |  | Messenger Straps | 613 | 598 |  | 0.97553

## AXLE COUNTER
Stationing | Track No | Location | Activity | Date | Progress | General Progress | Notes | DWG REF.
54600 | B1 | DIT-CHU | Axle Counter Installation |  | 0% | 0% | STATIONING SHOWN IS THAT OF THE NEAREST IJ, AXC STATIONING DOES NOT EXIST | B1-546
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B1 |  | Axle Counter Installation |  | 0% | 0% | NO INFO | B1-547
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
59297 | B1 | FOR-15S | Axle Counter Installation |  | 0% | 0% |  | B1-553
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B1 |  | Axle Counter Installation |  | 0% | 0% | NO INFO | B1-554
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
55687 | B1 | DIT-CHU | Axle Counter Installation |  | 0% | 0% |  | B1-557
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
56367 | B1 | CHU-FOR | Axle Counter Installation |  | 0% | 0% |  | B1-564
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
58524.6 | B1 | FORT HAMILTON PARKWAY | Axle Counter Installation |  | 0% | 0% |  | B1-585
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
59210.25 | B1 | FOR-15S | Axle Counter Installation |  | 0% | 0% |  | B1-592
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
62572.5 | B1 | FOR-15S | Axle Counter Installation |  | 0% | 0% |  | B1-626
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
63251.4 | B1 | 15S-7AV | Axle Counter Installation |  | 0% | 0% |  | B1-632
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
65387.3 | B1 | 15S-7AV | Axle Counter Installation |  | 0% | 0% |  | B1-654
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
66076 | B1 | 7AV-4TH | Axle Counter Installation |  | 0% | 0% |  | B1-661
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
73206.7 | B1 | SMI-CAR | Axle Counter Installation |  | 0% | 0% |  | B1-732
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
73932 | B1 | CAR-BER | Axle Counter Installation |  | 0% | 0% |  | B1-739
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
75408 | B1 | CAR-BER | Axle Counter Installation |  | 0% | 0% |  | B1-755
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
75669 | B1 | CAR-BER | Axle Counter Installation |  | 0% | 0% |  | B1-756
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
76352 | B1 | BER-HOY | Axle Counter Installation |  | 0% | 0% |  | B1-763, B1-764
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
76589 | B1 | HOYT-SCHERMERHORN | Axle Counter Installation |  | 0% | 0% |  | B1-766
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
76901.5 | B1 | HOY-FUL | Axle Counter Installation |  | 0% | 0% |  | B1-770
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
77088 | B1 | FUL-CLI | Axle Counter Installation |  | 0% | 0% |  | B1-771
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
54737 | B2 | DIT-CHU | Axle Counter Installation |  | 0% | 0% |  | B2-546
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
54731 | B2 |  | Axle Counter Installation |  | 0% | 0% |  | B2-547
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
55000 | B2 | DIT-CHU | Axle Counter Installation |  | 0% | 0% |  | B2-549
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
55498 | B2 | DIT-CHU | Axle Counter Installation |  | 0% | 0% |  | B2-554
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B2 |  | Axle Counter Installation |  | 0% | 0% | NO REF DWG EXISTS | B2-555
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B2 |  | Axle Counter Installation |  | 0% | 0% | NO REF DWG EXISTS | B2-556
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
55857 | B2 | CHURCH AVE | Axle Counter Installation |  | 0% | 0% |  | B2-558
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
58500 | B2 | FORT HAMILTON PARKWAY | Axle Counter Installation |  | 0% | 0% |  | B2-585
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
59203.8 | B2 | FOR-15S | Axle Counter Installation |  | 0% | 0% |  | B2-592
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
62550.6 | B2 |  | Axle Counter Installation |  | 0% | 0% |  | B2-625
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
65375.3 | B2 | 15S-7AV | Axle Counter Installation |  | 0% | 0% |  | B2-654
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
66062.3 | B2 | 7AV-4TH | Axle Counter Installation |  | 0% | 0% |  | B2-661
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B2 |  | Axle Counter Installation |  | 0% | 0% | NO REF DWG EXISTS | B2-665
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B2 |  | Axle Counter Installation |  | 0% | 0% | NO REF DWG EXISTS | B2-684
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B2 |  | Axle Counter Installation |  | 0% | 0% | NO REF DWG EXISTS | B2-691
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B2 |  | Axle Counter Installation |  | 0% | 0% | NO REF DWG EXISTS | B2-692
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B2 |  | Axle Counter Installation |  | 0% | 0% | NO REF DWG EXISTS | B2-692A
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B2 |  | Axle Counter Installation |  | 0% | 0% | NO REF DWG EXISTS | B2-693
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B2 |  | Axle Counter Installation |  | 0% | 0% | NO REF DWG EXISTS | B2-705
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B2 |  | Axle Counter Installation |  | 0% | 0% | NO REF DWG EXISTS | B2-712
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B2 |  | Axle Counter Installation |  | 0% | 0% | DWG EXISTS, BUT EMPTY | B2-732
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
73926.3 | B2 | CARROLL STREET | Axle Counter Installation |  | 0% | 0% |  | B2-739
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
75267 | B2 | CAR-BER | Axle Counter Installation |  | 0% | 0% |  | B2-753
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B2 |  | Axle Counter Installation |  | 0% | 0% | NO REF DWG EXISTS | B2-755
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
75646 | B2 | CAR-BER | Axle Counter Installation |  | 0% | 0% |  | B2-756
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
76352 | B2 |  | Axle Counter Installation |  | 0% | 0% |  | B2-763, B2-764
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
76536 | B2 |  | Axle Counter Installation |  | 0% | 0% |  | B2-765
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
76797 | B2 |  | Axle Counter Installation |  | 0% | 0% |  | B2-768
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
77116 | B2 |  | Axle Counter Installation |  | 0% | 0% |  | B2-770
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B3 |  | Axle Counter Installation |  | 0% | 0% | REF DWG EXISTS, NO STATIONINGS SHOWN | B3-546
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B3 |  | Axle Counter Installation |  | 0% | 0% | REF DWG EXISTS, NO STATIONINGS SHOWN | B3-548
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
53361 | B3 |  | Axle Counter Installation |  | 0% | 0% |  | B3-554
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
55626 | B3 |  | Axle Counter Installation |  | 0% | 0% |  | B3-555
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B3 |  | Axle Counter Installation |  | 0% | 0% | REF DWG EXISTS, NO STATIONINGS SHOWN | B3-556
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B3 |  | Axle Counter Installation |  | 0% | 0% | REF DWG EXISTS, NO STATIONINGS SHOWN | B3-557
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B3 |  | Axle Counter Installation |  | 0% | 0% | NO REF DWG EXISTS | B3-565
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
65384.6 | B3 |  | Axle Counter Installation |  | 0% | 0% |  | B3-654
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
66073.4 | B3 |  | Axle Counter Installation |  | 0% | 0% |  | B3-661
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B3 |  | Axle Counter Installation |  | 0% | 0% | NO REF DWG EXISTS | B3-689
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B3 |  | Axle Counter Installation |  | 0% | 0% | NO REF DWG EXISTS | B3-690
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B3 |  | Axle Counter Installation |  | 0% | 0% | NO REF DWG EXISTS | B3-691
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B3 |  | Axle Counter Installation |  | 0% | 0% | NO REF DWG EXISTS | B3-692
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B3 |  | Axle Counter Installation |  | 0% | 0% | NO REF DWG EXISTS | B3-693
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B3 |  | Axle Counter Installation |  | 0% | 0% | NO REF DWG EXISTS | B3-694
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B3 |  | Axle Counter Installation |  | 0% | 0% | NO REF DWG EXISTS | B3-695
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B3 |  | Axle Counter Installation |  | 0% | 0% | NO REF DWG EXISTS | B3-696
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
75405 | B3 |  | Axle Counter Installation |  | 0% | 0% |  | B3-754
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B3 |  | Axle Counter Installation |  | 0% | 0% | NO REF DWG EXISTS | B3-755
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
75405 | B3 |  | Axle Counter Installation |  | 0% | 0% |  | B3-756
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
76383 | B3 |  | Axle Counter Installation |  | 0% | 0% |  | B3-764
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
76920 | B3 |  | Axle Counter Installation |  | 0% | 0% |  | B3-769
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B4 |  | Axle Counter Installation |  | 0% | 0% | REF DWG EXISTS, NO STATIONINGS SHOWN | B4-547
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B4 |  | Axle Counter Installation |  | 0% | 0% | REF DWG EXISTS, NO STATIONINGS SHOWN | B4-551
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
| B4 |  | Axle Counter Installation |  | 0% | 0% | NO REF DWG EXISTS, AWAITING RESPONSE FROM THALES ON WHETHER THIS AXC WILL BE INSTALLED | B4-554A, B4-554B
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
55533 | B4 |  | Axle Counter Installation |  | 0% | 0% |  | B4-555
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
55685 | B4 |  | Axle Counter Installation |  | 0% | 0% |  | B4-556
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%
56396.5 | B4 |  | Axle Counter Installation |  | 0% | 0% |  | B4-564
|  |  | JB Installation |  | 0%
|  |  | Line Cable Installation |  | 0%
|  |  | Express Cable Installation |  | 0%
|  |  | Pre-Operation Testing |  | 0%

## SIGNALS
Stationing | Track No | Signal Type | Location | Activity | Date | Progress | General Progress | Notes
74076 | E1 | APPROACH |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
98643 | E1 | HOME |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
98903 | E1 | HOME |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
100068 | E1 | HOME |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
106031 | E1 | APPROACH |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
113852 | E1 | HOME |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
114110 | E1 | HOME |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
114869 | E1 | HOME |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
119024 | E1 | APPROACH |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
119485 | E1 | APPROACH |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
| E1 | APPROACH |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
121810 | E1 | HOME |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
122198 | E1 | HOME |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
122570 | E1 | HOME |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
122987 | E1 | HOME |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
123669 | D1 | HOME |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
73318 | E2 | APPROACH |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
98565 | E2 | HOME |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
99593 | E2 | HOME |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
99970 | E2 | HOME |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
106749 | E2 | APPROACH |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
112529 | E2 | HOME |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
113850 | E2 | HOME |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
118065 | E2 | APPROACH |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
119215 | E2 | APPROACH |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
123687 | D2 | HOME |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
124043 | D2 | HOME |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
99806 | E3 | HOME |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
100019 | E3 | HOME |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
99592 | E4 | HOME |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
122071 | E5 | HOME |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
122687 | E5 | HOME |  | Signal Installation |  | 0 | 0 | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0
|  |  |  | Stop Machine Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0

## SWITCH
Name | Stationing | Track No | Location | Activity | Date | Progress | General Progress | Notes
B331 | 76395 | B1 |  | Switch Machine Installation |  | 0 | 0
|  |  |  | Switch JB Installation |  | 0
|  |  |  | Switch Cable Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
B325 | 76395 | E2 |  | Switch Machine Installation |  | 0 | 0
|  |  |  | Switch JB Installation |  | 0
|  |  |  | Switch Cable Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
633A | 99999 | E1 |  | Switch Machine Installation |  | 0 | 0
|  |  |  | Switch JB Installation |  | 0
|  |  |  | Switch Cable Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
633B | 98900 | E3-4 |  | Switch Machine Installation |  | 0 | 0
|  |  |  | Switch JB Installation |  | 0
|  |  |  | Switch Cable Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
625A | 98808 | E3-4 |  | Switch Machine Installation |  | 0 | 0
|  |  |  | Switch JB Installation |  | 0
|  |  |  | Switch Cable Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
625B | 99949 | E2 |  | Switch Machine Installation |  | 0 | 0
|  |  |  | Switch JB Installation |  | 0
|  |  |  | Switch Cable Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
663 | 99628 | E3-4 |  | Switch Machine Installation |  | 0 | 0
|  |  |  | Switch JB Installation |  | 0
|  |  |  | Switch Cable Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
673A | 99999 | E1 |  | Switch Machine Installation |  | 0 | 0
|  |  |  | Switch JB Installation |  | 0
|  |  |  | Switch Cable Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
673B | 99826 | E3 |  | Switch Machine Installation |  | 0 | 0
|  |  |  | Switch JB Installation |  | 0
|  |  |  | Switch Cable Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
651A | 99761 | E4 |  | Switch Machine Installation |  | 0 | 0
|  |  |  | Switch JB Installation |  | 0
|  |  |  | Switch Cable Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
651B | 99949 | E2 |  | Switch Machine Installation |  | 0 | 0
|  |  |  | Switch JB Installation |  | 0
|  |  |  | Switch Cable Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
757A | 113880 | E1 |  | Switch Machine Installation |  | 0 | 0
|  |  |  | Switch JB Installation |  | 0
|  |  |  | Switch Cable Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
757B | 114010 | E2 |  | Switch Machine Installation |  | 0 | 0
|  |  |  | Switch JB Installation |  | 0
|  |  |  | Switch Cable Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
753A | 114010 | E1 |  | Switch Machine Installation |  | 0 | 0
|  |  |  | Switch JB Installation |  | 0
|  |  |  | Switch Cable Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
753B | 113880 | E2 |  | Switch Machine Installation |  | 0 | 0
|  |  |  | Switch JB Installation |  | 0
|  |  |  | Switch Cable Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
825 |  | E1 |  | Switch Machine Installation |  | 0 | 0 | Stationing missing
|  |  |  | Switch JB Installation |  | 0
|  |  |  | Switch Cable Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
815A | 121995 | E5 |  | Switch Machine Installation |  | 0 | 0
|  |  |  | Switch JB Installation |  | 0
|  |  |  | Switch Cable Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
815B | 121831 | E2 |  | Switch Machine Installation |  | 0 | 0
|  |  |  | Switch JB Installation |  | 0
|  |  |  | Switch Cable Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
851B | 122757 | E5 |  | Switch Machine Installation |  | 0 | 0
|  |  |  | Switch JB Installation |  | 0
|  |  |  | Switch Cable Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
851A | 122923 | E1 |  | Switch Machine Installation |  | 0 | 0
|  |  |  | Switch JB Installation |  | 0
|  |  |  | Switch Cable Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
841 | 122923 | E2 |  | Switch Machine Installation |  | 0 | 0
|  |  |  | Switch JB Installation |  | 0
|  |  |  | Switch Cable Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0
753B | 113880 | E2 |  | Switch Machine Installation |  | 0 | 0
|  |  |  | Switch JB Installation |  | 0
|  |  |  | Switch Cable Installation |  | 0
|  |  |  | Line Cable Installation |  | 0
|  |  |  | Breakdown Testing |  | 0
|  |  |  | Pre-Operation Testing |  | 0

## WRU
Stationing | Track No | Location | Activity | Date | Progress | General Progress | Notes
54000 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
54000 | B3 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
54000 | B4 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
54000 | B2 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
54000 | B5 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
55500 | B2 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
55500 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
56300 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
56500 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
57200 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
57400 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
58300 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
58400 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
59400 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
59700 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
60500 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
60800 | B2 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
60800 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
61900 | B2 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
61900 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
62300 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
63200 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
63300 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
64200 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
64300 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
65200 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
65200 | B2 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
66300 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
66300 | B2 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
67500 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
67500 | B2 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
68300 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
68300 | B2 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
69900 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
71400 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
73000 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
73000 | B2 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
74100 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
75300 | B1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
75300 | B2 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
88300 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
88600 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
90800 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
92400 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
93600 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
95000 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
96500 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
98200 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
99700 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
99700 | E2 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
100400 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
100600 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
101500 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
102600 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
103800 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
104700 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
105900 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
106900 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
108300 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
109900 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
111100 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
112200 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
113000 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
114300 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
115500 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
116900 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
118300 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
118300 | E2 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
119500 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
119500 | E2 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
120800 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
120800 | E2 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
121900 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
122800 | E1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
123900 | D1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
124900 | D1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
125900 | D1 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
123900 | D2 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
124900 | D2 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0
125900 | D2 |  | Radio Unit Installation |  | 0 | 0 | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0
|  |  | Fiber Box Installation |  | 0
|  |  | Antenna Installation |  | 0
|  |  | Antenna Cable Installation |  | 0
|  |  | Splitter Installation |  | 0
|  |  | Fiber Cable Splicing |  | 0
|  |  | Fiber Testing |  | 0
|  |  | Power Testing |  | 0

## Z-CASE
Stationing | Track No | Location | Activity | Date | Progress | General Progress | Notes
|  |  | CASE Install |  |  |  | Z-CASE IS BY E1-986 (Z)
Cable Connection/Termination
Pre-Op testing
|  |  | CASE Install |  |  |  | Z-CASE IS BY E1-1006 (Z)
Cable Connection/Termination
Pre-Op testing
|  |  | CASE Install |  |  |  | Z-CASE IS BY E1-1030 (Z)
Cable Connection/Termination
Pre-Op testing
|  |  | CASE Install |  |  |  | Z-CASE IS BY E1-1068 (Z)
Cable Connection/Termination
Pre-Op testing
115725 | E1 |  | CASE Install |  |  |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
Cable Connection/Termination
Pre-Op testing
121810 | E1 |  | CASE Install |  |  |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
Cable Connection/Termination
Pre-Op testing
| E1 |  | CASE Install |  |  |  | Z-CASE IS BY E1-1229 (Z)
Cable Connection/Termination
Pre-Op testing
| E1 |  | CASE Install |  |  |  | Z-CASE IS BY E1-1230 (Z)
Cable Connection/Termination
Pre-Op testing
98565 | E2 |  | CASE Install |  |  |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
Cable Connection/Termination
Pre-Op testing
114869 | E2 |  | CASE Install |  |  |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
Cable Connection/Termination
Pre-Op testing
| E2 |  | CASE Install |  |  |  | Z-CASE IS BY E2-1230(Z)
Cable Connection/Termination
Pre-Op testing
122071 | E5 |  | CASE Install |  |  |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
Cable Connection/Termination
Pre-Op testing
122687 | E5 |  | CASE Install |  |  |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
Cable Connection/Termination
Pre-Op testing

## TOPB
Stationing | Track No | Location | Activity | Date | Progress | General Progress | Notes
121810 | E1 |  | TOPB Install |  |  |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
Cable Connection/Termination
Pre-Op testing
122987 | E1 |  | TOPB Install |  |  |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
Cable Connection/Termination
Pre-Op testing
|  |  | TOPB Install |  |  |  | TOPB @ ~D1-1239
Cable Connection/Termination
Pre-Op testing
121809 | E2 |  | TOPB Install |  |  |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
Cable Connection/Termination
Pre-Op testing
122970 | E2 |  | TOPB Install |  |  |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
Cable Connection/Termination
Pre-Op testing
124043 | D2 |  | TOPB Install |  |  |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
Cable Connection/Termination
Pre-Op testing

## Report Screenshot
Tasks | Total Quantity | Installed/Tested Quantity
Acceptance Test (Ea) | 29 | 3
Antenna Cable (ft) | 61885 | 58432
Brackets (Ea) | 12147 | 11856
Coax Cable (Ea) | 59 | 59
Insertion Loss (Segment) (ft) | 47445 | 43615
Removals (ft) | 30946 | 2380
Coupler Plates | 27 | 27
DC Resistance (Segment) | 47410 | 43580
Megger (Segment) | 47445 | 43615
VSWR (Segment) | 47445 | 43615
End-To-End | 47445 | 33565
Heat Map Test | 47445 | 29175
Coverage Test/Survey | 47445 | 3160
Megger Coax Cable (Reel) | 4000 | 4000
Megger Antenna Cable (Reel) | 80000 | 80000
Megger 1/2in Cable (Reel) | 100 | 100
DC Resistance Coax Cable (Reel) | 4000 | 4000
DC Resistance Antenna Cable (Reel) | 80000 | 80000
DC Resistance 1/2in Cable (Reel) | 100 | 100

## Dashboard
RADIO INSTALLATION DASHBOARD
OVERALL TASK COMPLETION (ALL TRACKS)
TASK PERCENT COMPLETION (PER TRACK)
OVERALL INSTALLATION PROGRESS PER TRACK SECTION
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.