## Reference
Track No. | Column Side | Activities | Bracket Type | Station | Track Stationing | Tunnel | Description | Track Stationing | Notes
B1 | W | Steel Messenger Supports | 1 | Church Avenue | 556+96 to 563+56 | CHU-FOR | Church Ave to Fort Hamilton | 563+56 to 584+88
B2 | E | Messenger Clamps | 2 | Fort Hamilton Parkway | 584+88 to 591+90 | FOR-15S | Fort Hamilton to 15th Street | 591+90 to 625+70
B3 | W | Messenger Wire Pull | 3 | 15th Street Prospect Park | 625+70 to 632+30 | 15S-7AV | 15th Street to 7th Avenue | 632+30 to 653+96
B4 | E | Messenger Wire Tension | 4 | 7th Avenue | 653+96 to 660+56 | 7AV-4TH | 7th Avenue to 4th & 9th Street | 660+56-683+83
E1 | W | Cable Pull | 4A | 4th & 9th Street | 683+83 to 690+91 | 4TH-SMI | 4th & 9th Street to Smith & 9th Street | 690+91 to 705+11
E2 | E | Messenger Straps | 5 | Smith & 9th Street | 705+11 to 712+32 | SMI-CAR | Smith & 9th Street to Carroll Street | 712+32 to 732+89
E3 |  | 15inch CMRS |  | Carroll Street | 732+39 to 738+99 | CAR-BER | Carroll Street to Bergen Street | 738+99 to 756+82
E4 |  | 24inch CMRS |  | Bergen Street | 756+82 to 763+42 | BER-HOY | Bergen Street to Hoyt Schermerhorn | 763+42 to 761+84 | track goes from 768+XX to 693+95
E5 |  | Column mount CMRS |  | Hoyt Schermerhorn | 761+84 to 768+87 | HOY-FUL | Hoyt Schermerhorn to Fulton | 768+87 to 740+30
|  | Station Brackets |  | Fulton Street | 740+30 to 733+70 | FUL-CLI | Fulton to Clinton Washington | 733+70 to 951+82 | track goes from 733+15 to 934+96
Location |  | Grounding |  | Clinton Washington Avenue | 951+82 to 958+42 | CLI-CLA | Clinton Washington to Classon | 958+42 to 970+82
Church Avenue |  | Obstruction Brackets |  | Classon Avenue | 970+82 to 977+42 | CLA-BED | Classon to Bedford Nostand | 977+42 to 989+22
CHU-FOR |  | Cable Pull |  | Bedford Nostrand Avenue | 989+22 to 995+82 | BED-MYR | Bedford Nostrand to Myrtle Willoughby | 995+82 to 1017+47
Fort Hamilton Parkway |  | Cable Tray Brackets |  | Myrtle Willoughby Ave | 1017+47 to 1024+52 | MYR-FLU | Myrtle Willoughby to Flushing Avenue | 1024+52 to 1039+42
FOR-15S |  | Installing Tray |  | Flushing Avenue Station | 1039+42 to 1046+20 | FLU-BRO | Flushing Avenue to Broadway | 1046+20 to 1060+52
15th Street Prospect Park |  | Core Drilling |  | Broadway | 1060+52 to 1067+12 | BRO-MET | Broadway to Metropolitan | 1067+12 to 1132+45
15S-7AV |  | Cable Pull |  | Metropolitan Avenue | 1132+45 to 1139+50 | MET-NAS | Metropolitan to Nassau | 1139+50 to 1131+52
7th Avenue |  | Arch Bar Installation |  | Nassau Avenue | 1131+52 to 1138+32 | NAS-GRE | Nassau to Greenpoint | 1138+32 to 1157+00
7AV-4TH |  |  |  | Greenpoint Avenue | 1157+00 to 1164+32 | GRE-21S | Greenpoint to 21 St | 1164+32 to 1211+33
4th & 9th Street |  |  |  | 21 St Station | 1211+33 to 1217+92 | 21S-COU | 21 St to Court Square | 1217+92 to 1229+23
4TH-SMI |  |  |  | Court Square | 1229+23 to 1236+66 | COU-QUE | Court Square to Queens Plaza | 1236+66 to 1250+65
Smith & 9th Street |  |  |  | Queens Plaza | 1250+65 to 1257+27
SMI-CAR
Carroll Street |  |  |  | Signal Types
CAR-BER |  |  |  | HOME
Bergen Street* |  |  |  | APPROACH
BER-HOY |  |  |  | BUMPER
Hoyt Schermerhorn |  |  |  | REV. HOME
HOY-FUL |  |  |  | REV. APPROACH
Fulton Street
FUL-CLI
Clinton Washington Avenue
CLI-CLA
Classon Avenue
CLA-BED
Bedford Nostrand Avenue
BED-MYR
Myrtle Willoughby Ave
MYR-FLU
Flushing Avenue Station
FLU-BRO
Broadway
BRO-MET
Metropolitan Avenue
MET-NAS
Nassau Avenue
NAS-GRE
Greenpoint Avenue
GRE-21S
21 St Station
21S-COU
Court Square
COU-QUE
Queens Plaza

## Work Sheet (hidden)
OVERALL INSTALLATION PER AREA
Status | Count
Not Started | #REF!
In Progress | #REF!
Completed | #REF!
Remaining | #REF!
Total Tasks | #REF!
Completed Sections | #REF!
Remaining Sections | #REF!

## Ref Activity Bar (hidden)
RADIO INSTALLATION DASHBOARD
TRACK | C3/C4
TASK | COMPLETION PROGRESS
Removals | 12.5%
Grand Total | 12.5%

## Ref Progress per Activity (hidden)
TASK | Acceptance Test
|  | Not Started | 0 | Completed Sections | 13.04%
TRACK | Average of PROGRESS | In Progress | 0 | Remaining Sections | 86.96%
C1 | 16.67% | Completed | 0
C2 | 16.67%
C3 | 0%
C3/C4 | 14.29%
C4 | 0%
C5 | 0%
C6 | 0%
Grand Total | 13.04%

## CMRS
Start | Finish | Track No | Location | Activity | Total Quantity | QTY Installed | Date | Progress | General Progress | Notes | Notes
124510 | 124500 | D1 | COU-QUE | Steel Mess Supports | 798 | 148 |  | 0.18546 | 0.38668
|  |  |  | Messenger Clamps | 687 | 578 |  | 0.84134
|  |  |  | Messenger Wire Pull | 97 | 35 |  | 0.36082
|  |  |  | Messenger Wire Tension | 941 | 450 |  | 0.47821
|  |  |  | # Cables Pulled | 60 | 20 |  | 0.33333
|  |  |  | Messenger Straps | 91 | 11 |  | 0.12088
124500 | 124320 | D1 | COU-QUE | Steel Mess Supports | 50 | 44 |  | 0.88 | 0.77518
|  |  |  | Messenger Clamps | 688 | 290 |  | 0.42151
|  |  |  | Messenger Wire Pull | 630 | 430 |  | 0.68254
|  |  |  | Messenger Wire Tension | 476 | 430 |  | 0.90336
|  |  |  | # Cables Pulled | 354 | 352 |  | 0.99435
|  |  |  | Messenger Straps | 828 | 637 |  | 0.76932
124320 | 124100 | D1 | COU-QUE | Steel Mess Supports | 71 | 58 |  | 0.8169 | 0.55371
|  |  |  | Messenger Clamps | 195 | 54 |  | 0.27692
|  |  |  | Messenger Wire Pull | 576 | 451 |  | 0.78299
|  |  |  | Messenger Wire Tension | 536 | 224 |  | 0.41791
|  |  |  | # Cables Pulled | 541 | 325 |  | 0.60074
|  |  |  | Messenger Straps | 321 | 137 |  | 0.42679
124100 | 123970 | D1 | COU-QUE | Steel Mess Supports | 839 | 190 |  | 0.22646 | 0.4987
|  |  |  | Messenger Clamps | 830 | 434 |  | 0.52289
|  |  |  | Messenger Wire Pull | 304 | 262 |  | 0.86184
|  |  |  | Messenger Wire Tension | 983 | 98 |  | 0.099695
|  |  |  | # Cables Pulled | 789 | 563 |  | 0.71356
|  |  |  | Messenger Straps | 701 | 398 |  | 0.56776
123970 | 123930 | D1 | COU-QUE | 15" CMRS Install | 194 | 88 |  | 0.45361 | 0.35993
|  |  |  | Column Clamp | 736 | 132 |  | 0.17935
|  |  |  | Station Brackets | 371 | 141 |  | 0.38005
|  |  |  | Grounding | 581 | 239 |  | 0.41136
|  |  |  | Obstruction Brackets | 815 | 433 |  | 0.53129
|  |  |  | # Cables Pulled | 358 | 73 |  | 0.20391
123930 | 123715 | D1 | COU-QUE | 15" CMRS Install | 736 | 507 |  | 0.68886 | 0.32893
|  |  |  | Column Clamp | 279 | 51 |  | 0.1828
|  |  |  | Station Brackets | 976 | 351 |  | 0.35963
|  |  |  | Grounding | 405 | 271 |  | 0.66914
|  |  |  | Obstruction Brackets | 832 | 14 |  | 0.016827
|  |  |  | # Cables Pulled | 213 | 12 |  | 0.056338
|  | D1 | COU-QUE | Crossover (Arch Bar Installation) | 810 | 482 |  | 0.59506
122975 | 122827 | E1 | 21S-COU | Steel Mess Supports | 485 | 268 |  | 0.55258 | 0.53509
|  |  |  | Messenger Clamps | 112 | 39 |  | 0.34821
|  |  |  | Messenger Wire Pull | 394 | 251 |  | 0.63706
|  |  |  | Messenger Wire Tension | 764 | 279 |  | 0.36518
|  |  |  | # Cables Pulled | 927 | 803 |  | 0.86624
|  |  |  | Messenger Straps | 954 | 421 |  | 0.4413
122827 | 122250 | E1 | 21S-COU | 24" CMRS Install | 69 | 19 |  | 0.27536 | 0.27391
|  |  |  | Column Clamp | 333 | 16 |  | 0.048048
|  |  |  | Station Brackets | 639 | 81 |  | 0.12676
|  |  |  | Grounding | 26 | 2 |  | 0.076923
|  |  |  | Obstruction Brackets | 523 | 522 |  | 0.99809
|  |  |  | # Cables Pulled | 685 | 81 |  | 0.11825
122250 | 121833 | E1 | 21S-COU | Steel Mess Supports | 776 | 49 |  | 0.063144 | 0.40806
|  |  |  | Messenger Clamps | 187 | 17 |  | 0.090909
|  |  |  | Messenger Wire Pull | 284 | 63 |  | 0.22183
|  |  |  | Messenger Wire Tension | 785 | 694 |  | 0.88408
|  |  |  | # Cables Pulled | 977 | 242 |  | 0.2477
|  |  |  | Messenger Straps | 894 | 841 |  | 0.94072
121833 | 121030 | E1 | 21 STREET | Steel Mess Supports | 958 | 515 |  | 0.53758 | 0.43106
|  |  |  | Messenger Clamps | 806 | 486 |  | 0.60298
|  |  |  | Messenger Wire Pull | 129 | 50 |  | 0.3876
|  |  |  | Messenger Wire Tension | 410 | 217 |  | 0.52927
|  |  |  | # Cables Pulled | 153 | 8 |  | 0.052288
|  |  |  | Messenger Straps | 986 | 470 |  | 0.47667
121030 | 117010 | E1 | GRE-21S | 15" CMRS Install | 588 | 349 |  | 0.59354 | 0.55929
|  |  |  | Column Clamp | 766 | 432 |  | 0.56397
|  |  |  | Station Brackets | 681 | 145 |  | 0.21292
|  |  |  | Grounding | 429 | 308 |  | 0.71795
|  |  |  | Obstruction Brackets | 946 | 833 |  | 0.88055
|  |  |  | # Cables Pulled | 212 | 82 |  | 0.38679
117010 | 116810 | E1 | GRE-21S | 15" CMRS Install | 886 | 110 |  | 0.12415 | 0.31393
|  |  |  | Column Clamp | 691 | 387 |  | 0.56006
|  |  |  | Station Brackets | 596 | 20 |  | 0.033557
|  |  |  | Grounding | 205 | 36 |  | 0.17561
|  |  |  | Obstruction Brackets | 895 | 532 |  | 0.59441
|  |  |  | # Cables Pulled | 758 | 300 |  | 0.39578
116810 | 116471 | E1 | GRE-21S | 15" CMRS Install | 602 | 50 |  | 0.083056 | 0.62926
|  |  |  | Column Clamp | 464 | 224 |  | 0.48276
|  |  |  | Station Brackets | 900 | 709 |  | 0.78778
|  |  |  | Grounding | 777 | 695 |  | 0.89447
|  |  |  | Obstruction Brackets | 557 | 526 |  | 0.94434
|  |  |  | # Cables Pulled | 415 | 242 |  | 0.58313
116471 | 115694 | E1 | GREENPOINT | 24" CMRS Install | 253 | 17 |  | 0.067194 | 0.58602
|  |  |  | Column Clamp | 930 | 835 |  | 0.89785
|  |  |  | Station Brackets | 55 | 22 |  | 0.4
|  |  |  | Grounding | 435 | 383 |  | 0.88046
|  |  |  | Obstruction Brackets | 56 | 38 |  | 0.67857
|  |  |  | # Cables Pulled | 853 | 505 |  | 0.59203
115694 | 115628 | E1 | NAS-GRE | 24" CMRS Install | 507 | 188 |  | 0.37081 | 0.72479
|  |  |  | Column Clamp | 137 | 106 |  | 0.77372
|  |  |  | Station Brackets | 520 | 501 |  | 0.96346
|  |  |  | Grounding | 615 | 570 |  | 0.92683
|  |  |  | Obstruction Brackets | 244 | 181 |  | 0.7418
|  |  |  | # Cables Pulled | 430 | 246 |  | 0.57209
115628 | 114897 | E1 | NAS-GRE | 24" CMRS Install | 423 | 321 |  | 0.75887 | 0.6095
|  |  |  | Column Clamp | 338 | 167 |  | 0.49408
|  |  |  | Station Brackets | 246 | 231 |  | 0.93902
|  |  |  | Grounding | 432 | 344 |  | 0.7963
|  |  |  | Obstruction Brackets | 464 | 292 |  | 0.62931
|  |  |  | # Cables Pulled | 203 | 8 |  | 0.039409
114897 | 114719 | E1 | NAS-GRE | Steel Mess Supports | 34 | 6 |  | 0.17647 | 0.47457
|  |  |  | Messenger Clamps | 934 | 35 |  | 0.037473
|  |  |  | Messenger Wire Pull | 288 | 261 |  | 0.90625
|  |  |  | Messenger Wire Tension | 846 | 224 |  | 0.26478
|  |  |  | # Cables Pulled | 272 | 182 |  | 0.66912
|  |  |  | Messenger Straps | 150 | 119 |  | 0.79333
114719 | 114040 | E1 | NAS-GRE | 24" CMRS Install | 124 | 5 |  | 0.040323 | 0.40504
|  |  |  | Column Clamp | 971 | 231 |  | 0.2379
|  |  |  | Station Brackets | 769 | 442 |  | 0.57477
|  |  |  | Grounding | 693 | 305 |  | 0.44012
|  |  |  | Obstruction Brackets | 365 | 266 |  | 0.72877
|  |  |  | # Cables Pulled | 502 | 205 |  | 0.40837
114040 | 113815 | E1 | NAS-GRE | Steel Mess Supports | 554 | 229 |  | 0.41336 | 0.34776
|  |  |  | Messenger Clamps | 706 | 340 |  | 0.48159
|  |  |  | Messenger Wire Pull | 351 | 194 |  | 0.55271
|  |  |  | Messenger Wire Tension | 424 | 153 |  | 0.36085
|  |  |  | # Cables Pulled | 545 | 47 |  | 0.086239
|  |  |  | Messenger Straps | 808 | 155 |  | 0.19183
113815 | 113019 | E1 | NASSAU | 24" CMRS Install | 382 | 280 |  | 0.73298 | 0.62143 |  | weight: 6.7 lb/ft
|  |  |  | Column Clamp | 222 | 131 |  | 0.59009
|  |  |  | Station Brackets | 164 | 131 |  | 0.79878
|  |  |  | Grounding | 312 | 95 |  | 0.30449
|  |  |  | Obstruction Brackets | 600 | 435 |  | 0.725
|  |  |  | # Cables Pulled | 563 | 325 |  | 0.57726
|  | E1 | NASSAU | 24" CMRS Install | 890 | 281 |  | 0.31573 | 0.49644
|  |  |  | Column Clamp | 785 | 619 |  | 0.78854
|  |  |  | Station Brackets | 800 | 753 |  | 0.94125
|  |  |  | Grounding | 860 | 18 |  | 0.02093
|  |  |  | Obstruction Brackets | 802 | 487 |  | 0.60723
|  |  |  | # Cables Pulled | 482 | 147 |  | 0.30498
113019 | 112700 | E1 | MET-NAS | 24" CMRS Install | 130 | 80 |  | 0.61538 | 0.58451
|  |  |  | Column Clamp | 327 | 256 |  | 0.78287
|  |  |  | Station Brackets | 128 | 124 |  | 0.96875
|  |  |  | Grounding | 503 | 205 |  | 0.40755
|  |  |  | Obstruction Brackets | 684 | 169 |  | 0.24708
|  |  |  | # Cables Pulled | 618 | 300 |  | 0.48544
112700 | 110878 | E1 | MET-NAS | 15" CMRS Install | 722 | 643 |  | 0.89058 | 0.67605
|  |  |  | Column Clamp | 120 | 107 |  | 0.89167
|  |  |  | Station Brackets | 397 | 313 |  | 0.78841
|  |  |  | Grounding | 677 | 445 |  | 0.65731
|  |  |  | Obstruction Brackets | 791 | 264 |  | 0.33375
|  |  |  | # Cables Pulled | 734 | 363 |  | 0.49455
110878 | 110793 | E1 | MET-NAS | 15" CMRS Install | 487 | 367 |  | 0.75359 | 0.79027
|  |  |  | Column Clamp | 714 | 623 |  | 0.87255
|  |  |  | Station Brackets | 556 | 508 |  | 0.91367
|  |  |  | Grounding | 419 | 199 |  | 0.47494
|  |  |  | Obstruction Brackets | 818 | 741 |  | 0.90587
|  |  |  | # Cables Pulled | 352 | 289 |  | 0.82102
110793 | 109251 | E1 | MET-NAS | 15" CMRS Install | 44 | 24 |  | 0.54545 | 0.28263
|  |  |  | Column Clamp | 683 | 83 |  | 0.12152
|  |  |  | Station Brackets | 657 | 20 |  | 0.030441
|  |  |  | Grounding | 74 | 42 |  | 0.56757
|  |  |  | Obstruction Brackets | 876 | 310 |  | 0.35388
|  |  |  | # Cables Pulled | 39 | 3 |  | 0.076923
109251 | 109133 | E1 | MET-NAS | 15" CMRS Install | 582 | 545 |  | 0.93643 | 0.57079
|  |  |  | Column Clamp | 458 | 194 |  | 0.42358
|  |  |  | Station Brackets | 954 | 450 |  | 0.4717
|  |  |  | Grounding | 834 | 247 |  | 0.29616
|  |  |  | Obstruction Brackets | 330 | 282 |  | 0.85455
|  |  |  | # Cables Pulled | 156 | 69 |  | 0.44231
109133 | 108356 | E1 | METROPOLITAN | 15" CMRS Install | 392 | 387 |  | 0.98724 | 0.46952
|  |  |  | Column Clamp | 137 | 45 |  | 0.32847
|  |  |  | Station Brackets | 420 | 67 |  | 0.15952
|  |  |  | Grounding | 404 | 204 |  | 0.50495
|  |  |  | Obstruction Brackets | 162 | 65 |  | 0.40123
|  |  |  | # Cables Pulled | 824 | 359 |  | 0.43568
108356 | 107651 | E1 | BRO-MET | 15" CMRS Install | 609 | 104 |  | 0.17077 | 0.3253
|  |  |  | Column Clamp | 291 | 8 |  | 0.027491
|  |  |  | Station Brackets | 647 | 302 |  | 0.46677
|  |  |  | Grounding | 466 | 51 |  | 0.10944
|  |  |  | Obstruction Brackets | 375 | 286 |  | 0.76267
|  |  |  | # Cables Pulled | 41 | 17 |  | 0.41463
107651 | 107611 | E1 | BRO-MET | 15" CMRS Install | 362 | 115 |  | 0.31768 | 0.3994 |  | Check endings for specific stationings (DWG 48012-17N-006.0) where cable switches from 1 to 2
|  |  |  | Column Clamp | 658 | 42 |  | 0.06383
|  |  |  | Station Brackets | 504 | 383 |  | 0.75992
|  |  |  | Grounding | 465 | 130 |  | 0.27957
|  |  |  | Obstruction Brackets | 166 | 143 |  | 0.86145
|  |  |  | # Cables Pulled | 509 | 58 |  | 0.11395
107611 | 106768 | E1 | BRO-MET | 15" CMRS Install | 671 | 500 |  | 0.74516 | 0.35512
|  |  |  | Column Clamp | 700 | 247 |  | 0.35286
|  |  |  | Station Brackets | 406 | 21 |  | 0.051724
|  |  |  | Grounding | 447 | 111 |  | 0.24832
|  |  |  | Obstruction Brackets | 651 | 364 |  | 0.55914
|  |  |  | # Cables Pulled | 922 | 160 |  | 0.17354
106768 | 106702 | E1 | BRO-MET | 15" CMRS Install | 123 | 41 |  | 0.33333 | 0.51046
|  |  |  | Column Clamp | 865 | 254 |  | 0.29364
|  |  |  | Station Brackets | 614 | 81 |  | 0.13192
|  |  |  | Grounding | 311 | 282 |  | 0.90675
|  |  |  | Obstruction Brackets | 374 | 360 |  | 0.96257
|  |  |  | # Cables Pulled | 527 | 229 |  | 0.43454
106702 | 106011 | E1 | BROADWAY | 15" CMRS Install | 214 | 161 |  | 0.75234 | 0.3691
|  |  |  | Column Clamp | 766 | 173 |  | 0.22585
|  |  |  | Station Brackets | 116 | 9 |  | 0.077586
|  |  |  | Grounding | 844 | 195 |  | 0.23104
|  |  |  | Obstruction Brackets | 398 | 62 |  | 0.15578
|  |  |  | # Cables Pulled | 579 | 447 |  | 0.77202
|  | E1 | BROADWAY | 15" CMRS Install | 36 | 11 |  | 0.30556 | 0.29252
|  |  |  | Column Clamp | 932 | 43 |  | 0.046137
|  |  |  | Station Brackets | 250 | 31 |  | 0.124
|  |  |  | Grounding | 698 | 583 |  | 0.83524
|  |  |  | Obstruction Brackets | 695 | 99 |  | 0.14245
|  |  |  | # Cables Pulled | 401 | 121 |  | 0.30175
|  | E1 | BROADWAY | 15" CMRS Install | 815 | 579 |  | 0.71043 | 0.38254
|  |  |  | Column Clamp | 596 | 92 |  | 0.15436
|  |  |  | Station Brackets | 118 | 1 |  | 0.0084746
|  |  |  | Grounding | 168 | 88 |  | 0.52381
|  |  |  | Obstruction Brackets | 645 | 311 |  | 0.48217
|  |  |  | # Cables Pulled | 738 | 307 |  | 0.41599
106011 | 105293 | E1 | FLU-BRO | 15" CMRS Install | 804 | 494 |  | 0.61443 | 0.3528
|  |  |  | Column Clamp | 150 | 3 |  | 0.02
|  |  |  | Station Brackets | 327 | 84 |  | 0.25688
|  |  |  | Grounding | 947 | 114 |  | 0.12038
|  |  |  | Obstruction Brackets | 180 | 102 |  | 0.56667
|  |  |  | # Cables Pulled | 52 | 28 |  | 0.53846
105293 | 104667 | E1 | FLU-BRO | 15" CMRS Install | 254 | 120 |  | 0.47244 | 0.60175
|  |  |  | Column Clamp | 140 | 71 |  | 0.50714
|  |  |  | Station Brackets | 41 | 36 |  | 0.87805
|  |  |  | Grounding | 213 | 91 |  | 0.42723
|  |  |  | Obstruction Brackets | 382 | 341 |  | 0.89267
|  |  |  | # Cables Pulled | 910 | 394 |  | 0.43297
104667 | 103784 | E1 | FLUSHING | 15" CMRS Install | 985 | 169 |  | 0.17157 | 0.29832
|  |  |  | Column Clamp | 858 | 26 |  | 0.030303
|  |  |  | Station Brackets | 762 | 23 |  | 0.030184
|  |  |  | Grounding | 456 | 424 |  | 0.92982
|  |  |  | Obstruction Brackets | 709 | 431 |  | 0.6079
|  |  |  | # Cables Pulled | 497 | 10 |  | 0.020121
103784 | 103231 | E1 | MYR-FLU | 15" CMRS Install | 42 | 0 |  | 0 | 0.44401
|  |  |  | Column Clamp | 531 | 475 |  | 0.89454
|  |  |  | Station Brackets | 919 | 489 |  | 0.5321
|  |  |  | Grounding | 491 | 52 |  | 0.10591
|  |  |  | Obstruction Brackets | 675 | 528 |  | 0.78222
|  |  |  | # Cables Pulled | 793 | 277 |  | 0.34931
103231 | 103165 | E1 | MYR-FLU | 15" CMRS Install | 609 | 609 |  | 1 | 0.62294
|  |  |  | Column Clamp | 230 | 48 |  | 0.2087
|  |  |  | Station Brackets | 654 | 521 |  | 0.79664
|  |  |  | Grounding | 416 | 37 |  | 0.088942
|  |  |  | Obstruction Brackets | 656 | 531 |  | 0.80945
|  |  |  | # Cables Pulled | 849 | 708 |  | 0.83392
103165 | 102533 | E1 | MYR-FLU | 15" CMRS Install | 641 | 266 |  | 0.41498 | 0.70325
|  |  |  | Column Clamp | 471 | 396 |  | 0.84076
|  |  |  | Station Brackets | 143 | 123 |  | 0.86014
|  |  |  | Grounding | 849 | 688 |  | 0.81037
|  |  |  | Obstruction Brackets | 780 | 757 |  | 0.97051
|  |  |  | # Cables Pulled | 945 | 305 |  | 0.32275
102533 | 101595 | E1 | MYRTLE | 24" CMRS Install | 573 | 374 |  | 0.65271 | 0.5741
|  |  |  | Column Clamp | 40 | 37 |  | 0.925
|  |  |  | Station Brackets | 493 | 216 |  | 0.43813
|  |  |  | Grounding | 715 | 355 |  | 0.4965
|  |  |  | Obstruction Brackets | 635 | 160 |  | 0.25197
|  |  |  | # Cables Pulled | 269 | 183 |  | 0.6803
101595 | 101558 | E1 | BED-MYR | 24" CMRS Install | 89 | 54 |  | 0.60674 | 0.5875
|  |  |  | Column Clamp | 986 | 609 |  | 0.61765
|  |  |  | Station Brackets | 635 | 481 |  | 0.75748
|  |  |  | Grounding | 590 | 311 |  | 0.52712
|  |  |  | Obstruction Brackets | 934 | 606 |  | 0.64882
|  |  |  | # Cables Pulled | 128 | 47 |  | 0.36719
101558 | 101050 | E1 | BED-MYR | 24" CMRS Install | 434 | 127 |  | 0.29263 | 0.28304
|  |  |  | Column Clamp | 15 | 4 |  | 0.26667
|  |  |  | Station Brackets | 591 | 191 |  | 0.32318
|  |  |  | Grounding | 876 | 482 |  | 0.55023
|  |  |  | Obstruction Brackets | 864 | 89 |  | 0.10301
|  |  |  | # Cables Pulled | 480 | 78 |  | 0.1625
101050 | 101015 | E1 | BED-MYR | 24" CMRS Install | 852 | 202 |  | 0.23709 | 0.2936
|  |  |  | Column Clamp | 536 | 337 |  | 0.62873
|  |  |  | Station Brackets | 967 | 136 |  | 0.14064
|  |  |  | Grounding | 112 | 5 |  | 0.044643
|  |  |  | Obstruction Brackets | 942 | 7 |  | 0.007431
|  |  |  | # Cables Pulled | 559 | 393 |  | 0.70304
101015 | 100530 | E1 | BED-MYR | 24" CMRS Install | 522 | 420 |  | 0.8046 | 0.49246
|  |  |  | Column Clamp | 182 | 126 |  | 0.69231
|  |  |  | Station Brackets | 60 | 4 |  | 0.066667
|  |  |  | Grounding | 414 | 31 |  | 0.074879
|  |  |  | Obstruction Brackets | 769 | 316 |  | 0.41092
|  |  |  | # Cables Pulled | 296 | 268 |  | 0.90541
100530 | 100383 | E1 | BED-MYR | Steel Mess Supports | 447 | 123 |  | 0.27517 | 0.42949
|  |  |  | Messenger Clamps | 633 | 523 |  | 0.82622
|  |  |  | Messenger Wire Pull | 539 | 229 |  | 0.42486
|  |  |  | Messenger Wire Tension | 174 | 74 |  | 0.42529
|  |  |  | # Cables Pulled | 383 | 178 |  | 0.46475
|  |  |  | Messenger Straps | 772 | 124 |  | 0.16062
|  | E1 | BED-MYR | Crossover (Arch Bar Installation) | 60 | 0 |  | 0
100383 | 100282 | E1 | BED-MYR | Steel Mess Supports | 735 | 27 |  | 0.036735 | 0.55777
|  |  |  | Messenger Clamps | 160 | 134 |  | 0.8375
|  |  |  | Messenger Wire Pull | 908 | 727 |  | 0.80066
|  |  |  | Messenger Wire Tension | 262 | 211 |  | 0.80534
|  |  |  | # Cables Pulled | 877 | 449 |  | 0.51197
|  |  |  | Messenger Straps | 807 | 286 |  | 0.3544
100282 | 100036 | E1 | BED-MYR | Steel Mess Supports | 503 | 437 |  | 0.86879 | 0.56857
|  |  |  | Messenger Clamps | 342 | 166 |  | 0.48538
|  |  |  | Messenger Wire Pull | 783 | 35 |  | 0.0447
|  |  |  | Messenger Wire Tension | 170 | 170 |  | 1
|  |  |  | # Cables Pulled | 667 | 286 |  | 0.42879
|  |  |  | Messenger Straps | 603 | 352 |  | 0.58375
100036 | 99560 | E1 | BED-MYR | Steel Mess Supports | 570 | 339 |  | 0.59474 | 0.3584
|  |  |  | Messenger Clamps | 557 | 84 |  | 0.15081
|  |  |  | Messenger Wire Pull | 153 | 88 |  | 0.57516
|  |  |  | Messenger Wire Tension | 231 | 27 |  | 0.11688
|  |  |  | # Cables Pulled | 144 | 14 |  | 0.097222
|  |  |  | Messenger Straps | 346 | 213 |  | 0.61561
98845 | 98555 | E1 | CLA-BED | 24" CMRS Install | 831 | 413 |  | 0.49699 | 0.39316
|  |  |  | Column Clamp | 465 | 86 |  | 0.18495
|  |  |  | Station Brackets | 472 | 400 |  | 0.84746
|  |  |  | Grounding | 951 | 98 |  | 0.10305
|  |  |  | Obstruction Brackets | 555 | 379 |  | 0.68288
|  |  |  | # Cables Pulled | 504 | 22 |  | 0.043651
|  | E1 | CLA-BED | Crossover (Arch Bar Installation) | 851 | 660 |  | 0.77556
98555 | 98220 | E1 | CLA-BED | 24" CMRS Install | 973 | 704 |  | 0.72354 | 0.58548
|  |  |  | Column Clamp | 298 | 120 |  | 0.40268
|  |  |  | Station Brackets | 558 | 541 |  | 0.96953
|  |  |  | Grounding | 446 | 63 |  | 0.14126
|  |  |  | Obstruction Brackets | 794 | 472 |  | 0.59446
|  |  |  | # Cables Pulled | 951 | 648 |  | 0.68139
98220 | 98140 | E1 | CLA-BED | 24" CMRS Install | 893 | 798 |  | 0.89362 | 0.54104
|  |  |  | Column Clamp | 875 | 384 |  | 0.43886
|  |  |  | Station Brackets | 648 | 87 |  | 0.13426
|  |  |  | Grounding | 812 | 195 |  | 0.24015
|  |  |  | Obstruction Brackets | 878 | 479 |  | 0.54556
|  |  |  | # Cables Pulled | 322 | 320 |  | 0.99379
98140 | 97920 | E1 | CLA-BED | 24" CMRS Install | 884 | 641 |  | 0.72511 | 0.61057
|  |  |  | Column Clamp | 75 | 29 |  | 0.38667
|  |  |  | Station Brackets | 38 | 9 |  | 0.23684
|  |  |  | Grounding | 922 | 917 |  | 0.99458
|  |  |  | Obstruction Brackets | 337 | 289 |  | 0.85757
|  |  |  | # Cables Pulled | 495 | 229 |  | 0.46263
97920 | 97670 | E1 | CLA-BED | Steel Mess Supports | 316 | 257 |  | 0.81329 | 0.36919
|  |  |  | Messenger Clamps | 47 | 29 |  | 0.61702
|  |  |  | Messenger Wire Pull | 179 | 28 |  | 0.15642
|  |  |  | Messenger Wire Tension | 758 | 0 |  | 0
|  |  |  | # Cables Pulled | 454 | 100 |  | 0.22026
|  |  |  | Messenger Straps | 539 | 220 |  | 0.40816
97670 | 97580 | E1 | CLASSON | 24" CMRS Install | 446 | 265 |  | 0.59417 | 0.45847
|  |  |  | Column Clamp | 105 | 9 |  | 0.085714
|  |  |  | Station Brackets | 92 | 23 |  | 0.25
|  |  |  | Grounding | 950 | 774 |  | 0.81474
|  |  |  | Obstruction Brackets | 860 | 348 |  | 0.40465
|  |  |  | # Cables Pulled | 763 | 459 |  | 0.60157
97580 | 97230 | E1 | CLASSON | 24" CMRS Install | 869 | 811 |  | 0.93326 | 0.61819
|  |  |  | Column Clamp | 530 | 339 |  | 0.63962
|  |  |  | Station Brackets | 983 | 791 |  | 0.80468
|  |  |  | Grounding | 109 | 16 |  | 0.14679
|  |  |  | Obstruction Brackets | 781 | 317 |  | 0.40589
|  |  |  | # Cables Pulled | 303 | 236 |  | 0.77888
97230 | 96920 | E1 | CLASSON | 24" CMRS Install | 986 | 62 |  | 0.06288 | 0.60357
|  |  |  | Column Clamp | 682 | 587 |  | 0.8607
|  |  |  | Station Brackets | 602 | 498 |  | 0.82724
|  |  |  | Grounding | 378 | 270 |  | 0.71429
|  |  |  | Obstruction Brackets | 957 | 551 |  | 0.57576
|  |  |  | # Cables Pulled | 534 | 310 |  | 0.58052
96920 | 96685 | E1 | CLI-CLA | Steel Mess Supports | 83 | 7 |  | 0.084337 | 0.51808
|  |  |  | Messenger Clamps | 988 | 253 |  | 0.25607
|  |  |  | Messenger Wire Pull | 741 | 634 |  | 0.8556
|  |  |  | Messenger Wire Tension | 333 | 267 |  | 0.8018
|  |  |  | # Cables Pulled | 634 | 359 |  | 0.56625
|  |  |  | Messenger Straps | 349 | 190 |  | 0.54441
96685 | 96460 | E1 | CLI-CLA | 24" CMRS Install | 920 | 760 |  | 0.82609 | 0.51324
|  |  |  | Column Clamp | 952 | 705 |  | 0.74055
|  |  |  | Station Brackets | 390 | 116 |  | 0.29744
|  |  |  | Grounding | 608 | 307 |  | 0.50493
|  |  |  | Obstruction Brackets | 414 | 265 |  | 0.6401
|  |  |  | # Cables Pulled | 981 | 69 |  | 0.070336
96460 | 96387 | E1 | CLI-CLA | 24" CMRS Install | 666 | 247 |  | 0.37087 | 0.4856
|  |  |  | Column Clamp | 948 | 203 |  | 0.21414
|  |  |  | Station Brackets | 674 | 354 |  | 0.52522
|  |  |  | Grounding | 944 | 587 |  | 0.62182
|  |  |  | Obstruction Brackets | 140 | 129 |  | 0.92143
|  |  |  | # Cables Pulled | 469 | 122 |  | 0.26013
96387 | 96051 | E1 | CLI-CLA | 24" CMRS Install | 532 | 254 |  | 0.47744 | 0.44344
|  |  |  | Column Clamp | 501 | 342 |  | 0.68263
|  |  |  | Station Brackets | 385 | 100 |  | 0.25974
|  |  |  | Grounding | 899 | 268 |  | 0.29811
|  |  |  | Obstruction Brackets | 194 | 166 |  | 0.85567
|  |  |  | # Cables Pulled | 563 | 49 |  | 0.087034
96038 | 95998 | E1 | CLI-CLA | 24" CMRS Install | 523 | 142 |  | 0.27151 | 0.44195
|  |  |  | Column Clamp | 910 | 64 |  | 0.07033
|  |  |  | Station Brackets | 197 | 63 |  | 0.3198
|  |  |  | Grounding | 418 | 307 |  | 0.73445
|  |  |  | Obstruction Brackets | 155 | 110 |  | 0.70968
|  |  |  | # Cables Pulled | 185 | 101 |  | 0.54595
95998 | 95873 | E1 | CLI-CLA | 24" CMRS Install | 824 | 167 |  | 0.20267 | 0.62708
|  |  |  | Column Clamp | 881 | 842 |  | 0.95573
|  |  |  | Station Brackets | 665 | 557 |  | 0.83759
|  |  |  | Grounding | 764 | 674 |  | 0.8822
|  |  |  | Obstruction Brackets | 682 | 128 |  | 0.18768
|  |  |  | # Cables Pulled | 89 | 62 |  | 0.69663
95873 | 95781 | E1 | CLINTON-WASHINGTON | 24" CMRS Install | 599 | 385 |  | 0.64274 | 0.37056
|  |  |  | Column Clamp | 15 | 5 |  | 0.33333
|  |  |  | Station Brackets | 384 | 329 |  | 0.85677
|  |  |  | Grounding | 873 | 3 |  | 0.0034364
|  |  |  | Obstruction Brackets | 788 | 234 |  | 0.29695
|  |  |  | # Cables Pulled | 233 | 21 |  | 0.090129
95781 | 95695 | E1 | CLINTON-WASHINGTON | 24" CMRS Install | 478 | 469 |  | 0.98117 | 0.51601
|  |  |  | Column Clamp | 835 | 13 |  | 0.015569
|  |  |  | Station Brackets | 567 | 253 |  | 0.44621
|  |  |  | Grounding | 937 | 100 |  | 0.10672
|  |  |  | Obstruction Brackets | 358 | 277 |  | 0.77374
|  |  |  | # Cables Pulled | 519 | 401 |  | 0.77264
95695 | 95544 | E1 | CLINTON-WASHINGTON | 24" CMRS Install | 426 | 197 |  | 0.46244 | 0.53934
|  |  |  | Column Clamp | 631 | 313 |  | 0.49604
|  |  |  | Station Brackets | 152 | 147 |  | 0.96711
|  |  |  | Grounding | 76 | 32 |  | 0.42105
|  |  |  | Obstruction Brackets | 103 | 30 |  | 0.29126
|  |  |  | # Cables Pulled | 851 | 509 |  | 0.59812
95544 | 95155 | E1 | CLINTON-WASHINGTON | 24" CMRS Install | 335 | 293 |  | 0.87463 | 0.59254
|  |  |  | Column Clamp | 98 | 86 |  | 0.87755
|  |  |  | Station Brackets | 497 | 17 |  | 0.034205
|  |  |  | Grounding | 201 | 97 |  | 0.48259
|  |  |  | Obstruction Brackets | 319 | 245 |  | 0.76803
|  |  |  | # Cables Pulled | 301 | 156 |  | 0.51827
95155 | 95004 | E1 | CLINTON-WASHINGTON | 24" CMRS Install | 595 | 23 |  | 0.038655 | 0.34027
|  |  |  | Column Clamp | 343 | 215 |  | 0.62682
|  |  |  | Station Brackets | 79 | 44 |  | 0.55696
|  |  |  | Grounding | 657 | 131 |  | 0.19939
|  |  |  | Obstruction Brackets | 215 | 80 |  | 0.37209
|  |  |  | # Cables Pulled | 537 | 133 |  | 0.24767
95004 | 94266 | E1 | FUL-CLI | 24" CMRS Install | 267 | 133 |  | 0.49813 | 0.5883
|  |  |  | Column Clamp | 885 | 130 |  | 0.14689
|  |  |  | Station Brackets | 115 | 103 |  | 0.89565
|  |  |  | Grounding | 738 | 582 |  | 0.78862
|  |  |  | Obstruction Brackets | 424 | 290 |  | 0.68396
|  |  |  | # Cables Pulled | 302 | 156 |  | 0.51656
94266 | 94207 | E1 | FUL-CLI | 24" CMRS Install | 837 | 65 |  | 0.077658 | 0.38348
|  |  |  | Column Clamp | 654 | 82 |  | 0.12538
|  |  |  | Station Brackets | 599 | 203 |  | 0.3389
|  |  |  | Grounding | 92 | 43 |  | 0.46739
|  |  |  | Obstruction Brackets | 303 | 183 |  | 0.60396
|  |  |  | # Cables Pulled | 605 | 416 |  | 0.6876
94207 | 93350 | E1 | FUL-CLI | 24" CMRS Install | 802 | 505 |  | 0.62968 | 0.36063
|  |  |  | Column Clamp | 479 | 119 |  | 0.24843
|  |  |  | Station Brackets | 571 | 469 |  | 0.82137
|  |  |  | Grounding | 616 | 6 |  | 0.0097403
|  |  |  | Obstruction Brackets | 154 | 60 |  | 0.38961
|  |  |  | # Cables Pulled | 693 | 45 |  | 0.064935
73350 | 73690 | E1 | FULTON | 15" CMRS Install | 557 | 520 |  | 0.93357 | 0.50044
|  |  |  | Column Clamp | 400 | 222 |  | 0.555
|  |  |  | Station Brackets | 355 | 130 |  | 0.3662
|  |  |  | Grounding | 137 | 70 |  | 0.51095
|  |  |  | Obstruction Brackets | 890 | 549 |  | 0.61685
|  |  |  | # Cables Pulled | 797 | 16 |  | 0.020075
73690 | 74030 | E1 | FULTON | 15" CMRS Install | 841 | 340 |  | 0.40428 | 0.50574
|  |  |  | Column Clamp | 34 | 4 |  | 0.11765
|  |  |  | Station Brackets | 633 | 456 |  | 0.72038
|  |  |  | Grounding | 851 | 552 |  | 0.64865
|  |  |  | Obstruction Brackets | 28 | 20 |  | 0.71429
|  |  |  | # Cables Pulled | 459 | 197 |  | 0.42919
|  | E1 | FULTON | 15" CMRS Install | 143 | 39 |  | 0.27273 | 0.55759
|  |  |  | Column Clamp | 964 | 878 |  | 0.91079
|  |  |  | Station Brackets | 205 | 159 |  | 0.77561
|  |  |  | Grounding | 753 | 707 |  | 0.93891
|  |  |  | Obstruction Brackets | 55 | 11 |  | 0.2
|  |  |  | # Cables Pulled | 804 | 199 |  | 0.24751
74030 | 76085 | E1 | HOY-FUL | 24" CMRS Install | 603 | 421 |  | 0.69818 | 0.58306
|  |  |  | Column Clamp | 63 | 56 |  | 0.88889
|  |  |  | Station Brackets | 113 | 69 |  | 0.61062
|  |  |  | Grounding | 935 | 329 |  | 0.35187
|  |  |  | Obstruction Brackets | 1000 | 150 |  | 0.15
|  |  |  | # Cables Pulled | 169 | 135 |  | 0.79882
76085 | 76110 | E1 | HOY-FUL | 15" CMRS Install | 679 | 562 |  | 0.82769 | 0.49975
|  |  |  | Column Clamp | 826 | 355 |  | 0.42978
|  |  |  | Station Brackets | 747 | 437 |  | 0.58501
|  |  |  | Grounding | 216 | 88 |  | 0.40741
|  |  |  | Obstruction Brackets | 902 | 646 |  | 0.71619
|  |  |  | # Cables Pulled | 339 | 11 |  | 0.032448
76110 | 76165 | E1 | HOY-FUL | 15" CMRS Install | 239 | 114 |  | 0.47699 | 0.37372
|  |  |  | Column Clamp | 485 | 241 |  | 0.49691
|  |  |  | Station Brackets | 618 | 69 |  | 0.11165
|  |  |  | Grounding | 196 | 43 |  | 0.21939
|  |  |  | Obstruction Brackets | 208 | 163 |  | 0.78365
|  |  |  | # Cables Pulled | 735 | 113 |  | 0.15374
76165 | 77470 | E1 | HOYT SCHERMERHORN | 15" CMRS Install | 853 | 318 |  | 0.3728 | 0.61272
|  |  |  | Column Clamp | 89 | 79 |  | 0.88764
|  |  |  | Station Brackets | 149 | 61 |  | 0.4094
|  |  |  | Grounding | 543 | 525 |  | 0.96685
|  |  |  | Obstruction Brackets | 38 | 2 |  | 0.052632
|  |  |  | # Cables Pulled | 462 | 456 |  | 0.98701
77470 | 77595 | E1 | BER-HOY | 15" CMRS Install | 849 | 545 |  | 0.64193 | 0.37546
|  |  |  | Column Clamp | 576 | 35 |  | 0.060764
|  |  |  | Station Brackets | 455 | 113 |  | 0.24835
|  |  |  | Grounding | 587 | 171 |  | 0.29131
|  |  |  | Obstruction Brackets | 776 | 388 |  | 0.5
|  |  |  | # Cables Pulled | 192 | 98 |  | 0.51042
77595 | 78230 | E1 | BER-HOY | 24" CMRS Install | 869 | 573 |  | 0.65938 | 0.44474
|  |  |  | Column Clamp | 322 | 160 |  | 0.49689
|  |  |  | Station Brackets | 673 | 225 |  | 0.33432
|  |  |  | Grounding | 778 | 357 |  | 0.45887
|  |  |  | Obstruction Brackets | 696 | 109 |  | 0.15661
|  |  |  | # Cables Pulled | 802 | 451 |  | 0.56234
78230 | 78515 | E1 | BER-HOY | 24" CMRS Install | 199 | 124 |  | 0.62312 | 0.52087
|  |  |  | Column Clamp | 551 | 546 |  | 0.99093
|  |  |  | Station Brackets | 233 | 85 |  | 0.36481
|  |  |  | Grounding | 581 | 96 |  | 0.16523
|  |  |  | Obstruction Brackets | 687 | 197 |  | 0.28675
|  |  |  | # Cables Pulled | 409 | 284 |  | 0.69438
|  | E2 | BERGEN | Cable Tray Brackets | 702 | 672 |  | 0.95726 | 0.82634
|  |  |  | Installing Tray | 516 | 319 |  | 0.61822
|  |  |  | Core Drilling | 569 | 476 |  | 0.83656
|  |  |  | Cable Pull | 478 | 427 |  | 0.89331
78515 | 78315 | E2 | BER-HOY | Steel Mess Supports | 652 | 313 |  | 0.48006 | 0.48977
|  |  |  | Messenger Clamps | 109 | 99 |  | 0.90826
|  |  |  | Messenger Wire Pull | 757 | 35 |  | 0.046235
|  |  |  | Messenger Wire Tension | 837 | 374 |  | 0.44683
|  |  |  | # Cables Pulled | 893 | 88 |  | 0.098544
|  |  |  | Messenger Straps | 218 | 209 |  | 0.95872
78315 | 77655 | E2 | BER-HOY | 24" CMRS Install | 473 | 203 |  | 0.42918 | 0.37015
|  |  |  | Column Clamp | 966 | 348 |  | 0.36025
|  |  |  | Station Brackets | 326 | 176 |  | 0.53988
|  |  |  | Grounding | 161 | 137 |  | 0.85093
|  |  |  | Obstruction Brackets | 475 | 11 |  | 0.023158
|  |  |  | # Cables Pulled | 400 | 7 |  | 0.0175
77655 | 77585 | E2 | BER-HOY | 24" CMRS Install | 73 | 44 |  | 0.60274 | 0.54609
|  |  |  | Column Clamp | 319 | 212 |  | 0.66458
|  |  |  | Station Brackets | 589 | 337 |  | 0.57216
|  |  |  | Grounding | 355 | 1 |  | 0.0028169
|  |  |  | Obstruction Brackets | 472 | 469 |  | 0.99364
|  |  |  | # Cables Pulled | 960 | 423 |  | 0.44062
77585 | 76845 | E2 | BER-HOY | 24" CMRS Install | 484 | 190 |  | 0.39256 | 0.39586
|  |  |  | Column Clamp | 119 | 83 |  | 0.69748
|  |  |  | Station Brackets | 588 | 39 |  | 0.066327
|  |  |  | Grounding | 216 | 78 |  | 0.36111
|  |  |  | Obstruction Brackets | 113 | 51 |  | 0.45133
|  |  |  | # Cables Pulled | 785 | 319 |  | 0.40637
76845 | 76150 | E2 | HOYT SCHERMERHORN | 24" CMRS Install | 739 | 362 |  | 0.48985 | 0.67604
|  |  |  | Column Clamp | 745 | 523 |  | 0.70201
|  |  |  | Station Brackets | 194 | 162 |  | 0.83505
|  |  |  | Grounding | 854 | 606 |  | 0.7096
|  |  |  | Obstruction Brackets | 297 | 156 |  | 0.52525
|  |  |  | # Cables Pulled | 506 | 402 |  | 0.79447
76150 | 76090 | E2 | HOY-FUL | 24" CMRS Install | 186 | 160 |  | 0.86022 | 0.44602
|  |  |  | Column Clamp | 499 | 13 |  | 0.026052
|  |  |  | Station Brackets | 323 | 111 |  | 0.34365
|  |  |  | Grounding | 942 | 387 |  | 0.41083
|  |  |  | Obstruction Brackets | 909 | 641 |  | 0.70517
|  |  |  | # Cables Pulled | 318 | 105 |  | 0.33019
76090 | 75950 | E2 | HOY-FUL | 24" CMRS Install | 649 | 355 |  | 0.547 | 0.49356
|  |  |  | Column Clamp | 828 | 63 |  | 0.076087
|  |  |  | Station Brackets | 39 | 14 |  | 0.35897
|  |  |  | Grounding | 604 | 595 |  | 0.9851
|  |  |  | Obstruction Brackets | 783 | 483 |  | 0.61686
|  |  |  | # Cables Pulled | 212 | 80 |  | 0.37736
75950 | 75900 | E2 | HOY-FUL | Steel Mess Supports | 408 | 153 |  | 0.375 | 0.28997
|  |  |  | Messenger Clamps | 600 | 256 |  | 0.42667
|  |  |  | Messenger Wire Pull | 588 | 26 |  | 0.044218
|  |  |  | Messenger Wire Tension | 654 | 248 |  | 0.3792
|  |  |  | # Cables Pulled | 759 | 227 |  | 0.29908
|  |  |  | Messenger Straps | 983 | 212 |  | 0.21567
75900 | 74590 | E2 | HOY-FUL | 24" CMRS Install | 115 | 1 |  | 0.0086957 | 0.49193
|  |  |  | Column Clamp | 124 | 80 |  | 0.64516
|  |  |  | Station Brackets | 692 | 459 |  | 0.66329
|  |  |  | Grounding | 887 | 697 |  | 0.78579
|  |  |  | Obstruction Brackets | 886 | 396 |  | 0.44695
|  |  |  | # Cables Pulled | 590 | 237 |  | 0.40169
74590 | 74450 | E2 | HOY-FUL | Steel Mess Supports | 983 | 279 |  | 0.28383 | 0.32526
|  |  |  | Messenger Clamps | 501 | 192 |  | 0.38323
|  |  |  | Messenger Wire Pull | 581 | 98 |  | 0.16867
|  |  |  | Messenger Wire Tension | 605 | 226 |  | 0.37355
|  |  |  | # Cables Pulled | 44 | 28 |  | 0.63636
|  |  |  | Messenger Straps | 708 | 75 |  | 0.10593
74450 | 74070 | E2 | HOY-FUL | 24" CMRS Install | 330 | 162 |  | 0.49091 | 0.46079
|  |  |  | Column Clamp | 759 | 216 |  | 0.28458
|  |  |  | Station Brackets | 149 | 46 |  | 0.30872
|  |  |  | Grounding | 58 | 5 |  | 0.086207
|  |  |  | Obstruction Brackets | 622 | 577 |  | 0.92765
|  |  |  | # Cables Pulled | 15 | 10 |  | 0.66667
74070 | 74030 | E2 | HOY-FUL | 24" CMRS Install | 958 | 416 |  | 0.43424 | 0.64638
|  |  |  | Column Clamp | 659 | 576 |  | 0.87405
|  |  |  | Station Brackets | 397 | 211 |  | 0.53149
|  |  |  | Grounding | 113 | 84 |  | 0.74336
|  |  |  | Obstruction Brackets | 692 | 392 |  | 0.56647
|  |  |  | # Cables Pulled | 925 | 674 |  | 0.72865
74030 | 73690 | E2 | FULTON | 15" CMRS Install | 977 | 927 |  | 0.94882 | 0.58538
|  |  |  | Column Clamp | 495 | 196 |  | 0.39596
|  |  |  | Station Brackets | 996 | 831 |  | 0.83434
|  |  |  | Grounding | 651 | 572 |  | 0.87865
|  |  |  | Obstruction Brackets | 955 | 266 |  | 0.27853
|  |  |  | # Cables Pulled | 716 | 126 |  | 0.17598
73690 | 73250 | E2 | FULTON | 15" CMRS Install | 38 | 13 |  | 0.34211 | 0.49412 | Cable Management Takeoffs Cell F110* - 147LF instead of 440LF | Cable Management Takeoffs Cell F110* - 147LF instead of 440LF
|  |  |  | Column Clamp | 264 | 100 |  | 0.37879
|  |  |  | Station Brackets | 114 | 50 |  | 0.4386
|  |  |  | Grounding | 983 | 680 |  | 0.69176
|  |  |  | Obstruction Brackets | 19 | 16 |  | 0.84211
|  |  |  | # Cables Pulled | 785 | 213 |  | 0.27134
|  | E2 | FULTON | 15" CMRS Install | 700 | 443 |  | 0.63286 | 0.5745
|  |  |  | Column Clamp | 864 | 368 |  | 0.42593
|  |  |  | Station Brackets | 807 | 268 |  | 0.33209
|  |  |  | Grounding | 535 | 387 |  | 0.72336
|  |  |  | Obstruction Brackets | 817 | 398 |  | 0.48715
|  |  |  | # Cables Pulled | 272 | 230 |  | 0.84559
73250 | 72315 | E2 | FUL-CLI | 24" CMRS Install | 187 | 4 |  | 0.02139 | 0.44342
|  |  |  | Column Clamp | 285 | 86 |  | 0.30175
|  |  |  | Station Brackets | 846 | 719 |  | 0.84988
|  |  |  | Grounding | 24 | 23 |  | 0.95833
|  |  |  | Obstruction Brackets | 474 | 95 |  | 0.20042
|  |  |  | # Cables Pulled | 219 | 72 |  | 0.32877
94400 | 94989 | E2 | FUL-CLI | 24" CMRS Install | 246 | 129 |  | 0.52439 | 0.48906
|  |  |  | Column Clamp | 154 | 46 |  | 0.2987
|  |  |  | Station Brackets | 811 | 324 |  | 0.39951
|  |  |  | Grounding | 778 | 654 |  | 0.84062
|  |  |  | Obstruction Brackets | 111 | 56 |  | 0.5045
|  |  |  | # Cables Pulled | 911 | 334 |  | 0.36663
94989 | 95114 | E2 | FUL-CLI | 24" CMRS Install | 361 | 114 |  | 0.31579 | 0.59308
|  |  |  | Column Clamp | 895 | 824 |  | 0.92067
|  |  |  | Station Brackets | 149 | 119 |  | 0.79866
|  |  |  | Grounding | 665 | 497 |  | 0.74737
|  |  |  | Obstruction Brackets | 15 | 9 |  | 0.6
|  |  |  | # Cables Pulled | 608 | 107 |  | 0.17599
94989 | 95114 | E2 | CLINTON-WASHINGTON | 24" CMRS Install | 669 | 424 |  | 0.63378 | 0.61806
|  |  |  | Column Clamp | 384 | 193 |  | 0.5026
|  |  |  | Station Brackets | 948 | 803 |  | 0.84705
|  |  |  | Grounding | 799 | 566 |  | 0.70839
|  |  |  | Obstruction Brackets | 106 | 63 |  | 0.59434
|  |  |  | # Cables Pulled | 135 | 57 |  | 0.42222
95503 | 95701 | E2 | CLINTON-WASHINGTON | 24" CMRS Install | 870 | 196 |  | 0.22529 | 0.4169
|  |  |  | Column Clamp | 784 | 748 |  | 0.95408
|  |  |  | Station Brackets | 672 | 5 |  | 0.0074405
|  |  |  | Grounding | 792 | 225 |  | 0.28409
|  |  |  | Obstruction Brackets | 804 | 688 |  | 0.85572
|  |  |  | # Cables Pulled | 309 | 54 |  | 0.17476
95767 | 95852 | E2 | CLINTON-WASHINGTON | 24" CMRS Install | 530 | 378 |  | 0.71321 | 0.52394
|  |  |  | Column Clamp | 984 | 559 |  | 0.56809
|  |  |  | Station Brackets | 651 | 417 |  | 0.64055
|  |  |  | Grounding | 767 | 427 |  | 0.55671
|  |  |  | Obstruction Brackets | 633 | 41 |  | 0.064771
|  |  |  | # Cables Pulled | 718 | 431 |  | 0.60028
95852 | 96366 | E2 | CLINTON-WASHINGTON | 24" CMRS Install | 166 | 144 |  | 0.86747 | 0.61227
|  |  |  | Column Clamp | 575 | 368 |  | 0.64
|  |  |  | Station Brackets | 40 | 34 |  | 0.85
|  |  |  | Grounding | 610 | 530 |  | 0.86885
|  |  |  | Obstruction Brackets | 397 | 73 |  | 0.18388
|  |  |  | # Cables Pulled | 987 | 260 |  | 0.26342
96366 | 96432 | E2 | CLINTON-WASHINGTON | 24" CMRS Install | 524 | 411 |  | 0.78435 | 0.44123
|  |  |  | Column Clamp | 934 | 137 |  | 0.14668
|  |  |  | Station Brackets | 169 | 18 |  | 0.10651
|  |  |  | Grounding | 532 | 490 |  | 0.92105
|  |  |  | Obstruction Brackets | 267 | 2 |  | 0.0074906
|  |  |  | # Cables Pulled | 251 | 171 |  | 0.68127
96432 | 96649 | E2 | CLINTON-WASHINGTON | 24" CMRS Install | 99 | 7 |  | 0.070707 | 0.34053
|  |  |  | Column Clamp | 273 | 245 |  | 0.89744
|  |  |  | Station Brackets | 73 | 0 |  | 0
|  |  |  | Grounding | 342 | 25 |  | 0.073099
|  |  |  | Obstruction Brackets | 79 | 19 |  | 0.24051
|  |  |  | # Cables Pulled | 415 | 316 |  | 0.76145
95767 | 95852 | E2 | CLINTON-WASHINGTON | 24" CMRS Install | 701 | 512 |  | 0.73039 | 0.37314
|  |  |  | Column Clamp | 945 | 196 |  | 0.20741
|  |  |  | Station Brackets | 122 | 3 |  | 0.02459
|  |  |  | Grounding | 239 | 105 |  | 0.43933
|  |  |  | Obstruction Brackets | 596 | 257 |  | 0.43121
|  |  |  | # Cables Pulled | 473 | 192 |  | 0.40592
95852 | 96366 | E2 | CLI-CLA | 24" CMRS Install | 341 | 54 |  | 0.15836 | 0.49545
|  |  |  | Column Clamp | 272 | 49 |  | 0.18015
|  |  |  | Station Brackets | 211 | 209 |  | 0.99052
|  |  |  | Grounding | 783 | 444 |  | 0.56705
|  |  |  | Obstruction Brackets | 505 | 81 |  | 0.1604
|  |  |  | # Cables Pulled | 549 | 503 |  | 0.91621
96366 | 96432 | E2 | CLI-CLA | 24" CMRS Install | 146 | 134 |  | 0.91781 | 0.50896
|  |  |  | Column Clamp | 599 | 303 |  | 0.50584
|  |  |  | Station Brackets | 927 | 569 |  | 0.61381
|  |  |  | Grounding | 736 | 12 |  | 0.016304
|  |  |  | Obstruction Brackets | 742 | 552 |  | 0.74394
|  |  |  | # Cables Pulled | 289 | 74 |  | 0.25606
96432 | 96649 | E2 | CLI-CLA | 24" CMRS Install | 693 | 262 |  | 0.37807 | 0.53387
|  |  |  | Column Clamp | 16 | 3 |  | 0.1875
|  |  |  | Station Brackets | 300 | 221 |  | 0.73667
|  |  |  | Grounding | 322 | 128 |  | 0.39752
|  |  |  | Obstruction Brackets | 476 | 326 |  | 0.68487
|  |  |  | # Cables Pulled | 915 | 749 |  | 0.81858
96649 | 96770 | E2 | CLI-CLA | 24" CMRS Install | 750 | 573 |  | 0.764 | 0.68888
|  |  |  | Column Clamp | 547 | 533 |  | 0.97441
|  |  |  | Station Brackets | 728 | 412 |  | 0.56593
|  |  |  | Grounding | 46 | 3 |  | 0.065217
|  |  |  | Obstruction Brackets | 728 | 660 |  | 0.90659
|  |  |  | # Cables Pulled | 546 | 468 |  | 0.85714
96770 | 96990 | E2 | CLI-CLA | Steel Mess Supports | 247 | 47 |  | 0.19028 | 0.43788
|  |  |  | Messenger Clamps | 545 | 366 |  | 0.67156
|  |  |  | Messenger Wire Pull | 135 | 66 |  | 0.48889
|  |  |  | Messenger Wire Tension | 378 | 102 |  | 0.26984
|  |  |  | # Cables Pulled | 496 | 470 |  | 0.94758
|  |  |  | Messenger Straps | 998 | 59 |  | 0.059118
96990 | 97230 | E2 | CLASSON | 24" CMRS Install | 790 | 261 |  | 0.33038 | 0.3503
|  |  |  | Column Clamp | 69 | 36 |  | 0.52174
|  |  |  | Station Brackets | 188 | 11 |  | 0.058511
|  |  |  | Grounding | 460 | 449 |  | 0.97609
|  |  |  | Obstruction Brackets | 812 | 133 |  | 0.16379
|  |  |  | # Cables Pulled | 195 | 10 |  | 0.051282
97230 | 97538 | E2 | CLASSON | 24" CMRS Install | 937 | 682 |  | 0.72785 | 0.4969
|  |  |  | Column Clamp | 574 | 237 |  | 0.41289
|  |  |  | Station Brackets | 73 | 1 |  | 0.013699
|  |  |  | Grounding | 135 | 80 |  | 0.59259
|  |  |  | Obstruction Brackets | 91 | 35 |  | 0.38462
|  |  |  | # Cables Pulled | 426 | 362 |  | 0.84977
97538 | 97670 | E2 | CLASSON | 24" CMRS Install | 693 | 62 |  | 0.089466 | 0.54357
|  |  |  | Column Clamp | 741 | 294 |  | 0.39676
|  |  |  | Station Brackets | 975 | 877 |  | 0.89949
|  |  |  | Grounding | 787 | 677 |  | 0.86023
|  |  |  | Obstruction Brackets | 784 | 315 |  | 0.40179
|  |  |  | # Cables Pulled | 717 | 440 |  | 0.61367
97670 | 98015 | E2 | CLA-BED | Steel Mess Supports | 697 | 363 |  | 0.5208 | 0.50215
|  |  |  | Messenger Clamps | 372 | 268 |  | 0.72043
|  |  |  | Messenger Wire Pull | 229 | 40 |  | 0.17467
|  |  |  | Messenger Wire Tension | 249 | 175 |  | 0.70281
|  |  |  | # Cables Pulled | 718 | 164 |  | 0.22841
|  |  |  | Messenger Straps | 757 | 504 |  | 0.66579
98015 | 98125 | E2 | CLA-BED | 24" CMRS Install | 711 | 165 |  | 0.23207 | 0.34138
|  |  |  | Column Clamp | 914 | 291 |  | 0.31838
|  |  |  | Station Brackets | 838 | 219 |  | 0.26134
|  |  |  | Grounding | 919 | 82 |  | 0.089227
|  |  |  | Obstruction Brackets | 614 | 270 |  | 0.43974
|  |  |  | # Cables Pulled | 742 | 525 |  | 0.70755
98125 | 98185 | E2 | CLA-BED | 24" CMRS Install | 490 | 67 |  | 0.13673 | 0.47354
|  |  |  | Column Clamp | 304 | 273 |  | 0.89803
|  |  |  | Station Brackets | 781 | 296 |  | 0.379
|  |  |  | Grounding | 748 | 483 |  | 0.64572
|  |  |  | Obstruction Brackets | 705 | 502 |  | 0.71206
|  |  |  | # Cables Pulled | 976 | 68 |  | 0.069672
98185 | 98440 | E2 | CLA-BED | 24" CMRS Install | 119 | 13 |  | 0.10924 | 0.42237
|  |  |  | Column Clamp | 75 | 27 |  | 0.36
|  |  |  | Station Brackets | 941 | 853 |  | 0.90648
|  |  |  | Grounding | 93 | 10 |  | 0.10753
|  |  |  | Obstruction Brackets | 530 | 27 |  | 0.050943
|  |  |  | # Cables Pulled | 251 | 251 |  | 1
|  | E2 | CLA-BED | Crossover (Arch Bar Installation) | 363 | 231 |  | 0.63636
98440 | 98586 | E2 | CLA-BED | 24" CMRS Install | 287 | 30 |  | 0.10453 | 0.53433
|  |  |  | Column Clamp | 647 | 304 |  | 0.46986
|  |  |  | Station Brackets | 344 | 306 |  | 0.88953
|  |  |  | Grounding | 987 | 286 |  | 0.28977
|  |  |  | Obstruction Brackets | 815 | 614 |  | 0.75337
|  |  |  | # Cables Pulled | 993 | 694 |  | 0.69889
98586 | 98836 | E2 | CLA-BED | Steel Mess Supports | 595 | 51 |  | 0.085714 | 0.34204
|  |  |  | Messenger Clamps | 27 | 10 |  | 0.37037
|  |  |  | Messenger Wire Pull | 493 | 419 |  | 0.8499
|  |  |  | Messenger Wire Tension | 381 | 143 |  | 0.37533
|  |  |  | # Cables Pulled | 612 | 74 |  | 0.12092
|  |  |  | Messenger Straps | 344 | 86 |  | 0.25
98836 | 99505 | E2 | BEDFORD NOSTRAND | Cable Tray Brackets | 697 | 508 |  | 0.72884 | 0.54108
|  |  |  | Installing Tray | 249 | 128 |  | 0.51406
|  |  |  | Core Drilling | 421 | 70 |  | 0.16627
|  |  |  | Cable Pull | 290 | 219 |  | 0.75517
99505 | 99950 | E2 | BED-MYR | Steel Mess Supports | 734 | 693 |  | 0.94414 | 0.71769
|  |  |  | Messenger Clamps | 802 | 74 |  | 0.092269
|  |  |  | Messenger Wire Pull | 331 | 177 |  | 0.53474
|  |  |  | Messenger Wire Tension | 154 | 153 |  | 0.99351
|  |  |  | # Cables Pulled | 822 | 674 |  | 0.81995
|  |  |  | Messenger Straps | 599 | 552 |  | 0.92154
|  | E2 | CLA-BED | Crossover (Arch Bar Installation) | 293 | 93 |  | 0.31741
99950 | 100290 | E2 | BED-MYR | 24" CMRS Install | 897 | 280 |  | 0.31215 | 0.54731
|  |  |  | Column Clamp | 425 | 62 |  | 0.14588
|  |  |  | Station Brackets | 534 | 501 |  | 0.9382
|  |  |  | Grounding | 874 | 866 |  | 0.99085
|  |  |  | Obstruction Brackets | 475 | 314 |  | 0.66105
|  |  |  | # Cables Pulled | 280 | 66 |  | 0.23571
100290 | 100740 | E2 | BED-MYR | 24" CMRS Install | 652 | 357 |  | 0.54755 | 0.43463
|  |  |  | Column Clamp | 987 | 276 |  | 0.27964
|  |  |  | Station Brackets | 42 | 2 |  | 0.047619
|  |  |  | Grounding | 364 | 216 |  | 0.59341
|  |  |  | Obstruction Brackets | 519 | 513 |  | 0.98844
|  |  |  | # Cables Pulled | 258 | 39 |  | 0.15116
100740 | 100792 | E2 | BED-MYR | 24" CMRS Install | 89 | 24 |  | 0.26966 | 0.3849
|  |  |  | Column Clamp | 55 | 11 |  | 0.2
|  |  |  | Station Brackets | 269 | 20 |  | 0.074349
|  |  |  | Grounding | 418 | 258 |  | 0.61722
|  |  |  | Obstruction Brackets | 802 | 611 |  | 0.76185
|  |  |  | # Cables Pulled | 730 | 282 |  | 0.3863
100792 | 101595 | E2 | BED-MYR | 24" CMRS Install | 975 | 116 |  | 0.11897 | 0.29999
|  |  |  | Column Clamp | 140 | 37 |  | 0.26429
|  |  |  | Station Brackets | 190 | 4 |  | 0.021053
|  |  |  | Grounding | 611 | 596 |  | 0.97545
|  |  |  | Obstruction Brackets | 889 | 290 |  | 0.32621
|  |  |  | # Cables Pulled | 532 | 50 |  | 0.093985
101595 | 101688 | E2 | BED-MYR | 24" CMRS Install | 199 | 126 |  | 0.63317 | 0.52958
|  |  |  | Column Clamp | 616 | 436 |  | 0.70779
|  |  |  | Station Brackets | 882 | 235 |  | 0.26644
|  |  |  | Grounding | 380 | 299 |  | 0.78684
|  |  |  | Obstruction Brackets | 630 | 295 |  | 0.46825
|  |  |  | # Cables Pulled | 762 | 240 |  | 0.31496
101688 | 102400 | E2 | MYRTLE AVE | 15" CMRS Install | 891 | 510 |  | 0.57239 | 0.40729
|  |  |  | Column Clamp | 33 | 6 |  | 0.18182
|  |  |  | Station Brackets | 329 | 228 |  | 0.69301
|  |  |  | Grounding | 840 | 471 |  | 0.56071
|  |  |  | Obstruction Brackets | 214 | 19 |  | 0.088785
|  |  |  | # Cables Pulled | 634 | 220 |  | 0.347
102400 | 102550 | E2 | MYR-FLU | Steel Mess Supports | 859 | 455 |  | 0.52969 | 0.54451
|  |  |  | Messenger Clamps | 907 | 142 |  | 0.15656
|  |  |  | Messenger Wire Pull | 253 | 155 |  | 0.61265
|  |  |  | Messenger Wire Tension | 625 | 260 |  | 0.416
|  |  |  | # Cables Pulled | 993 | 905 |  | 0.91138
|  |  |  | Messenger Straps | 206 | 132 |  | 0.64078
102550 | 103165 | E2 | MYR-FLU | 15" CMRS Install | 519 | 413 |  | 0.79576 | 0.53469
|  |  |  | Column Clamp | 813 | 104 |  | 0.12792
|  |  |  | Station Brackets | 192 | 180 |  | 0.9375
|  |  |  | Grounding | 451 | 203 |  | 0.45011
|  |  |  | Obstruction Brackets | 774 | 573 |  | 0.74031
|  |  |  | # Cables Pulled | 115 | 18 |  | 0.15652
103165 | 103230 | E2 | MYR-FLU | 15" CMRS Install | 676 | 145 |  | 0.2145 | 0.47729
|  |  |  | Column Clamp | 280 | 260 |  | 0.92857
|  |  |  | Station Brackets | 225 | 73 |  | 0.32444
|  |  |  | Grounding | 269 | 49 |  | 0.18216
|  |  |  | Obstruction Brackets | 450 | 288 |  | 0.64
|  |  |  | # Cables Pulled | 108 | 62 |  | 0.57407
103230 | 103809 | E2 | MYR-FLU | 15" CMRS Install | 596 | 246 |  | 0.41275 | 0.2644
|  |  |  | Column Clamp | 174 | 80 |  | 0.45977
|  |  |  | Station Brackets | 760 | 114 |  | 0.15
|  |  |  | Grounding | 182 | 34 |  | 0.18681
|  |  |  | Obstruction Brackets | 689 | 43 |  | 0.062409
|  |  |  | # Cables Pulled | 321 | 101 |  | 0.31464
103809 | 103902 | E2 | MYR-FLU | 15" CMRS Install | 231 | 127 |  | 0.54978 | 0.39819
|  |  |  | Column Clamp | 650 | 158 |  | 0.24308
|  |  |  | Station Brackets | 644 | 257 |  | 0.39907
|  |  |  | Grounding | 396 | 184 |  | 0.46465
|  |  |  | Obstruction Brackets | 395 | 190 |  | 0.48101
|  |  |  | # Cables Pulled | 791 | 199 |  | 0.25158
103902 | 104595 | E2 | FLUSHING | 15" CMRS Install | 318 | 176 |  | 0.55346 | 0.60989
|  |  |  | Column Clamp | 954 | 615 |  | 0.64465
|  |  |  | Station Brackets | 709 | 601 |  | 0.84767
|  |  |  | Grounding | 984 | 209 |  | 0.2124
|  |  |  | Obstruction Brackets | 369 | 237 |  | 0.64228
|  |  |  | # Cables Pulled | 647 | 491 |  | 0.75889
104595 | 104750 | E2 | FLU-BRO | Steel Mess Supports | 827 | 673 |  | 0.81378 | 0.58373
|  |  |  | Messenger Clamps | 1000 | 925 |  | 0.925
|  |  |  | Messenger Wire Pull | 691 | 640 |  | 0.92619
|  |  |  | Messenger Wire Tension | 911 | 434 |  | 0.4764
|  |  |  | # Cables Pulled | 631 | 40 |  | 0.063391
|  |  |  | Messenger Straps | 373 | 111 |  | 0.29759
104750 | 105270 | E2 | FLU-BRO | 15" CMRS Install | 508 | 28 |  | 0.055118 | 0.29403
|  |  |  | Column Clamp | 77 | 57 |  | 0.74026
|  |  |  | Station Brackets | 683 | 230 |  | 0.33675
|  |  |  | Grounding | 527 | 47 |  | 0.089184
|  |  |  | Obstruction Brackets | 430 | 14 |  | 0.032558
|  |  |  | # Cables Pulled | 533 | 272 |  | 0.51032
105270 | 105930 | E2 | FLU-BRO | 15" CMRS Install | 532 | 20 |  | 0.037594 | 0.47605
|  |  |  | Column Clamp | 661 | 456 |  | 0.68986
|  |  |  | Station Brackets | 293 | 229 |  | 0.78157
|  |  |  | Grounding | 517 | 23 |  | 0.044487
|  |  |  | Obstruction Brackets | 724 | 541 |  | 0.74724
|  |  |  | # Cables Pulled | 63 | 35 |  | 0.55556
105930 | 106003 | E2 | FLU-BRO | 15" CMRS Install | 827 | 595 |  | 0.71947 | 0.55731
|  |  |  | Column Clamp | 149 | 55 |  | 0.36913
|  |  |  | Station Brackets | 62 | 22 |  | 0.35484
|  |  |  | Grounding | 362 | 288 |  | 0.79558
|  |  |  | Obstruction Brackets | 313 | 228 |  | 0.72843
|  |  |  | # Cables Pulled | 712 | 268 |  | 0.3764
106003 | 106648 | E2 | BROADWAY | 15" CMRS Install | 645 | 8 |  | 0.012403 | 0.36325
|  |  |  | Column Clamp | 223 | 137 |  | 0.61435
|  |  |  | Station Brackets | 828 | 680 |  | 0.82126
|  |  |  | Grounding | 368 | 190 |  | 0.5163
|  |  |  | Obstruction Brackets | 856 | 118 |  | 0.13785
|  |  |  | # Cables Pulled | 362 | 28 |  | 0.077348
|  | E2 | BROADWAY | 15" CMRS Install | 722 | 182 |  | 0.25208 | 0.47567
|  |  |  | Column Clamp | 227 | 188 |  | 0.82819
|  |  |  | Station Brackets | 897 | 616 |  | 0.68673
|  |  |  | Grounding | 891 | 544 |  | 0.61055
|  |  |  | Obstruction Brackets | 720 | 2 |  | 0.0027778
|  |  |  | # Cables Pulled | 38 | 18 |  | 0.47368
|  | E2 | BROADWAY | 15" CMRS Install | 610 | 367 |  | 0.60164 | 0.45379
|  |  |  | Column Clamp | 573 | 396 |  | 0.6911
|  |  |  | Station Brackets | 144 | 71 |  | 0.49306
|  |  |  | Grounding | 52 | 11 |  | 0.21154
|  |  |  | Obstruction Brackets | 664 | 371 |  | 0.55873
|  |  |  | # Cables Pulled | 24 | 4 |  | 0.16667
106650 | 106920 | E2 | BRO-MET | Steel Mess Supports | 351 | 136 |  | 0.38746 | 0.65613
|  |  |  | Messenger Clamps | 152 | 94 |  | 0.61842
|  |  |  | Messenger Wire Pull | 888 | 802 |  | 0.90315
|  |  |  | Messenger Wire Tension | 359 | 287 |  | 0.79944
|  |  |  | # Cables Pulled | 887 | 483 |  | 0.54453
|  |  |  | Messenger Straps | 721 | 493 |  | 0.68377
106918 | 107620 | E2 | BRO-MET | 15" CMRS Install | 883 | 669 |  | 0.75764 | 0.60083
|  |  |  | Column Clamp | 52 | 40 |  | 0.76923
|  |  |  | Station Brackets | 113 | 39 |  | 0.34513
|  |  |  | Grounding | 132 | 89 |  | 0.67424
|  |  |  | Obstruction Brackets | 285 | 282 |  | 0.98947
|  |  |  | # Cables Pulled | 982 | 68 |  | 0.069246
107620 | 107683 | E2 | BRO-MET | 15" CMRS Install | 374 | 81 |  | 0.21658 | 0.45785
|  |  |  | Column Clamp | 800 | 264 |  | 0.33
|  |  |  | Station Brackets | 470 | 58 |  | 0.1234
|  |  |  | Grounding | 451 | 58 |  | 0.1286
|  |  |  | Obstruction Brackets | 655 | 629 |  | 0.96031
|  |  |  | # Cables Pulled | 340 | 336 |  | 0.98824
107683 | 108360 | E2 | BRO-MET | 15" CMRS Install | 290 | 71 |  | 0.24483 | 0.47588
|  |  |  | Column Clamp | 617 | 150 |  | 0.24311
|  |  |  | Station Brackets | 302 | 188 |  | 0.62252
|  |  |  | Grounding | 394 | 123 |  | 0.31218
|  |  |  | Obstruction Brackets | 445 | 278 |  | 0.62472
|  |  |  | # Cables Pulled | 151 | 122 |  | 0.80795
108360 | 109235 | E2 | METROPOLITAN | 15" CMRS Install | 61 | 21 |  | 0.34426 | 0.58479
|  |  |  | Column Clamp | 143 | 28 |  | 0.1958
|  |  |  | Station Brackets | 710 | 286 |  | 0.40282
|  |  |  | Grounding | 777 | 710 |  | 0.91377
|  |  |  | Obstruction Brackets | 543 | 432 |  | 0.79558
|  |  |  | # Cables Pulled | 906 | 776 |  | 0.85651
109235 | 110795 | E2 | MET-NAS | 24" CMRS Install | 893 | 455 |  | 0.50952 | 0.40027
|  |  |  | Column Clamp | 812 | 180 |  | 0.22167
|  |  |  | Station Brackets | 138 | 133 |  | 0.96377
|  |  |  | Grounding | 353 | 71 |  | 0.20113
|  |  |  | Obstruction Brackets | 908 | 5 |  | 0.0055066
|  |  |  | # Cables Pulled | 22 | 11 |  | 0.5
110795 | 110865 | E2 | MET-NAS | 24" CMRS Install | 217 | 74 |  | 0.34101 | 0.59816
|  |  |  | Column Clamp | 93 | 46 |  | 0.49462
|  |  |  | Station Brackets | 579 | 479 |  | 0.82729
|  |  |  | Grounding | 266 | 184 |  | 0.69173
|  |  |  | Obstruction Brackets | 554 | 414 |  | 0.74729
|  |  |  | # Cables Pulled | 154 | 75 |  | 0.48701
110865 | 113020 | E2 | MET-NAS | 24" CMRS Install | 960 | 165 |  | 0.17188 | 0.32898
|  |  |  | Column Clamp | 253 | 102 |  | 0.40316
|  |  |  | Station Brackets | 985 | 313 |  | 0.31777
|  |  |  | Grounding | 948 | 651 |  | 0.68671
|  |  |  | Obstruction Brackets | 679 | 52 |  | 0.076583
|  |  |  | # Cables Pulled | 985 | 313 |  | 0.31777
113020 | 113155 | E2 | MET-NAS | 24" CMRS Install | 481 | 380 |  | 0.79002 | 0.57376
|  |  |  | Column Clamp | 416 | 241 |  | 0.57933
|  |  |  | Station Brackets | 88 | 76 |  | 0.86364
|  |  |  | Grounding | 483 | 131 |  | 0.27122
|  |  |  | Obstruction Brackets | 765 | 477 |  | 0.62353
|  |  |  | # Cables Pulled | 559 | 176 |  | 0.31485
113155 | 113815 | E2 | NASSAU | 24" CMRS Install | 74 | 63 |  | 0.85135 | 0.56878
|  |  |  | Column Clamp | 552 | 492 |  | 0.8913
|  |  |  | Station Brackets | 918 | 448 |  | 0.48802
|  |  |  | Grounding | 159 | 21 |  | 0.13208
|  |  |  | Obstruction Brackets | 447 | 258 |  | 0.57718
|  |  |  | # Cables Pulled | 349 | 165 |  | 0.47278
113815 | 114105 | E2 | NAS-GRE | Steel Mess Supports | 821 | 44 |  | 0.053593 | 0.51083
|  |  |  | Messenger Clamps | 583 | 385 |  | 0.66038
|  |  |  | Messenger Wire Pull | 877 | 752 |  | 0.85747
|  |  |  | Messenger Wire Tension | 466 | 375 |  | 0.80472
|  |  |  | # Cables Pulled | 414 | 77 |  | 0.18599
|  |  |  | Messenger Straps | 710 | 357 |  | 0.50282
114105 | 114730 | E2 | NAS-GRE | 24" CMRS Install | 225 | 150 |  | 0.66667 | 0.46137
|  |  |  | Column Clamp | 808 | 304 |  | 0.37624
|  |  |  | Station Brackets | 453 | 185 |  | 0.40839
|  |  |  | Grounding | 580 | 429 |  | 0.73966
|  |  |  | Obstruction Brackets | 626 | 144 |  | 0.23003
|  |  |  | # Cables Pulled | 72 | 25 |  | 0.34722
114730 | 114910 | E2 | NAS-GRE | Steel Mess Supports | 392 | 74 |  | 0.18878 | 0.73785
|  |  |  | Messenger Clamps | 252 | 184 |  | 0.73016
|  |  |  | Messenger Wire Pull | 74 | 73 |  | 0.98649
|  |  |  | Messenger Wire Tension | 807 | 671 |  | 0.83147
|  |  |  | # Cables Pulled | 958 | 783 |  | 0.81733
|  |  |  | Messenger Straps | 354 | 309 |  | 0.87288
114910 | 115625 | E2 | NAS-GRE | 24" CMRS Install | 272 | 27 |  | 0.099265 | 0.40419
|  |  |  | Column Clamp | 233 | 144 |  | 0.61803
|  |  |  | Station Brackets | 650 | 415 |  | 0.63846
|  |  |  | Grounding | 556 | 288 |  | 0.51799
|  |  |  | Obstruction Brackets | 914 | 504 |  | 0.55142
|  |  |  | # Cables Pulled | 22 | 0 |  | 0
115625 | 116435 | E2 | GREENPOINT | 24" CMRS Install | 955 | 33 |  | 0.034555 | 0.41226
|  |  |  | Column Clamp | 888 | 792 |  | 0.89189
|  |  |  | Station Brackets | 506 | 288 |  | 0.56917
|  |  |  | Grounding | 446 | 166 |  | 0.3722
|  |  |  | Obstruction Brackets | 108 | 39 |  | 0.36111
|  |  |  | # Cables Pulled | 233 | 57 |  | 0.24464
116435 | 117130 | E2 | GRE-21S | 24" CMRS Install | 211 | 91 |  | 0.43128 | 0.65716
|  |  |  | Column Clamp | 805 | 780 |  | 0.96894
|  |  |  | Station Brackets | 77 | 70 |  | 0.90909
|  |  |  | Grounding | 759 | 634 |  | 0.83531
|  |  |  | Obstruction Brackets | 938 | 617 |  | 0.65778
|  |  |  | # Cables Pulled | 491 | 69 |  | 0.14053
|  | E2 | GRE-21S | Crossover (Arch Bar Installation) | 206 | 72 |  | 0.34951
117130 | 121035 | E2 | GRE-21S | 24" CMRS Install | 899 | 708 |  | 0.78754 | 0.34486
|  |  |  | Column Clamp | 69 | 29 |  | 0.42029
|  |  |  | Station Brackets | 110 | 11 |  | 0.1
|  |  |  | Grounding | 162 | 51 |  | 0.31481
|  |  |  | Obstruction Brackets | 677 | 238 |  | 0.35155
|  |  |  | # Cables Pulled | 495 | 47 |  | 0.094949
121035 | 122030 | E2 | 21ST STATION | Steel Mess Supports | 870 | 611 |  | 0.7023 | 0.43275
|  |  |  | Messenger Clamps | 495 | 104 |  | 0.2101
|  |  |  | Messenger Wire Pull | 601 | 229 |  | 0.38103
|  |  |  | Messenger Wire Tension | 176 | 81 |  | 0.46023
|  |  |  | # Cables Pulled | 182 | 54 |  | 0.2967
|  |  |  | Messenger Straps | 130 | 71 |  | 0.54615
122030 | 122430 | E2 | 21S-COU | 24" CMRS Install | 410 | 200 |  | 0.4878 | 0.54183
|  |  |  | Column Clamp | 756 | 99 |  | 0.13095
|  |  |  | Station Brackets | 726 | 504 |  | 0.69421
|  |  |  | Grounding | 493 | 145 |  | 0.29412
|  |  |  | Obstruction Brackets | 467 | 362 |  | 0.77516
|  |  |  | # Cables Pulled | 655 | 569 |  | 0.8687
122430 | 122660 | E2 | 21S-COU | Steel Mess Supports | 605 | 595 |  | 0.98347 | 0.60874
|  |  |  | Messenger Clamps | 338 | 284 |  | 0.84024
|  |  |  | Messenger Wire Pull | 15 | 13 |  | 0.86667
|  |  |  | Messenger Wire Tension | 228 | 65 |  | 0.28509
|  |  |  | # Cables Pulled | 468 | 17 |  | 0.036325
|  |  |  | Messenger Straps | 615 | 394 |  | 0.64065
122660 | 122827 | E2 | 21S-COU | 24" CMRS Install | 51 | 50 |  | 0.98039 | 0.5142
|  |  |  | Column Clamp | 593 | 103 |  | 0.17369
|  |  |  | Station Brackets | 53 | 15 |  | 0.28302
|  |  |  | Grounding | 436 | 349 |  | 0.80046
|  |  |  | Obstruction Brackets | 989 | 130 |  | 0.13145
|  |  |  | # Cables Pulled | 983 | 704 |  | 0.71617
122827 | 123085 | E2 | 21S-COU | Steel Mess Supports | 515 | 350 |  | 0.67961 | 0.35231
|  |  |  | Messenger Clamps | 777 | 228 |  | 0.29344
|  |  |  | Messenger Wire Pull | 334 | 44 |  | 0.13174
|  |  |  | Messenger Wire Tension | 696 | 485 |  | 0.69684
|  |  |  | # Cables Pulled | 569 | 89 |  | 0.15641
|  |  |  | Messenger Straps | 77 | 12 |  | 0.15584
123085 | 123690 | E2 | COURT SQ | Cable Tray Brackets | 981 | 279 |  | 0.2844 | 0.4174
|  |  |  | Installing Tray | 788 | 611 |  | 0.77538
|  |  |  | Core Drilling | 815 | 72 |  | 0.088344
|  |  |  | Cable Pull | 303 | 158 |  | 0.52145
123690 | 123750 | E2 | COU-QUE | Steel Mess Supports | 796 | 10 |  | 0.012563 | 0.31035
|  |  |  | Messenger Clamps | 867 | 562 |  | 0.64821
|  |  |  | Messenger Wire Pull | 265 | 12 |  | 0.045283
|  |  |  | Messenger Wire Tension | 900 | 408 |  | 0.45333
|  |  |  | # Cables Pulled | 703 | 160 |  | 0.2276
|  |  |  | Messenger Straps | 482 | 229 |  | 0.4751
123750 | 123950 | E2 | COU-QUE | Steel Mess Supports | 302 | 74 |  | 0.24503 | 0.52158
|  |  |  | Messenger Clamps | 13 | 10 |  | 0.76923
|  |  |  | Messenger Wire Pull | 634 | 216 |  | 0.34069
|  |  |  | Messenger Wire Tension | 967 | 228 |  | 0.23578
|  |  |  | # Cables Pulled | 545 | 359 |  | 0.65872
|  |  |  | Messenger Straps | 25 | 22 |  | 0.88
123950 | 124050 | E2 | COU-QUE | Steel Mess Supports | 112 | 59 |  | 0.52679 | 0.6846
|  |  |  | Messenger Clamps | 972 | 413 |  | 0.4249
|  |  |  | Messenger Wire Pull | 995 | 567 |  | 0.56985
|  |  |  | Messenger Wire Tension | 895 | 837 |  | 0.9352
|  |  |  | # Cables Pulled | 915 | 649 |  | 0.70929
|  |  |  | Messenger Straps | 308 | 290 |  | 0.94156
124050 | 124190 | E2 | COU-QUE | Steel Mess Supports | 681 | 495 |  | 0.72687 | 0.45447
|  |  |  | Messenger Clamps | 951 | 680 |  | 0.71504
|  |  |  | Messenger Wire Pull | 81 | 5 |  | 0.061728
|  |  |  | Messenger Wire Tension | 602 | 46 |  | 0.076412
|  |  |  | # Cables Pulled | 408 | 233 |  | 0.57108
|  |  |  | Messenger Straps | 773 | 445 |  | 0.57568
124190 | 124490 | E2 | COU-QUE | Steel Mess Supports | 687 | 430 |  | 0.62591 | 0.5461
|  |  |  | Messenger Clamps | 244 | 193 |  | 0.79098
|  |  |  | Messenger Wire Pull | 867 | 432 |  | 0.49827
|  |  |  | Messenger Wire Tension | 886 | 360 |  | 0.40632
|  |  |  | # Cables Pulled | 1000 | 727 |  | 0.727
|  |  |  | Messenger Straps | 263 | 60 |  | 0.22814
124490 | 124700 | E2 | COU-QUE | Steel Mess Supports | 753 | 696 |  | 0.9243 | 0.70513
|  |  |  | Messenger Clamps | 429 | 402 |  | 0.93706
|  |  |  | Messenger Wire Pull | 763 | 518 |  | 0.6789
|  |  |  | Messenger Wire Tension | 878 | 206 |  | 0.23462
|  |  |  | # Cables Pulled | 702 | 542 |  | 0.77208
|  |  |  | Messenger Straps | 835 | 571 |  | 0.68383
124700 | 125010 | E2 | COU-QUE | Steel Mess Supports | 554 | 537 |  | 0.96931 | 0.37605
|  |  |  | Messenger Clamps | 558 | 28 |  | 0.050179
|  |  |  | Messenger Wire Pull | 385 | 228 |  | 0.59221
|  |  |  | Messenger Wire Tension | 536 | 113 |  | 0.21082
|  |  |  | # Cables Pulled | 560 | 223 |  | 0.39821
|  |  |  | Messenger Straps | 478 | 17 |  | 0.035565
|  | E2 | COU-QUE | Crossover (Arch Bar Installation) | 285 | 153 |  | 0.53684
75650 | 78244 | B3 | BERGEN ST | Steel Mess Supports | 860 | 509 |  | 0.59186 | 0.70157
|  |  |  | Messenger Clamps | 211 | 134 |  | 0.63507
|  |  |  | Messenger Wire Pull | 324 | 286 |  | 0.88272
|  |  |  | Messenger Wire Tension | 750 | 561 |  | 0.748
|  |  |  | # Cables Pulled | 627 | 401 |  | 0.63955
|  |  |  | Messenger Straps | 973 | 693 |  | 0.71223
|  | B3 | BER-JAY | Steel Mess Supports | 377 | 329 |  | 0.87268 | 0.58358
|  |  |  | Messenger Clamps | 420 | 335 |  | 0.79762
|  |  |  | Messenger Wire Pull | 168 | 29 |  | 0.17262
|  |  |  | Messenger Wire Tension | 713 | 343 |  | 0.48107
|  |  |  | # Cables Pulled | 250 | 110 |  | 0.44
|  |  |  | Messenger Straps | 240 | 177 |  | 0.7375
|  | B4 | BER-JAY | Steel Mess Supports | 878 | 621 |  | 0.70729 | 0.58878
|  |  |  | Messenger Clamps | 865 | 109 |  | 0.12601
|  |  |  | Messenger Wire Pull | 157 | 77 |  | 0.49045
|  |  |  | Messenger Wire Tension | 172 | 58 |  | 0.33721
|  |  |  | # Cables Pulled | 920 | 802 |  | 0.87174
|  |  |  | Messenger Straps | 423 | 423 |  | 1
|  | E3/E4 | COURT SQ | Steel Mess Supports | 796 | 278 |  | 0.34925 | 0.49026
|  |  |  | Messenger Clamps | 794 | 185 |  | 0.233
|  |  |  | Messenger Wire Pull | 283 | 36 |  | 0.12721
|  |  |  | Messenger Wire Tension | 104 | 34 |  | 0.32692
|  |  |  | # Cables Pulled | 904 | 871 |  | 0.9635
|  |  |  | Messenger Straps | 583 | 549 |  | 0.94168
75640 | 75300 | B1 | BER-CAR | Steel Mess Supports | 73 | 39 |  | 0.53425 | 0.56492
|  |  |  | Messenger Clamps | 540 | 263 |  | 0.48704
|  |  |  | Messenger Wire Pull | 368 | 185 |  | 0.50272
|  |  |  | Messenger Wire Tension | 813 | 709 |  | 0.87208
|  |  |  | # Cables Pulled | 608 | 300 |  | 0.49342
|  |  |  | Messenger Straps | 144 | 72 |  | 0.5
68570 | 68330 | B3 | 4TH AVE | Steel Mess Supports | 961 | 301 |  | 0.31322 | 0.41417
|  |  |  | Messenger Clamps | 461 | 140 |  | 0.30369
|  |  |  | Messenger Wire Pull | 719 | 539 |  | 0.74965
|  |  |  | Messenger Wire Tension | 185 | 41 |  | 0.22162
|  |  |  | # Cables Pulled | 919 | 455 |  | 0.4951
|  |  |  | Messenger Straps | 458 | 184 |  | 0.40175
68330 | 68030 | B3 | 4AV-7AV | Steel Mess Supports | 906 | 241 |  | 0.266 | 0.39758
|  |  |  | Messenger Clamps | 947 | 732 |  | 0.77297
|  |  |  | Messenger Wire Pull | 782 | 247 |  | 0.31586
|  |  |  | Messenger Wire Tension | 379 | 123 |  | 0.32454
|  |  |  | # Cables Pulled | 455 | 137 |  | 0.3011
|  |  |  | Messenger Straps | 716 | 290 |  | 0.40503
66070 | 66000 | B3 | 4AV-7AV | Steel Mess Supports | 790 | 133 |  | 0.16835 | 0.40111
|  |  |  | Messenger Clamps | 343 | 212 |  | 0.61808
|  |  |  | Messenger Wire Pull | 932 | 706 |  | 0.75751
|  |  |  | Messenger Wire Tension | 88 | 33 |  | 0.375
|  |  |  | # Cables Pulled | 665 | 316 |  | 0.47519
|  |  |  | Messenger Straps | 798 | 10 |  | 0.012531
60350 | 60000 | B1 | 15S-FOR | Steel Mess Supports | 405 | 204 |  | 0.5037 | 0.46251
|  |  |  | Messenger Clamps | 453 | 308 |  | 0.67991
|  |  |  | Messenger Wire Pull | 955 | 15 |  | 0.015707
|  |  |  | Messenger Wire Tension | 48 | 48 |  | 1
|  |  |  | # Cables Pulled | 240 | 133 |  | 0.55417
|  |  |  | Messenger Straps | 417 | 9 |  | 0.021583
56440 | 56350 | B1 | FOR-CHU | Steel Mess Supports | 432 | 371 |  | 0.8588 | 0.55084
|  |  |  | Messenger Clamps | 138 | 117 |  | 0.84783
|  |  |  | Messenger Wire Pull | 645 | 324 |  | 0.50233
|  |  |  | Messenger Wire Tension | 709 | 579 |  | 0.81664
|  |  |  | # Cables Pulled | 270 | 55 |  | 0.2037
|  |  |  | Messenger Straps | 198 | 15 |  | 0.075758
55580 | 54500 | B2 | CHU-DIT | Steel Mess Supports | 926 | 586 |  | 0.63283 | 0.69611
|  |  |  | Messenger Clamps | 139 | 124 |  | 0.89209
|  |  |  | Messenger Wire Pull | 950 | 590 |  | 0.62105
|  |  |  | Messenger Wire Tension | 35 | 17 |  | 0.48571
|  |  |  | # Cables Pulled | 156 | 141 |  | 0.90385
|  |  |  | Messenger Straps | 574 | 368 |  | 0.64111
54730 | 55000 | B2 | CHU-DIT | Steel Mess Supports | 819 | 5 |  | 0.006105 | 0.53882
|  |  |  | Messenger Clamps | 27 | 15 |  | 0.55556
|  |  |  | Messenger Wire Pull | 595 | 553 |  | 0.92941
|  |  |  | Messenger Wire Tension | 736 | 388 |  | 0.52717
|  |  |  | # Cables Pulled | 286 | 133 |  | 0.46503
|  |  |  | Messenger Straps | 751 | 563 |  | 0.74967
55485 | 55725 | B2 | CHU-DIT | Steel Mess Supports | 219 | 130 |  | 0.59361 | 0.46563
|  |  |  | Messenger Clamps | 137 | 34 |  | 0.24818
|  |  |  | Messenger Wire Pull | 254 | 138 |  | 0.54331
|  |  |  | Messenger Wire Tension | 235 | 118 |  | 0.50213
|  |  |  | # Cables Pulled | 1000 | 534 |  | 0.534
|  |  |  | Messenger Straps | 51 | 19 |  | 0.37255
55725 | 56635 | B2 | CHURCH AVE | Steel Mess Supports | 440 | 314 |  | 0.71364 | 0.57383
|  |  |  | Messenger Clamps | 238 | 114 |  | 0.47899
|  |  |  | Messenger Wire Pull | 445 | 387 |  | 0.86966
|  |  |  | Messenger Wire Tension | 116 | 97 |  | 0.83621
|  |  |  | # Cables Pulled | 297 | 11 |  | 0.037037
|  |  |  | Messenger Straps | 67 | 34 |  | 0.50746
57320 | 57445 | B2 | CHU-FOR | Steel Mess Supports | 688 | 630 |  | 0.9157 | 0.32443
|  |  |  | Messenger Clamps | 927 | 235 |  | 0.25351
|  |  |  | Messenger Wire Pull | 432 | 10 |  | 0.023148
|  |  |  | Messenger Wire Tension | 461 | 174 |  | 0.37744
|  |  |  | # Cables Pulled | 832 | 161 |  | 0.19351
|  |  |  | Messenger Straps | 251 | 46 |  | 0.18327
60165 | 60620 | B2 | 15S-FOR | Steel Mess Supports | 609 | 115 |  | 0.18883 | 0.4742
|  |  |  | Messenger Clamps | 696 | 62 |  | 0.08908
|  |  |  | Messenger Wire Pull | 139 | 79 |  | 0.56835
|  |  |  | Messenger Wire Tension | 961 | 461 |  | 0.47971
|  |  |  | # Cables Pulled | 949 | 497 |  | 0.52371
|  |  |  | Messenger Straps | 898 | 894 |  | 0.99555
62560 | 63425 | B2 | 15TH STREET PROSPECT PARK | Steel Mess Supports | 33 | 25 |  | 0.75758 | 0.43505
|  |  |  | Messenger Clamps | 604 | 63 |  | 0.1043
|  |  |  | Messenger Wire Pull | 640 | 10 |  | 0.015625
|  |  |  | Messenger Wire Tension | 606 | 439 |  | 0.72442
|  |  |  | # Cables Pulled | 535 | 367 |  | 0.68598
|  |  |  | Messenger Straps | 977 | 315 |  | 0.32242
67950 | 68330 | B4/B2 | 4AV-7AV | Steel Mess Supports | 561 | 301 |  | 0.53654 | 0.48568
|  |  |  | Messenger Clamps | 879 | 23 |  | 0.026166
|  |  |  | Messenger Wire Pull | 294 | 43 |  | 0.14626
|  |  |  | Messenger Wire Tension | 167 | 165 |  | 0.98802
|  |  |  | # Cables Pulled | 765 | 341 |  | 0.44575
|  |  |  | Messenger Straps | 831 | 641 |  | 0.77136
74740 | 74840 | B2 | CAR-BER | Steel Mess Supports | 714 | 347 |  | 0.48599 | 0.42121
|  |  |  | Messenger Clamps | 557 | 127 |  | 0.22801
|  |  |  | Messenger Wire Pull | 832 | 385 |  | 0.46274
|  |  |  | Messenger Wire Tension | 280 | 126 |  | 0.45
|  |  |  | # Cables Pulled | 768 | 204 |  | 0.26562
|  |  |  | Messenger Straps | 189 | 120 |  | 0.63492
75395 | 75650 | B2 | CAR-BER | Steel Mess Supports | 284 | 160 |  | 0.56338 | 0.60465
|  |  |  | Messenger Clamps | 975 | 399 |  | 0.40923
|  |  |  | Messenger Wire Pull | 882 | 634 |  | 0.71882
|  |  |  | Messenger Wire Tension | 861 | 371 |  | 0.43089
|  |  |  | # Cables Pulled | 60 | 37 |  | 0.61667
|  |  |  | Messenger Straps | 198 | 176 |  | 0.88889
78905 | 75950 | B3 | JAY-BER | Steel Mess Supports | 621 | 361 |  | 0.58132 | 0.49603
|  |  |  | Messenger Clamps | 517 | 74 |  | 0.14313
|  |  |  | Messenger Wire Pull | 335 | 213 |  | 0.63582
|  |  |  | Messenger Wire Tension | 718 | 576 |  | 0.80223
|  |  |  | # Cables Pulled | 866 | 533 |  | 0.61547
|  |  |  | Messenger Straps | 888 | 176 |  | 0.1982
75950 | 75650 | B3 | BERGEN ST | Steel Mess Supports | 129 | 129 |  | 1 | 0.61388
|  |  |  | Messenger Clamps | 85 | 37 |  | 0.43529
|  |  |  | Messenger Wire Pull | 562 | 353 |  | 0.62811
|  |  |  | Messenger Wire Tension | 783 | 241 |  | 0.30779
|  |  |  | # Cables Pulled | 590 | 396 |  | 0.67119
|  |  |  | Messenger Straps | 802 | 514 |  | 0.6409
75650 | 75420 | B3 | BER-CAR | Steel Mess Supports | 606 | 566 |  | 0.93399 | 0.48848
|  |  |  | Messenger Clamps | 493 | 155 |  | 0.3144
|  |  |  | Messenger Wire Pull | 496 | 31 |  | 0.0625
|  |  |  | Messenger Wire Tension | 675 | 304 |  | 0.45037
|  |  |  | # Cables Pulled | 632 | 115 |  | 0.18196
|  |  |  | Messenger Straps | 808 | 798 |  | 0.98762
73285 | 72960 | B3 | BER-CAR | Steel Mess Supports | 922 | 277 |  | 0.30043 | 0.43871
|  |  |  | Messenger Clamps | 563 | 116 |  | 0.20604
|  |  |  | Messenger Wire Pull | 192 | 32 |  | 0.16667
|  |  |  | Messenger Wire Tension | 585 | 451 |  | 0.77094
|  |  |  | # Cables Pulled | 187 | 81 |  | 0.43316
|  |  |  | Messenger Straps | 298 | 225 |  | 0.75503
72960 | 72035 | B3/B4 | CAR-4TH | Steel Mess Supports | 712 | 400 |  | 0.5618 | 0.50659
|  |  |  | Messenger Clamps | 925 | 264 |  | 0.28541
|  |  |  | Messenger Wire Pull | 756 | 663 |  | 0.87698
|  |  |  | Messenger Wire Tension | 941 | 182 |  | 0.19341
|  |  |  | # Cables Pulled | 282 | 104 |  | 0.36879
|  |  |  | Messenger Straps | 956 | 720 |  | 0.75314
71150 | 70965 | B3/B4 | CAR-4TH | Steel Mess Supports | 654 | 455 |  | 0.69572 | 0.61797
|  |  |  | Messenger Clamps | 420 | 397 |  | 0.94524
|  |  |  | Messenger Wire Pull | 885 | 743 |  | 0.83955
|  |  |  | Messenger Wire Tension | 432 | 259 |  | 0.59954
|  |  |  | # Cables Pulled | 783 | 429 |  | 0.54789
|  |  |  | Messenger Straps | 288 | 23 |  | 0.079861
70965 | 70445 | B3/B6 | CAR-4TH | Steel Mess Supports | 766 | 361 |  | 0.47128 | 0.46336
|  |  |  | Messenger Clamps | 215 | 38 |  | 0.17674
|  |  |  | Messenger Wire Pull | 130 | 82 |  | 0.63077
|  |  |  | Messenger Wire Tension | 222 | 81 |  | 0.36486
|  |  |  | # Cables Pulled | 681 | 278 |  | 0.40822
|  |  |  | Messenger Straps | 979 | 713 |  | 0.72829
70445 | 70045 | B3/B7 | CAR-4TH | Steel Mess Supports | 969 | 352 |  | 0.36326 | 0.68283
|  |  |  | Messenger Clamps | 816 | 721 |  | 0.88358
|  |  |  | Messenger Wire Pull | 480 | 352 |  | 0.73333
|  |  |  | Messenger Wire Tension | 264 | 230 |  | 0.87121
|  |  |  | # Cables Pulled | 29 | 12 |  | 0.41379
|  |  |  | Messenger Straps | 428 | 356 |  | 0.83178
68625 | 68400 | B3/B8 | CAR-4TH | Steel Mess Supports | 758 | 422 |  | 0.55673 | 0.47043
|  |  |  | Messenger Clamps | 745 | 312 |  | 0.41879
|  |  |  | Messenger Wire Pull | 853 | 123 |  | 0.1442
|  |  |  | Messenger Wire Tension | 93 | 46 |  | 0.49462
|  |  |  | # Cables Pulled | 22 | 9 |  | 0.40909
|  |  |  | Messenger Straps | 702 | 561 |  | 0.79915
68400 | 68330 | B3/B9 | CAR-4TH | Steel Mess Supports | 934 | 921 |  | 0.98608 | 0.55624
|  |  |  | Messenger Clamps | 896 | 667 |  | 0.74442
|  |  |  | Messenger Wire Pull | 379 | 112 |  | 0.29551
|  |  |  | Messenger Wire Tension | 302 | 255 |  | 0.84437
|  |  |  | # Cables Pulled | 377 | 44 |  | 0.11671
|  |  |  | Messenger Straps | 548 | 192 |  | 0.35036

## AXLE COUNTER
Stationing | Track No | Location | Activity | Date | Progress | General Progress | Notes | DWG REF.
54600 | B1 | DIT-CHU | Axle Counter Installation |  | 19.49% | 31.44% | STATIONING SHOWN IS THAT OF THE NEAREST IJ, AXC STATIONING DOES NOT EXIST | B1-546
|  |  | JB Installation |  | 12.19%
|  |  | Line Cable Installation |  | 21.78%
|  |  | Express Cable Installation |  | 7.434%
|  |  | Pre-Operation Testing |  | 96.28%
| B1 |  | Axle Counter Installation |  | 14.49% | 52.13% | NO INFO | B1-547
|  |  | JB Installation |  | 67.96%
|  |  | Line Cable Installation |  | 82.93%
|  |  | Express Cable Installation |  | 19.18%
|  |  | Pre-Operation Testing |  | 76.09%
59297 | B1 | FOR-15S | Axle Counter Installation |  | 42.44% | 55.53% |  | B1-553
|  |  | JB Installation |  | 12.19%
|  |  | Line Cable Installation |  | 86.96%
|  |  | Express Cable Installation |  | 69.43%
|  |  | Pre-Operation Testing |  | 66.64%
| B1 |  | Axle Counter Installation |  | 56% | 65.69% | NO INFO | B1-554
|  |  | JB Installation |  | 6.2%
|  |  | Line Cable Installation |  | 83.27%
|  |  | Express Cable Installation |  | 90.58%
|  |  | Pre-Operation Testing |  | 92.42%
55687 | B1 | DIT-CHU | Axle Counter Installation |  | 82.21% | 42.73% |  | B1-557
|  |  | JB Installation |  | 9.016%
|  |  | Line Cable Installation |  | 41.28%
|  |  | Express Cable Installation |  | 16.11%
|  |  | Pre-Operation Testing |  | 65.04%
56367 | B1 | CHU-FOR | Axle Counter Installation |  | 35.73% | 50.96% |  | B1-564
|  |  | JB Installation |  | 52.11%
|  |  | Line Cable Installation |  | 41.77%
|  |  | Express Cable Installation |  | 57.21%
|  |  | Pre-Operation Testing |  | 68%
58524.6 | B1 | FORT HAMILTON PARKWAY | Axle Counter Installation |  | 2.19% | 55.69% |  | B1-585
|  |  | JB Installation |  | 35.09%
|  |  | Line Cable Installation |  | 90.05%
|  |  | Express Cable Installation |  | 55.5%
|  |  | Pre-Operation Testing |  | 95.63%
59210.25 | B1 | FOR-15S | Axle Counter Installation |  | 9.861% | 48.45% |  | B1-592
|  |  | JB Installation |  | 97.45%
|  |  | Line Cable Installation |  | 50.31%
|  |  | Express Cable Installation |  | 9.4%
|  |  | Pre-Operation Testing |  | 75.22%
62572.5 | B1 | FOR-15S | Axle Counter Installation |  | 31.66% | 44.42% |  | B1-626
|  |  | JB Installation |  | 56.33%
|  |  | Line Cable Installation |  | 24.54%
|  |  | Express Cable Installation |  | 17.53%
|  |  | Pre-Operation Testing |  | 92.04%
63251.4 | B1 | 15S-7AV | Axle Counter Installation |  | 34.63% | 38.2% |  | B1-632
|  |  | JB Installation |  | 17.28%
|  |  | Line Cable Installation |  | 36.39%
|  |  | Express Cable Installation |  | 77.49%
|  |  | Pre-Operation Testing |  | 25.19%
65387.3 | B1 | 15S-7AV | Axle Counter Installation |  | 41.35% | 38.29% |  | B1-654
|  |  | JB Installation |  | 50.9%
|  |  | Line Cable Installation |  | 24.28%
|  |  | Express Cable Installation |  | 18.14%
|  |  | Pre-Operation Testing |  | 56.77%
66076 | B1 | 7AV-4TH | Axle Counter Installation |  | 62.28% | 33.9% |  | B1-661
|  |  | JB Installation |  | 44.9%
|  |  | Line Cable Installation |  | 29.85%
|  |  | Express Cable Installation |  | 10.2%
|  |  | Pre-Operation Testing |  | 22.28%
73206.7 | B1 | SMI-CAR | Axle Counter Installation |  | 74.39% | 66.19% |  | B1-732
|  |  | JB Installation |  | 91.93%
|  |  | Line Cable Installation |  | 44.26%
|  |  | Express Cable Installation |  | 53.52%
|  |  | Pre-Operation Testing |  | 66.83%
73932 | B1 | CAR-BER | Axle Counter Installation |  | 72.27% | 65.14% |  | B1-739
|  |  | JB Installation |  | 73.95%
|  |  | Line Cable Installation |  | 55.57%
|  |  | Express Cable Installation |  | 55.6%
|  |  | Pre-Operation Testing |  | 68.29%
75408 | B1 | CAR-BER | Axle Counter Installation |  | 5.729% | 36.56% |  | B1-755
|  |  | JB Installation |  | 1.171%
|  |  | Line Cable Installation |  | 79.02%
|  |  | Express Cable Installation |  | 53%
|  |  | Pre-Operation Testing |  | 43.9%
75669 | B1 | CAR-BER | Axle Counter Installation |  | 45.71% | 45.77% |  | B1-756
|  |  | JB Installation |  | 71%
|  |  | Line Cable Installation |  | 37.75%
|  |  | Express Cable Installation |  | 6.254%
|  |  | Pre-Operation Testing |  | 68.12%
76352 | B1 | BER-HOY | Axle Counter Installation |  | 33.57% | 45.68% |  | B1-763, B1-764
|  |  | JB Installation |  | 49.37%
|  |  | Line Cable Installation |  | 36.94%
|  |  | Express Cable Installation |  | 15.22%
|  |  | Pre-Operation Testing |  | 93.29%
76589 | B1 | HOYT-SCHERMERHORN | Axle Counter Installation |  | 70.83% | 51.34% |  | B1-766
|  |  | JB Installation |  | 65.62%
|  |  | Line Cable Installation |  | 38.96%
|  |  | Express Cable Installation |  | 71.73%
|  |  | Pre-Operation Testing |  | 9.568%
76901.5 | B1 | HOY-FUL | Axle Counter Installation |  | 56.95% | 53.16% |  | B1-770
|  |  | JB Installation |  | 76.69%
|  |  | Line Cable Installation |  | 39.78%
|  |  | Express Cable Installation |  | 13.35%
|  |  | Pre-Operation Testing |  | 79.02%
77088 | B1 | FUL-CLI | Axle Counter Installation |  | 83.41% | 51.82% |  | B1-771
|  |  | JB Installation |  | 72.15%
|  |  | Line Cable Installation |  | 62.69%
|  |  | Express Cable Installation |  | 16.97%
|  |  | Pre-Operation Testing |  | 23.88%
54737 | B2 | DIT-CHU | Axle Counter Installation |  | 58.64% | 58.12% |  | B2-546
|  |  | JB Installation |  | 34.52%
|  |  | Line Cable Installation |  | 72.14%
|  |  | Express Cable Installation |  | 69.24%
|  |  | Pre-Operation Testing |  | 56.05%
54731 | B2 |  | Axle Counter Installation |  | 36.07% | 43.94% |  | B2-547
|  |  | JB Installation |  | 38.84%
|  |  | Line Cable Installation |  | 43.01%
|  |  | Express Cable Installation |  | 44.38%
|  |  | Pre-Operation Testing |  | 57.38%
55000 | B2 | DIT-CHU | Axle Counter Installation |  | 39.13% | 48.98% |  | B2-549
|  |  | JB Installation |  | 19.91%
|  |  | Line Cable Installation |  | 85.09%
|  |  | Express Cable Installation |  | 13.52%
|  |  | Pre-Operation Testing |  | 87.28%
55498 | B2 | DIT-CHU | Axle Counter Installation |  | 34.04% | 49.15% |  | B2-554
|  |  | JB Installation |  | 22.64%
|  |  | Line Cable Installation |  | 31.57%
|  |  | Express Cable Installation |  | 92.58%
|  |  | Pre-Operation Testing |  | 64.94%
| B2 |  | Axle Counter Installation |  | 42.09% | 28.48% | NO REF DWG EXISTS | B2-555
|  |  | JB Installation |  | 9.353%
|  |  | Line Cable Installation |  | 13.61%
|  |  | Express Cable Installation |  | 60.44%
|  |  | Pre-Operation Testing |  | 16.91%
| B2 |  | Axle Counter Installation |  | 7.064% | 39.51% | NO REF DWG EXISTS | B2-556
|  |  | JB Installation |  | 68.51%
|  |  | Line Cable Installation |  | 99.42%
|  |  | Express Cable Installation |  | 10.36%
|  |  | Pre-Operation Testing |  | 12.18%
55857 | B2 | CHURCH AVE | Axle Counter Installation |  | 6.867% | 49.72% |  | B2-558
|  |  | JB Installation |  | 84.7%
|  |  | Line Cable Installation |  | 47.23%
|  |  | Express Cable Installation |  | 75.36%
|  |  | Pre-Operation Testing |  | 34.44%
58500 | B2 | FORT HAMILTON PARKWAY | Axle Counter Installation |  | 16.73% | 41.37% |  | B2-585
|  |  | JB Installation |  | 18.46%
|  |  | Line Cable Installation |  | 40.8%
|  |  | Express Cable Installation |  | 51%
|  |  | Pre-Operation Testing |  | 79.87%
59203.8 | B2 | FOR-15S | Axle Counter Installation |  | 33.23% | 51.33% |  | B2-592
|  |  | JB Installation |  | 88.56%
|  |  | Line Cable Installation |  | 53.56%
|  |  | Express Cable Installation |  | 45.14%
|  |  | Pre-Operation Testing |  | 36.18%
62550.6 | B2 |  | Axle Counter Installation |  | 87.7% | 46.23% |  | B2-625
|  |  | JB Installation |  | 70.61%
|  |  | Line Cable Installation |  | 20.82%
|  |  | Express Cable Installation |  | 20.62%
|  |  | Pre-Operation Testing |  | 31.41%
65375.3 | B2 | 15S-7AV | Axle Counter Installation |  | 62.15% | 59.65% |  | B2-654
|  |  | JB Installation |  | 90.38%
|  |  | Line Cable Installation |  | 27.02%
|  |  | Express Cable Installation |  | 87.59%
|  |  | Pre-Operation Testing |  | 31.1%
66062.3 | B2 | 7AV-4TH | Axle Counter Installation |  | 53.36% | 65.13% |  | B2-661
|  |  | JB Installation |  | 76.27%
|  |  | Line Cable Installation |  | 85.57%
|  |  | Express Cable Installation |  | 48.85%
|  |  | Pre-Operation Testing |  | 61.59%
| B2 |  | Axle Counter Installation |  | 22.66% | 52.97% | NO REF DWG EXISTS | B2-665
|  |  | JB Installation |  | 45.85%
|  |  | Line Cable Installation |  | 97.42%
|  |  | Express Cable Installation |  | 75.36%
|  |  | Pre-Operation Testing |  | 23.54%
| B2 |  | Axle Counter Installation |  | 15.18% | 25.15% | NO REF DWG EXISTS | B2-684
|  |  | JB Installation |  | 9.963%
|  |  | Line Cable Installation |  | 46.15%
|  |  | Express Cable Installation |  | 24.05%
|  |  | Pre-Operation Testing |  | 30.4%
| B2 |  | Axle Counter Installation |  | 45.21% | 34.15% | NO REF DWG EXISTS | B2-691
|  |  | JB Installation |  | 1.894%
|  |  | Line Cable Installation |  | 10.62%
|  |  | Express Cable Installation |  | 78.03%
|  |  | Pre-Operation Testing |  | 34.98%
| B2 |  | Axle Counter Installation |  | 77.54% | 45.55% | NO REF DWG EXISTS | B2-692
|  |  | JB Installation |  | 42.24%
|  |  | Line Cable Installation |  | 25.22%
|  |  | Express Cable Installation |  | 50.85%
|  |  | Pre-Operation Testing |  | 31.9%
| B2 |  | Axle Counter Installation |  | 53.27% | 48.21% | NO REF DWG EXISTS | B2-692A
|  |  | JB Installation |  | 56.49%
|  |  | Line Cable Installation |  | 29.35%
|  |  | Express Cable Installation |  | 57.44%
|  |  | Pre-Operation Testing |  | 44.49%
| B2 |  | Axle Counter Installation |  | 98.91% | 65.77% | NO REF DWG EXISTS | B2-693
|  |  | JB Installation |  | 54.87%
|  |  | Line Cable Installation |  | 91.31%
|  |  | Express Cable Installation |  | 42.68%
|  |  | Pre-Operation Testing |  | 41.06%
| B2 |  | Axle Counter Installation |  | 17.48% | 39.28% | NO REF DWG EXISTS | B2-705
|  |  | JB Installation |  | 38.42%
|  |  | Line Cable Installation |  | 4.429%
|  |  | Express Cable Installation |  | 91.08%
|  |  | Pre-Operation Testing |  | 44.98%
| B2 |  | Axle Counter Installation |  | 57.08% | 25.7% | NO REF DWG EXISTS | B2-712
|  |  | JB Installation |  | 19.08%
|  |  | Line Cable Installation |  | 21.53%
|  |  | Express Cable Installation |  | 20.77%
|  |  | Pre-Operation Testing |  | 10.02%
| B2 |  | Axle Counter Installation |  | 75.31% | 57.2% | DWG EXISTS, BUT EMPTY | B2-732
|  |  | JB Installation |  | 93.11%
|  |  | Line Cable Installation |  | 68.93%
|  |  | Express Cable Installation |  | 2.556%
|  |  | Pre-Operation Testing |  | 46.1%
73926.3 | B2 | CARROLL STREET | Axle Counter Installation |  | 21.05% | 38.32% |  | B2-739
|  |  | JB Installation |  | 4.12%
|  |  | Line Cable Installation |  | 16.06%
|  |  | Express Cable Installation |  | 74.85%
|  |  | Pre-Operation Testing |  | 75.53%
75267 | B2 | CAR-BER | Axle Counter Installation |  | 79.93% | 46.36% |  | B2-753
|  |  | JB Installation |  | 50.97%
|  |  | Line Cable Installation |  | 13.27%
|  |  | Express Cable Installation |  | 11.16%
|  |  | Pre-Operation Testing |  | 76.48%
| B2 |  | Axle Counter Installation |  | 80.85% | 53.66% | NO REF DWG EXISTS | B2-755
|  |  | JB Installation |  | 69.38%
|  |  | Line Cable Installation |  | 27.94%
|  |  | Express Cable Installation |  | 18.74%
|  |  | Pre-Operation Testing |  | 71.37%
75646 | B2 | CAR-BER | Axle Counter Installation |  | 81.91% | 59.07% |  | B2-756
|  |  | JB Installation |  | 10.16%
|  |  | Line Cable Installation |  | 85.32%
|  |  | Express Cable Installation |  | 37.28%
|  |  | Pre-Operation Testing |  | 80.69%
76352 | B2 |  | Axle Counter Installation |  | 38.64% | 44.9% |  | B2-763, B2-764
|  |  | JB Installation |  | 64.78%
|  |  | Line Cable Installation |  | 3.955%
|  |  | Express Cable Installation |  | 31.63%
|  |  | Pre-Operation Testing |  | 85.48%
76536 | B2 |  | Axle Counter Installation |  | 4.642% | 40.76% |  | B2-765
|  |  | JB Installation |  | 18.57%
|  |  | Line Cable Installation |  | 88.33%
|  |  | Express Cable Installation |  | 3.292%
|  |  | Pre-Operation Testing |  | 88.98%
76797 | B2 |  | Axle Counter Installation |  | 27.15% | 59.78% |  | B2-768
|  |  | JB Installation |  | 44.67%
|  |  | Line Cable Installation |  | 60.05%
|  |  | Express Cable Installation |  | 69.21%
|  |  | Pre-Operation Testing |  | 97.82%
77116 | B2 |  | Axle Counter Installation |  | 66.62% | 71% |  | B2-770
|  |  | JB Installation |  | 52.91%
|  |  | Line Cable Installation |  | 79.41%
|  |  | Express Cable Installation |  | 78.01%
|  |  | Pre-Operation Testing |  | 78.03%
| B3 |  | Axle Counter Installation |  | 19.78% | 52.15% | REF DWG EXISTS, NO STATIONINGS SHOWN | B3-546
|  |  | JB Installation |  | 97.01%
|  |  | Line Cable Installation |  | 58.43%
|  |  | Express Cable Installation |  | 10.54%
|  |  | Pre-Operation Testing |  | 75.01%
| B3 |  | Axle Counter Installation |  | 1.45% | 57.92% | REF DWG EXISTS, NO STATIONINGS SHOWN | B3-548
|  |  | JB Installation |  | 70.9%
|  |  | Line Cable Installation |  | 26.4%
|  |  | Express Cable Installation |  | 97.46%
|  |  | Pre-Operation Testing |  | 93.4%
53361 | B3 |  | Axle Counter Installation |  | 13.57% | 26.1% |  | B3-554
|  |  | JB Installation |  | 52.52%
|  |  | Line Cable Installation |  | 15.58%
|  |  | Express Cable Installation |  | 9.434%
|  |  | Pre-Operation Testing |  | 39.39%
55626 | B3 |  | Axle Counter Installation |  | 89.76% | 44.29% |  | B3-555
|  |  | JB Installation |  | 67.79%
|  |  | Line Cable Installation |  | 29.78%
|  |  | Express Cable Installation |  | 33.37%
|  |  | Pre-Operation Testing |  | 0.7336%
| B3 |  | Axle Counter Installation |  | 40.56% | 77.87% | REF DWG EXISTS, NO STATIONINGS SHOWN | B3-556
|  |  | JB Installation |  | 90%
|  |  | Line Cable Installation |  | 87.61%
|  |  | Express Cable Installation |  | 99.85%
|  |  | Pre-Operation Testing |  | 71.32%
| B3 |  | Axle Counter Installation |  | 35.88% | 45.89% | REF DWG EXISTS, NO STATIONINGS SHOWN | B3-557
|  |  | JB Installation |  | 27.99%
|  |  | Line Cable Installation |  | 81.72%
|  |  | Express Cable Installation |  | 29.2%
|  |  | Pre-Operation Testing |  | 54.66%
| B3 |  | Axle Counter Installation |  | 72.6% | 49.45% | NO REF DWG EXISTS | B3-565
|  |  | JB Installation |  | 46.41%
|  |  | Line Cable Installation |  | 30.31%
|  |  | Express Cable Installation |  | 15.53%
|  |  | Pre-Operation Testing |  | 82.42%
65384.6 | B3 |  | Axle Counter Installation |  | 9.157% | 22.87% |  | B3-654
|  |  | JB Installation |  | 15.34%
|  |  | Line Cable Installation |  | 69.94%
|  |  | Express Cable Installation |  | 15.78%
|  |  | Pre-Operation Testing |  | 4.14%
66073.4 | B3 |  | Axle Counter Installation |  | 1.772% | 42.26% |  | B3-661
|  |  | JB Installation |  | 68.85%
|  |  | Line Cable Installation |  | 90.43%
|  |  | Express Cable Installation |  | 45.43%
|  |  | Pre-Operation Testing |  | 4.797%
| B3 |  | Axle Counter Installation |  | 12.66% | 28.77% | NO REF DWG EXISTS | B3-689
|  |  | JB Installation |  | 25.97%
|  |  | Line Cable Installation |  | 6.037%
|  |  | Express Cable Installation |  | 67.53%
|  |  | Pre-Operation Testing |  | 31.64%
| B3 |  | Axle Counter Installation |  | 40.82% | 43.07% | NO REF DWG EXISTS | B3-690
|  |  | JB Installation |  | 12.4%
|  |  | Line Cable Installation |  | 99.81%
|  |  | Express Cable Installation |  | 44.58%
|  |  | Pre-Operation Testing |  | 17.73%
| B3 |  | Axle Counter Installation |  | 46.87% | 51.16% | NO REF DWG EXISTS | B3-691
|  |  | JB Installation |  | 27.84%
|  |  | Line Cable Installation |  | 58.89%
|  |  | Express Cable Installation |  | 44.75%
|  |  | Pre-Operation Testing |  | 77.47%
| B3 |  | Axle Counter Installation |  | 93.48% | 47.62% | NO REF DWG EXISTS | B3-692
|  |  | JB Installation |  | 10.14%
|  |  | Line Cable Installation |  | 81.54%
|  |  | Express Cable Installation |  | 48.12%
|  |  | Pre-Operation Testing |  | 4.795%
| B3 |  | Axle Counter Installation |  | 86.44% | 70.11% | NO REF DWG EXISTS | B3-693
|  |  | JB Installation |  | 89.19%
|  |  | Line Cable Installation |  | 83.43%
|  |  | Express Cable Installation |  | 45.08%
|  |  | Pre-Operation Testing |  | 46.39%
| B3 |  | Axle Counter Installation |  | 32.14% | 45.76% | NO REF DWG EXISTS | B3-694
|  |  | JB Installation |  | 5.033%
|  |  | Line Cable Installation |  | 83.88%
|  |  | Express Cable Installation |  | 49.94%
|  |  | Pre-Operation Testing |  | 57.8%
| B3 |  | Axle Counter Installation |  | 57.4% | 54.09% | NO REF DWG EXISTS | B3-695
|  |  | JB Installation |  | 45.65%
|  |  | Line Cable Installation |  | 72.64%
|  |  | Express Cable Installation |  | 43.89%
|  |  | Pre-Operation Testing |  | 50.88%
| B3 |  | Axle Counter Installation |  | 29.49% | 63.05% | NO REF DWG EXISTS | B3-696
|  |  | JB Installation |  | 90.06%
|  |  | Line Cable Installation |  | 84.31%
|  |  | Express Cable Installation |  | 24.57%
|  |  | Pre-Operation Testing |  | 86.85%
75405 | B3 |  | Axle Counter Installation |  | 56.95% | 48.52% |  | B3-754
|  |  | JB Installation |  | 37.76%
|  |  | Line Cable Installation |  | 51.83%
|  |  | Express Cable Installation |  | 6.828%
|  |  | Pre-Operation Testing |  | 89.23%
| B3 |  | Axle Counter Installation |  | 44.81% | 33.47% | NO REF DWG EXISTS | B3-755
|  |  | JB Installation |  | 0.9551%
|  |  | Line Cable Installation |  | 10%
|  |  | Express Cable Installation |  | 98.95%
|  |  | Pre-Operation Testing |  | 12.62%
75405 | B3 |  | Axle Counter Installation |  | 18.88% | 48.33% |  | B3-756
|  |  | JB Installation |  | 21.67%
|  |  | Line Cable Installation |  | 44.69%
|  |  | Express Cable Installation |  | 68.07%
|  |  | Pre-Operation Testing |  | 88.33%
76383 | B3 |  | Axle Counter Installation |  | 31.49% | 54.38% |  | B3-764
|  |  | JB Installation |  | 0.9809%
|  |  | Line Cable Installation |  | 70.92%
|  |  | Express Cable Installation |  | 72.77%
|  |  | Pre-Operation Testing |  | 95.74%
76920 | B3 |  | Axle Counter Installation |  | 22.01% | 43.4% |  | B3-769
|  |  | JB Installation |  | 65.1%
|  |  | Line Cable Installation |  | 3.371%
|  |  | Express Cable Installation |  | 38.47%
|  |  | Pre-Operation Testing |  | 88.06%
| B4 |  | Axle Counter Installation |  | 65.61% | 67.53% | REF DWG EXISTS, NO STATIONINGS SHOWN | B4-547
|  |  | JB Installation |  | 29.14%
|  |  | Line Cable Installation |  | 89.58%
|  |  | Express Cable Installation |  | 64.63%
|  |  | Pre-Operation Testing |  | 88.67%
| B4 |  | Axle Counter Installation |  | 17.39% | 52.44% | REF DWG EXISTS, NO STATIONINGS SHOWN | B4-551
|  |  | JB Installation |  | 57.9%
|  |  | Line Cable Installation |  | 20.57%
|  |  | Express Cable Installation |  | 72.96%
|  |  | Pre-Operation Testing |  | 93.4%
| B4 |  | Axle Counter Installation |  | 13.78% | 36.95% | NO REF DWG EXISTS, AWAITING RESPONSE FROM THALES ON WHETHER THIS AXC WILL BE INSTALLED | B4-554A, B4-554B
|  |  | JB Installation |  | 54.04%
|  |  | Line Cable Installation |  | 32.39%
|  |  | Express Cable Installation |  | 32.59%
|  |  | Pre-Operation Testing |  | 51.96%
55533 | B4 |  | Axle Counter Installation |  | 58.47% | 73.85% |  | B4-555
|  |  | JB Installation |  | 55.62%
|  |  | Line Cable Installation |  | 95.42%
|  |  | Express Cable Installation |  | 88.43%
|  |  | Pre-Operation Testing |  | 71.31%
55685 | B4 |  | Axle Counter Installation |  | 70.37% | 66.74% |  | B4-556
|  |  | JB Installation |  | 84.35%
|  |  | Line Cable Installation |  | 47.58%
|  |  | Express Cable Installation |  | 61.84%
|  |  | Pre-Operation Testing |  | 69.56%
56396.5 | B4 |  | Axle Counter Installation |  | 62.03% | 49.62% |  | B4-564
|  |  | JB Installation |  | 18.15%
|  |  | Line Cable Installation |  | 17.31%
|  |  | Express Cable Installation |  | 82.65%
|  |  | Pre-Operation Testing |  | 67.96%

## SIGNALS
Stationing | Track No | Signal Type | Location | Activity | Date | Progress | General Progress | Notes
74076 | E1 | APPROACH |  | Signal Installation |  | 80.77% | 60.77% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 47.74%
|  |  |  | Stop Machine Installation |  | 1.095%
|  |  |  | Line Cable Installation |  | 86.91%
|  |  |  | Breakdown Testing |  | 73.68%
|  |  |  | Pre-Operation Testing |  | 61.39%
98643 | E1 | HOME |  | Signal Installation |  | 20.49% | 46.95% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 47.11%
|  |  |  | Stop Machine Installation |  | 61.71%
|  |  |  | Line Cable Installation |  | 56.72%
|  |  |  | Breakdown Testing |  | 60.6%
|  |  |  | Pre-Operation Testing |  | 35.21%
98903 | E1 | HOME |  | Signal Installation |  | 54.16% | 68.19% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 74.4%
|  |  |  | Stop Machine Installation |  | 86.44%
|  |  |  | Line Cable Installation |  | 36.9%
|  |  |  | Breakdown Testing |  | 83.98%
|  |  |  | Pre-Operation Testing |  | 79.49%
100068 | E1 | HOME |  | Signal Installation |  | 66.3% | 46% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 30.19%
|  |  |  | Stop Machine Installation |  | 6.692%
|  |  |  | Line Cable Installation |  | 7.652%
|  |  |  | Breakdown Testing |  | 59.53%
|  |  |  | Pre-Operation Testing |  | 89.81%
106031 | E1 | APPROACH |  | Signal Installation |  | 70.13% | 47.25% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 8.331%
|  |  |  | Stop Machine Installation |  | 64.4%
|  |  |  | Line Cable Installation |  | 58.45%
|  |  |  | Breakdown Testing |  | 37.56%
|  |  |  | Pre-Operation Testing |  | 5.715%
113852 | E1 | HOME |  | Signal Installation |  | 62.59% | 53.88% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 53.88%
|  |  |  | Stop Machine Installation |  | 62.58%
|  |  |  | Line Cable Installation |  | 81.08%
|  |  |  | Breakdown Testing |  | 13.91%
|  |  |  | Pre-Operation Testing |  | 49.27%
114110 | E1 | HOME |  | Signal Installation |  | 79.38% | 51.53% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 96.59%
|  |  |  | Stop Machine Installation |  | 50.11%
|  |  |  | Line Cable Installation |  | 57.21%
|  |  |  | Breakdown Testing |  | 33.11%
|  |  |  | Pre-Operation Testing |  | 37.84%
114869 | E1 | HOME |  | Signal Installation |  | 13.07% | 39.01% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 96.19%
|  |  |  | Stop Machine Installation |  | 38.72%
|  |  |  | Line Cable Installation |  | 81.35%
|  |  |  | Breakdown Testing |  | 33.62%
|  |  |  | Pre-Operation Testing |  | 28.29%
119024 | E1 | APPROACH |  | Signal Installation |  | 96.67% | 42.01% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 13.82%
|  |  |  | Stop Machine Installation |  | 0.5569%
|  |  |  | Line Cable Installation |  | 49.99%
|  |  |  | Breakdown Testing |  | 8.153%
|  |  |  | Pre-Operation Testing |  | 54.67%
119485 | E1 | APPROACH |  | Signal Installation |  | 12.91% | 64.57% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 20.36%
|  |  |  | Stop Machine Installation |  | 82.06%
|  |  |  | Line Cable Installation |  | 65%
|  |  |  | Breakdown Testing |  | 79.64%
|  |  |  | Pre-Operation Testing |  | 83.21%
| E1 | APPROACH |  | Signal Installation |  | 29.45% | 65.37% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 92.63%
|  |  |  | Stop Machine Installation |  | 71.96%
|  |  |  | Line Cable Installation |  | 75.93%
|  |  |  | Breakdown Testing |  | 55.07%
|  |  |  | Pre-Operation Testing |  | 94.44%
121810 | E1 | HOME |  | Signal Installation |  | 8.683% | 54.37% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 21.2%
|  |  |  | Stop Machine Installation |  | 62.29%
|  |  |  | Line Cable Installation |  | 76.21%
|  |  |  | Breakdown Testing |  | 33.81%
|  |  |  | Pre-Operation Testing |  | 90.86%
122198 | E1 | HOME |  | Signal Installation |  | 72.69% | 57.13% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 10.68%
|  |  |  | Stop Machine Installation |  | 0.935%
|  |  |  | Line Cable Installation |  | 80.3%
|  |  |  | Breakdown Testing |  | 92.72%
|  |  |  | Pre-Operation Testing |  | 39.02%
122570 | E1 | HOME |  | Signal Installation |  | 6.527% | 23.86% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 41.59%
|  |  |  | Stop Machine Installation |  | 31.61%
|  |  |  | Line Cable Installation |  | 31.51%
|  |  |  | Breakdown Testing |  | 32.43%
|  |  |  | Pre-Operation Testing |  | 17.23%
122987 | E1 | HOME |  | Signal Installation |  | 57.48% | 69.6% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 21.68%
|  |  |  | Stop Machine Installation |  | 56.01%
|  |  |  | Line Cable Installation |  | 90.43%
|  |  |  | Breakdown Testing |  | 80.67%
|  |  |  | Pre-Operation Testing |  | 63.4%
123669 | D1 | HOME |  | Signal Installation |  | 73.57% | 77.24% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 49.29%
|  |  |  | Stop Machine Installation |  | 86.06%
|  |  |  | Line Cable Installation |  | 74.59%
|  |  |  | Breakdown Testing |  | 65.1%
|  |  |  | Pre-Operation Testing |  | 86.88%
73318 | E2 | APPROACH |  | Signal Installation |  | 94.58% | 68.74% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 40.5%
|  |  |  | Stop Machine Installation |  | 86.49%
|  |  |  | Line Cable Installation |  | 15.37%
|  |  |  | Breakdown Testing |  | 71.44%
|  |  |  | Pre-Operation Testing |  | 75.8%
98565 | E2 | HOME |  | Signal Installation |  | 4.262% | 26.68% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 34.5%
|  |  |  | Stop Machine Installation |  | 6.57%
|  |  |  | Line Cable Installation |  | 17.27%
|  |  |  | Breakdown Testing |  | 82.49%
|  |  |  | Pre-Operation Testing |  | 22.82%
99593 | E2 | HOME |  | Signal Installation |  | 9.02% | 54% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 89.73%
|  |  |  | Stop Machine Installation |  | 99.08%
|  |  |  | Line Cable Installation |  | 42.86%
|  |  |  | Breakdown Testing |  | 55.19%
|  |  |  | Pre-Operation Testing |  | 63.86%
99970 | E2 | HOME |  | Signal Installation |  | 51.19% | 57.94% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 7.028%
|  |  |  | Stop Machine Installation |  | 43.71%
|  |  |  | Line Cable Installation |  | 78.05%
|  |  |  | Breakdown Testing |  | 56.49%
|  |  |  | Pre-Operation Testing |  | 60.25%
106749 | E2 | APPROACH |  | Signal Installation |  | 4.009% | 54.79% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 88.84%
|  |  |  | Stop Machine Installation |  | 62.57%
|  |  |  | Line Cable Installation |  | 29.9%
|  |  |  | Breakdown Testing |  | 80.38%
|  |  |  | Pre-Operation Testing |  | 97.1%
112529 | E2 | HOME |  | Signal Installation |  | 93.72% | 62.82% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 22.46%
|  |  |  | Stop Machine Installation |  | 4.914%
|  |  |  | Line Cable Installation |  | 71.61%
|  |  |  | Breakdown Testing |  | 44.61%
|  |  |  | Pre-Operation Testing |  | 99.25%
113850 | E2 | HOME |  | Signal Installation |  | 25.15% | 57% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 49.84%
|  |  |  | Stop Machine Installation |  | 53.01%
|  |  |  | Line Cable Installation |  | 51.98%
|  |  |  | Breakdown Testing |  | 97.77%
|  |  |  | Pre-Operation Testing |  | 57.09%
118065 | E2 | APPROACH |  | Signal Installation |  | 94.38% | 45.61% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 67.35%
|  |  |  | Stop Machine Installation |  | 54%
|  |  |  | Line Cable Installation |  | 12.48%
|  |  |  | Breakdown Testing |  | 43.67%
|  |  |  | Pre-Operation Testing |  | 23.49%
119215 | E2 | APPROACH |  | Signal Installation |  | 17.26% | 28.7% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 15.52%
|  |  |  | Stop Machine Installation |  | 38.34%
|  |  |  | Line Cable Installation |  | 18.5%
|  |  |  | Breakdown Testing |  | 67.12%
|  |  |  | Pre-Operation Testing |  | 2.256%
123687 | D2 | HOME |  | Signal Installation |  | 37.73% | 39.79% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 27.06%
|  |  |  | Stop Machine Installation |  | 55.69%
|  |  |  | Line Cable Installation |  | 35.56%
|  |  |  | Breakdown Testing |  | 49.33%
|  |  |  | Pre-Operation Testing |  | 20.66%
124043 | D2 | HOME |  | Signal Installation |  | 91.3% | 44.33% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 10.33%
|  |  |  | Stop Machine Installation |  | 19.57%
|  |  |  | Line Cable Installation |  | 72.33%
|  |  |  | Breakdown Testing |  | 3.758%
|  |  |  | Pre-Operation Testing |  | 34.7%
99806 | E3 | HOME |  | Signal Installation |  | 42.15% | 44.65% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 43.69%
|  |  |  | Stop Machine Installation |  | 22.91%
|  |  |  | Line Cable Installation |  | 36.15%
|  |  |  | Breakdown Testing |  | 32.15%
|  |  |  | Pre-Operation Testing |  | 89.88%
100019 | E3 | HOME |  | Signal Installation |  | 61.26% | 48.43% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 55.74%
|  |  |  | Stop Machine Installation |  | 26.61%
|  |  |  | Line Cable Installation |  | 36.03%
|  |  |  | Breakdown Testing |  | 19.88%
|  |  |  | Pre-Operation Testing |  | 98.36%
99592 | E4 | HOME |  | Signal Installation |  | 32.74% | 53.02% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 15.21%
|  |  |  | Stop Machine Installation |  | 65.03%
|  |  |  | Line Cable Installation |  | 78.53%
|  |  |  | Breakdown Testing |  | 61.26%
|  |  |  | Pre-Operation Testing |  | 27.53%
122071 | E5 | HOME |  | Signal Installation |  | 2.395% | 36.65% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 79.17%
|  |  |  | Stop Machine Installation |  | 5.943%
|  |  |  | Line Cable Installation |  | 59.49%
|  |  |  | Breakdown Testing |  | 96.65%
|  |  |  | Pre-Operation Testing |  | 18.8%
122687 | E5 | HOME |  | Signal Installation |  | 36.37% | 56.93% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 34.76%
|  |  |  | Stop Machine Installation |  | 35.05%
|  |  |  | Line Cable Installation |  | 31.71%
|  |  |  | Breakdown Testing |  | 89.76%
|  |  |  | Pre-Operation Testing |  | 91.74%

## SWITCH
Name | Stationing | Track No | Location | Activity | Date | Progress | General Progress | Notes
B331 | 76395 | B1 |  | Switch Machine Installation |  | 78.05% | 60.89%
|  |  |  | Switch JB Installation |  | 20.27%
|  |  |  | Switch Cable Installation |  | 0.8483%
|  |  |  | Line Cable Installation |  | 99.9%
|  |  |  | Breakdown Testing |  | 75.5%
|  |  |  | Pre-Operation Testing |  | 50.13%
B325 | 76395 | E2 |  | Switch Machine Installation |  | 16.85% | 52.83%
|  |  |  | Switch JB Installation |  | 88.61%
|  |  |  | Switch Cable Installation |  | 87.25%
|  |  |  | Line Cable Installation |  | 94.89%
|  |  |  | Breakdown Testing |  | 58.9%
|  |  |  | Pre-Operation Testing |  | 6.291%
633A | 99999 | E1 |  | Switch Machine Installation |  | 20.21% | 43.38%
|  |  |  | Switch JB Installation |  | 10.4%
|  |  |  | Switch Cable Installation |  | 64.14%
|  |  |  | Line Cable Installation |  | 17.87%
|  |  |  | Breakdown Testing |  | 15.89%
|  |  |  | Pre-Operation Testing |  | 98.8%
633B | 98900 | E3-4 |  | Switch Machine Installation |  | 74.03% | 68.76%
|  |  |  | Switch JB Installation |  | 51.95%
|  |  |  | Switch Cable Installation |  | 49.35%
|  |  |  | Line Cable Installation |  | 47.22%
|  |  |  | Breakdown Testing |  | 78.22%
|  |  |  | Pre-Operation Testing |  | 94.99%
625A | 98808 | E3-4 |  | Switch Machine Installation |  | 12.07% | 43.22%
|  |  |  | Switch JB Installation |  | 4.048%
|  |  |  | Switch Cable Installation |  | 38.3%
|  |  |  | Line Cable Installation |  | 84.6%
|  |  |  | Breakdown Testing |  | 40.34%
|  |  |  | Pre-Operation Testing |  | 40.8%
625B | 99949 | E2 |  | Switch Machine Installation |  | 70% | 57.52%
|  |  |  | Switch JB Installation |  | 50.41%
|  |  |  | Switch Cable Installation |  | 95.01%
|  |  |  | Line Cable Installation |  | 57.35%
|  |  |  | Breakdown Testing |  | 13.91%
|  |  |  | Pre-Operation Testing |  | 51.33%
663 | 99628 | E3-4 |  | Switch Machine Installation |  | 36.25% | 59.9%
|  |  |  | Switch JB Installation |  | 30.74%
|  |  |  | Switch Cable Installation |  | 69.28%
|  |  |  | Line Cable Installation |  | 61.32%
|  |  |  | Breakdown Testing |  | 50.21%
|  |  |  | Pre-Operation Testing |  | 82.42%
673A | 99999 | E1 |  | Switch Machine Installation |  | 37.36% | 25.91%
|  |  |  | Switch JB Installation |  | 70.03%
|  |  |  | Switch Cable Installation |  | 61.78%
|  |  |  | Line Cable Installation |  | 16.59%
|  |  |  | Breakdown Testing |  | 6.598%
|  |  |  | Pre-Operation Testing |  | 7.245%
673B | 99826 | E3 |  | Switch Machine Installation |  | 50.96% | 49.87%
|  |  |  | Switch JB Installation |  | 48.41%
|  |  |  | Switch Cable Installation |  | 72.55%
|  |  |  | Line Cable Installation |  | 86.63%
|  |  |  | Breakdown Testing |  | 0.8013%
|  |  |  | Pre-Operation Testing |  | 38.41%
651A | 99761 | E4 |  | Switch Machine Installation |  | 79.8% | 46.98%
|  |  |  | Switch JB Installation |  | 94.09%
|  |  |  | Switch Cable Installation |  | 19.6%
|  |  |  | Line Cable Installation |  | 27.42%
|  |  |  | Breakdown Testing |  | 79.54%
|  |  |  | Pre-Operation Testing |  | 28.52%
651B | 99949 | E2 |  | Switch Machine Installation |  | 31.2% | 43.17%
|  |  |  | Switch JB Installation |  | 35.93%
|  |  |  | Switch Cable Installation |  | 91.14%
|  |  |  | Line Cable Installation |  | 64.6%
|  |  |  | Breakdown Testing |  | 13.81%
|  |  |  | Pre-Operation Testing |  | 15.12%
757A | 113880 | E1 |  | Switch Machine Installation |  | 98.42% | 43.34%
|  |  |  | Switch JB Installation |  | 63.37%
|  |  |  | Switch Cable Installation |  | 7.233%
|  |  |  | Line Cable Installation |  | 20.41%
|  |  |  | Breakdown Testing |  | 89.77%
|  |  |  | Pre-Operation Testing |  | 0.8742%
757B | 114010 | E2 |  | Switch Machine Installation |  | 86.08% | 50.67%
|  |  |  | Switch JB Installation |  | 33.14%
|  |  |  | Switch Cable Installation |  | 36.52%
|  |  |  | Line Cable Installation |  | 66.36%
|  |  |  | Breakdown Testing |  | 25.84%
|  |  |  | Pre-Operation Testing |  | 38.57%
753A | 114010 | E1 |  | Switch Machine Installation |  | 64.2% | 34.28%
|  |  |  | Switch JB Installation |  | 4.899%
|  |  |  | Switch Cable Installation |  | 5.935%
|  |  |  | Line Cable Installation |  | 63.21%
|  |  |  | Breakdown Testing |  | 27.65%
|  |  |  | Pre-Operation Testing |  | 10.39%
753B | 113880 | E2 |  | Switch Machine Installation |  | 88.19% | 47.46%
|  |  |  | Switch JB Installation |  | 8.33%
|  |  |  | Switch Cable Installation |  | 10.31%
|  |  |  | Line Cable Installation |  | 58.78%
|  |  |  | Breakdown Testing |  | 1.841%
|  |  |  | Pre-Operation Testing |  | 78.15%
825 |  | E1 |  | Switch Machine Installation |  | 77.36% | 55.86% | Stationing missing
|  |  |  | Switch JB Installation |  | 84.45%
|  |  |  | Switch Cable Installation |  | 19.43%
|  |  |  | Line Cable Installation |  | 21.27%
|  |  |  | Breakdown Testing |  | 70.58%
|  |  |  | Pre-Operation Testing |  | 90.65%
815A | 121995 | E5 |  | Switch Machine Installation |  | 51.79% | 59.68%
|  |  |  | Switch JB Installation |  | 52.58%
|  |  |  | Switch Cable Installation |  | 62.47%
|  |  |  | Line Cable Installation |  | 88.74%
|  |  |  | Breakdown Testing |  | 15.58%
|  |  |  | Pre-Operation Testing |  | 79.81%
815B | 121831 | E2 |  | Switch Machine Installation |  | 61.58% | 25.69%
|  |  |  | Switch JB Installation |  | 89.76%
|  |  |  | Switch Cable Installation |  | 0.9972%
|  |  |  | Line Cable Installation |  | 32.79%
|  |  |  | Breakdown Testing |  | 4.742%
|  |  |  | Pre-Operation Testing |  | 28.33%
851B | 122757 | E5 |  | Switch Machine Installation |  | 13.23% | 34.62%
|  |  |  | Switch JB Installation |  | 70.46%
|  |  |  | Switch Cable Installation |  | 63.43%
|  |  |  | Line Cable Installation |  | 6.049%
|  |  |  | Breakdown Testing |  | 24.33%
|  |  |  | Pre-Operation Testing |  | 66.09%
851A | 122923 | E1 |  | Switch Machine Installation |  | 56.97% | 44.46%
|  |  |  | Switch JB Installation |  | 62.74%
|  |  |  | Switch Cable Installation |  | 12.91%
|  |  |  | Line Cable Installation |  | 53.93%
|  |  |  | Breakdown Testing |  | 26%
|  |  |  | Pre-Operation Testing |  | 72.47%
841 | 122923 | E2 |  | Switch Machine Installation |  | 38.49% | 44.69%
|  |  |  | Switch JB Installation |  | 34.59%
|  |  |  | Switch Cable Installation |  | 37.88%
|  |  |  | Line Cable Installation |  | 3.889%
|  |  |  | Breakdown Testing |  | 91.19%
|  |  |  | Pre-Operation Testing |  | 52.01%
753B | 113880 | E2 |  | Switch Machine Installation |  | 93.23% | 89.03%
|  |  |  | Switch JB Installation |  | 7.28%
|  |  |  | Switch Cable Installation |  | 88.94%
|  |  |  | Line Cable Installation |  | 78.57%
|  |  |  | Breakdown Testing |  | 99.36%
|  |  |  | Pre-Operation Testing |  | 85.04%

## WRU
Stationing | Track No | Location | Activity | Date | Progress | General Progress | Notes
54000 | B1 |  | Radio Unit Installation |  | 71% | 59.36% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 97.15%
|  |  | Fiber Box Installation |  | 69.03%
|  |  | Antenna Installation |  | 71.34%
|  |  | Antenna Cable Installation |  | 4.794%
|  |  | Splitter Installation |  | 86.29%
|  |  | Fiber Cable Splicing |  | 61.49%
|  |  | Fiber Testing |  | 8.733%
|  |  | Power Testing |  | 64.37%
54000 | B3 |  | Radio Unit Installation |  | 6.083% | 35.98% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 84.8%
|  |  | Fiber Box Installation |  | 1.59%
|  |  | Antenna Installation |  | 20.33%
|  |  | Antenna Cable Installation |  | 69.89%
|  |  | Splitter Installation |  | 63.83%
|  |  | Fiber Cable Splicing |  | 11.58%
|  |  | Fiber Testing |  | 37.76%
|  |  | Power Testing |  | 27.97%
54000 | B4 |  | Radio Unit Installation |  | 99.56% | 54.96% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 28.91%
|  |  | Fiber Box Installation |  | 61.86%
|  |  | Antenna Installation |  | 41.53%
|  |  | Antenna Cable Installation |  | 1.532%
|  |  | Splitter Installation |  | 75.17%
|  |  | Fiber Cable Splicing |  | 15.81%
|  |  | Fiber Testing |  | 96.43%
|  |  | Power Testing |  | 73.79%
54000 | B2 |  | Radio Unit Installation |  | 89.94% | 40.27% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 89.47%
|  |  | Fiber Box Installation |  | 32.96%
|  |  | Antenna Installation |  | 21.56%
|  |  | Antenna Cable Installation |  | 64.71%
|  |  | Splitter Installation |  | 22.05%
|  |  | Fiber Cable Splicing |  | 5.758%
|  |  | Fiber Testing |  | 19.41%
|  |  | Power Testing |  | 16.6%
54000 | B5 |  | Radio Unit Installation |  | 98.95% | 55.54% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 57.62%
|  |  | Fiber Box Installation |  | 16.3%
|  |  | Antenna Installation |  | 28.11%
|  |  | Antenna Cable Installation |  | 85.78%
|  |  | Splitter Installation |  | 75.59%
|  |  | Fiber Cable Splicing |  | 46.85%
|  |  | Fiber Testing |  | 83.37%
|  |  | Power Testing |  | 7.32%
55500 | B2 |  | Radio Unit Installation |  | 11.78% | 45.28% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 22.6%
|  |  | Fiber Box Installation |  | 52.42%
|  |  | Antenna Installation |  | 50.07%
|  |  | Antenna Cable Installation |  | 92.09%
|  |  | Splitter Installation |  | 62.24%
|  |  | Fiber Cable Splicing |  | 8.119%
|  |  | Fiber Testing |  | 75.29%
|  |  | Power Testing |  | 32.96%
55500 | B1 |  | Radio Unit Installation |  | 77.6% | 50.22% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 7.893%
|  |  | Fiber Box Installation |  | 27.45%
|  |  | Antenna Installation |  | 63.25%
|  |  | Antenna Cable Installation |  | 40.64%
|  |  | Splitter Installation |  | 87.71%
|  |  | Fiber Cable Splicing |  | 92.67%
|  |  | Fiber Testing |  | 16.89%
|  |  | Power Testing |  | 37.84%
56300 | B1 |  | Radio Unit Installation |  | 21.07% | 57.92% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 92.14%
|  |  | Fiber Box Installation |  | 94.41%
|  |  | Antenna Installation |  | 49.92%
|  |  | Antenna Cable Installation |  | 85.88%
|  |  | Splitter Installation |  | 16.78%
|  |  | Fiber Cable Splicing |  | 44.49%
|  |  | Fiber Testing |  | 56.41%
|  |  | Power Testing |  | 60.14%
56500 | B1 |  | Radio Unit Installation |  | 34.44% | 50.37% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 19.76%
|  |  | Fiber Box Installation |  | 55.59%
|  |  | Antenna Installation |  | 38.91%
|  |  | Antenna Cable Installation |  | 30.35%
|  |  | Splitter Installation |  | 47.28%
|  |  | Fiber Cable Splicing |  | 53.63%
|  |  | Fiber Testing |  | 99.72%
|  |  | Power Testing |  | 73.65%
57200 | B1 |  | Radio Unit Installation |  | 8.829% | 51.91% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 98.43%
|  |  | Fiber Box Installation |  | 54.33%
|  |  | Antenna Installation |  | 31.22%
|  |  | Antenna Cable Installation |  | 88.35%
|  |  | Splitter Installation |  | 57.17%
|  |  | Fiber Cable Splicing |  | 74.72%
|  |  | Fiber Testing |  | 38.36%
|  |  | Power Testing |  | 15.78%
57400 | B1 |  | Radio Unit Installation |  | 5.038% | 21.37% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 23.24%
|  |  | Fiber Box Installation |  | 18.54%
|  |  | Antenna Installation |  | 32.1%
|  |  | Antenna Cable Installation |  | 48.96%
|  |  | Splitter Installation |  | 1.109%
|  |  | Fiber Cable Splicing |  | 32.97%
|  |  | Fiber Testing |  | 4.316%
|  |  | Power Testing |  | 26.03%
58300 | B1 |  | Radio Unit Installation |  | 14.75% | 35.24% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 59.67%
|  |  | Fiber Box Installation |  | 19.22%
|  |  | Antenna Installation |  | 32.07%
|  |  | Antenna Cable Installation |  | 17.7%
|  |  | Splitter Installation |  | 56.12%
|  |  | Fiber Cable Splicing |  | 27.19%
|  |  | Fiber Testing |  | 11.58%
|  |  | Power Testing |  | 78.9%
58400 | B1 |  | Radio Unit Installation |  | 24.17% | 38.13% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 41.7%
|  |  | Fiber Box Installation |  | 66.92%
|  |  | Antenna Installation |  | 55.78%
|  |  | Antenna Cable Installation |  | 14.42%
|  |  | Splitter Installation |  | 5.324%
|  |  | Fiber Cable Splicing |  | 38.12%
|  |  | Fiber Testing |  | 24.09%
|  |  | Power Testing |  | 72.6%
59400 | B1 |  | Radio Unit Installation |  | 53.65% | 71.36% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 92.72%
|  |  | Fiber Box Installation |  | 99.67%
|  |  | Antenna Installation |  | 88.7%
|  |  | Antenna Cable Installation |  | 32.15%
|  |  | Splitter Installation |  | 39.09%
|  |  | Fiber Cable Splicing |  | 86.13%
|  |  | Fiber Testing |  | 82.03%
|  |  | Power Testing |  | 68.11%
59700 | B1 |  | Radio Unit Installation |  | 52.76% | 50.02% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 50.62%
|  |  | Fiber Box Installation |  | 44.54%
|  |  | Antenna Installation |  | 1.28%
|  |  | Antenna Cable Installation |  | 77.61%
|  |  | Splitter Installation |  | 55.68%
|  |  | Fiber Cable Splicing |  | 39.69%
|  |  | Fiber Testing |  | 90.72%
|  |  | Power Testing |  | 37.24%
60500 | B1 |  | Radio Unit Installation |  | 13.16% | 52.24% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 46.33%
|  |  | Fiber Box Installation |  | 89.97%
|  |  | Antenna Installation |  | 38.7%
|  |  | Antenna Cable Installation |  | 19.52%
|  |  | Splitter Installation |  | 87.15%
|  |  | Fiber Cable Splicing |  | 62.7%
|  |  | Fiber Testing |  | 20.32%
|  |  | Power Testing |  | 92.35%
60800 | B2 |  | Radio Unit Installation |  | 34.5% | 54.83% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 60.43%
|  |  | Fiber Box Installation |  | 88.93%
|  |  | Antenna Installation |  | 96.34%
|  |  | Antenna Cable Installation |  | 81.88%
|  |  | Splitter Installation |  | 55.83%
|  |  | Fiber Cable Splicing |  | 7.557%
|  |  | Fiber Testing |  | 50.33%
|  |  | Power Testing |  | 17.68%
60800 | B1 |  | Radio Unit Installation |  | 66.24% | 45.76% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 15.37%
|  |  | Fiber Box Installation |  | 5.712%
|  |  | Antenna Installation |  | 59.78%
|  |  | Antenna Cable Installation |  | 54.47%
|  |  | Splitter Installation |  | 33.47%
|  |  | Fiber Cable Splicing |  | 83.14%
|  |  | Fiber Testing |  | 16.37%
|  |  | Power Testing |  | 77.27%
61900 | B2 |  | Radio Unit Installation |  | 28.28% | 44.05% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 9.142%
|  |  | Fiber Box Installation |  | 66.43%
|  |  | Antenna Installation |  | 58.46%
|  |  | Antenna Cable Installation |  | 35.17%
|  |  | Splitter Installation |  | 73.76%
|  |  | Fiber Cable Splicing |  | 23.06%
|  |  | Fiber Testing |  | 62.53%
|  |  | Power Testing |  | 39.63%
61900 | B1 |  | Radio Unit Installation |  | 58.85% | 50.01% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 54.88%
|  |  | Fiber Box Installation |  | 45%
|  |  | Antenna Installation |  | 66.89%
|  |  | Antenna Cable Installation |  | 65.86%
|  |  | Splitter Installation |  | 15.5%
|  |  | Fiber Cable Splicing |  | 72.34%
|  |  | Fiber Testing |  | 37.87%
|  |  | Power Testing |  | 32.86%
62300 | B1 |  | Radio Unit Installation |  | 66.6% | 58.54% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 71.15%
|  |  | Fiber Box Installation |  | 96.14%
|  |  | Antenna Installation |  | 58.49%
|  |  | Antenna Cable Installation |  | 12.9%
|  |  | Splitter Installation |  | 62.29%
|  |  | Fiber Cable Splicing |  | 49.34%
|  |  | Fiber Testing |  | 29.1%
|  |  | Power Testing |  | 80.85%
63200 | B1 |  | Radio Unit Installation |  | 19.89% | 50% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 52.74%
|  |  | Fiber Box Installation |  | 81.26%
|  |  | Antenna Installation |  | 66.39%
|  |  | Antenna Cable Installation |  | 97.68%
|  |  | Splitter Installation |  | 26.08%
|  |  | Fiber Cable Splicing |  | 36.07%
|  |  | Fiber Testing |  | 4.414%
|  |  | Power Testing |  | 65.5%
63300 | B1 |  | Radio Unit Installation |  | 87.54% | 50.42% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 2.46%
|  |  | Fiber Box Installation |  | 35.94%
|  |  | Antenna Installation |  | 94.07%
|  |  | Antenna Cable Installation |  | 79.5%
|  |  | Splitter Installation |  | 42.15%
|  |  | Fiber Cable Splicing |  | 27.4%
|  |  | Fiber Testing |  | 33%
|  |  | Power Testing |  | 51.68%
64200 | B1 |  | Radio Unit Installation |  | 18.73% | 55.63% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 92.35%
|  |  | Fiber Box Installation |  | 51.72%
|  |  | Antenna Installation |  | 97.11%
|  |  | Antenna Cable Installation |  | 2.972%
|  |  | Splitter Installation |  | 47.75%
|  |  | Fiber Cable Splicing |  | 53.79%
|  |  | Fiber Testing |  | 39.86%
|  |  | Power Testing |  | 96.37%
64300 | B1 |  | Radio Unit Installation |  | 14.46% | 59.47% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 75.4%
|  |  | Fiber Box Installation |  | 83.17%
|  |  | Antenna Installation |  | 73.55%
|  |  | Antenna Cable Installation |  | 43.9%
|  |  | Splitter Installation |  | 93.52%
|  |  | Fiber Cable Splicing |  | 53.09%
|  |  | Fiber Testing |  | 52.23%
|  |  | Power Testing |  | 45.94%
65200 | B1 |  | Radio Unit Installation |  | 18.7% | 41.92% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 90.96%
|  |  | Fiber Box Installation |  | 16.27%
|  |  | Antenna Installation |  | 57.31%
|  |  | Antenna Cable Installation |  | 17.74%
|  |  | Splitter Installation |  | 37.47%
|  |  | Fiber Cable Splicing |  | 15.36%
|  |  | Fiber Testing |  | 34.96%
|  |  | Power Testing |  | 88.57%
65200 | B2 |  | Radio Unit Installation |  | 71.46% | 53.65% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 17.51%
|  |  | Fiber Box Installation |  | 37.59%
|  |  | Antenna Installation |  | 96.73%
|  |  | Antenna Cable Installation |  | 14.83%
|  |  | Splitter Installation |  | 67.25%
|  |  | Fiber Cable Splicing |  | 15.03%
|  |  | Fiber Testing |  | 92.55%
|  |  | Power Testing |  | 69.86%
66300 | B1 |  | Radio Unit Installation |  | 78.8% | 63.31% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 15.55%
|  |  | Fiber Box Installation |  | 99.01%
|  |  | Antenna Installation |  | 65.17%
|  |  | Antenna Cable Installation |  | 79.52%
|  |  | Splitter Installation |  | 34.78%
|  |  | Fiber Cable Splicing |  | 58.65%
|  |  | Fiber Testing |  | 43.21%
|  |  | Power Testing |  | 95.12%
66300 | B2 |  | Radio Unit Installation |  | 48.7% | 55.98% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 18.46%
|  |  | Fiber Box Installation |  | 13.56%
|  |  | Antenna Installation |  | 64.83%
|  |  | Antenna Cable Installation |  | 57%
|  |  | Splitter Installation |  | 66.89%
|  |  | Fiber Cable Splicing |  | 89.86%
|  |  | Fiber Testing |  | 70.69%
|  |  | Power Testing |  | 73.8%
67500 | B1 |  | Radio Unit Installation |  | 79.74% | 66.53% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 82.43%
|  |  | Fiber Box Installation |  | 71.04%
|  |  | Antenna Installation |  | 72.84%
|  |  | Antenna Cable Installation |  | 75.64%
|  |  | Splitter Installation |  | 46.32%
|  |  | Fiber Cable Splicing |  | 43.15%
|  |  | Fiber Testing |  | 89.67%
|  |  | Power Testing |  | 37.95%
67500 | B2 |  | Radio Unit Installation |  | 80.45% | 53.5% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 39.19%
|  |  | Fiber Box Installation |  | 5.539%
|  |  | Antenna Installation |  | 76.77%
|  |  | Antenna Cable Installation |  | 66.24%
|  |  | Splitter Installation |  | 44.01%
|  |  | Fiber Cable Splicing |  | 49.37%
|  |  | Fiber Testing |  | 92.01%
|  |  | Power Testing |  | 27.92%
68300 | B1 |  | Radio Unit Installation |  | 26.47% | 50.47% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 27.98%
|  |  | Fiber Box Installation |  | 0.2036%
|  |  | Antenna Installation |  | 88.81%
|  |  | Antenna Cable Installation |  | 78.57%
|  |  | Splitter Installation |  | 41.72%
|  |  | Fiber Cable Splicing |  | 89.08%
|  |  | Fiber Testing |  | 46.09%
|  |  | Power Testing |  | 55.29%
68300 | B2 |  | Radio Unit Installation |  | 82.37% | 36.16% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 51.84%
|  |  | Fiber Box Installation |  | 29.67%
|  |  | Antenna Installation |  | 47.7%
|  |  | Antenna Cable Installation |  | 10.81%
|  |  | Splitter Installation |  | 18.22%
|  |  | Fiber Cable Splicing |  | 46.79%
|  |  | Fiber Testing |  | 6.892%
|  |  | Power Testing |  | 31.09%
69900 | B1 |  | Radio Unit Installation |  | 54.7% | 52.79% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 50.51%
|  |  | Fiber Box Installation |  | 65.2%
|  |  | Antenna Installation |  | 93.39%
|  |  | Antenna Cable Installation |  | 85.68%
|  |  | Splitter Installation |  | 56.58%
|  |  | Fiber Cable Splicing |  | 12.56%
|  |  | Fiber Testing |  | 13.44%
|  |  | Power Testing |  | 43.06%
71400 | B1 |  | Radio Unit Installation |  | 99.62% | 63.08% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 83.21%
|  |  | Fiber Box Installation |  | 60.38%
|  |  | Antenna Installation |  | 56.19%
|  |  | Antenna Cable Installation |  | 75.63%
|  |  | Splitter Installation |  | 51.18%
|  |  | Fiber Cable Splicing |  | 63.58%
|  |  | Fiber Testing |  | 31.26%
|  |  | Power Testing |  | 46.69%
73000 | B1 |  | Radio Unit Installation |  | 96.38% | 58.05% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 44.53%
|  |  | Fiber Box Installation |  | 81.08%
|  |  | Antenna Installation |  | 84.47%
|  |  | Antenna Cable Installation |  | 85.62%
|  |  | Splitter Installation |  | 47.73%
|  |  | Fiber Cable Splicing |  | 4.721%
|  |  | Fiber Testing |  | 41.87%
|  |  | Power Testing |  | 36%
73000 | B2 |  | Radio Unit Installation |  | 23.47% | 40.91% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 55.31%
|  |  | Fiber Box Installation |  | 2.849%
|  |  | Antenna Installation |  | 17.92%
|  |  | Antenna Cable Installation |  | 87.07%
|  |  | Splitter Installation |  | 7.197%
|  |  | Fiber Cable Splicing |  | 79.94%
|  |  | Fiber Testing |  | 45.57%
|  |  | Power Testing |  | 48.83%
74100 | B1 |  | Radio Unit Installation |  | 42.59% | 37.41% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 22.74%
|  |  | Fiber Box Installation |  | 14.65%
|  |  | Antenna Installation |  | 92.62%
|  |  | Antenna Cable Installation |  | 92.14%
|  |  | Splitter Installation |  | 46.88%
|  |  | Fiber Cable Splicing |  | 17.18%
|  |  | Fiber Testing |  | 2.276%
|  |  | Power Testing |  | 5.621%
75300 | B1 |  | Radio Unit Installation |  | 91.46% | 55.88% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 16.86%
|  |  | Fiber Box Installation |  | 86.48%
|  |  | Antenna Installation |  | 19.24%
|  |  | Antenna Cable Installation |  | 40.67%
|  |  | Splitter Installation |  | 43.29%
|  |  | Fiber Cable Splicing |  | 62.67%
|  |  | Fiber Testing |  | 44.59%
|  |  | Power Testing |  | 97.67%
75300 | B2 |  | Radio Unit Installation |  | 69.99% | 48.01% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 91.9%
|  |  | Fiber Box Installation |  | 53.33%
|  |  | Antenna Installation |  | 45.96%
|  |  | Antenna Cable Installation |  | 40.15%
|  |  | Splitter Installation |  | 56.18%
|  |  | Fiber Cable Splicing |  | 40.64%
|  |  | Fiber Testing |  | 2.834%
|  |  | Power Testing |  | 31.06%
88300 | E1 |  | Radio Unit Installation |  | 97.43% | 41.07% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 43.43%
|  |  | Fiber Box Installation |  | 49.39%
|  |  | Antenna Installation |  | 2.516%
|  |  | Antenna Cable Installation |  | 68.24%
|  |  | Splitter Installation |  | 21.22%
|  |  | Fiber Cable Splicing |  | 0.04842%
|  |  | Fiber Testing |  | 78.86%
|  |  | Power Testing |  | 8.448%
88600 | E1 |  | Radio Unit Installation |  | 93.76% | 66.34% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 96.47%
|  |  | Fiber Box Installation |  | 47.39%
|  |  | Antenna Installation |  | 73.28%
|  |  | Antenna Cable Installation |  | 58.71%
|  |  | Splitter Installation |  | 85.39%
|  |  | Fiber Cable Splicing |  | 59.47%
|  |  | Fiber Testing |  | 74.5%
|  |  | Power Testing |  | 8.041%
90800 | E1 |  | Radio Unit Installation |  | 41.04% | 39.28% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 89.77%
|  |  | Fiber Box Installation |  | 31.96%
|  |  | Antenna Installation |  | 19.15%
|  |  | Antenna Cable Installation |  | 86.69%
|  |  | Splitter Installation |  | 18.93%
|  |  | Fiber Cable Splicing |  | 24.27%
|  |  | Fiber Testing |  | 39.11%
|  |  | Power Testing |  | 2.617%
92400 | E1 |  | Radio Unit Installation |  | 38.39% | 35.55% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 21.49%
|  |  | Fiber Box Installation |  | 18.71%
|  |  | Antenna Installation |  | 95.97%
|  |  | Antenna Cable Installation |  | 37.95%
|  |  | Splitter Installation |  | 36.65%
|  |  | Fiber Cable Splicing |  | 3.532%
|  |  | Fiber Testing |  | 26.39%
|  |  | Power Testing |  | 40.83%
93600 | E1 |  | Radio Unit Installation |  | 63.83% | 44.03% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 20.51%
|  |  | Fiber Box Installation |  | 45.36%
|  |  | Antenna Installation |  | 76.96%
|  |  | Antenna Cable Installation |  | 82.17%
|  |  | Splitter Installation |  | 50.83%
|  |  | Fiber Cable Splicing |  | 29.99%
|  |  | Fiber Testing |  | 17.57%
|  |  | Power Testing |  | 9.052%
95000 | E1 |  | Radio Unit Installation |  | 14.86% | 37.79% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 3.335%
|  |  | Fiber Box Installation |  | 25.53%
|  |  | Antenna Installation |  | 66.49%
|  |  | Antenna Cable Installation |  | 46.26%
|  |  | Splitter Installation |  | 77.29%
|  |  | Fiber Cable Splicing |  | 47.17%
|  |  | Fiber Testing |  | 24.87%
|  |  | Power Testing |  | 34.29%
96500 | E1 |  | Radio Unit Installation |  | 28.95% | 56.46% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 97.13%
|  |  | Fiber Box Installation |  | 60.88%
|  |  | Antenna Installation |  | 51.29%
|  |  | Antenna Cable Installation |  | 17.64%
|  |  | Splitter Installation |  | 87.82%
|  |  | Fiber Cable Splicing |  | 79.68%
|  |  | Fiber Testing |  | 17.75%
|  |  | Power Testing |  | 67.04%
98200 | E1 |  | Radio Unit Installation |  | 49.91% | 51.52% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 92.73%
|  |  | Fiber Box Installation |  | 97.96%
|  |  | Antenna Installation |  | 80.85%
|  |  | Antenna Cable Installation |  | 2.75%
|  |  | Splitter Installation |  | 53.12%
|  |  | Fiber Cable Splicing |  | 16.82%
|  |  | Fiber Testing |  | 21.19%
|  |  | Power Testing |  | 48.3%
99700 | E1 |  | Radio Unit Installation |  | 93.09% | 60.35% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 21.33%
|  |  | Fiber Box Installation |  | 99.85%
|  |  | Antenna Installation |  | 90.2%
|  |  | Antenna Cable Installation |  | 23.31%
|  |  | Splitter Installation |  | 66.77%
|  |  | Fiber Cable Splicing |  | 26.33%
|  |  | Fiber Testing |  | 83.86%
|  |  | Power Testing |  | 38.38%
99700 | E2 |  | Radio Unit Installation |  | 74.03% | 56.7% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 12.16%
|  |  | Fiber Box Installation |  | 90.21%
|  |  | Antenna Installation |  | 90.62%
|  |  | Antenna Cable Installation |  | 11.22%
|  |  | Splitter Installation |  | 40.16%
|  |  | Fiber Cable Splicing |  | 40.5%
|  |  | Fiber Testing |  | 56.84%
|  |  | Power Testing |  | 94.56%
100400 | E1 |  | Radio Unit Installation |  | 24.4% | 31.3% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 8.668%
|  |  | Fiber Box Installation |  | 52.84%
|  |  | Antenna Installation |  | 1.694%
|  |  | Antenna Cable Installation |  | 9.87%
|  |  | Splitter Installation |  | 49.42%
|  |  | Fiber Cable Splicing |  | 82.69%
|  |  | Fiber Testing |  | 6.672%
|  |  | Power Testing |  | 45.47%
100600 | E1 |  | Radio Unit Installation |  | 42.83% | 56.99% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 41.41%
|  |  | Fiber Box Installation |  | 69.55%
|  |  | Antenna Installation |  | 34.7%
|  |  | Antenna Cable Installation |  | 95.58%
|  |  | Splitter Installation |  | 79.79%
|  |  | Fiber Cable Splicing |  | 66.54%
|  |  | Fiber Testing |  | 54.42%
|  |  | Power Testing |  | 28.11%
101500 | E1 |  | Radio Unit Installation |  | 97.86% | 55.93% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 85.3%
|  |  | Fiber Box Installation |  | 7.732%
|  |  | Antenna Installation |  | 43.57%
|  |  | Antenna Cable Installation |  | 15.61%
|  |  | Splitter Installation |  | 9.138%
|  |  | Fiber Cable Splicing |  | 79.38%
|  |  | Fiber Testing |  | 80.1%
|  |  | Power Testing |  | 84.66%
102600 | E1 |  | Radio Unit Installation |  | 43.82% | 42.54% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 82.82%
|  |  | Fiber Box Installation |  | 72.12%
|  |  | Antenna Installation |  | 62.09%
|  |  | Antenna Cable Installation |  | 25.23%
|  |  | Splitter Installation |  | 3.569%
|  |  | Fiber Cable Splicing |  | 42.24%
|  |  | Fiber Testing |  | 46.24%
|  |  | Power Testing |  | 4.772%
103800 | E1 |  | Radio Unit Installation |  | 99.86% | 54.47% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 64.97%
|  |  | Fiber Box Installation |  | 13.08%
|  |  | Antenna Installation |  | 21.52%
|  |  | Antenna Cable Installation |  | 9.634%
|  |  | Splitter Installation |  | 82.25%
|  |  | Fiber Cable Splicing |  | 85.29%
|  |  | Fiber Testing |  | 80.12%
|  |  | Power Testing |  | 33.47%
104700 | E1 |  | Radio Unit Installation |  | 37.54% | 35.42% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 16.56%
|  |  | Fiber Box Installation |  | 78.14%
|  |  | Antenna Installation |  | 20.88%
|  |  | Antenna Cable Installation |  | 1.383%
|  |  | Splitter Installation |  | 68.63%
|  |  | Fiber Cable Splicing |  | 54.42%
|  |  | Fiber Testing |  | 31.62%
|  |  | Power Testing |  | 9.658%
105900 | E1 |  | Radio Unit Installation |  | 89.72% | 49.38% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 66.8%
|  |  | Fiber Box Installation |  | 51.98%
|  |  | Antenna Installation |  | 5.979%
|  |  | Antenna Cable Installation |  | 20.61%
|  |  | Splitter Installation |  | 5.667%
|  |  | Fiber Cable Splicing |  | 77.94%
|  |  | Fiber Testing |  | 34.57%
|  |  | Power Testing |  | 91.13%
106900 | E1 |  | Radio Unit Installation |  | 3.147% | 55.43% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 89.95%
|  |  | Fiber Box Installation |  | 41.59%
|  |  | Antenna Installation |  | 83.48%
|  |  | Antenna Cable Installation |  | 25.64%
|  |  | Splitter Installation |  | 72.51%
|  |  | Fiber Cable Splicing |  | 32.44%
|  |  | Fiber Testing |  | 77.37%
|  |  | Power Testing |  | 72.73%
108300 | E1 |  | Radio Unit Installation |  | 57.61% | 49.34% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 12.72%
|  |  | Fiber Box Installation |  | 54.48%
|  |  | Antenna Installation |  | 76.15%
|  |  | Antenna Cable Installation |  | 61.14%
|  |  | Splitter Installation |  | 27.14%
|  |  | Fiber Cable Splicing |  | 40.17%
|  |  | Fiber Testing |  | 91.55%
|  |  | Power Testing |  | 23.11%
109900 | E1 |  | Radio Unit Installation |  | 4.3% | 47.02% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 87.28%
|  |  | Fiber Box Installation |  | 82.22%
|  |  | Antenna Installation |  | 94.25%
|  |  | Antenna Cable Installation |  | 33.36%
|  |  | Splitter Installation |  | 33.69%
|  |  | Fiber Cable Splicing |  | 42.54%
|  |  | Fiber Testing |  | 14.27%
|  |  | Power Testing |  | 31.22%
111100 | E1 |  | Radio Unit Installation |  | 97.21% | 64.26% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 47.79%
|  |  | Fiber Box Installation |  | 99.61%
|  |  | Antenna Installation |  | 63.91%
|  |  | Antenna Cable Installation |  | 50.53%
|  |  | Splitter Installation |  | 72.67%
|  |  | Fiber Cable Splicing |  | 74.77%
|  |  | Fiber Testing |  | 24.91%
|  |  | Power Testing |  | 46.91%
112200 | E1 |  | Radio Unit Installation |  | 41.94% | 56.73% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 67.51%
|  |  | Fiber Box Installation |  | 17.49%
|  |  | Antenna Installation |  | 78.09%
|  |  | Antenna Cable Installation |  | 86.69%
|  |  | Splitter Installation |  | 43.62%
|  |  | Fiber Cable Splicing |  | 92.5%
|  |  | Fiber Testing |  | 35.11%
|  |  | Power Testing |  | 47.64%
113000 | E1 |  | Radio Unit Installation |  | 88.54% | 52.68% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 39.98%
|  |  | Fiber Box Installation |  | 58.57%
|  |  | Antenna Installation |  | 9.447%
|  |  | Antenna Cable Installation |  | 98.05%
|  |  | Splitter Installation |  | 83.38%
|  |  | Fiber Cable Splicing |  | 69.2%
|  |  | Fiber Testing |  | 5.57%
|  |  | Power Testing |  | 21.4%
114300 | E1 |  | Radio Unit Installation |  | 16.64% | 39.19% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 15.64%
|  |  | Fiber Box Installation |  | 87.84%
|  |  | Antenna Installation |  | 4.724%
|  |  | Antenna Cable Installation |  | 27.49%
|  |  | Splitter Installation |  | 50.5%
|  |  | Fiber Cable Splicing |  | 0.3891%
|  |  | Fiber Testing |  | 82.76%
|  |  | Power Testing |  | 66.75%
115500 | E1 |  | Radio Unit Installation |  | 16.59% | 32.07% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 29.54%
|  |  | Fiber Box Installation |  | 84.38%
|  |  | Antenna Installation |  | 13.43%
|  |  | Antenna Cable Installation |  | 22.59%
|  |  | Splitter Installation |  | 5.895%
|  |  | Fiber Cable Splicing |  | 80.66%
|  |  | Fiber Testing |  | 6.038%
|  |  | Power Testing |  | 29.5%
116900 | E1 |  | Radio Unit Installation |  | 53.29% | 44.17% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 79.64%
|  |  | Fiber Box Installation |  | 36.45%
|  |  | Antenna Installation |  | 53.42%
|  |  | Antenna Cable Installation |  | 16.26%
|  |  | Splitter Installation |  | 15.14%
|  |  | Fiber Cable Splicing |  | 65.17%
|  |  | Fiber Testing |  | 62.43%
|  |  | Power Testing |  | 15.69%
118300 | E1 |  | Radio Unit Installation |  | 29.91% | 51.19% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 99.3%
|  |  | Fiber Box Installation |  | 32.72%
|  |  | Antenna Installation |  | 83.5%
|  |  | Antenna Cable Installation |  | 58.33%
|  |  | Splitter Installation |  | 68.92%
|  |  | Fiber Cable Splicing |  | 6.954%
|  |  | Fiber Testing |  | 8.296%
|  |  | Power Testing |  | 72.81%
118300 | E2 |  | Radio Unit Installation |  | 6.72% | 44.26% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 69.3%
|  |  | Fiber Box Installation |  | 99.69%
|  |  | Antenna Installation |  | 7.163%
|  |  | Antenna Cable Installation |  | 48.18%
|  |  | Splitter Installation |  | 46.14%
|  |  | Fiber Cable Splicing |  | 28.2%
|  |  | Fiber Testing |  | 86.05%
|  |  | Power Testing |  | 6.956%
119500 | E1 |  | Radio Unit Installation |  | 95.89% | 59.8% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 74.69%
|  |  | Fiber Box Installation |  | 72.97%
|  |  | Antenna Installation |  | 28.66%
|  |  | Antenna Cable Installation |  | 78.71%
|  |  | Splitter Installation |  | 47.91%
|  |  | Fiber Cable Splicing |  | 53.3%
|  |  | Fiber Testing |  | 41.21%
|  |  | Power Testing |  | 44.9%
119500 | E2 |  | Radio Unit Installation |  | 38.72% | 38.43% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 61.35%
|  |  | Fiber Box Installation |  | 28.68%
|  |  | Antenna Installation |  | 6.363%
|  |  | Antenna Cable Installation |  | 67.03%
|  |  | Splitter Installation |  | 82.93%
|  |  | Fiber Cable Splicing |  | 2.07%
|  |  | Fiber Testing |  | 23.1%
|  |  | Power Testing |  | 35.66%
120800 | E1 |  | Radio Unit Installation |  | 59.45% | 60.69% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 48.62%
|  |  | Fiber Box Installation |  | 52.3%
|  |  | Antenna Installation |  | 75.76%
|  |  | Antenna Cable Installation |  | 29.53%
|  |  | Splitter Installation |  | 90.03%
|  |  | Fiber Cable Splicing |  | 60.67%
|  |  | Fiber Testing |  | 90.1%
|  |  | Power Testing |  | 39.73%
120800 | E2 |  | Radio Unit Installation |  | 34.62% | 57.51% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 4.868%
|  |  | Fiber Box Installation |  | 55.46%
|  |  | Antenna Installation |  | 78.35%
|  |  | Antenna Cable Installation |  | 98.23%
|  |  | Splitter Installation |  | 28.26%
|  |  | Fiber Cable Splicing |  | 83.01%
|  |  | Fiber Testing |  | 34.87%
|  |  | Power Testing |  | 99.94%
121900 | E1 |  | Radio Unit Installation |  | 53.58% | 63.99% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 78.4%
|  |  | Fiber Box Installation |  | 62.81%
|  |  | Antenna Installation |  | 96.32%
|  |  | Antenna Cable Installation |  | 43.8%
|  |  | Splitter Installation |  | 98.22%
|  |  | Fiber Cable Splicing |  | 52.86%
|  |  | Fiber Testing |  | 13.89%
|  |  | Power Testing |  | 76.05%
122800 | E1 |  | Radio Unit Installation |  | 91.56% | 63.87% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 2.632%
|  |  | Fiber Box Installation |  | 94.86%
|  |  | Antenna Installation |  | 91.84%
|  |  | Antenna Cable Installation |  | 37.13%
|  |  | Splitter Installation |  | 66.67%
|  |  | Fiber Cable Splicing |  | 17.51%
|  |  | Fiber Testing |  | 77.07%
|  |  | Power Testing |  | 95.57%
123900 | D1 |  | Radio Unit Installation |  | 93.8% | 46.14% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 55.57%
|  |  | Fiber Box Installation |  | 80.35%
|  |  | Antenna Installation |  | 45.28%
|  |  | Antenna Cable Installation |  | 8.774%
|  |  | Splitter Installation |  | 15.41%
|  |  | Fiber Cable Splicing |  | 3.748%
|  |  | Fiber Testing |  | 62.54%
|  |  | Power Testing |  | 49.77%
124900 | D1 |  | Radio Unit Installation |  | 82.87% | 59.86% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 41.67%
|  |  | Fiber Box Installation |  | 80.97%
|  |  | Antenna Installation |  | 8.809%
|  |  | Antenna Cable Installation |  | 25.7%
|  |  | Splitter Installation |  | 43.45%
|  |  | Fiber Cable Splicing |  | 89.08%
|  |  | Fiber Testing |  | 99.33%
|  |  | Power Testing |  | 66.86%
125900 | D1 |  | Radio Unit Installation |  | 76.92% | 61.4% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 78.82%
|  |  | Fiber Box Installation |  | 87.02%
|  |  | Antenna Installation |  | 94.4%
|  |  | Antenna Cable Installation |  | 27.49%
|  |  | Splitter Installation |  | 83.94%
|  |  | Fiber Cable Splicing |  | 24.21%
|  |  | Fiber Testing |  | 3.251%
|  |  | Power Testing |  | 76.53%
123900 | D2 |  | Radio Unit Installation |  | 3.909% | 28.06% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 9.195%
|  |  | Fiber Box Installation |  | 36.02%
|  |  | Antenna Installation |  | 14.88%
|  |  | Antenna Cable Installation |  | 72.69%
|  |  | Splitter Installation |  | 9.91%
|  |  | Fiber Cable Splicing |  | 62.94%
|  |  | Fiber Testing |  | 32.94%
|  |  | Power Testing |  | 10.08%
124900 | D2 |  | Radio Unit Installation |  | 79.05% | 44.89% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 44.01%
|  |  | Fiber Box Installation |  | 6.412%
|  |  | Antenna Installation |  | 90.79%
|  |  | Antenna Cable Installation |  | 29.79%
|  |  | Splitter Installation |  | 46.16%
|  |  | Fiber Cable Splicing |  | 80.42%
|  |  | Fiber Testing |  | 6.411%
|  |  | Power Testing |  | 21.02%
125900 | D2 |  | Radio Unit Installation |  | 39.41% | 52.98% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 4.597%
|  |  | Fiber Box Installation |  | 87.49%
|  |  | Antenna Installation |  | 47.74%
|  |  | Antenna Cable Installation |  | 39.15%
|  |  | Splitter Installation |  | 59.29%
|  |  | Fiber Cable Splicing |  | 97.24%
|  |  | Fiber Testing |  | 19.06%
|  |  | Power Testing |  | 82.81%

## Z-CASE
Stationing | Track No | Location | Activity | Date | Progress | General Progress | Notes
|  |  | CASE Install |  | 34.23% |  | Z-CASE IS BY E1-986 (Z)
|  |  | Cable Connection/Termination |  | 22.64%
|  |  | Pre-Op testing |  | 42.34%
|  |  | CASE Install |  | 76.44% |  | Z-CASE IS BY E1-1006 (Z)
|  |  | Cable Connection/Termination |  | 84.07%
|  |  | Pre-Op testing |  | 49.26%
|  |  | CASE Install |  | 51.63% |  | Z-CASE IS BY E1-1030 (Z)
|  |  | Cable Connection/Termination |  | 44.82%
|  |  | Pre-Op testing |  | 18.49%
|  |  | CASE Install |  | 50.74% |  | Z-CASE IS BY E1-1068 (Z)
|  |  | Cable Connection/Termination |  | 94.88%
|  |  | Pre-Op testing |  | 98.74%
115725 | E1 |  | CASE Install |  | 87.08% |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
|  |  | Cable Connection/Termination |  | 47.54%
|  |  | Pre-Op testing |  | 17%
121810 | E1 |  | CASE Install |  | 68.14% |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
|  |  | Cable Connection/Termination |  | 84.47%
|  |  | Pre-Op testing |  | 79.75%
| E1 |  | CASE Install |  | 34.82% |  | Z-CASE IS BY E1-1229 (Z)
|  |  | Cable Connection/Termination |  | 97.62%
|  |  | Pre-Op testing |  | 53.46%
| E1 |  | CASE Install |  | 34.44% |  | Z-CASE IS BY E1-1230 (Z)
|  |  | Cable Connection/Termination |  | 41.17%
|  |  | Pre-Op testing |  | 20.38%
98565 | E2 |  | CASE Install |  | 6.489% |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
|  |  | Cable Connection/Termination |  | 79.91%
|  |  | Pre-Op testing |  | 78.06%
114869 | E2 |  | CASE Install |  | 7.539% |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
|  |  | Cable Connection/Termination |  | 94.8%
|  |  | Pre-Op testing |  | 44.21%
| E2 |  | CASE Install |  | 69.97% |  | Z-CASE IS BY E2-1230(Z)
|  |  | Cable Connection/Termination |  | 84.4%
|  |  | Pre-Op testing |  | 58.35%
122071 | E5 |  | CASE Install |  | 42.85% |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
|  |  | Cable Connection/Termination |  | 19.18%
|  |  | Pre-Op testing |  | 4.533%
122687 | E5 |  | CASE Install |  | 60.41% |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
|  |  | Cable Connection/Termination |  | 9.643%
|  |  | Pre-Op testing |  | 87.2%

## TOPB
Stationing | Track No | Location | Activity | Date | Progress | General Progress | Notes
121810 | E1 |  | TOPB Install |  | 39.08% |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
|  |  | Cable Connection/Termination |  | 84.89%
|  |  | Pre-Op testing |  | 5.63%
122987 | E1 |  | TOPB Install |  | 21.88% |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
|  |  | Cable Connection/Termination |  | 33.48%
|  |  | Pre-Op testing |  | 63.23%
|  |  | TOPB Install |  | 25.62% |  | TOPB @ ~D1-1239
|  |  | Cable Connection/Termination |  | 93.43%
|  |  | Pre-Op testing |  | 81.18%
121809 | E2 |  | TOPB Install |  | 93.44% |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
|  |  | Cable Connection/Termination |  | 9.659%
|  |  | Pre-Op testing |  | 39.79%
122970 | E2 |  | TOPB Install |  | 81.89% |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
|  |  | Cable Connection/Termination |  | 1.943%
|  |  | Pre-Op testing |  | 27.22%
124043 | D2 |  | TOPB Install |  | 97.87% |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
|  |  | Cable Connection/Termination |  | 51.68%
|  |  | Pre-Op testing |  | 86.64%

## Report Screenshot
Tasks | Total Quantity | Installed/Tested Quantity
Acceptance Test (Ea) | 29 | 3
Antenna Cable (ft) | 61885 | 58432
Brackets (Ea) | 12147 | 11856
Coax Cable (Ea) | 59 | 59
Insertion Loss (Segment) (ft) | 47445 | 43615
Removals (ft) | 30946 | 2380
Coupler Plates | 27 | 27
DC Resistance (Segment) | 47410 | 43580
Megger (Segment) | 47445 | 43615
VSWR (Segment) | 47445 | 43615
End-To-End | 47445 | 33565
Heat Map Test | 47445 | 29175
Coverage Test/Survey | 47445 | 3160
Megger Coax Cable (Reel) | 4000 | 4000
Megger Antenna Cable (Reel) | 80000 | 80000
Megger 1/2in Cable (Reel) | 100 | 100
DC Resistance Coax Cable (Reel) | 4000 | 4000
DC Resistance Antenna Cable (Reel) | 80000 | 80000
DC Resistance 1/2in Cable (Reel) | 100 | 100

## Dashboard
RADIO INSTALLATION DASHBOARD
OVERALL TASK COMPLETION (ALL TRACKS)
TASK PERCENT COMPLETION (PER TRACK)
OVERALL INSTALLATION PROGRESS PER TRACK SECTION
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.