## Reference
Track No. | Column Side | Activities | Bracket Type | Station | Track Stationing | Tunnel | Description | Track Stationing | Notes
B1 | W | Steel Messenger Supports | 1 | Church Avenue | 556+96 to 563+56 | CHU-FOR | Church Ave to Fort Hamilton | 563+56 to 584+88
B2 | E | Messenger Clamps | 2 | Fort Hamilton Parkway | 584+88 to 591+90 | FOR-15S | Fort Hamilton to 15th Street | 591+90 to 625+70
B3 | W | Messenger Wire Pull | 3 | 15th Street Prospect Park | 625+70 to 632+30 | 15S-7AV | 15th Street to 7th Avenue | 632+30 to 653+96
B4 | E | Messenger Wire Tension | 4 | 7th Avenue | 653+96 to 660+56 | 7AV-4TH | 7th Avenue to 4th & 9th Street | 660+56-683+83
E1 | W | Cable Pull | 4A | 4th & 9th Street | 683+83 to 690+91 | 4TH-SMI | 4th & 9th Street to Smith & 9th Street | 690+91 to 705+11
E2 | E | Messenger Straps | 5 | Smith & 9th Street | 705+11 to 712+32 | SMI-CAR | Smith & 9th Street to Carroll Street | 712+32 to 732+89
E3 |  | 15inch CMRS |  | Carroll Street | 732+39 to 738+99 | CAR-BER | Carroll Street to Bergen Street | 738+99 to 756+82
E4 |  | 24inch CMRS |  | Bergen Street | 756+82 to 763+42 | BER-HOY | Bergen Street to Hoyt Schermerhorn | 763+42 to 761+84 | track goes from 768+XX to 693+95
E5 |  | Column mount CMRS |  | Hoyt Schermerhorn | 761+84 to 768+87 | HOY-FUL | Hoyt Schermerhorn to Fulton | 768+87 to 740+30
|  | Station Brackets |  | Fulton Street | 740+30 to 733+70 | FUL-CLI | Fulton to Clinton Washington | 733+70 to 951+82 | track goes from 733+15 to 934+96
Location |  | Grounding |  | Clinton Washington Avenue | 951+82 to 958+42 | CLI-CLA | Clinton Washington to Classon | 958+42 to 970+82
Church Avenue |  | Obstruction Brackets |  | Classon Avenue | 970+82 to 977+42 | CLA-BED | Classon to Bedford Nostand | 977+42 to 989+22
CHU-FOR |  | Cable Pull |  | Bedford Nostrand Avenue | 989+22 to 995+82 | BED-MYR | Bedford Nostrand to Myrtle Willoughby | 995+82 to 1017+47
Fort Hamilton Parkway |  | Cable Tray Brackets |  | Myrtle Willoughby Ave | 1017+47 to 1024+52 | MYR-FLU | Myrtle Willoughby to Flushing Avenue | 1024+52 to 1039+42
FOR-15S |  | Installing Tray |  | Flushing Avenue Station | 1039+42 to 1046+20 | FLU-BRO | Flushing Avenue to Broadway | 1046+20 to 1060+52
15th Street Prospect Park |  | Core Drilling |  | Broadway | 1060+52 to 1067+12 | BRO-MET | Broadway to Metropolitan | 1067+12 to 1132+45
15S-7AV |  | Cable Pull |  | Metropolitan Avenue | 1132+45 to 1139+50 | MET-NAS | Metropolitan to Nassau | 1139+50 to 1131+52
7th Avenue |  | Arch Bar Installation |  | Nassau Avenue | 1131+52 to 1138+32 | NAS-GRE | Nassau to Greenpoint | 1138+32 to 1157+00
7AV-4TH |  |  |  | Greenpoint Avenue | 1157+00 to 1164+32 | GRE-21S | Greenpoint to 21 St | 1164+32 to 1211+33
4th & 9th Street |  |  |  | 21 St Station | 1211+33 to 1217+92 | 21S-COU | 21 St to Court Square | 1217+92 to 1229+23
4TH-SMI |  |  |  | Court Square | 1229+23 to 1236+66 | COU-QUE | Court Square to Queens Plaza | 1236+66 to 1250+65
Smith & 9th Street |  |  |  | Queens Plaza | 1250+65 to 1257+27
SMI-CAR
Carroll Street |  |  |  | Signal Types
CAR-BER |  |  |  | HOME
Bergen Street* |  |  |  | APPROACH
BER-HOY |  |  |  | BUMPER
Hoyt Schermerhorn |  |  |  | REV. HOME
HOY-FUL |  |  |  | REV. APPROACH
Fulton Street
FUL-CLI
Clinton Washington Avenue
CLI-CLA
Classon Avenue
CLA-BED
Bedford Nostrand Avenue
BED-MYR
Myrtle Willoughby Ave
MYR-FLU
Flushing Avenue Station
FLU-BRO
Broadway
BRO-MET
Metropolitan Avenue
MET-NAS
Nassau Avenue
NAS-GRE
Greenpoint Avenue
GRE-21S
21 St Station
21S-COU
Court Square
COU-QUE
Queens Plaza

## Work Sheet (hidden)
OVERALL INSTALLATION PER AREA
Status | Count
Not Started | #REF!
In Progress | #REF!
Completed | #REF!
Remaining | #REF!
Total Tasks | #REF!
Completed Sections | #REF!
Remaining Sections | #REF!

## Ref Activity Bar (hidden)
RADIO INSTALLATION DASHBOARD
TRACK | C3/C4
TASK | COMPLETION PROGRESS
Removals | 12.5%
Grand Total | 12.5%

## Ref Progress per Activity (hidden)
TASK | Acceptance Test
|  | Not Started | 0 | Completed Sections | 13.04%
TRACK | Average of PROGRESS | In Progress | 0 | Remaining Sections | 86.96%
C1 | 16.67% | Completed | 0
C2 | 16.67%
C3 | 0%
C3/C4 | 14.29%
C4 | 0%
C5 | 0%
C6 | 0%
Grand Total | 13.04%

## CMRS
Start | Finish | Track No | Location | Activity | Total Quantity | QTY Installed | Date | Progress | General Progress | Notes | Notes
124510 | 124500 | D1 | COU-QUE | Steel Mess Supports | 252 | 56 |  | 0.22222 | 0.52721
|  |  |  | Messenger Clamps | 905 | 826 |  | 0.91271
|  |  |  | Messenger Wire Pull | 71 | 64 |  | 0.90141
|  |  |  | Messenger Wire Tension | 463 | 112 |  | 0.2419
|  |  |  | # Cables Pulled | 206 | 97 |  | 0.47087
|  |  |  | Messenger Straps | 821 | 340 |  | 0.41413
124500 | 124320 | D1 | COU-QUE | Steel Mess Supports | 56 | 16 |  | 0.28571 | 0.46451
|  |  |  | Messenger Clamps | 115 | 87 |  | 0.75652
|  |  |  | Messenger Wire Pull | 727 | 561 |  | 0.77166
|  |  |  | Messenger Wire Tension | 574 | 3 |  | 0.0052265
|  |  |  | # Cables Pulled | 129 | 29 |  | 0.22481
|  |  |  | Messenger Straps | 109 | 81 |  | 0.74312
124320 | 124100 | D1 | COU-QUE | Steel Mess Supports | 172 | 167 |  | 0.97093 | 0.30909
|  |  |  | Messenger Clamps | 423 | 122 |  | 0.28842
|  |  |  | Messenger Wire Pull | 786 | 43 |  | 0.054707
|  |  |  | Messenger Wire Tension | 908 | 250 |  | 0.27533
|  |  |  | # Cables Pulled | 741 | 101 |  | 0.1363
|  |  |  | Messenger Straps | 163 | 21 |  | 0.12883
124100 | 123970 | D1 | COU-QUE | Steel Mess Supports | 197 | 162 |  | 0.82234 | 0.7143
|  |  |  | Messenger Clamps | 450 | 214 |  | 0.47556
|  |  |  | Messenger Wire Pull | 662 | 655 |  | 0.98943
|  |  |  | Messenger Wire Tension | 112 | 79 |  | 0.70536
|  |  |  | # Cables Pulled | 619 | 422 |  | 0.68174
|  |  |  | Messenger Straps | 561 | 343 |  | 0.61141
123970 | 123930 | D1 | COU-QUE | 15" CMRS Install | 109 | 78 |  | 0.7156 | 0.70313
|  |  |  | Column Clamp | 622 | 393 |  | 0.63183
|  |  |  | Station Brackets | 42 | 17 |  | 0.40476
|  |  |  | Grounding | 398 | 365 |  | 0.91709
|  |  |  | Obstruction Brackets | 956 | 541 |  | 0.5659
|  |  |  | # Cables Pulled | 183 | 180 |  | 0.98361
123930 | 123715 | D1 | COU-QUE | 15" CMRS Install | 105 | 86 |  | 0.81905 | 0.57803
|  |  |  | Column Clamp | 942 | 833 |  | 0.88429
|  |  |  | Station Brackets | 144 | 133 |  | 0.92361
|  |  |  | Grounding | 458 | 163 |  | 0.3559
|  |  |  | Obstruction Brackets | 943 | 406 |  | 0.43054
|  |  |  | # Cables Pulled | 73 | 4 |  | 0.054795
|  | D1 | COU-QUE | Crossover (Arch Bar Installation) | 58 | 29 |  | 0.5
122975 | 122827 | E1 | 21S-COU | Steel Mess Supports | 876 | 8 |  | 0.0091324 | 0.30952
|  |  |  | Messenger Clamps | 204 | 59 |  | 0.28922
|  |  |  | Messenger Wire Pull | 150 | 48 |  | 0.32
|  |  |  | Messenger Wire Tension | 993 | 172 |  | 0.17321
|  |  |  | # Cables Pulled | 160 | 138 |  | 0.8625
|  |  |  | Messenger Straps | 719 | 146 |  | 0.20306
122827 | 122250 | E1 | 21S-COU | 24" CMRS Install | 443 | 357 |  | 0.80587 | 0.69733
|  |  |  | Column Clamp | 356 | 331 |  | 0.92978
|  |  |  | Station Brackets | 711 | 21 |  | 0.029536
|  |  |  | Grounding | 851 | 402 |  | 0.47239
|  |  |  | Obstruction Brackets | 343 | 335 |  | 0.97668
|  |  |  | # Cables Pulled | 628 | 609 |  | 0.96975
122250 | 121833 | E1 | 21S-COU | Steel Mess Supports | 26 | 12 |  | 0.46154 | 0.69369
|  |  |  | Messenger Clamps | 147 | 84 |  | 0.57143
|  |  |  | Messenger Wire Pull | 544 | 510 |  | 0.9375
|  |  |  | Messenger Wire Tension | 269 | 196 |  | 0.72862
|  |  |  | # Cables Pulled | 740 | 727 |  | 0.98243
|  |  |  | Messenger Straps | 258 | 124 |  | 0.48062
121833 | 121030 | E1 | 21 STREET | Steel Mess Supports | 443 | 369 |  | 0.83296 | 0.68865
|  |  |  | Messenger Clamps | 580 | 562 |  | 0.96897
|  |  |  | Messenger Wire Pull | 633 | 497 |  | 0.78515
|  |  |  | Messenger Wire Tension | 860 | 614 |  | 0.71395
|  |  |  | # Cables Pulled | 130 | 73 |  | 0.56154
|  |  |  | Messenger Straps | 854 | 230 |  | 0.26932
121030 | 117010 | E1 | GRE-21S | 15" CMRS Install | 124 | 10 |  | 0.080645 | 0.19809
|  |  |  | Column Clamp | 381 | 161 |  | 0.42257
|  |  |  | Station Brackets | 440 | 29 |  | 0.065909
|  |  |  | Grounding | 897 | 155 |  | 0.1728
|  |  |  | Obstruction Brackets | 297 | 50 |  | 0.16835
|  |  |  | # Cables Pulled | 442 | 123 |  | 0.27828
117010 | 116810 | E1 | GRE-21S | 15" CMRS Install | 290 | 83 |  | 0.28621 | 0.34105
|  |  |  | Column Clamp | 580 | 13 |  | 0.022414
|  |  |  | Station Brackets | 694 | 129 |  | 0.18588
|  |  |  | Grounding | 207 | 45 |  | 0.21739
|  |  |  | Obstruction Brackets | 825 | 379 |  | 0.45939
|  |  |  | # Cables Pulled | 64 | 56 |  | 0.875
116810 | 116471 | E1 | GRE-21S | 15" CMRS Install | 890 | 285 |  | 0.32022 | 0.61789
|  |  |  | Column Clamp | 179 | 138 |  | 0.77095
|  |  |  | Station Brackets | 580 | 539 |  | 0.92931
|  |  |  | Grounding | 287 | 213 |  | 0.74216
|  |  |  | Obstruction Brackets | 563 | 234 |  | 0.41563
|  |  |  | # Cables Pulled | 654 | 346 |  | 0.52905
116471 | 115694 | E1 | GREENPOINT | 24" CMRS Install | 508 | 451 |  | 0.8878 | 0.72848
|  |  |  | Column Clamp | 910 | 497 |  | 0.54615
|  |  |  | Station Brackets | 93 | 88 |  | 0.94624
|  |  |  | Grounding | 939 | 832 |  | 0.88605
|  |  |  | Obstruction Brackets | 725 | 388 |  | 0.53517
|  |  |  | # Cables Pulled | 367 | 209 |  | 0.56948
115694 | 115628 | E1 | NAS-GRE | 24" CMRS Install | 387 | 76 |  | 0.19638 | 0.28946
|  |  |  | Column Clamp | 160 | 47 |  | 0.29375
|  |  |  | Station Brackets | 424 | 55 |  | 0.12972
|  |  |  | Grounding | 495 | 239 |  | 0.48283
|  |  |  | Obstruction Brackets | 256 | 88 |  | 0.34375
|  |  |  | # Cables Pulled | 124 | 36 |  | 0.29032
115628 | 114897 | E1 | NAS-GRE | 24" CMRS Install | 257 | 203 |  | 0.78988 | 0.49704
|  |  |  | Column Clamp | 145 | 22 |  | 0.15172
|  |  |  | Station Brackets | 894 | 191 |  | 0.21365
|  |  |  | Grounding | 360 | 121 |  | 0.33611
|  |  |  | Obstruction Brackets | 708 | 705 |  | 0.99576
|  |  |  | # Cables Pulled | 204 | 101 |  | 0.4951
114897 | 114719 | E1 | NAS-GRE | Steel Mess Supports | 692 | 313 |  | 0.45231 | 0.45849
|  |  |  | Messenger Clamps | 475 | 121 |  | 0.25474
|  |  |  | Messenger Wire Pull | 810 | 800 |  | 0.98765
|  |  |  | Messenger Wire Tension | 979 | 65 |  | 0.066394
|  |  |  | # Cables Pulled | 279 | 0 |  | 0
|  |  |  | Messenger Straps | 888 | 879 |  | 0.98986
114719 | 114040 | E1 | NAS-GRE | 24" CMRS Install | 124 | 32 |  | 0.25806 | 0.40649
|  |  |  | Column Clamp | 395 | 174 |  | 0.44051
|  |  |  | Station Brackets | 254 | 112 |  | 0.44094
|  |  |  | Grounding | 590 | 440 |  | 0.74576
|  |  |  | Obstruction Brackets | 261 | 93 |  | 0.35632
|  |  |  | # Cables Pulled | 978 | 193 |  | 0.19734
114040 | 113815 | E1 | NAS-GRE | Steel Mess Supports | 795 | 257 |  | 0.32327 | 0.39034
|  |  |  | Messenger Clamps | 720 | 238 |  | 0.33056
|  |  |  | Messenger Wire Pull | 699 | 92 |  | 0.13162
|  |  |  | Messenger Wire Tension | 928 | 203 |  | 0.21875
|  |  |  | # Cables Pulled | 18 | 9 |  | 0.5
|  |  |  | Messenger Straps | 481 | 403 |  | 0.83784
113815 | 113019 | E1 | NASSAU | 24" CMRS Install | 327 | 41 |  | 0.12538 | 0.64763 |  | weight: 6.7 lb/ft
|  |  |  | Column Clamp | 841 | 545 |  | 0.64804
|  |  |  | Station Brackets | 374 | 358 |  | 0.95722
|  |  |  | Grounding | 995 | 706 |  | 0.70955
|  |  |  | Obstruction Brackets | 969 | 434 |  | 0.44788
|  |  |  | # Cables Pulled | 867 | 865 |  | 0.99769
|  | E1 | NASSAU | 24" CMRS Install | 341 | 68 |  | 0.19941 | 0.59987
|  |  |  | Column Clamp | 705 | 390 |  | 0.55319
|  |  |  | Station Brackets | 232 | 149 |  | 0.64224
|  |  |  | Grounding | 613 | 549 |  | 0.8956
|  |  |  | Obstruction Brackets | 656 | 533 |  | 0.8125
|  |  |  | # Cables Pulled | 673 | 334 |  | 0.49629
113019 | 112700 | E1 | MET-NAS | 24" CMRS Install | 338 | 120 |  | 0.35503 | 0.48127
|  |  |  | Column Clamp | 439 | 252 |  | 0.57403
|  |  |  | Station Brackets | 143 | 34 |  | 0.23776
|  |  |  | Grounding | 716 | 228 |  | 0.31844
|  |  |  | Obstruction Brackets | 556 | 411 |  | 0.73921
|  |  |  | # Cables Pulled | 95 | 63 |  | 0.66316
112700 | 110878 | E1 | MET-NAS | 15" CMRS Install | 80 | 8 |  | 0.1 | 0.22671
|  |  |  | Column Clamp | 831 | 272 |  | 0.32732
|  |  |  | Station Brackets | 806 | 194 |  | 0.24069
|  |  |  | Grounding | 143 | 12 |  | 0.083916
|  |  |  | Obstruction Brackets | 564 | 292 |  | 0.51773
|  |  |  | # Cables Pulled | 640 | 58 |  | 0.090625
110878 | 110793 | E1 | MET-NAS | 15" CMRS Install | 766 | 679 |  | 0.88642 | 0.5876
|  |  |  | Column Clamp | 113 | 34 |  | 0.30088
|  |  |  | Station Brackets | 891 | 493 |  | 0.55331
|  |  |  | Grounding | 751 | 379 |  | 0.50466
|  |  |  | Obstruction Brackets | 55 | 53 |  | 0.96364
|  |  |  | # Cables Pulled | 480 | 152 |  | 0.31667
110793 | 109251 | E1 | MET-NAS | 15" CMRS Install | 262 | 253 |  | 0.96565 | 0.64786
|  |  |  | Column Clamp | 865 | 24 |  | 0.027746
|  |  |  | Station Brackets | 105 | 92 |  | 0.87619
|  |  |  | Grounding | 458 | 160 |  | 0.34934
|  |  |  | Obstruction Brackets | 804 | 634 |  | 0.78856
|  |  |  | # Cables Pulled | 748 | 658 |  | 0.87968
109251 | 109133 | E1 | MET-NAS | 15" CMRS Install | 854 | 69 |  | 0.080796 | 0.39764
|  |  |  | Column Clamp | 763 | 181 |  | 0.23722
|  |  |  | Station Brackets | 58 | 1 |  | 0.017241
|  |  |  | Grounding | 190 | 104 |  | 0.54737
|  |  |  | Obstruction Brackets | 125 | 85 |  | 0.68
|  |  |  | # Cables Pulled | 345 | 284 |  | 0.82319
109133 | 108356 | E1 | METROPOLITAN | 15" CMRS Install | 572 | 271 |  | 0.47378 | 0.47243
|  |  |  | Column Clamp | 635 | 34 |  | 0.053543
|  |  |  | Station Brackets | 444 | 171 |  | 0.38514
|  |  |  | Grounding | 915 | 857 |  | 0.93661
|  |  |  | Obstruction Brackets | 484 | 189 |  | 0.3905
|  |  |  | # Cables Pulled | 479 | 285 |  | 0.59499
108356 | 107651 | E1 | BRO-MET | 15" CMRS Install | 71 | 15 |  | 0.21127 | 0.32791
|  |  |  | Column Clamp | 372 | 29 |  | 0.077957
|  |  |  | Station Brackets | 371 | 139 |  | 0.37466
|  |  |  | Grounding | 50 | 11 |  | 0.22
|  |  |  | Obstruction Brackets | 551 | 468 |  | 0.84936
|  |  |  | # Cables Pulled | 901 | 211 |  | 0.23418
107651 | 107611 | E1 | BRO-MET | 15" CMRS Install | 490 | 160 |  | 0.32653 | 0.23579 |  | Check endings for specific stationings (DWG 48012-17N-006.0) where cable switches from 1 to 2
|  |  |  | Column Clamp | 730 | 451 |  | 0.61781
|  |  |  | Station Brackets | 547 | 64 |  | 0.117
|  |  |  | Grounding | 391 | 8 |  | 0.02046
|  |  |  | Obstruction Brackets | 960 | 245 |  | 0.25521
|  |  |  | # Cables Pulled | 296 | 23 |  | 0.077703
107611 | 106768 | E1 | BRO-MET | 15" CMRS Install | 732 | 260 |  | 0.35519 | 0.6679
|  |  |  | Column Clamp | 740 | 682 |  | 0.92162
|  |  |  | Station Brackets | 281 | 175 |  | 0.62278
|  |  |  | Grounding | 829 | 325 |  | 0.39204
|  |  |  | Obstruction Brackets | 210 | 201 |  | 0.95714
|  |  |  | # Cables Pulled | 58 | 44 |  | 0.75862
106768 | 106702 | E1 | BRO-MET | 15" CMRS Install | 152 | 99 |  | 0.65132 | 0.47688
|  |  |  | Column Clamp | 171 | 17 |  | 0.099415
|  |  |  | Station Brackets | 867 | 677 |  | 0.78085
|  |  |  | Grounding | 114 | 100 |  | 0.87719
|  |  |  | Obstruction Brackets | 383 | 149 |  | 0.38903
|  |  |  | # Cables Pulled | 898 | 57 |  | 0.063474
106702 | 106011 | E1 | BROADWAY | 15" CMRS Install | 313 | 312 |  | 0.99681 | 0.45016
|  |  |  | Column Clamp | 135 | 18 |  | 0.13333
|  |  |  | Station Brackets | 17 | 13 |  | 0.76471
|  |  |  | Grounding | 568 | 215 |  | 0.37852
|  |  |  | Obstruction Brackets | 77 | 8 |  | 0.1039
|  |  |  | # Cables Pulled | 519 | 168 |  | 0.3237
|  | E1 | BROADWAY | 15" CMRS Install | 245 | 28 |  | 0.11429 | 0.60844
|  |  |  | Column Clamp | 646 | 256 |  | 0.39628
|  |  |  | Station Brackets | 232 | 162 |  | 0.69828
|  |  |  | Grounding | 740 | 739 |  | 0.99865
|  |  |  | Obstruction Brackets | 414 | 293 |  | 0.70773
|  |  |  | # Cables Pulled | 412 | 303 |  | 0.73544
|  | E1 | BROADWAY | 15" CMRS Install | 247 | 65 |  | 0.26316 | 0.38163
|  |  |  | Column Clamp | 585 | 71 |  | 0.12137
|  |  |  | Station Brackets | 512 | 150 |  | 0.29297
|  |  |  | Grounding | 788 | 530 |  | 0.67259
|  |  |  | Obstruction Brackets | 245 | 193 |  | 0.78776
|  |  |  | # Cables Pulled | 533 | 81 |  | 0.15197
106011 | 105293 | E1 | FLU-BRO | 15" CMRS Install | 425 | 1 |  | 0.0023529 | 0.14687
|  |  |  | Column Clamp | 291 | 131 |  | 0.45017
|  |  |  | Station Brackets | 415 | 12 |  | 0.028916
|  |  |  | Grounding | 669 | 145 |  | 0.21674
|  |  |  | Obstruction Brackets | 503 | 49 |  | 0.097416
|  |  |  | # Cables Pulled | 829 | 71 |  | 0.085645
105293 | 104667 | E1 | FLU-BRO | 15" CMRS Install | 186 | 176 |  | 0.94624 | 0.58701
|  |  |  | Column Clamp | 972 | 698 |  | 0.71811
|  |  |  | Station Brackets | 956 | 705 |  | 0.73745
|  |  |  | Grounding | 55 | 30 |  | 0.54545
|  |  |  | Obstruction Brackets | 457 | 3 |  | 0.0065646
|  |  |  | # Cables Pulled | 403 | 229 |  | 0.56824
104667 | 103784 | E1 | FLUSHING | 15" CMRS Install | 884 | 124 |  | 0.14027 | 0.61768
|  |  |  | Column Clamp | 412 | 369 |  | 0.89563
|  |  |  | Station Brackets | 473 | 402 |  | 0.84989
|  |  |  | Grounding | 282 | 191 |  | 0.6773
|  |  |  | Obstruction Brackets | 554 | 190 |  | 0.34296
|  |  |  | # Cables Pulled | 395 | 316 |  | 0.8
103784 | 103231 | E1 | MYR-FLU | 15" CMRS Install | 493 | 56 |  | 0.11359 | 0.61615
|  |  |  | Column Clamp | 625 | 582 |  | 0.9312
|  |  |  | Station Brackets | 364 | 93 |  | 0.25549
|  |  |  | Grounding | 551 | 393 |  | 0.71325
|  |  |  | Obstruction Brackets | 22 | 20 |  | 0.90909
|  |  |  | # Cables Pulled | 669 | 518 |  | 0.77429
103231 | 103165 | E1 | MYR-FLU | 15" CMRS Install | 985 | 261 |  | 0.26497 | 0.41088
|  |  |  | Column Clamp | 965 | 41 |  | 0.042487
|  |  |  | Station Brackets | 583 | 360 |  | 0.6175
|  |  |  | Grounding | 511 | 338 |  | 0.66145
|  |  |  | Obstruction Brackets | 892 | 777 |  | 0.87108
|  |  |  | # Cables Pulled | 128 | 1 |  | 0.0078125
103165 | 102533 | E1 | MYR-FLU | 15" CMRS Install | 783 | 648 |  | 0.82759 | 0.59265
|  |  |  | Column Clamp | 636 | 529 |  | 0.83176
|  |  |  | Station Brackets | 638 | 45 |  | 0.070533
|  |  |  | Grounding | 84 | 57 |  | 0.67857
|  |  |  | Obstruction Brackets | 293 | 138 |  | 0.47099
|  |  |  | # Cables Pulled | 306 | 207 |  | 0.67647
102533 | 101595 | E1 | MYRTLE AVE | 24" CMRS Install | 170 | 21 |  | 0.12353 | 0.43612
|  |  |  | Column Clamp | 797 | 217 |  | 0.27227
|  |  |  | Station Brackets | 795 | 244 |  | 0.30692
|  |  |  | Grounding | 125 | 39 |  | 0.312
|  |  |  | Obstruction Brackets | 850 | 628 |  | 0.73882
|  |  |  | # Cables Pulled | 592 | 511 |  | 0.86318
101595 | 101558 | E1 | BED-MYR | 24" CMRS Install | 808 | 470 |  | 0.58168 | 0.4611
|  |  |  | Column Clamp | 374 | 340 |  | 0.90909
|  |  |  | Station Brackets | 224 | 139 |  | 0.62054
|  |  |  | Grounding | 522 | 172 |  | 0.3295
|  |  |  | Obstruction Brackets | 727 | 129 |  | 0.17744
|  |  |  | # Cables Pulled | 654 | 97 |  | 0.14832
101558 | 101050 | E1 | BED-MYR | 24" CMRS Install | 815 | 299 |  | 0.36687 | 0.54025
|  |  |  | Column Clamp | 329 | 136 |  | 0.41337
|  |  |  | Station Brackets | 336 | 324 |  | 0.96429
|  |  |  | Grounding | 71 | 25 |  | 0.35211
|  |  |  | Obstruction Brackets | 623 | 204 |  | 0.32745
|  |  |  | # Cables Pulled | 734 | 600 |  | 0.81744
101050 | 101015 | E1 | BED-MYR | 24" CMRS Install | 364 | 121 |  | 0.33242 | 0.39882
|  |  |  | Column Clamp | 34 | 2 |  | 0.058824
|  |  |  | Station Brackets | 556 | 535 |  | 0.96223
|  |  |  | Grounding | 524 | 56 |  | 0.10687
|  |  |  | Obstruction Brackets | 635 | 400 |  | 0.62992
|  |  |  | # Cables Pulled | 152 | 46 |  | 0.30263
101015 | 100530 | E1 | BED-MYR | 24" CMRS Install | 753 | 461 |  | 0.61222 | 0.46314
|  |  |  | Column Clamp | 608 | 78 |  | 0.12829
|  |  |  | Station Brackets | 593 | 411 |  | 0.69309
|  |  |  | Grounding | 226 | 105 |  | 0.4646
|  |  |  | Obstruction Brackets | 861 | 543 |  | 0.63066
|  |  |  | # Cables Pulled | 20 | 5 |  | 0.25
100530 | 100383 | E1 | BED-MYR | Steel Mess Supports | 857 | 776 |  | 0.90548 | 0.49427
|  |  |  | Messenger Clamps | 22 | 17 |  | 0.77273
|  |  |  | Messenger Wire Pull | 137 | 2 |  | 0.014599
|  |  |  | Messenger Wire Tension | 662 | 528 |  | 0.79758
|  |  |  | # Cables Pulled | 532 | 203 |  | 0.38158
|  |  |  | Messenger Straps | 534 | 50 |  | 0.093633
|  | E1 | BED-MYR | Crossover (Arch Bar Installation) | 779 | 189 |  | 0.24262
100383 | 100282 | E1 | BED-MYR | Steel Mess Supports | 332 | 6 |  | 0.018072 | 0.3295
|  |  |  | Messenger Clamps | 33 | 11 |  | 0.33333
|  |  |  | Messenger Wire Pull | 411 | 396 |  | 0.9635
|  |  |  | Messenger Wire Tension | 903 | 332 |  | 0.36766
|  |  |  | # Cables Pulled | 422 | 19 |  | 0.045024
|  |  |  | Messenger Straps | 882 | 220 |  | 0.24943
100282 | 100036 | E1 | BED-MYR | Steel Mess Supports | 491 | 113 |  | 0.23014 | 0.43211
|  |  |  | Messenger Clamps | 326 | 52 |  | 0.15951
|  |  |  | Messenger Wire Pull | 531 | 171 |  | 0.32203
|  |  |  | Messenger Wire Tension | 767 | 654 |  | 0.85267
|  |  |  | # Cables Pulled | 47 | 47 |  | 1
|  |  |  | Messenger Straps | 954 | 27 |  | 0.028302
100036 | 99560 | E1 | BED-MYR | Steel Mess Supports | 759 | 57 |  | 0.075099 | 0.1343
|  |  |  | Messenger Clamps | 529 | 41 |  | 0.077505
|  |  |  | Messenger Wire Pull | 725 | 73 |  | 0.10069
|  |  |  | Messenger Wire Tension | 733 | 104 |  | 0.14188
|  |  |  | # Cables Pulled | 812 | 175 |  | 0.21552
|  |  |  | Messenger Straps | 41 | 8 |  | 0.19512
98845 | 98555 | E1 | CLA-BED | 24" CMRS Install | 520 | 469 |  | 0.90192 | 0.57907
|  |  |  | Column Clamp | 389 | 350 |  | 0.89974
|  |  |  | Station Brackets | 299 | 214 |  | 0.71572
|  |  |  | Grounding | 604 | 78 |  | 0.12914
|  |  |  | Obstruction Brackets | 818 | 486 |  | 0.59413
|  |  |  | # Cables Pulled | 907 | 212 |  | 0.23374
|  | E1 | CLA-BED | Crossover (Arch Bar Installation) | 314 | 310 |  | 0.98726
98555 | 98220 | E1 | CLA-BED | 24" CMRS Install | 125 | 102 |  | 0.816 | 0.51201
|  |  |  | Column Clamp | 883 | 540 |  | 0.61155
|  |  |  | Station Brackets | 558 | 421 |  | 0.75448
|  |  |  | Grounding | 102 | 23 |  | 0.22549
|  |  |  | Obstruction Brackets | 991 | 70 |  | 0.070636
|  |  |  | # Cables Pulled | 197 | 117 |  | 0.59391
98220 | 98140 | E1 | CLA-BED | 24" CMRS Install | 130 | 84 |  | 0.64615 | 0.54877
|  |  |  | Column Clamp | 61 | 0 |  | 0
|  |  |  | Station Brackets | 212 | 86 |  | 0.40566
|  |  |  | Grounding | 451 | 218 |  | 0.48337
|  |  |  | Obstruction Brackets | 866 | 827 |  | 0.95497
|  |  |  | # Cables Pulled | 81 | 65 |  | 0.80247
98140 | 97920 | E1 | CLA-BED | 24" CMRS Install | 917 | 180 |  | 0.19629 | 0.37666
|  |  |  | Column Clamp | 595 | 189 |  | 0.31765
|  |  |  | Station Brackets | 61 | 6 |  | 0.098361
|  |  |  | Grounding | 703 | 525 |  | 0.7468
|  |  |  | Obstruction Brackets | 932 | 709 |  | 0.76073
|  |  |  | # Cables Pulled | 157 | 22 |  | 0.14013
97920 | 97670 | E1 | CLA-BED | Steel Mess Supports | 837 | 554 |  | 0.66189 | 0.48495
|  |  |  | Messenger Clamps | 989 | 596 |  | 0.60263
|  |  |  | Messenger Wire Pull | 815 | 287 |  | 0.35215
|  |  |  | Messenger Wire Tension | 127 | 56 |  | 0.44094
|  |  |  | # Cables Pulled | 812 | 677 |  | 0.83374
|  |  |  | Messenger Straps | 708 | 13 |  | 0.018362
97670 | 97580 | E1 | CLASSON | 24" CMRS Install | 863 | 450 |  | 0.52144 | 0.53313
|  |  |  | Column Clamp | 831 | 611 |  | 0.73526
|  |  |  | Station Brackets | 708 | 467 |  | 0.6596
|  |  |  | Grounding | 788 | 254 |  | 0.32234
|  |  |  | Obstruction Brackets | 153 | 43 |  | 0.28105
|  |  |  | # Cables Pulled | 349 | 237 |  | 0.67908
97580 | 97230 | E1 | CLASSON | 24" CMRS Install | 168 | 58 |  | 0.34524 | 0.23411
|  |  |  | Column Clamp | 214 | 11 |  | 0.051402
|  |  |  | Station Brackets | 25 | 13 |  | 0.52
|  |  |  | Grounding | 886 | 134 |  | 0.15124
|  |  |  | Obstruction Brackets | 612 | 193 |  | 0.31536
|  |  |  | # Cables Pulled | 888 | 19 |  | 0.021396
97230 | 96920 | E1 | CLASSON | 24" CMRS Install | 738 | 189 |  | 0.2561 | 0.62264
|  |  |  | Column Clamp | 742 | 656 |  | 0.8841
|  |  |  | Station Brackets | 951 | 398 |  | 0.41851
|  |  |  | Grounding | 115 | 93 |  | 0.8087
|  |  |  | Obstruction Brackets | 951 | 393 |  | 0.41325
|  |  |  | # Cables Pulled | 625 | 597 |  | 0.9552
96920 | 96685 | E1 | CLI-CLA | Steel Mess Supports | 333 | 103 |  | 0.30931 | 0.49702
|  |  |  | Messenger Clamps | 536 | 120 |  | 0.22388
|  |  |  | Messenger Wire Pull | 145 | 88 |  | 0.6069
|  |  |  | Messenger Wire Tension | 478 | 118 |  | 0.24686
|  |  |  | # Cables Pulled | 927 | 888 |  | 0.95793
|  |  |  | Messenger Straps | 306 | 195 |  | 0.63725
96685 | 96460 | E1 | CLI-CLA | 24" CMRS Install | 254 | 32 |  | 0.12598 | 0.46159
|  |  |  | Column Clamp | 984 | 532 |  | 0.54065
|  |  |  | Station Brackets | 12 | 1 |  | 0.083333
|  |  |  | Grounding | 540 | 326 |  | 0.6037
|  |  |  | Obstruction Brackets | 945 | 753 |  | 0.79683
|  |  |  | # Cables Pulled | 189 | 117 |  | 0.61905
96460 | 96387 | E1 | CLI-CLA | 24" CMRS Install | 245 | 183 |  | 0.74694 | 0.37695
|  |  |  | Column Clamp | 293 | 9 |  | 0.030717
|  |  |  | Station Brackets | 421 | 40 |  | 0.095012
|  |  |  | Grounding | 513 | 300 |  | 0.5848
|  |  |  | Obstruction Brackets | 833 | 380 |  | 0.45618
|  |  |  | # Cables Pulled | 181 | 63 |  | 0.34807
96387 | 96051 | E1 | CLI-CLA | 24" CMRS Install | 624 | 437 |  | 0.70032 | 0.46776
|  |  |  | Column Clamp | 986 | 392 |  | 0.39757
|  |  |  | Station Brackets | 457 | 372 |  | 0.814
|  |  |  | Grounding | 876 | 589 |  | 0.67237
|  |  |  | Obstruction Brackets | 244 | 47 |  | 0.19262
|  |  |  | # Cables Pulled | 371 | 11 |  | 0.02965
96038 | 95998 | E1 | CLI-CLA | 24" CMRS Install | 72 | 3 |  | 0.041667 | 0.54449
|  |  |  | Column Clamp | 481 | 314 |  | 0.65281
|  |  |  | Station Brackets | 461 | 315 |  | 0.6833
|  |  |  | Grounding | 544 | 308 |  | 0.56618
|  |  |  | Obstruction Brackets | 318 | 311 |  | 0.97799
|  |  |  | # Cables Pulled | 1000 | 345 |  | 0.345
95998 | 95873 | E1 | CLI-CLA | 24" CMRS Install | 690 | 229 |  | 0.33188 | 0.35701
|  |  |  | Column Clamp | 32 | 14 |  | 0.4375
|  |  |  | Station Brackets | 160 | 97 |  | 0.60625
|  |  |  | Grounding | 932 | 211 |  | 0.22639
|  |  |  | Obstruction Brackets | 717 | 218 |  | 0.30404
|  |  |  | # Cables Pulled | 250 | 59 |  | 0.236
95873 | 95781 | E1 | CLINTON-WASHINGTON | 24" CMRS Install | 632 | 611 |  | 0.96677 | 0.47802
|  |  |  | Column Clamp | 387 | 86 |  | 0.22222
|  |  |  | Station Brackets | 822 | 123 |  | 0.14964
|  |  |  | Grounding | 367 | 31 |  | 0.084469
|  |  |  | Obstruction Brackets | 291 | 133 |  | 0.45704
|  |  |  | # Cables Pulled | 997 | 985 |  | 0.98796
95781 | 95695 | E1 | CLINTON-WASHINGTON | 24" CMRS Install | 139 | 56 |  | 0.40288 | 0.6555
|  |  |  | Column Clamp | 541 | 477 |  | 0.8817
|  |  |  | Station Brackets | 523 | 337 |  | 0.64436
|  |  |  | Grounding | 969 | 383 |  | 0.39525
|  |  |  | Obstruction Brackets | 393 | 353 |  | 0.89822
|  |  |  | # Cables Pulled | 463 | 329 |  | 0.71058
95695 | 95544 | E1 | CLINTON-WASHINGTON | 24" CMRS Install | 247 | 168 |  | 0.68016 | 0.59119
|  |  |  | Column Clamp | 499 | 250 |  | 0.501
|  |  |  | Station Brackets | 465 | 304 |  | 0.65376
|  |  |  | Grounding | 582 | 328 |  | 0.56357
|  |  |  | Obstruction Brackets | 581 | 256 |  | 0.44062
|  |  |  | # Cables Pulled | 137 | 97 |  | 0.70803
95544 | 95155 | E1 | CLINTON-WASHINGTON | 24" CMRS Install | 597 | 385 |  | 0.64489 | 0.41888
|  |  |  | Column Clamp | 212 | 64 |  | 0.30189
|  |  |  | Station Brackets | 506 | 430 |  | 0.8498
|  |  |  | Grounding | 765 | 161 |  | 0.21046
|  |  |  | Obstruction Brackets | 181 | 78 |  | 0.43094
|  |  |  | # Cables Pulled | 797 | 60 |  | 0.075282
95155 | 95004 | E1 | CLINTON-WASHINGTON | 24" CMRS Install | 431 | 305 |  | 0.70766 | 0.58735
|  |  |  | Column Clamp | 516 | 447 |  | 0.86628
|  |  |  | Station Brackets | 816 | 494 |  | 0.60539
|  |  |  | Grounding | 425 | 70 |  | 0.16471
|  |  |  | Obstruction Brackets | 780 | 633 |  | 0.81154
|  |  |  | # Cables Pulled | 890 | 328 |  | 0.36854
95004 | 94266 | E1 | FUL-CLI | 24" CMRS Install | 735 | 465 |  | 0.63265 | 0.50482
|  |  |  | Column Clamp | 326 | 28 |  | 0.08589
|  |  |  | Station Brackets | 603 | 392 |  | 0.65008
|  |  |  | Grounding | 271 | 141 |  | 0.5203
|  |  |  | Obstruction Brackets | 786 | 341 |  | 0.43384
|  |  |  | # Cables Pulled | 211 | 149 |  | 0.70616
94266 | 94207 | E1 | FUL-CLI | 24" CMRS Install | 885 | 224 |  | 0.25311 | 0.41156
|  |  |  | Column Clamp | 393 | 82 |  | 0.20865
|  |  |  | Station Brackets | 585 | 37 |  | 0.063248
|  |  |  | Grounding | 486 | 382 |  | 0.78601
|  |  |  | Obstruction Brackets | 592 | 401 |  | 0.67736
|  |  |  | # Cables Pulled | 447 | 215 |  | 0.48098
94207 | 93350 | E1 | FUL-CLI | 24" CMRS Install | 383 | 7 |  | 0.018277 | 0.40522
|  |  |  | Column Clamp | 971 | 313 |  | 0.32235
|  |  |  | Station Brackets | 629 | 109 |  | 0.17329
|  |  |  | Grounding | 972 | 925 |  | 0.95165
|  |  |  | Obstruction Brackets | 405 | 179 |  | 0.44198
|  |  |  | # Cables Pulled | 21 | 11 |  | 0.52381
73350 | 73690 | E1 | FULTON | 15" CMRS Install | 113 | 78 |  | 0.69027 | 0.46091
|  |  |  | Column Clamp | 98 | 91 |  | 0.92857
|  |  |  | Station Brackets | 116 | 25 |  | 0.21552
|  |  |  | Grounding | 995 | 532 |  | 0.53467
|  |  |  | Obstruction Brackets | 449 | 96 |  | 0.21381
|  |  |  | # Cables Pulled | 805 | 147 |  | 0.18261
73690 | 74030 | E1 | FULTON | 15" CMRS Install | 61 | 12 |  | 0.19672 | 0.38311
|  |  |  | Column Clamp | 42 | 39 |  | 0.92857
|  |  |  | Station Brackets | 654 | 102 |  | 0.15596
|  |  |  | Grounding | 314 | 50 |  | 0.15924
|  |  |  | Obstruction Brackets | 302 | 239 |  | 0.79139
|  |  |  | # Cables Pulled | 824 | 55 |  | 0.066748
|  | E1 | FULTON | 15" CMRS Install | 111 | 101 |  | 0.90991 | 0.45888
|  |  |  | Column Clamp | 920 | 74 |  | 0.080435
|  |  |  | Station Brackets | 513 | 66 |  | 0.12865
|  |  |  | Grounding | 770 | 519 |  | 0.67403
|  |  |  | Obstruction Brackets | 856 | 192 |  | 0.2243
|  |  |  | # Cables Pulled | 996 | 733 |  | 0.73594
74030 | 76085 | E1 | HOY-FUL | 24" CMRS Install | 560 | 247 |  | 0.44107 | 0.53754
|  |  |  | Column Clamp | 357 | 311 |  | 0.87115
|  |  |  | Station Brackets | 399 | 22 |  | 0.055138
|  |  |  | Grounding | 194 | 178 |  | 0.91753
|  |  |  | Obstruction Brackets | 273 | 139 |  | 0.50916
|  |  |  | # Cables Pulled | 654 | 282 |  | 0.43119
76085 | 76110 | E1 | HOY-FUL | 15" CMRS Install | 351 | 214 |  | 0.60969 | 0.60479
|  |  |  | Column Clamp | 614 | 498 |  | 0.81107
|  |  |  | Station Brackets | 515 | 467 |  | 0.9068
|  |  |  | Grounding | 945 | 301 |  | 0.31852
|  |  |  | Obstruction Brackets | 882 | 474 |  | 0.53741
|  |  |  | # Cables Pulled | 831 | 370 |  | 0.44525
76110 | 76165 | E1 | HOY-FUL | 15" CMRS Install | 835 | 658 |  | 0.78802 | 0.55437
|  |  |  | Column Clamp | 507 | 481 |  | 0.94872
|  |  |  | Station Brackets | 728 | 659 |  | 0.90522
|  |  |  | Grounding | 983 | 189 |  | 0.19227
|  |  |  | Obstruction Brackets | 663 | 319 |  | 0.48115
|  |  |  | # Cables Pulled | 645 | 7 |  | 0.010853
76165 | 77470 | E1 | HOYT SCHERMERHORN | 15" CMRS Install | 642 | 509 |  | 0.79283 | 0.42524
|  |  |  | Column Clamp | 359 | 51 |  | 0.14206
|  |  |  | Station Brackets | 82 | 72 |  | 0.87805
|  |  |  | Grounding | 732 | 237 |  | 0.32377
|  |  |  | Obstruction Brackets | 466 | 29 |  | 0.062232
|  |  |  | # Cables Pulled | 556 | 196 |  | 0.35252
77470 | 77595 | E1 | BER-HOY | 15" CMRS Install | 469 | 172 |  | 0.36674 | 0.5228
|  |  |  | Column Clamp | 404 | 164 |  | 0.40594
|  |  |  | Station Brackets | 841 | 14 |  | 0.016647
|  |  |  | Grounding | 401 | 313 |  | 0.78055
|  |  |  | Obstruction Brackets | 458 | 268 |  | 0.58515
|  |  |  | # Cables Pulled | 713 | 700 |  | 0.98177
77595 | 78230 | E1 | BER-HOY | 24" CMRS Install | 744 | 585 |  | 0.78629 | 0.46228
|  |  |  | Column Clamp | 428 | 387 |  | 0.90421
|  |  |  | Station Brackets | 485 | 83 |  | 0.17113
|  |  |  | Grounding | 187 | 5 |  | 0.026738
|  |  |  | Obstruction Brackets | 557 | 197 |  | 0.35368
|  |  |  | # Cables Pulled | 79 | 42 |  | 0.53165
78230 | 78515 | E1 | BER-HOY | 24" CMRS Install | 672 | 420 |  | 0.625 | 0.55361
|  |  |  | Column Clamp | 463 | 89 |  | 0.19222
|  |  |  | Station Brackets | 945 | 195 |  | 0.20635
|  |  |  | Grounding | 885 | 573 |  | 0.64746
|  |  |  | Obstruction Brackets | 515 | 396 |  | 0.76893
|  |  |  | # Cables Pulled | 913 | 805 |  | 0.88171
|  | E2 | BERGEN | Cable Tray Brackets | 693 | 61 |  | 0.088023 | 0.57149
|  |  |  | Installing Tray | 270 | 216 |  | 0.8
|  |  |  | Core Drilling | 116 | 75 |  | 0.64655
|  |  |  | Cable Pull | 362 | 272 |  | 0.75138
78515 | 78315 | E2 | BER-HOY | Steel Mess Supports | 798 | 626 |  | 0.78446 | 0.71682
|  |  |  | Messenger Clamps | 65 | 44 |  | 0.67692
|  |  |  | Messenger Wire Pull | 642 | 189 |  | 0.29439
|  |  |  | Messenger Wire Tension | 857 | 717 |  | 0.83664
|  |  |  | # Cables Pulled | 311 | 304 |  | 0.97749
|  |  |  | Messenger Straps | 829 | 606 |  | 0.731
78315 | 77655 | E2 | BER-HOY | 24" CMRS Install | 684 | 510 |  | 0.74561 | 0.37426
|  |  |  | Column Clamp | 460 | 28 |  | 0.06087
|  |  |  | Station Brackets | 988 | 3 |  | 0.0030364
|  |  |  | Grounding | 505 | 82 |  | 0.16238
|  |  |  | Obstruction Brackets | 516 | 402 |  | 0.77907
|  |  |  | # Cables Pulled | 184 | 91 |  | 0.49457
77655 | 77585 | E2 | BER-HOY | 24" CMRS Install | 528 | 246 |  | 0.46591 | 0.63105
|  |  |  | Column Clamp | 909 | 574 |  | 0.63146
|  |  |  | Station Brackets | 525 | 337 |  | 0.6419
|  |  |  | Grounding | 425 | 405 |  | 0.95294
|  |  |  | Obstruction Brackets | 212 | 127 |  | 0.59906
|  |  |  | # Cables Pulled | 804 | 398 |  | 0.49502
77585 | 76845 | E2 | BER-HOY | 24" CMRS Install | 328 | 5 |  | 0.015244 | 0.48792
|  |  |  | Column Clamp | 965 | 706 |  | 0.73161
|  |  |  | Station Brackets | 734 | 191 |  | 0.26022
|  |  |  | Grounding | 789 | 552 |  | 0.69962
|  |  |  | Obstruction Brackets | 923 | 503 |  | 0.54496
|  |  |  | # Cables Pulled | 506 | 342 |  | 0.67589
76845 | 76150 | E2 | HOYT SCHERMERHORN | 24" CMRS Install | 189 | 29 |  | 0.15344 | 0.45971
|  |  |  | Column Clamp | 358 | 49 |  | 0.13687
|  |  |  | Station Brackets | 18 | 6 |  | 0.33333
|  |  |  | Grounding | 970 | 706 |  | 0.72784
|  |  |  | Obstruction Brackets | 791 | 739 |  | 0.93426
|  |  |  | # Cables Pulled | 982 | 464 |  | 0.47251
76150 | 76090 | E2 | HOY-FUL | 24" CMRS Install | 908 | 124 |  | 0.13656 | 0.47522
|  |  |  | Column Clamp | 587 | 346 |  | 0.58944
|  |  |  | Station Brackets | 774 | 123 |  | 0.15891
|  |  |  | Grounding | 970 | 189 |  | 0.19485
|  |  |  | Obstruction Brackets | 571 | 549 |  | 0.96147
|  |  |  | # Cables Pulled | 953 | 772 |  | 0.81007
76090 | 75950 | E2 | HOY-FUL | 24" CMRS Install | 428 | 162 |  | 0.3785 | 0.39243
|  |  |  | Column Clamp | 217 | 134 |  | 0.61751
|  |  |  | Station Brackets | 213 | 31 |  | 0.14554
|  |  |  | Grounding | 754 | 632 |  | 0.8382
|  |  |  | Obstruction Brackets | 749 | 218 |  | 0.29105
|  |  |  | # Cables Pulled | 191 | 16 |  | 0.08377
75950 | 75900 | E2 | HOY-FUL | Steel Mess Supports | 986 | 812 |  | 0.82353 | 0.51228
|  |  |  | Messenger Clamps | 570 | 548 |  | 0.9614
|  |  |  | Messenger Wire Pull | 125 | 43 |  | 0.344
|  |  |  | Messenger Wire Tension | 398 | 179 |  | 0.44975
|  |  |  | # Cables Pulled | 670 | 19 |  | 0.028358
|  |  |  | Messenger Straps | 45 | 21 |  | 0.46667
75900 | 74590 | E2 | HOY-FUL | 24" CMRS Install | 68 | 35 |  | 0.51471 | 0.54522
|  |  |  | Column Clamp | 520 | 370 |  | 0.71154
|  |  |  | Station Brackets | 460 | 344 |  | 0.74783
|  |  |  | Grounding | 894 | 72 |  | 0.080537
|  |  |  | Obstruction Brackets | 981 | 932 |  | 0.95005
|  |  |  | # Cables Pulled | 30 | 8 |  | 0.26667
74590 | 74450 | E2 | HOY-FUL | Steel Mess Supports | 460 | 227 |  | 0.49348 | 0.5415
|  |  |  | Messenger Clamps | 218 | 93 |  | 0.42661
|  |  |  | Messenger Wire Pull | 923 | 160 |  | 0.17335
|  |  |  | Messenger Wire Tension | 709 | 596 |  | 0.84062
|  |  |  | # Cables Pulled | 840 | 777 |  | 0.925
|  |  |  | Messenger Straps | 795 | 310 |  | 0.38994
74450 | 74070 | E2 | HOY-FUL | 24" CMRS Install | 734 | 434 |  | 0.59128 | 0.39951
|  |  |  | Column Clamp | 227 | 2 |  | 0.0088106
|  |  |  | Station Brackets | 967 | 751 |  | 0.77663
|  |  |  | Grounding | 895 | 78 |  | 0.087151
|  |  |  | Obstruction Brackets | 497 | 317 |  | 0.63783
|  |  |  | # Cables Pulled | 237 | 70 |  | 0.29536
74070 | 74030 | E2 | HOY-FUL | 24" CMRS Install | 523 | 206 |  | 0.39388 | 0.48643
|  |  |  | Column Clamp | 758 | 237 |  | 0.31266
|  |  |  | Station Brackets | 844 | 393 |  | 0.46564
|  |  |  | Grounding | 504 | 58 |  | 0.11508
|  |  |  | Obstruction Brackets | 726 | 585 |  | 0.80579
|  |  |  | # Cables Pulled | 596 | 492 |  | 0.8255
74030 | 73690 | E2 | FULTON | 15" CMRS Install | 718 | 198 |  | 0.27577 | 0.57912
|  |  |  | Column Clamp | 272 | 121 |  | 0.44485
|  |  |  | Station Brackets | 648 | 452 |  | 0.69753
|  |  |  | Grounding | 571 | 341 |  | 0.5972
|  |  |  | Obstruction Brackets | 745 | 373 |  | 0.50067
|  |  |  | # Cables Pulled | 848 | 813 |  | 0.95873
73690 | 73250 | E2 | FULTON | 15" CMRS Install | 180 | 144 |  | 0.8 | 0.51018 | Cable Management Takeoffs Cell F110* - 147LF instead of 440LF | Cable Management Takeoffs Cell F110* - 147LF instead of 440LF
|  |  |  | Column Clamp | 656 | 150 |  | 0.22866
|  |  |  | Station Brackets | 220 | 172 |  | 0.78182
|  |  |  | Grounding | 729 | 155 |  | 0.21262
|  |  |  | Obstruction Brackets | 521 | 71 |  | 0.13628
|  |  |  | # Cables Pulled | 407 | 367 |  | 0.90172
|  | E2 | FULTON | 15" CMRS Install | 290 | 47 |  | 0.16207 | 0.65278
|  |  |  | Column Clamp | 838 | 793 |  | 0.9463
|  |  |  | Station Brackets | 51 | 50 |  | 0.98039
|  |  |  | Grounding | 635 | 260 |  | 0.40945
|  |  |  | Obstruction Brackets | 862 | 572 |  | 0.66357
|  |  |  | # Cables Pulled | 975 | 736 |  | 0.75487
73250 | 72315 | E2 | FUL-CLI | 24" CMRS Install | 356 | 222 |  | 0.6236 | 0.59578
|  |  |  | Column Clamp | 837 | 641 |  | 0.76583
|  |  |  | Station Brackets | 981 | 224 |  | 0.22834
|  |  |  | Grounding | 184 | 53 |  | 0.28804
|  |  |  | Obstruction Brackets | 252 | 195 |  | 0.77381
|  |  |  | # Cables Pulled | 667 | 597 |  | 0.89505
94400 | 94989 | E2 | FUL-CLI | 24" CMRS Install | 420 | 354 |  | 0.84286 | 0.58018
|  |  |  | Column Clamp | 202 | 55 |  | 0.27228
|  |  |  | Station Brackets | 686 | 372 |  | 0.54227
|  |  |  | Grounding | 712 | 685 |  | 0.96208
|  |  |  | Obstruction Brackets | 816 | 71 |  | 0.08701
|  |  |  | # Cables Pulled | 967 | 749 |  | 0.77456
94989 | 95114 | E2 | FUL-CLI | 24" CMRS Install | 605 | 300 |  | 0.49587 | 0.59604
|  |  |  | Column Clamp | 482 | 424 |  | 0.87967
|  |  |  | Station Brackets | 196 | 61 |  | 0.31122
|  |  |  | Grounding | 749 | 368 |  | 0.49132
|  |  |  | Obstruction Brackets | 314 | 166 |  | 0.52866
|  |  |  | # Cables Pulled | 820 | 713 |  | 0.86951
94989 | 95114 | E2 | CLINTON-WASHINGTON | 24" CMRS Install | 175 | 14 |  | 0.08 | 0.59778
|  |  |  | Column Clamp | 31 | 29 |  | 0.93548
|  |  |  | Station Brackets | 93 | 72 |  | 0.77419
|  |  |  | Grounding | 276 | 244 |  | 0.88406
|  |  |  | Obstruction Brackets | 640 | 270 |  | 0.42188
|  |  |  | # Cables Pulled | 112 | 55 |  | 0.49107
95503 | 95701 | E2 | CLINTON-WASHINGTON | 24" CMRS Install | 398 | 177 |  | 0.44472 | 0.51427
|  |  |  | Column Clamp | 916 | 31 |  | 0.033843
|  |  |  | Station Brackets | 935 | 858 |  | 0.91765
|  |  |  | Grounding | 839 | 564 |  | 0.67223
|  |  |  | Obstruction Brackets | 609 | 44 |  | 0.07225
|  |  |  | # Cables Pulled | 218 | 206 |  | 0.94495
95767 | 95852 | E2 | CLINTON-WASHINGTON | 24" CMRS Install | 484 | 89 |  | 0.18388 | 0.63909
|  |  |  | Column Clamp | 920 | 877 |  | 0.95326
|  |  |  | Station Brackets | 505 | 473 |  | 0.93663
|  |  |  | Grounding | 11 | 5 |  | 0.45455
|  |  |  | Obstruction Brackets | 974 | 532 |  | 0.5462
|  |  |  | # Cables Pulled | 375 | 285 |  | 0.76
95852 | 96366 | E2 | CLINTON-WASHINGTON | 24" CMRS Install | 208 | 176 |  | 0.84615 | 0.56339
|  |  |  | Column Clamp | 954 | 176 |  | 0.18449
|  |  |  | Station Brackets | 273 | 267 |  | 0.97802
|  |  |  | Grounding | 235 | 138 |  | 0.58723
|  |  |  | Obstruction Brackets | 714 | 129 |  | 0.18067
|  |  |  | # Cables Pulled | 265 | 160 |  | 0.60377
96366 | 96432 | E2 | CLINTON-WASHINGTON | 24" CMRS Install | 568 | 80 |  | 0.14085 | 0.29978
|  |  |  | Column Clamp | 764 | 455 |  | 0.59555
|  |  |  | Station Brackets | 145 | 43 |  | 0.29655
|  |  |  | Grounding | 18 | 0 |  | 0
|  |  |  | Obstruction Brackets | 593 | 417 |  | 0.7032
|  |  |  | # Cables Pulled | 944 | 59 |  | 0.0625
96432 | 96649 | E2 | CLINTON-WASHINGTON | 24" CMRS Install | 146 | 32 |  | 0.21918 | 0.41952
|  |  |  | Column Clamp | 140 | 100 |  | 0.71429
|  |  |  | Station Brackets | 122 | 8 |  | 0.065574
|  |  |  | Grounding | 86 | 29 |  | 0.33721
|  |  |  | Obstruction Brackets | 147 | 54 |  | 0.36735
|  |  |  | # Cables Pulled | 724 | 589 |  | 0.81354
95767 | 95852 | E2 | CLINTON-WASHINGTON | 24" CMRS Install | 256 | 29 |  | 0.11328 | 0.47184
|  |  |  | Column Clamp | 603 | 441 |  | 0.73134
|  |  |  | Station Brackets | 943 | 564 |  | 0.59809
|  |  |  | Grounding | 541 | 214 |  | 0.39556
|  |  |  | Obstruction Brackets | 893 | 21 |  | 0.023516
|  |  |  | # Cables Pulled | 585 | 567 |  | 0.96923
95852 | 96366 | E2 | CLI-CLA | 24" CMRS Install | 166 | 147 |  | 0.88554 | 0.51135
|  |  |  | Column Clamp | 517 | 56 |  | 0.10832
|  |  |  | Station Brackets | 893 | 640 |  | 0.71669
|  |  |  | Grounding | 191 | 96 |  | 0.50262
|  |  |  | Obstruction Brackets | 854 | 703 |  | 0.82319
|  |  |  | # Cables Pulled | 63 | 2 |  | 0.031746
96366 | 96432 | E2 | CLI-CLA | 24" CMRS Install | 505 | 86 |  | 0.1703 | 0.42114
|  |  |  | Column Clamp | 817 | 682 |  | 0.83476
|  |  |  | Station Brackets | 723 | 102 |  | 0.14108
|  |  |  | Grounding | 270 | 124 |  | 0.45926
|  |  |  | Obstruction Brackets | 117 | 71 |  | 0.60684
|  |  |  | # Cables Pulled | 391 | 123 |  | 0.31458
96432 | 96649 | E2 | CLI-CLA | 24" CMRS Install | 879 | 27 |  | 0.030717 | 0.39359
|  |  |  | Column Clamp | 115 | 80 |  | 0.69565
|  |  |  | Station Brackets | 119 | 2 |  | 0.016807
|  |  |  | Grounding | 995 | 928 |  | 0.93266
|  |  |  | Obstruction Brackets | 50 | 26 |  | 0.52
|  |  |  | # Cables Pulled | 356 | 59 |  | 0.16573
96649 | 96770 | E2 | CLI-CLA | 24" CMRS Install | 626 | 407 |  | 0.65016 | 0.53145
|  |  |  | Column Clamp | 157 | 16 |  | 0.10191
|  |  |  | Station Brackets | 230 | 195 |  | 0.84783
|  |  |  | Grounding | 246 | 182 |  | 0.73984
|  |  |  | Obstruction Brackets | 426 | 176 |  | 0.41315
|  |  |  | # Cables Pulled | 335 | 146 |  | 0.43582
96770 | 96990 | E2 | CLI-CLA | Steel Mess Supports | 290 | 215 |  | 0.74138 | 0.68452
|  |  |  | Messenger Clamps | 145 | 103 |  | 0.71034
|  |  |  | Messenger Wire Pull | 872 | 846 |  | 0.97018
|  |  |  | Messenger Wire Tension | 680 | 385 |  | 0.56618
|  |  |  | # Cables Pulled | 22 | 10 |  | 0.45455
|  |  |  | Messenger Straps | 912 | 606 |  | 0.66447
96990 | 97230 | E2 | CLASSON | 24" CMRS Install | 719 | 421 |  | 0.58554 | 0.34368
|  |  |  | Column Clamp | 385 | 164 |  | 0.42597
|  |  |  | Station Brackets | 890 | 496 |  | 0.5573
|  |  |  | Grounding | 72 | 4 |  | 0.055556
|  |  |  | Obstruction Brackets | 375 | 52 |  | 0.13867
|  |  |  | # Cables Pulled | 204 | 61 |  | 0.29902
97230 | 97538 | E2 | CLASSON | 24" CMRS Install | 665 | 410 |  | 0.61654 | 0.56866
|  |  |  | Column Clamp | 120 | 29 |  | 0.24167
|  |  |  | Station Brackets | 278 | 212 |  | 0.76259
|  |  |  | Grounding | 69 | 15 |  | 0.21739
|  |  |  | Obstruction Brackets | 427 | 245 |  | 0.57377
|  |  |  | # Cables Pulled | 808 | 808 |  | 1
97538 | 97670 | E2 | CLASSON | 24" CMRS Install | 759 | 151 |  | 0.19895 | 0.36664
|  |  |  | Column Clamp | 964 | 163 |  | 0.16909
|  |  |  | Station Brackets | 642 | 369 |  | 0.57477
|  |  |  | Grounding | 328 | 215 |  | 0.65549
|  |  |  | Obstruction Brackets | 841 | 439 |  | 0.522
|  |  |  | # Cables Pulled | 88 | 7 |  | 0.079545
97670 | 98015 | E2 | CLA-BED | Steel Mess Supports | 76 | 48 |  | 0.63158 | 0.60676
|  |  |  | Messenger Clamps | 108 | 108 |  | 1
|  |  |  | Messenger Wire Pull | 179 | 50 |  | 0.27933
|  |  |  | Messenger Wire Tension | 280 | 197 |  | 0.70357
|  |  |  | # Cables Pulled | 718 | 457 |  | 0.63649
|  |  |  | Messenger Straps | 652 | 254 |  | 0.38957
98015 | 98125 | E2 | CLA-BED | 24" CMRS Install | 975 | 16 |  | 0.01641 | 0.5002
|  |  |  | Column Clamp | 824 | 711 |  | 0.86286
|  |  |  | Station Brackets | 115 | 103 |  | 0.89565
|  |  |  | Grounding | 532 | 413 |  | 0.77632
|  |  |  | Obstruction Brackets | 110 | 34 |  | 0.30909
|  |  |  | # Cables Pulled | 944 | 133 |  | 0.14089
98125 | 98185 | E2 | CLA-BED | 24" CMRS Install | 584 | 261 |  | 0.44692 | 0.57658
|  |  |  | Column Clamp | 683 | 402 |  | 0.58858
|  |  |  | Station Brackets | 869 | 685 |  | 0.78826
|  |  |  | Grounding | 744 | 535 |  | 0.71909
|  |  |  | Obstruction Brackets | 241 | 145 |  | 0.60166
|  |  |  | # Cables Pulled | 727 | 229 |  | 0.31499
98185 | 98440 | E2 | CLA-BED | 24" CMRS Install | 96 | 62 |  | 0.64583 | 0.51122
|  |  |  | Column Clamp | 661 | 647 |  | 0.97882
|  |  |  | Station Brackets | 644 | 375 |  | 0.5823
|  |  |  | Grounding | 888 | 215 |  | 0.24212
|  |  |  | Obstruction Brackets | 894 | 260 |  | 0.29083
|  |  |  | # Cables Pulled | 507 | 166 |  | 0.32742
|  | E2 | CLA-BED | Crossover (Arch Bar Installation) | 469 | 375 |  | 0.79957
98440 | 98586 | E2 | CLA-BED | 24" CMRS Install | 503 | 411 |  | 0.8171 | 0.67029
|  |  |  | Column Clamp | 928 | 65 |  | 0.070043
|  |  |  | Station Brackets | 537 | 313 |  | 0.58287
|  |  |  | Grounding | 895 | 740 |  | 0.82682
|  |  |  | Obstruction Brackets | 318 | 268 |  | 0.84277
|  |  |  | # Cables Pulled | 280 | 247 |  | 0.88214
98586 | 98836 | E2 | CLA-BED | Steel Mess Supports | 249 | 196 |  | 0.78715 | 0.3723
|  |  |  | Messenger Clamps | 164 | 15 |  | 0.091463
|  |  |  | Messenger Wire Pull | 568 | 558 |  | 0.98239
|  |  |  | Messenger Wire Tension | 185 | 57 |  | 0.30811
|  |  |  | # Cables Pulled | 124 | 6 |  | 0.048387
|  |  |  | Messenger Straps | 184 | 3 |  | 0.016304
98836 | 99505 | E2 | BEDFORD NOSTRAND | Cable Tray Brackets | 816 | 270 |  | 0.33088 | 0.62366
|  |  |  | Installing Tray | 847 | 800 |  | 0.94451
|  |  |  | Core Drilling | 398 | 168 |  | 0.42211
|  |  |  | Cable Pull | 769 | 613 |  | 0.79714
99505 | 99950 | E2 | BED-MYR | Steel Mess Supports | 190 | 154 |  | 0.81053 | 0.42278
|  |  |  | Messenger Clamps | 893 | 372 |  | 0.41657
|  |  |  | Messenger Wire Pull | 610 | 495 |  | 0.81148
|  |  |  | Messenger Wire Tension | 884 | 32 |  | 0.036199
|  |  |  | # Cables Pulled | 523 | 224 |  | 0.4283
|  |  |  | Messenger Straps | 863 | 29 |  | 0.033604
|  | E2 | CLA-BED | Crossover (Arch Bar Installation) | 395 | 144 |  | 0.36456
99950 | 100290 | E2 | BED-MYR | 24" CMRS Install | 156 | 128 |  | 0.82051 | 0.53491
|  |  |  | Column Clamp | 16 | 9 |  | 0.5625
|  |  |  | Station Brackets | 609 | 490 |  | 0.8046
|  |  |  | Grounding | 418 | 212 |  | 0.50718
|  |  |  | Obstruction Brackets | 565 | 186 |  | 0.3292
|  |  |  | # Cables Pulled | 372 | 69 |  | 0.18548
100290 | 100740 | E2 | BED-MYR | 24" CMRS Install | 796 | 681 |  | 0.85553 | 0.53898
|  |  |  | Column Clamp | 539 | 36 |  | 0.06679
|  |  |  | Station Brackets | 66 | 16 |  | 0.24242
|  |  |  | Grounding | 95 | 84 |  | 0.88421
|  |  |  | Obstruction Brackets | 793 | 516 |  | 0.65069
|  |  |  | # Cables Pulled | 146 | 78 |  | 0.53425
100740 | 100792 | E2 | BED-MYR | 24" CMRS Install | 559 | 430 |  | 0.76923 | 0.52489
|  |  |  | Column Clamp | 420 | 88 |  | 0.20952
|  |  |  | Station Brackets | 944 | 718 |  | 0.76059
|  |  |  | Grounding | 433 | 161 |  | 0.37182
|  |  |  | Obstruction Brackets | 180 | 91 |  | 0.50556
|  |  |  | # Cables Pulled | 368 | 196 |  | 0.53261
100792 | 101595 | E2 | BED-MYR | 24" CMRS Install | 693 | 35 |  | 0.050505 | 0.48665
|  |  |  | Column Clamp | 314 | 151 |  | 0.48089
|  |  |  | Station Brackets | 949 | 854 |  | 0.89989
|  |  |  | Grounding | 886 | 155 |  | 0.17494
|  |  |  | Obstruction Brackets | 107 | 63 |  | 0.58879
|  |  |  | # Cables Pulled | 716 | 519 |  | 0.72486
101595 | 101688 | E2 | BED-MYR | 24" CMRS Install | 770 | 445 |  | 0.57792 | 0.38133
|  |  |  | Column Clamp | 933 | 62 |  | 0.066452
|  |  |  | Station Brackets | 138 | 21 |  | 0.15217
|  |  |  | Grounding | 311 | 5 |  | 0.016077
|  |  |  | Obstruction Brackets | 330 | 319 |  | 0.96667
|  |  |  | # Cables Pulled | 230 | 117 |  | 0.5087
101688 | 102400 | E2 | MYRTLE AVE | 15" CMRS Install | 776 | 411 |  | 0.52964 | 0.34608
|  |  |  | Column Clamp | 976 | 676 |  | 0.69262
|  |  |  | Station Brackets | 984 | 47 |  | 0.047764
|  |  |  | Grounding | 228 | 95 |  | 0.41667
|  |  |  | Obstruction Brackets | 975 | 274 |  | 0.28103
|  |  |  | # Cables Pulled | 239 | 26 |  | 0.10879
102400 | 102550 | E2 | MYR-FLU | Steel Mess Supports | 543 | 529 |  | 0.97422 | 0.49462
|  |  |  | Messenger Clamps | 860 | 257 |  | 0.29884
|  |  |  | Messenger Wire Pull | 277 | 73 |  | 0.26354
|  |  |  | Messenger Wire Tension | 517 | 35 |  | 0.067698
|  |  |  | # Cables Pulled | 80 | 35 |  | 0.4375
|  |  |  | Messenger Straps | 513 | 475 |  | 0.92593
102550 | 103165 | E2 | MYR-FLU | 15" CMRS Install | 588 | 407 |  | 0.69218 | 0.68406
|  |  |  | Column Clamp | 25 | 14 |  | 0.56
|  |  |  | Station Brackets | 945 | 547 |  | 0.57884
|  |  |  | Grounding | 412 | 341 |  | 0.82767
|  |  |  | Obstruction Brackets | 668 | 584 |  | 0.87425
|  |  |  | # Cables Pulled | 14 | 8 |  | 0.57143
103165 | 103230 | E2 | MYR-FLU | 15" CMRS Install | 486 | 238 |  | 0.48971 | 0.56726
|  |  |  | Column Clamp | 304 | 285 |  | 0.9375
|  |  |  | Station Brackets | 617 | 279 |  | 0.45219
|  |  |  | Grounding | 921 | 240 |  | 0.26059
|  |  |  | Obstruction Brackets | 974 | 412 |  | 0.423
|  |  |  | # Cables Pulled | 897 | 754 |  | 0.84058
103230 | 103809 | E2 | MYR-FLU | 15" CMRS Install | 852 | 657 |  | 0.77113 | 0.50294
|  |  |  | Column Clamp | 674 | 632 |  | 0.93769
|  |  |  | Station Brackets | 755 | 155 |  | 0.2053
|  |  |  | Grounding | 352 | 24 |  | 0.068182
|  |  |  | Obstruction Brackets | 446 | 98 |  | 0.21973
|  |  |  | # Cables Pulled | 743 | 606 |  | 0.81561
103809 | 103902 | E2 | MYR-FLU | 15" CMRS Install | 290 | 233 |  | 0.80345 | 0.48268
|  |  |  | Column Clamp | 78 | 55 |  | 0.70513
|  |  |  | Station Brackets | 50 | 49 |  | 0.98
|  |  |  | Grounding | 244 | 9 |  | 0.036885
|  |  |  | Obstruction Brackets | 106 | 9 |  | 0.084906
|  |  |  | # Cables Pulled | 238 | 68 |  | 0.28571
103902 | 104595 | E2 | FLUSHING | 15" CMRS Install | 661 | 433 |  | 0.65507 | 0.49577
|  |  |  | Column Clamp | 484 | 393 |  | 0.81198
|  |  |  | Station Brackets | 620 | 298 |  | 0.48065
|  |  |  | Grounding | 82 | 16 |  | 0.19512
|  |  |  | Obstruction Brackets | 361 | 262 |  | 0.72576
|  |  |  | # Cables Pulled | 198 | 21 |  | 0.10606
104595 | 104750 | E2 | FLU-BRO | Steel Mess Supports | 518 | 346 |  | 0.66795 | 0.55195
|  |  |  | Messenger Clamps | 426 | 340 |  | 0.79812
|  |  |  | Messenger Wire Pull | 970 | 661 |  | 0.68144
|  |  |  | Messenger Wire Tension | 405 | 24 |  | 0.059259
|  |  |  | # Cables Pulled | 763 | 399 |  | 0.52294
|  |  |  | Messenger Straps | 500 | 291 |  | 0.582
104750 | 105270 | E2 | FLU-BRO | 15" CMRS Install | 90 | 34 |  | 0.37778 | 0.47957
|  |  |  | Column Clamp | 541 | 510 |  | 0.9427
|  |  |  | Station Brackets | 269 | 65 |  | 0.24164
|  |  |  | Grounding | 311 | 134 |  | 0.43087
|  |  |  | Obstruction Brackets | 267 | 196 |  | 0.73408
|  |  |  | # Cables Pulled | 951 | 143 |  | 0.15037
105270 | 105930 | E2 | FLU-BRO | 15" CMRS Install | 721 | 42 |  | 0.058252 | 0.24023
|  |  |  | Column Clamp | 810 | 51 |  | 0.062963
|  |  |  | Station Brackets | 468 | 110 |  | 0.23504
|  |  |  | Grounding | 986 | 151 |  | 0.15314
|  |  |  | Obstruction Brackets | 914 | 314 |  | 0.34354
|  |  |  | # Cables Pulled | 328 | 193 |  | 0.58841
105930 | 106003 | E2 | FLU-BRO | 15" CMRS Install | 437 | 84 |  | 0.19222 | 0.52352
|  |  |  | Column Clamp | 651 | 512 |  | 0.78648
|  |  |  | Station Brackets | 703 | 695 |  | 0.98862
|  |  |  | Grounding | 235 | 127 |  | 0.54043
|  |  |  | Obstruction Brackets | 79 | 34 |  | 0.43038
|  |  |  | # Cables Pulled | 202 | 41 |  | 0.20297
106003 | 106648 | E2 | BROADWAY | 15" CMRS Install | 187 | 66 |  | 0.35294 | 0.62077
|  |  |  | Column Clamp | 14 | 14 |  | 1
|  |  |  | Station Brackets | 884 | 651 |  | 0.73643
|  |  |  | Grounding | 847 | 83 |  | 0.097993
|  |  |  | Obstruction Brackets | 621 | 356 |  | 0.57327
|  |  |  | # Cables Pulled | 250 | 241 |  | 0.964
|  | E2 | BROADWAY | 15" CMRS Install | 645 | 526 |  | 0.8155 | 0.57433
|  |  |  | Column Clamp | 435 | 311 |  | 0.71494
|  |  |  | Station Brackets | 783 | 636 |  | 0.81226
|  |  |  | Grounding | 30 | 5 |  | 0.16667
|  |  |  | Obstruction Brackets | 863 | 698 |  | 0.80881
|  |  |  | # Cables Pulled | 360 | 46 |  | 0.12778
|  | E2 | BROADWAY | 15" CMRS Install | 690 | 581 |  | 0.84203 | 0.47967
|  |  |  | Column Clamp | 34 | 6 |  | 0.17647
|  |  |  | Station Brackets | 244 | 144 |  | 0.59016
|  |  |  | Grounding | 263 | 152 |  | 0.57795
|  |  |  | Obstruction Brackets | 661 | 401 |  | 0.60666
|  |  |  | # Cables Pulled | 59 | 5 |  | 0.084746
106650 | 106920 | E2 | BRO-MET | Steel Mess Supports | 983 | 819 |  | 0.83316 | 0.72111
|  |  |  | Messenger Clamps | 135 | 66 |  | 0.48889
|  |  |  | Messenger Wire Pull | 450 | 362 |  | 0.80444
|  |  |  | Messenger Wire Tension | 956 | 809 |  | 0.84623
|  |  |  | # Cables Pulled | 682 | 288 |  | 0.42229
|  |  |  | Messenger Straps | 234 | 218 |  | 0.93162
106918 | 107620 | E2 | BRO-MET | 15" CMRS Install | 906 | 565 |  | 0.62362 | 0.51886
|  |  |  | Column Clamp | 624 | 540 |  | 0.86538
|  |  |  | Station Brackets | 373 | 111 |  | 0.29759
|  |  |  | Grounding | 582 | 424 |  | 0.72852
|  |  |  | Obstruction Brackets | 23 | 12 |  | 0.52174
|  |  |  | # Cables Pulled | 760 | 58 |  | 0.076316
107620 | 107683 | E2 | BRO-MET | 15" CMRS Install | 81 | 62 |  | 0.76543 | 0.47461
|  |  |  | Column Clamp | 714 | 493 |  | 0.69048
|  |  |  | Station Brackets | 810 | 142 |  | 0.17531
|  |  |  | Grounding | 267 | 73 |  | 0.27341
|  |  |  | Obstruction Brackets | 954 | 697 |  | 0.73061
|  |  |  | # Cables Pulled | 193 | 41 |  | 0.21244
107683 | 108360 | E2 | BRO-MET | 15" CMRS Install | 750 | 656 |  | 0.87467 | 0.54655
|  |  |  | Column Clamp | 887 | 770 |  | 0.86809
|  |  |  | Station Brackets | 159 | 150 |  | 0.9434
|  |  |  | Grounding | 792 | 321 |  | 0.4053
|  |  |  | Obstruction Brackets | 610 | 71 |  | 0.11639
|  |  |  | # Cables Pulled | 56 | 4 |  | 0.071429
108360 | 109235 | E2 | METROPOLITAN | 15" CMRS Install | 852 | 219 |  | 0.25704 | 0.53864
|  |  |  | Column Clamp | 99 | 61 |  | 0.61616
|  |  |  | Station Brackets | 828 | 119 |  | 0.14372
|  |  |  | Grounding | 170 | 116 |  | 0.68235
|  |  |  | Obstruction Brackets | 931 | 580 |  | 0.62299
|  |  |  | # Cables Pulled | 984 | 895 |  | 0.90955
109235 | 110795 | E2 | MET-NAS | 24" CMRS Install | 71 | 6 |  | 0.084507 | 0.44139
|  |  |  | Column Clamp | 159 | 110 |  | 0.69182
|  |  |  | Station Brackets | 636 | 232 |  | 0.36478
|  |  |  | Grounding | 760 | 751 |  | 0.98816
|  |  |  | Obstruction Brackets | 778 | 175 |  | 0.22494
|  |  |  | # Cables Pulled | 17 | 5 |  | 0.29412
110795 | 110865 | E2 | MET-NAS | 24" CMRS Install | 505 | 479 |  | 0.94851 | 0.57205
|  |  |  | Column Clamp | 125 | 97 |  | 0.776
|  |  |  | Station Brackets | 156 | 33 |  | 0.21154
|  |  |  | Grounding | 703 | 39 |  | 0.055477
|  |  |  | Obstruction Brackets | 160 | 74 |  | 0.4625
|  |  |  | # Cables Pulled | 644 | 630 |  | 0.97826
110865 | 113020 | E2 | MET-NAS | 24" CMRS Install | 922 | 49 |  | 0.053145 | 0.3354
|  |  |  | Column Clamp | 527 | 91 |  | 0.17268
|  |  |  | Station Brackets | 408 | 290 |  | 0.71078
|  |  |  | Grounding | 13 | 0 |  | 0
|  |  |  | Obstruction Brackets | 624 | 285 |  | 0.45673
|  |  |  | # Cables Pulled | 21 | 13 |  | 0.61905
113020 | 113155 | E2 | MET-NAS | 24" CMRS Install | 520 | 73 |  | 0.14038 | 0.58774
|  |  |  | Column Clamp | 443 | 226 |  | 0.51016
|  |  |  | Station Brackets | 291 | 227 |  | 0.78007
|  |  |  | Grounding | 284 | 271 |  | 0.95423
|  |  |  | Obstruction Brackets | 450 | 114 |  | 0.25333
|  |  |  | # Cables Pulled | 358 | 318 |  | 0.88827
113155 | 113815 | E2 | NASSAU | 24" CMRS Install | 891 | 5 |  | 0.0056117 | 0.42909
|  |  |  | Column Clamp | 694 | 508 |  | 0.73199
|  |  |  | Station Brackets | 220 | 156 |  | 0.70909
|  |  |  | Grounding | 265 | 105 |  | 0.39623
|  |  |  | Obstruction Brackets | 570 | 23 |  | 0.040351
|  |  |  | # Cables Pulled | 677 | 468 |  | 0.69129
113815 | 114105 | E2 | NAS-GRE | Steel Mess Supports | 545 | 251 |  | 0.46055 | 0.43935
|  |  |  | Messenger Clamps | 444 | 261 |  | 0.58784
|  |  |  | Messenger Wire Pull | 302 | 33 |  | 0.10927
|  |  |  | Messenger Wire Tension | 683 | 304 |  | 0.4451
|  |  |  | # Cables Pulled | 161 | 148 |  | 0.91925
|  |  |  | Messenger Straps | 973 | 111 |  | 0.11408
114105 | 114730 | E2 | NAS-GRE | 24" CMRS Install | 448 | 100 |  | 0.22321 | 0.16143
|  |  |  | Column Clamp | 928 | 2 |  | 0.0021552
|  |  |  | Station Brackets | 979 | 260 |  | 0.26558
|  |  |  | Grounding | 18 | 1 |  | 0.055556
|  |  |  | Obstruction Brackets | 974 | 338 |  | 0.34702
|  |  |  | # Cables Pulled | 626 | 47 |  | 0.07508
114730 | 114910 | E2 | NAS-GRE | Steel Mess Supports | 189 | 15 |  | 0.079365 | 0.27984
|  |  |  | Messenger Clamps | 828 | 263 |  | 0.31763
|  |  |  | Messenger Wire Pull | 783 | 312 |  | 0.39847
|  |  |  | Messenger Wire Tension | 566 | 100 |  | 0.17668
|  |  |  | # Cables Pulled | 79 | 45 |  | 0.56962
|  |  |  | Messenger Straps | 765 | 105 |  | 0.13725
114910 | 115625 | E2 | NAS-GRE | 24" CMRS Install | 565 | 194 |  | 0.34336 | 0.51588
|  |  |  | Column Clamp | 131 | 52 |  | 0.39695
|  |  |  | Station Brackets | 151 | 144 |  | 0.95364
|  |  |  | Grounding | 267 | 126 |  | 0.47191
|  |  |  | Obstruction Brackets | 579 | 159 |  | 0.27461
|  |  |  | # Cables Pulled | 956 | 626 |  | 0.65481
115625 | 116435 | E2 | GREENPOINT | 24" CMRS Install | 986 | 84 |  | 0.085193 | 0.36838
|  |  |  | Column Clamp | 884 | 27 |  | 0.030543
|  |  |  | Station Brackets | 703 | 304 |  | 0.43243
|  |  |  | Grounding | 335 | 216 |  | 0.64478
|  |  |  | Obstruction Brackets | 736 | 408 |  | 0.55435
|  |  |  | # Cables Pulled | 108 | 50 |  | 0.46296
116435 | 117130 | E2 | GRE-21S | 24" CMRS Install | 926 | 405 |  | 0.43737 | 0.54677
|  |  |  | Column Clamp | 312 | 183 |  | 0.58654
|  |  |  | Station Brackets | 841 | 841 |  | 1
|  |  |  | Grounding | 346 | 213 |  | 0.61561
|  |  |  | Obstruction Brackets | 690 | 31 |  | 0.044928
|  |  |  | # Cables Pulled | 260 | 155 |  | 0.59615
|  | E2 | GRE-21S | Crossover (Arch Bar Installation) | 974 | 954 |  | 0.97947
117130 | 121035 | E2 | GRE-21S | 24" CMRS Install | 792 | 85 |  | 0.10732 | 0.25594
|  |  |  | Column Clamp | 586 | 2 |  | 0.003413
|  |  |  | Station Brackets | 417 | 30 |  | 0.071942
|  |  |  | Grounding | 145 | 40 |  | 0.27586
|  |  |  | Obstruction Brackets | 56 | 42 |  | 0.75
|  |  |  | # Cables Pulled | 749 | 245 |  | 0.3271
121035 | 122030 | E2 | 21ST STATION | Steel Mess Supports | 44 | 24 |  | 0.54545 | 0.43112
|  |  |  | Messenger Clamps | 686 | 282 |  | 0.41108
|  |  |  | Messenger Wire Pull | 942 | 72 |  | 0.076433
|  |  |  | Messenger Wire Tension | 665 | 433 |  | 0.65113
|  |  |  | # Cables Pulled | 586 | 466 |  | 0.79522
|  |  |  | Messenger Straps | 596 | 64 |  | 0.10738
122030 | 122430 | E2 | 21S-COU | 24" CMRS Install | 321 | 69 |  | 0.21495 | 0.52912
|  |  |  | Column Clamp | 757 | 522 |  | 0.68956
|  |  |  | Station Brackets | 854 | 605 |  | 0.70843
|  |  |  | Grounding | 165 | 133 |  | 0.80606
|  |  |  | Obstruction Brackets | 595 | 2 |  | 0.0033613
|  |  |  | # Cables Pulled | 852 | 641 |  | 0.75235
122430 | 122660 | E2 | 21S-COU | Steel Mess Supports | 268 | 262 |  | 0.97761 | 0.60192
|  |  |  | Messenger Clamps | 317 | 130 |  | 0.41009
|  |  |  | Messenger Wire Pull | 624 | 79 |  | 0.1266
|  |  |  | Messenger Wire Tension | 56 | 14 |  | 0.25
|  |  |  | # Cables Pulled | 281 | 278 |  | 0.98932
|  |  |  | Messenger Straps | 570 | 489 |  | 0.85789
122660 | 122827 | E2 | 21S-COU | 24" CMRS Install | 443 | 365 |  | 0.82393 | 0.73675
|  |  |  | Column Clamp | 486 | 372 |  | 0.76543
|  |  |  | Station Brackets | 560 | 371 |  | 0.6625
|  |  |  | Grounding | 848 | 751 |  | 0.88561
|  |  |  | Obstruction Brackets | 482 | 301 |  | 0.62448
|  |  |  | # Cables Pulled | 41 | 27 |  | 0.65854
122827 | 123085 | E2 | 21S-COU | Steel Mess Supports | 892 | 12 |  | 0.013453 | 0.25475
|  |  |  | Messenger Clamps | 864 | 388 |  | 0.44907
|  |  |  | Messenger Wire Pull | 482 | 46 |  | 0.095436
|  |  |  | Messenger Wire Tension | 669 | 264 |  | 0.39462
|  |  |  | # Cables Pulled | 742 | 267 |  | 0.35984
|  |  |  | Messenger Straps | 560 | 121 |  | 0.21607
123085 | 123690 | E2 | COURT SQ | Cable Tray Brackets | 792 | 346 |  | 0.43687 | 0.36182
|  |  |  | Installing Tray | 756 | 72 |  | 0.095238
|  |  |  | Core Drilling | 887 | 449 |  | 0.5062
|  |  |  | Cable Pull | 780 | 319 |  | 0.40897
123690 | 123750 | E2 | COU-QUE | Steel Mess Supports | 52 | 32 |  | 0.61538 | 0.50758
|  |  |  | Messenger Clamps | 587 | 161 |  | 0.27428
|  |  |  | Messenger Wire Pull | 851 | 347 |  | 0.40776
|  |  |  | Messenger Wire Tension | 545 | 545 |  | 1
|  |  |  | # Cables Pulled | 531 | 332 |  | 0.62524
|  |  |  | Messenger Straps | 464 | 57 |  | 0.12284
123750 | 123950 | E2 | COU-QUE | Steel Mess Supports | 885 | 401 |  | 0.45311 | 0.63533
|  |  |  | Messenger Clamps | 700 | 691 |  | 0.98714
|  |  |  | Messenger Wire Pull | 197 | 196 |  | 0.99492
|  |  |  | Messenger Wire Tension | 802 | 403 |  | 0.50249
|  |  |  | # Cables Pulled | 434 | 248 |  | 0.57143
|  |  |  | Messenger Straps | 208 | 63 |  | 0.30288
123950 | 124050 | E2 | COU-QUE | Steel Mess Supports | 247 | 133 |  | 0.53846 | 0.52346
|  |  |  | Messenger Clamps | 10 | 9 |  | 0.9
|  |  |  | Messenger Wire Pull | 88 | 9 |  | 0.10227
|  |  |  | Messenger Wire Tension | 744 | 637 |  | 0.85618
|  |  |  | # Cables Pulled | 745 | 509 |  | 0.68322
|  |  |  | Messenger Straps | 462 | 28 |  | 0.060606
124050 | 124190 | E2 | COU-QUE | Steel Mess Supports | 516 | 90 |  | 0.17442 | 0.4388
|  |  |  | Messenger Clamps | 308 | 64 |  | 0.20779
|  |  |  | Messenger Wire Pull | 309 | 178 |  | 0.57605
|  |  |  | Messenger Wire Tension | 55 | 33 |  | 0.6
|  |  |  | # Cables Pulled | 899 | 413 |  | 0.4594
|  |  |  | Messenger Straps | 634 | 390 |  | 0.61514
124190 | 124490 | E2 | COU-QUE | Steel Mess Supports | 590 | 380 |  | 0.64407 | 0.67604
|  |  |  | Messenger Clamps | 713 | 554 |  | 0.777
|  |  |  | Messenger Wire Pull | 832 | 617 |  | 0.74159
|  |  |  | Messenger Wire Tension | 251 | 126 |  | 0.50199
|  |  |  | # Cables Pulled | 848 | 534 |  | 0.62972
|  |  |  | Messenger Straps | 21 | 16 |  | 0.7619
124490 | 124700 | E2 | COU-QUE | Steel Mess Supports | 58 | 22 |  | 0.37931 | 0.53001
|  |  |  | Messenger Clamps | 831 | 365 |  | 0.43923
|  |  |  | Messenger Wire Pull | 114 | 5 |  | 0.04386
|  |  |  | Messenger Wire Tension | 926 | 852 |  | 0.92009
|  |  |  | # Cables Pulled | 255 | 130 |  | 0.5098
|  |  |  | Messenger Straps | 998 | 886 |  | 0.88778
124700 | 125010 | E2 | COU-QUE | Steel Mess Supports | 776 | 610 |  | 0.78608 | 0.49116
|  |  |  | Messenger Clamps | 25 | 8 |  | 0.32
|  |  |  | Messenger Wire Pull | 875 | 278 |  | 0.31771
|  |  |  | Messenger Wire Tension | 717 | 532 |  | 0.74198
|  |  |  | # Cables Pulled | 502 | 248 |  | 0.49402
|  |  |  | Messenger Straps | 902 | 259 |  | 0.28714
|  | E2 | COU-QUE | Crossover (Arch Bar Installation) | 446 | 253 |  | 0.56726
75650 | 78244 | B3 | BERGEN ST | Steel Mess Supports | 218 | 11 |  | 0.050459 | 0.4402
|  |  |  | Messenger Clamps | 478 | 262 |  | 0.54812
|  |  |  | Messenger Wire Pull | 96 | 17 |  | 0.17708
|  |  |  | Messenger Wire Tension | 239 | 204 |  | 0.85356
|  |  |  | # Cables Pulled | 520 | 208 |  | 0.4
|  |  |  | Messenger Straps | 634 | 388 |  | 0.61199
|  | B3 | BER-JAY | Steel Mess Supports | 374 | 29 |  | 0.07754 | 0.48414
|  |  |  | Messenger Clamps | 687 | 524 |  | 0.76274
|  |  |  | Messenger Wire Pull | 234 | 59 |  | 0.25214
|  |  |  | Messenger Wire Tension | 174 | 140 |  | 0.8046
|  |  |  | # Cables Pulled | 935 | 822 |  | 0.87914
|  |  |  | Messenger Straps | 202 | 26 |  | 0.12871
|  | B4 | BER-JAY | Steel Mess Supports | 492 | 392 |  | 0.79675 | 0.58976
|  |  |  | Messenger Clamps | 49 | 0 |  | 0
|  |  |  | Messenger Wire Pull | 564 | 288 |  | 0.51064
|  |  |  | Messenger Wire Tension | 854 | 601 |  | 0.70375
|  |  |  | # Cables Pulled | 536 | 353 |  | 0.65858
|  |  |  | Messenger Straps | 61 | 53 |  | 0.86885
|  | E3/E4 | COURT SQ | Steel Mess Supports | 554 | 49 |  | 0.088448 | 0.38889
|  |  |  | Messenger Clamps | 364 | 104 |  | 0.28571
|  |  |  | Messenger Wire Pull | 759 | 461 |  | 0.60738
|  |  |  | Messenger Wire Tension | 952 | 543 |  | 0.57038
|  |  |  | # Cables Pulled | 495 | 217 |  | 0.43838
|  |  |  | Messenger Straps | 548 | 188 |  | 0.34307
75640 | 75300 | B1 | CAR-BER | Steel Mess Supports | 744 | 40 |  | 0.053763 | 0.4392
|  |  |  | Messenger Clamps | 167 | 14 |  | 0.083832
|  |  |  | Messenger Wire Pull | 829 | 530 |  | 0.63932
|  |  |  | Messenger Wire Tension | 429 | 396 |  | 0.92308
|  |  |  | # Cables Pulled | 657 | 89 |  | 0.13546
|  |  |  | Messenger Straps | 804 | 643 |  | 0.79975
68570 | 68330 | B3 | 4TH AVE | Steel Mess Supports | 90 | 71 |  | 0.78889 | 0.68051
|  |  |  | Messenger Clamps | 155 | 100 |  | 0.64516
|  |  |  | Messenger Wire Pull | 385 | 250 |  | 0.64935
|  |  |  | Messenger Wire Tension | 753 | 601 |  | 0.79814
|  |  |  | # Cables Pulled | 612 | 247 |  | 0.40359
|  |  |  | Messenger Straps | 480 | 383 |  | 0.79792
68330 | 68030 | B3 | 4AV-7AV | Steel Mess Supports | 634 | 43 |  | 0.067823 | 0.49085
|  |  |  | Messenger Clamps | 149 | 67 |  | 0.44966
|  |  |  | Messenger Wire Pull | 168 | 113 |  | 0.67262
|  |  |  | Messenger Wire Tension | 145 | 129 |  | 0.88966
|  |  |  | # Cables Pulled | 381 | 137 |  | 0.35958
|  |  |  | Messenger Straps | 174 | 88 |  | 0.50575
66070 | 66000 | B3 | 4AV-7AV | Steel Mess Supports | 558 | 459 |  | 0.82258 | 0.72954
|  |  |  | Messenger Clamps | 95 | 74 |  | 0.77895
|  |  |  | Messenger Wire Pull | 539 | 509 |  | 0.94434
|  |  |  | Messenger Wire Tension | 263 | 86 |  | 0.327
|  |  |  | # Cables Pulled | 243 | 130 |  | 0.53498
|  |  |  | Messenger Straps | 98 | 95 |  | 0.96939
60350 | 60000 | B1 | FOR-15S | Steel Mess Supports | 590 | 32 |  | 0.054237 | 0.63368
|  |  |  | Messenger Clamps | 548 | 477 |  | 0.87044
|  |  |  | Messenger Wire Pull | 194 | 183 |  | 0.9433
|  |  |  | Messenger Wire Tension | 325 | 246 |  | 0.75692
|  |  |  | # Cables Pulled | 931 | 166 |  | 0.1783
|  |  |  | Messenger Straps | 914 | 913 |  | 0.99891
56440 | 56350 | B1 | CHU-FOR | Steel Mess Supports | 107 | 61 |  | 0.57009 | 0.46192
|  |  |  | Messenger Clamps | 939 | 91 |  | 0.096912
|  |  |  | Messenger Wire Pull | 519 | 276 |  | 0.53179
|  |  |  | Messenger Wire Tension | 517 | 77 |  | 0.14894
|  |  |  | # Cables Pulled | 515 | 236 |  | 0.45825
|  |  |  | Messenger Straps | 957 | 924 |  | 0.96552
55580 | 54500 | B2 | CHU-DIT | Steel Mess Supports | 653 | 177 |  | 0.27106 | 0.57695
|  |  |  | Messenger Clamps | 770 | 718 |  | 0.93247
|  |  |  | Messenger Wire Pull | 22 | 1 |  | 0.045455
|  |  |  | Messenger Wire Tension | 219 | 117 |  | 0.53425
|  |  |  | # Cables Pulled | 526 | 367 |  | 0.69772
|  |  |  | Messenger Straps | 727 | 713 |  | 0.98074
54730 | 55000 | B2 | CHU-DIT | Steel Mess Supports | 519 | 356 |  | 0.68593 | 0.52987
|  |  |  | Messenger Clamps | 91 | 64 |  | 0.7033
|  |  |  | Messenger Wire Pull | 881 | 227 |  | 0.25766
|  |  |  | Messenger Wire Tension | 141 | 38 |  | 0.2695
|  |  |  | # Cables Pulled | 265 | 114 |  | 0.43019
|  |  |  | Messenger Straps | 926 | 771 |  | 0.83261
55485 | 55725 | B2 | CHU-DIT | Steel Mess Supports | 792 | 620 |  | 0.78283 | 0.53972
|  |  |  | Messenger Clamps | 369 | 369 |  | 1
|  |  |  | Messenger Wire Pull | 739 | 13 |  | 0.017591
|  |  |  | Messenger Wire Tension | 128 | 56 |  | 0.4375
|  |  |  | # Cables Pulled | 270 | 123 |  | 0.45556
|  |  |  | Messenger Straps | 714 | 389 |  | 0.54482
55725 | 56635 | B2 | CHURCH AVE | Steel Mess Supports | 59 | 28 |  | 0.47458 | 0.47194
|  |  |  | Messenger Clamps | 174 | 169 |  | 0.97126
|  |  |  | Messenger Wire Pull | 536 | 83 |  | 0.15485
|  |  |  | Messenger Wire Tension | 80 | 62 |  | 0.775
|  |  |  | # Cables Pulled | 712 | 124 |  | 0.17416
|  |  |  | Messenger Straps | 976 | 275 |  | 0.28176
57320 | 57445 | B2 | CHU-FOR | Steel Mess Supports | 982 | 804 |  | 0.81874 | 0.58716
|  |  |  | Messenger Clamps | 993 | 151 |  | 0.15206
|  |  |  | Messenger Wire Pull | 503 | 404 |  | 0.80318
|  |  |  | Messenger Wire Tension | 70 | 41 |  | 0.58571
|  |  |  | # Cables Pulled | 632 | 273 |  | 0.43196
|  |  |  | Messenger Straps | 908 | 664 |  | 0.73128
60165 | 60620 | B2 | FOR-15S | Steel Mess Supports | 620 | 207 |  | 0.33387 | 0.60586
|  |  |  | Messenger Clamps | 275 | 223 |  | 0.81091
|  |  |  | Messenger Wire Pull | 278 | 223 |  | 0.80216
|  |  |  | Messenger Wire Tension | 389 | 77 |  | 0.19794
|  |  |  | # Cables Pulled | 210 | 176 |  | 0.8381
|  |  |  | Messenger Straps | 23 | 15 |  | 0.65217
62560 | 63425 | B2 | 15TH STREET PROSPECT PARK | Steel Mess Supports | 220 | 200 |  | 0.90909 | 0.49471
|  |  |  | Messenger Clamps | 403 | 347 |  | 0.86104
|  |  |  | Messenger Wire Pull | 340 | 105 |  | 0.30882
|  |  |  | Messenger Wire Tension | 459 | 82 |  | 0.17865
|  |  |  | # Cables Pulled | 639 | 128 |  | 0.20031
|  |  |  | Messenger Straps | 629 | 321 |  | 0.51033
67950 | 68330 | B4/B2 | 4AV-7AV | Steel Mess Supports | 29 | 29 |  | 1 | 0.51218
|  |  |  | Messenger Clamps | 65 | 51 |  | 0.78462
|  |  |  | Messenger Wire Pull | 409 | 51 |  | 0.12469
|  |  |  | Messenger Wire Tension | 635 | 368 |  | 0.57953
|  |  |  | # Cables Pulled | 813 | 249 |  | 0.30627
|  |  |  | Messenger Straps | 680 | 189 |  | 0.27794
74740 | 74840 | B2 | CAR-BER | Steel Mess Supports | 257 | 107 |  | 0.41634 | 0.49946
|  |  |  | Messenger Clamps | 916 | 464 |  | 0.50655
|  |  |  | Messenger Wire Pull | 903 | 159 |  | 0.17608
|  |  |  | Messenger Wire Tension | 254 | 11 |  | 0.043307
|  |  |  | # Cables Pulled | 995 | 964 |  | 0.96884
|  |  |  | Messenger Straps | 857 | 759 |  | 0.88565
75395 | 75650 | B2 | CAR-BER | Steel Mess Supports | 432 | 183 |  | 0.42361 | 0.47435
|  |  |  | Messenger Clamps | 223 | 42 |  | 0.18834
|  |  |  | Messenger Wire Pull | 781 | 640 |  | 0.81946
|  |  |  | Messenger Wire Tension | 470 | 327 |  | 0.69574
|  |  |  | # Cables Pulled | 867 | 484 |  | 0.55825
|  |  |  | Messenger Straps | 865 | 139 |  | 0.16069
78905 | 75950 | B3 | JAY-BER | Steel Mess Supports | 827 | 739 |  | 0.89359 | 0.67465
|  |  |  | Messenger Clamps | 55 | 45 |  | 0.81818
|  |  |  | Messenger Wire Pull | 332 | 261 |  | 0.78614
|  |  |  | Messenger Wire Tension | 874 | 331 |  | 0.37872
|  |  |  | # Cables Pulled | 467 | 213 |  | 0.4561
|  |  |  | Messenger Straps | 323 | 231 |  | 0.71517
75950 | 75650 | B3 | BERGEN ST | Steel Mess Supports | 177 | 69 |  | 0.38983 | 0.36949
|  |  |  | Messenger Clamps | 784 | 98 |  | 0.125
|  |  |  | Messenger Wire Pull | 655 | 489 |  | 0.74656
|  |  |  | Messenger Wire Tension | 883 | 211 |  | 0.23896
|  |  |  | # Cables Pulled | 996 | 620 |  | 0.62249
|  |  |  | Messenger Straps | 744 | 70 |  | 0.094086
75650 | 75420 | B3 | CAR-BER | Steel Mess Supports | 915 | 192 |  | 0.20984 | 0.46659
|  |  |  | Messenger Clamps | 790 | 123 |  | 0.1557
|  |  |  | Messenger Wire Pull | 707 | 382 |  | 0.54031
|  |  |  | Messenger Wire Tension | 359 | 261 |  | 0.72702
|  |  |  | # Cables Pulled | 798 | 189 |  | 0.23684
|  |  |  | Messenger Straps | 171 | 159 |  | 0.92982
73285 | 72960 | B3 | CAR-BER | Steel Mess Supports | 59 | 21 |  | 0.35593 | 0.59412
|  |  |  | Messenger Clamps | 526 | 322 |  | 0.61217
|  |  |  | Messenger Wire Pull | 689 | 95 |  | 0.13788
|  |  |  | Messenger Wire Tension | 230 | 230 |  | 1
|  |  |  | # Cables Pulled | 178 | 108 |  | 0.60674
|  |  |  | Messenger Straps | 777 | 662 |  | 0.85199
72960 | 72035 | B3/B4 | CAR-4TH | Steel Mess Supports | 242 | 117 |  | 0.48347 | 0.49476
|  |  |  | Messenger Clamps | 639 | 236 |  | 0.36933
|  |  |  | Messenger Wire Pull | 486 | 343 |  | 0.70576
|  |  |  | Messenger Wire Tension | 13 | 4 |  | 0.30769
|  |  |  | # Cables Pulled | 106 | 98 |  | 0.92453
|  |  |  | Messenger Straps | 45 | 8 |  | 0.17778
71150 | 70965 | B3/B4 | CAR-4TH | Steel Mess Supports | 996 | 75 |  | 0.075301 | 0.25376
|  |  |  | Messenger Clamps | 589 | 125 |  | 0.21222
|  |  |  | Messenger Wire Pull | 872 | 179 |  | 0.20528
|  |  |  | Messenger Wire Tension | 697 | 348 |  | 0.49928
|  |  |  | # Cables Pulled | 877 | 25 |  | 0.028506
|  |  |  | Messenger Straps | 508 | 255 |  | 0.50197
70965 | 70445 | B3/B6 | CAR-4TH | Steel Mess Supports | 148 | 65 |  | 0.43919 | 0.64667
|  |  |  | Messenger Clamps | 658 | 333 |  | 0.50608
|  |  |  | Messenger Wire Pull | 759 | 727 |  | 0.95784
|  |  |  | Messenger Wire Tension | 424 | 216 |  | 0.50943
|  |  |  | # Cables Pulled | 599 | 457 |  | 0.76294
|  |  |  | Messenger Straps | 572 | 403 |  | 0.70455
70445 | 70045 | B3/B7 | CAR-4TH | Steel Mess Supports | 698 | 161 |  | 0.23066 | 0.35534
|  |  |  | Messenger Clamps | 55 | 16 |  | 0.29091
|  |  |  | Messenger Wire Pull | 94 | 33 |  | 0.35106
|  |  |  | Messenger Wire Tension | 229 | 36 |  | 0.15721
|  |  |  | # Cables Pulled | 817 | 208 |  | 0.25459
|  |  |  | Messenger Straps | 466 | 395 |  | 0.84764
68625 | 68400 | B3/B8 | CAR-4TH | Steel Mess Supports | 691 | 295 |  | 0.42692 | 0.36275
|  |  |  | Messenger Clamps | 258 | 53 |  | 0.20543
|  |  |  | Messenger Wire Pull | 762 | 94 |  | 0.12336
|  |  |  | Messenger Wire Tension | 917 | 358 |  | 0.3904
|  |  |  | # Cables Pulled | 964 | 531 |  | 0.55083
|  |  |  | Messenger Straps | 784 | 376 |  | 0.47959
68400 | 68330 | B3/B9 | CAR-4TH | Steel Mess Supports | 385 | 1 |  | 0.0025974 | 0.49448
|  |  |  | Messenger Clamps | 137 | 9 |  | 0.065693
|  |  |  | Messenger Wire Pull | 882 | 671 |  | 0.76077
|  |  |  | Messenger Wire Tension | 788 | 635 |  | 0.80584
|  |  |  | # Cables Pulled | 471 | 196 |  | 0.41614
|  |  |  | Messenger Straps | 903 | 827 |  | 0.91584

## AXLE COUNTER
Stationing | Track No | Location | Activity | Date | Progress | General Progress | Notes | DWG REF.
54600 | B1 | DIT-CHU | Axle Counter Installation |  | 96.82% | 73.79% | STATIONING SHOWN IS THAT OF THE NEAREST IJ, AXC STATIONING DOES NOT EXIST | B1-546
|  |  | JB Installation |  | 77.75%
|  |  | Line Cable Installation |  | 64.47%
|  |  | Express Cable Installation |  | 61.14%
|  |  | Pre-Operation Testing |  | 68.77%
| B1 |  | Axle Counter Installation |  | 32.34% | 40.23% | NO INFO | B1-547
|  |  | JB Installation |  | 6.538%
|  |  | Line Cable Installation |  | 49.69%
|  |  | Express Cable Installation |  | 63.91%
|  |  | Pre-Operation Testing |  | 48.7%
59297 | B1 | FOR-15S | Axle Counter Installation |  | 39.44% | 36.74% |  | B1-553
|  |  | JB Installation |  | 38.81%
|  |  | Line Cable Installation |  | 51.66%
|  |  | Express Cable Installation |  | 32.74%
|  |  | Pre-Operation Testing |  | 21.03%
| B1 |  | Axle Counter Installation |  | 68.17% | 49.59% | NO INFO | B1-554
|  |  | JB Installation |  | 21.46%
|  |  | Line Cable Installation |  | 59.56%
|  |  | Express Cable Installation |  | 80.49%
|  |  | Pre-Operation Testing |  | 18.29%
55687 | B1 | DIT-CHU | Axle Counter Installation |  | 60.6% | 45.58% |  | B1-557
|  |  | JB Installation |  | 76.76%
|  |  | Line Cable Installation |  | 11.53%
|  |  | Express Cable Installation |  | 19.96%
|  |  | Pre-Operation Testing |  | 59.07%
56367 | B1 | CHU-FOR | Axle Counter Installation |  | 12.48% | 45.26% |  | B1-564
|  |  | JB Installation |  | 25.4%
|  |  | Line Cable Installation |  | 50.21%
|  |  | Express Cable Installation |  | 61.66%
|  |  | Pre-Operation Testing |  | 76.57%
58524.6 | B1 | FORT HAMILTON PARKWAY | Axle Counter Installation |  | 55.49% | 48.36% |  | B1-585
|  |  | JB Installation |  | 32.09%
|  |  | Line Cable Installation |  | 46.47%
|  |  | Express Cable Installation |  | 65.37%
|  |  | Pre-Operation Testing |  | 42.36%
59210.25 | B1 | FOR-15S | Axle Counter Installation |  | 47.37% | 50.82% |  | B1-592
|  |  | JB Installation |  | 9.139%
|  |  | Line Cable Installation |  | 74.08%
|  |  | Express Cable Installation |  | 66.09%
|  |  | Pre-Operation Testing |  | 57.42%
62572.5 | B1 | FOR-15S | Axle Counter Installation |  | 80.87% | 53.61% |  | B1-626
|  |  | JB Installation |  | 99.68%
|  |  | Line Cable Installation |  | 63.59%
|  |  | Express Cable Installation |  | 18.21%
|  |  | Pre-Operation Testing |  | 5.69%
63251.4 | B1 | 15S-7AV | Axle Counter Installation |  | 18.28% | 56.84% |  | B1-632
|  |  | JB Installation |  | 87.81%
|  |  | Line Cable Installation |  | 56.24%
|  |  | Express Cable Installation |  | 28.05%
|  |  | Pre-Operation Testing |  | 93.83%
65387.3 | B1 | 15S-7AV | Axle Counter Installation |  | 14.04% | 35.83% |  | B1-654
|  |  | JB Installation |  | 77.1%
|  |  | Line Cable Installation |  | 20.62%
|  |  | Express Cable Installation |  | 30.51%
|  |  | Pre-Operation Testing |  | 36.88%
66076 | B1 | 7AV-4TH | Axle Counter Installation |  | 56.74% | 55.82% |  | B1-661
|  |  | JB Installation |  | 22.66%
|  |  | Line Cable Installation |  | 88.05%
|  |  | Express Cable Installation |  | 37.85%
|  |  | Pre-Operation Testing |  | 73.8%
73206.7 | B1 | SMI-CAR | Axle Counter Installation |  | 40.76% | 46.26% |  | B1-732
|  |  | JB Installation |  | 12.67%
|  |  | Line Cable Installation |  | 52.75%
|  |  | Express Cable Installation |  | 77.93%
|  |  | Pre-Operation Testing |  | 47.2%
73932 | B1 | CAR-BER | Axle Counter Installation |  | 35.46% | 23.55% |  | B1-739
|  |  | JB Installation |  | 7.405%
|  |  | Line Cable Installation |  | 37.3%
|  |  | Express Cable Installation |  | 14.98%
|  |  | Pre-Operation Testing |  | 22.57%
75408 | B1 | CAR-BER | Axle Counter Installation |  | 40% | 46.29% |  | B1-755
|  |  | JB Installation |  | 15.58%
|  |  | Line Cable Installation |  | 26.67%
|  |  | Express Cable Installation |  | 65.97%
|  |  | Pre-Operation Testing |  | 83.24%
75669 | B1 | CAR-BER | Axle Counter Installation |  | 85.55% | 44.13% |  | B1-756
|  |  | JB Installation |  | 19.3%
|  |  | Line Cable Installation |  | 7.314%
|  |  | Express Cable Installation |  | 31.77%
|  |  | Pre-Operation Testing |  | 76.7%
76352 | B1 | BER-HOY | Axle Counter Installation |  | 80.56% | 70.8% |  | B1-763, B1-764
|  |  | JB Installation |  | 80.02%
|  |  | Line Cable Installation |  | 64.04%
|  |  | Express Cable Installation |  | 77.41%
|  |  | Pre-Operation Testing |  | 51.98%
76589 | B1 | HOYT-SCHERMERHORN | Axle Counter Installation |  | 21.4% | 50.27% |  | B1-766
|  |  | JB Installation |  | 77.93%
|  |  | Line Cable Installation |  | 16.71%
|  |  | Express Cable Installation |  | 74.26%
|  |  | Pre-Operation Testing |  | 61.04%
76901.5 | B1 | HOY-FUL | Axle Counter Installation |  | 41.17% | 64.96% |  | B1-770
|  |  | JB Installation |  | 84.44%
|  |  | Line Cable Installation |  | 83.32%
|  |  | Express Cable Installation |  | 85.29%
|  |  | Pre-Operation Testing |  | 30.55%
77088 | B1 | FUL-CLI | Axle Counter Installation |  | 32.96% | 37.38% |  | B1-771
|  |  | JB Installation |  | 26.96%
|  |  | Line Cable Installation |  | 59.89%
|  |  | Express Cable Installation |  | 23.18%
|  |  | Pre-Operation Testing |  | 43.9%
54737 | B2 | DIT-CHU | Axle Counter Installation |  | 64.74% | 53.9% |  | B2-546
|  |  | JB Installation |  | 85.02%
|  |  | Line Cable Installation |  | 22.48%
|  |  | Express Cable Installation |  | 73.31%
|  |  | Pre-Operation Testing |  | 23.94%
54731 | B2 |  | Axle Counter Installation |  | 8.221% | 45.17% |  | B2-547
|  |  | JB Installation |  | 64.88%
|  |  | Line Cable Installation |  | 60.88%
|  |  | Express Cable Installation |  | 31.54%
|  |  | Pre-Operation Testing |  | 60.33%
55000 | B2 | DIT-CHU | Axle Counter Installation |  | 45.12% | 62.71% |  | B2-549
|  |  | JB Installation |  | 62.26%
|  |  | Line Cable Installation |  | 22.95%
|  |  | Express Cable Installation |  | 91.8%
|  |  | Pre-Operation Testing |  | 91.41%
55498 | B2 | DIT-CHU | Axle Counter Installation |  | 74.98% | 52.55% |  | B2-554
|  |  | JB Installation |  | 16.55%
|  |  | Line Cable Installation |  | 13.55%
|  |  | Express Cable Installation |  | 71.96%
|  |  | Pre-Operation Testing |  | 85.71%
| B2 |  | Axle Counter Installation |  | 10.65% | 55.85% | NO REF DWG EXISTS | B2-555
|  |  | JB Installation |  | 97.05%
|  |  | Line Cable Installation |  | 76.83%
|  |  | Express Cable Installation |  | 12.73%
|  |  | Pre-Operation Testing |  | 81.97%
| B2 |  | Axle Counter Installation |  | 13.04% | 30.49% | NO REF DWG EXISTS | B2-556
|  |  | JB Installation |  | 41.08%
|  |  | Line Cable Installation |  | 36.59%
|  |  | Express Cable Installation |  | 6.332%
|  |  | Pre-Operation Testing |  | 55.4%
55857 | B2 | CHURCH AVE | Axle Counter Installation |  | 25.79% | 48.52% |  | B2-558
|  |  | JB Installation |  | 60.67%
|  |  | Line Cable Installation |  | 81.62%
|  |  | Express Cable Installation |  | 29.04%
|  |  | Pre-Operation Testing |  | 45.46%
58500 | B2 | FORT HAMILTON PARKWAY | Axle Counter Installation |  | 87.33% | 62.87% |  | B2-585
|  |  | JB Installation |  | 68.8%
|  |  | Line Cable Installation |  | 90.03%
|  |  | Express Cable Installation |  | 18.62%
|  |  | Pre-Operation Testing |  | 49.54%
59203.8 | B2 | FOR-15S | Axle Counter Installation |  | 77.33% | 77.08% |  | B2-592
|  |  | JB Installation |  | 89.73%
|  |  | Line Cable Installation |  | 79.55%
|  |  | Express Cable Installation |  | 91.62%
|  |  | Pre-Operation Testing |  | 47.16%
62550.6 | B2 |  | Axle Counter Installation |  | 34.25% | 46.62% |  | B2-625
|  |  | JB Installation |  | 59.61%
|  |  | Line Cable Installation |  | 13.31%
|  |  | Express Cable Installation |  | 97.51%
|  |  | Pre-Operation Testing |  | 28.43%
65375.3 | B2 | 15S-7AV | Axle Counter Installation |  | 63.35% | 30.48% |  | B2-654
|  |  | JB Installation |  | 0.003693%
|  |  | Line Cable Installation |  | 39.3%
|  |  | Express Cable Installation |  | 38.88%
|  |  | Pre-Operation Testing |  | 10.86%
66062.3 | B2 | 7AV-4TH | Axle Counter Installation |  | 23.74% | 33.65% |  | B2-661
|  |  | JB Installation |  | 53.26%
|  |  | Line Cable Installation |  | 58.65%
|  |  | Express Cable Installation |  | 24.19%
|  |  | Pre-Operation Testing |  | 8.418%
| B2 |  | Axle Counter Installation |  | 68.25% | 51.73% | NO REF DWG EXISTS | B2-665
|  |  | JB Installation |  | 72.03%
|  |  | Line Cable Installation |  | 19.36%
|  |  | Express Cable Installation |  | 52.14%
|  |  | Pre-Operation Testing |  | 46.88%
| B2 |  | Axle Counter Installation |  | 53.75% | 38.94% | NO REF DWG EXISTS | B2-684
|  |  | JB Installation |  | 28.77%
|  |  | Line Cable Installation |  | 35.32%
|  |  | Express Cable Installation |  | 22.19%
|  |  | Pre-Operation Testing |  | 54.68%
| B2 |  | Axle Counter Installation |  | 18.07% | 55.03% | NO REF DWG EXISTS | B2-691
|  |  | JB Installation |  | 87.61%
|  |  | Line Cable Installation |  | 72.55%
|  |  | Express Cable Installation |  | 21.22%
|  |  | Pre-Operation Testing |  | 75.72%
| B2 |  | Axle Counter Installation |  | 89.45% | 38.85% | NO REF DWG EXISTS | B2-692
|  |  | JB Installation |  | 3.275%
|  |  | Line Cable Installation |  | 16.95%
|  |  | Express Cable Installation |  | 79.72%
|  |  | Pre-Operation Testing |  | 4.86%
| B2 |  | Axle Counter Installation |  | 11.49% | 40.31% | NO REF DWG EXISTS | B2-692A
|  |  | JB Installation |  | 32.4%
|  |  | Line Cable Installation |  | 79.98%
|  |  | Express Cable Installation |  | 37.68%
|  |  | Pre-Operation Testing |  | 40.02%
| B2 |  | Axle Counter Installation |  | 53.78% | 72.96% | NO REF DWG EXISTS | B2-693
|  |  | JB Installation |  | 67.77%
|  |  | Line Cable Installation |  | 63.71%
|  |  | Express Cable Installation |  | 89.97%
|  |  | Pre-Operation Testing |  | 89.58%
| B2 |  | Axle Counter Installation |  | 35.02% | 50.84% | NO REF DWG EXISTS | B2-705
|  |  | JB Installation |  | 88.9%
|  |  | Line Cable Installation |  | 25.09%
|  |  | Express Cable Installation |  | 28.49%
|  |  | Pre-Operation Testing |  | 76.73%
| B2 |  | Axle Counter Installation |  | 10.41% | 52.42% | NO REF DWG EXISTS | B2-712
|  |  | JB Installation |  | 36.44%
|  |  | Line Cable Installation |  | 94.5%
|  |  | Express Cable Installation |  | 72.12%
|  |  | Pre-Operation Testing |  | 48.63%
| B2 |  | Axle Counter Installation |  | 23.2% | 42.42% | DWG EXISTS, BUT EMPTY | B2-732
|  |  | JB Installation |  | 20.12%
|  |  | Line Cable Installation |  | 85.51%
|  |  | Express Cable Installation |  | 15.74%
|  |  | Pre-Operation Testing |  | 67.51%
73926.3 | B2 | CARROLL STREET | Axle Counter Installation |  | 78.1% | 67.61% |  | B2-739
|  |  | JB Installation |  | 45.58%
|  |  | Line Cable Installation |  | 84.61%
|  |  | Express Cable Installation |  | 71.25%
|  |  | Pre-Operation Testing |  | 58.52%
75267 | B2 | CAR-BER | Axle Counter Installation |  | 29.35% | 47.12% |  | B2-753
|  |  | JB Installation |  | 94.8%
|  |  | Line Cable Installation |  | 21.36%
|  |  | Express Cable Installation |  | 35.89%
|  |  | Pre-Operation Testing |  | 54.18%
| B2 |  | Axle Counter Installation |  | 79.44% | 56.98% | NO REF DWG EXISTS | B2-755
|  |  | JB Installation |  | 13.73%
|  |  | Line Cable Installation |  | 93.42%
|  |  | Express Cable Installation |  | 48.74%
|  |  | Pre-Operation Testing |  | 49.57%
75646 | B2 | CAR-BER | Axle Counter Installation |  | 20.93% | 46.98% |  | B2-756
|  |  | JB Installation |  | 54.91%
|  |  | Line Cable Installation |  | 30%
|  |  | Express Cable Installation |  | 93.03%
|  |  | Pre-Operation Testing |  | 36.01%
76352 | B2 |  | Axle Counter Installation |  | 80% | 63.48% |  | B2-763, B2-764
|  |  | JB Installation |  | 85.48%
|  |  | Line Cable Installation |  | 68.62%
|  |  | Express Cable Installation |  | 58.98%
|  |  | Pre-Operation Testing |  | 24.31%
76536 | B2 |  | Axle Counter Installation |  | 15.68% | 43.85% |  | B2-765
|  |  | JB Installation |  | 37.37%
|  |  | Line Cable Installation |  | 38.93%
|  |  | Express Cable Installation |  | 52.21%
|  |  | Pre-Operation Testing |  | 75.02%
76797 | B2 |  | Axle Counter Installation |  | 44.45% | 44.05% |  | B2-768
|  |  | JB Installation |  | 36.26%
|  |  | Line Cable Installation |  | 16.5%
|  |  | Express Cable Installation |  | 41.05%
|  |  | Pre-Operation Testing |  | 81.99%
77116 | B2 |  | Axle Counter Installation |  | 72.29% | 37.53% |  | B2-770
|  |  | JB Installation |  | 19.31%
|  |  | Line Cable Installation |  | 79.64%
|  |  | Express Cable Installation |  | 10.76%
|  |  | Pre-Operation Testing |  | 5.636%
| B3 |  | Axle Counter Installation |  | 53.11% | 55.35% | REF DWG EXISTS, NO STATIONINGS SHOWN | B3-546
|  |  | JB Installation |  | 49.77%
|  |  | Line Cable Installation |  | 4.511%
|  |  | Express Cable Installation |  | 83.43%
|  |  | Pre-Operation Testing |  | 85.91%
| B3 |  | Axle Counter Installation |  | 27.29% | 48.61% | REF DWG EXISTS, NO STATIONINGS SHOWN | B3-548
|  |  | JB Installation |  | 25.23%
|  |  | Line Cable Installation |  | 97.31%
|  |  | Express Cable Installation |  | 43.78%
|  |  | Pre-Operation Testing |  | 49.43%
53361 | B3 |  | Axle Counter Installation |  | 26.44% | 50.37% |  | B3-554
|  |  | JB Installation |  | 25.32%
|  |  | Line Cable Installation |  | 74.88%
|  |  | Express Cable Installation |  | 72.86%
|  |  | Pre-Operation Testing |  | 52.37%
55626 | B3 |  | Axle Counter Installation |  | 1.782% | 33.99% |  | B3-555
|  |  | JB Installation |  | 20.56%
|  |  | Line Cable Installation |  | 77.22%
|  |  | Express Cable Installation |  | 48.85%
|  |  | Pre-Operation Testing |  | 21.53%
| B3 |  | Axle Counter Installation |  | 36.83% | 57.24% | REF DWG EXISTS, NO STATIONINGS SHOWN | B3-556
|  |  | JB Installation |  | 40.47%
|  |  | Line Cable Installation |  | 91.23%
|  |  | Express Cable Installation |  | 23.46%
|  |  | Pre-Operation Testing |  | 94.19%
| B3 |  | Axle Counter Installation |  | 22.92% | 43.99% | REF DWG EXISTS, NO STATIONINGS SHOWN | B3-557
|  |  | JB Installation |  | 24.98%
|  |  | Line Cable Installation |  | 85.23%
|  |  | Express Cable Installation |  | 47.97%
|  |  | Pre-Operation Testing |  | 38.82%
| B3 |  | Axle Counter Installation |  | 69.83% | 52.13% | NO REF DWG EXISTS | B3-565
|  |  | JB Installation |  | 73.75%
|  |  | Line Cable Installation |  | 86.48%
|  |  | Express Cable Installation |  | 0.9729%
|  |  | Pre-Operation Testing |  | 29.59%
65384.6 | B3 |  | Axle Counter Installation |  | 73.63% | 47.42% |  | B3-654
|  |  | JB Installation |  | 22.1%
|  |  | Line Cable Installation |  | 4.385%
|  |  | Express Cable Installation |  | 56.11%
|  |  | Pre-Operation Testing |  | 80.87%
66073.4 | B3 |  | Axle Counter Installation |  | 42.55% | 77.73% |  | B3-661
|  |  | JB Installation |  | 94.24%
|  |  | Line Cable Installation |  | 74.31%
|  |  | Express Cable Installation |  | 83.71%
|  |  | Pre-Operation Testing |  | 93.84%
| B3 |  | Axle Counter Installation |  | 65.57% | 54.37% | NO REF DWG EXISTS | B3-689
|  |  | JB Installation |  | 52.22%
|  |  | Line Cable Installation |  | 87.44%
|  |  | Express Cable Installation |  | 10.39%
|  |  | Pre-Operation Testing |  | 56.26%
| B3 |  | Axle Counter Installation |  | 50.98% | 53.18% | NO REF DWG EXISTS | B3-690
|  |  | JB Installation |  | 76.05%
|  |  | Line Cable Installation |  | 73.27%
|  |  | Express Cable Installation |  | 40.73%
|  |  | Pre-Operation Testing |  | 24.89%
| B3 |  | Axle Counter Installation |  | 26.89% | 45.62% | NO REF DWG EXISTS | B3-691
|  |  | JB Installation |  | 94.71%
|  |  | Line Cable Installation |  | 34.83%
|  |  | Express Cable Installation |  | 16.42%
|  |  | Pre-Operation Testing |  | 55.23%
| B3 |  | Axle Counter Installation |  | 37.71% | 42.92% | NO REF DWG EXISTS | B3-692
|  |  | JB Installation |  | 9.283%
|  |  | Line Cable Installation |  | 19.52%
|  |  | Express Cable Installation |  | 81.76%
|  |  | Pre-Operation Testing |  | 66.36%
| B3 |  | Axle Counter Installation |  | 98.76% | 53.76% | NO REF DWG EXISTS | B3-693
|  |  | JB Installation |  | 60.28%
|  |  | Line Cable Installation |  | 57.03%
|  |  | Express Cable Installation |  | 5.831%
|  |  | Pre-Operation Testing |  | 46.89%
| B3 |  | Axle Counter Installation |  | 36.08% | 59.23% | NO REF DWG EXISTS | B3-694
|  |  | JB Installation |  | 66.63%
|  |  | Line Cable Installation |  | 78.73%
|  |  | Express Cable Installation |  | 47.51%
|  |  | Pre-Operation Testing |  | 67.18%
| B3 |  | Axle Counter Installation |  | 80% | 41.01% | NO REF DWG EXISTS | B3-695
|  |  | JB Installation |  | 51.48%
|  |  | Line Cable Installation |  | 23.92%
|  |  | Express Cable Installation |  | 49.35%
|  |  | Pre-Operation Testing |  | 0.2739%
| B3 |  | Axle Counter Installation |  | 54.82% | 36.08% | NO REF DWG EXISTS | B3-696
|  |  | JB Installation |  | 13.11%
|  |  | Line Cable Installation |  | 33.6%
|  |  | Express Cable Installation |  | 11.68%
|  |  | Pre-Operation Testing |  | 67.16%
75405 | B3 |  | Axle Counter Installation |  | 40.75% | 54.9% |  | B3-754
|  |  | JB Installation |  | 47.03%
|  |  | Line Cable Installation |  | 76.52%
|  |  | Express Cable Installation |  | 33.06%
|  |  | Pre-Operation Testing |  | 77.15%
| B3 |  | Axle Counter Installation |  | 21.35% | 60.9% | NO REF DWG EXISTS | B3-755
|  |  | JB Installation |  | 69.64%
|  |  | Line Cable Installation |  | 70.55%
|  |  | Express Cable Installation |  | 69.72%
|  |  | Pre-Operation Testing |  | 73.26%
75405 | B3 |  | Axle Counter Installation |  | 28.16% | 58.98% |  | B3-756
|  |  | JB Installation |  | 10.34%
|  |  | Line Cable Installation |  | 87.26%
|  |  | Express Cable Installation |  | 94%
|  |  | Pre-Operation Testing |  | 75.16%
76383 | B3 |  | Axle Counter Installation |  | 17.88% | 42.53% |  | B3-764
|  |  | JB Installation |  | 15.62%
|  |  | Line Cable Installation |  | 27.37%
|  |  | Express Cable Installation |  | 68.52%
|  |  | Pre-Operation Testing |  | 83.23%
76920 | B3 |  | Axle Counter Installation |  | 52% | 69.53% |  | B3-769
|  |  | JB Installation |  | 92.22%
|  |  | Line Cable Installation |  | 76.37%
|  |  | Express Cable Installation |  | 40.04%
|  |  | Pre-Operation Testing |  | 87.05%
| B4 |  | Axle Counter Installation |  | 63.93% | 45.95% | REF DWG EXISTS, NO STATIONINGS SHOWN | B4-547
|  |  | JB Installation |  | 17.36%
|  |  | Line Cable Installation |  | 5.626%
|  |  | Express Cable Installation |  | 43.76%
|  |  | Pre-Operation Testing |  | 99.07%
| B4 |  | Axle Counter Installation |  | 68.35% | 71.06% | REF DWG EXISTS, NO STATIONINGS SHOWN | B4-551
|  |  | JB Installation |  | 78.87%
|  |  | Line Cable Installation |  | 63.23%
|  |  | Express Cable Installation |  | 90.98%
|  |  | Pre-Operation Testing |  | 53.85%
| B4 |  | Axle Counter Installation |  | 63.21% | 55.64% | NO REF DWG EXISTS, AWAITING RESPONSE FROM THALES ON WHETHER THIS AXC WILL BE INSTALLED | B4-554A, B4-554B
|  |  | JB Installation |  | 85.64%
|  |  | Line Cable Installation |  | 54.07%
|  |  | Express Cable Installation |  | 13.61%
|  |  | Pre-Operation Testing |  | 61.69%
55533 | B4 |  | Axle Counter Installation |  | 65.65% | 59.92% |  | B4-555
|  |  | JB Installation |  | 70.32%
|  |  | Line Cable Installation |  | 91.17%
|  |  | Express Cable Installation |  | 34.59%
|  |  | Pre-Operation Testing |  | 37.86%
55685 | B4 |  | Axle Counter Installation |  | 93.15% | 62.03% |  | B4-556
|  |  | JB Installation |  | 56.28%
|  |  | Line Cable Installation |  | 17.04%
|  |  | Express Cable Installation |  | 80.05%
|  |  | Pre-Operation Testing |  | 63.64%
56396.5 | B4 |  | Axle Counter Installation |  | 1.725% | 34.62% |  | B4-564
|  |  | JB Installation |  | 7.297%
|  |  | Line Cable Installation |  | 62.31%
|  |  | Express Cable Installation |  | 95.32%
|  |  | Pre-Operation Testing |  | 6.461%

## SIGNALS
Stationing | Track No | Signal Type | Location | Activity | Date | Progress | General Progress | Notes
74076 | E1 | APPROACH |  | Signal Installation |  | 54.86% | 47.85% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 41.67%
|  |  |  | Stop Machine Installation |  | 1.532%
|  |  |  | Line Cable Installation |  | 77.66%
|  |  |  | Breakdown Testing |  | 14.67%
|  |  |  | Pre-Operation Testing |  | 90.52%
98643 | E1 | HOME |  | Signal Installation |  | 54.51% | 38.12% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 3.337%
|  |  |  | Stop Machine Installation |  | 27.15%
|  |  |  | Line Cable Installation |  | 14.29%
|  |  |  | Breakdown Testing |  | 11.9%
|  |  |  | Pre-Operation Testing |  | 82.74%
98903 | E1 | HOME |  | Signal Installation |  | 87.24% | 55.8% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 52.8%
|  |  |  | Stop Machine Installation |  | 82.24%
|  |  |  | Line Cable Installation |  | 37.39%
|  |  |  | Breakdown Testing |  | 23.36%
|  |  |  | Pre-Operation Testing |  | 48.76%
100068 | E1 | HOME |  | Signal Installation |  | 14.56% | 39.05% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 61%
|  |  |  | Stop Machine Installation |  | 31.26%
|  |  |  | Line Cable Installation |  | 87.17%
|  |  |  | Breakdown Testing |  | 16.46%
|  |  |  | Pre-Operation Testing |  | 45.81%
106031 | E1 | APPROACH |  | Signal Installation |  | 3.884% | 42.21% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 66.54%
|  |  |  | Stop Machine Installation |  | 33.29%
|  |  |  | Line Cable Installation |  | 35.41%
|  |  |  | Breakdown Testing |  | 81.62%
|  |  |  | Pre-Operation Testing |  | 56.84%
113852 | E1 | HOME |  | Signal Installation |  | 84.57% | 59.5% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 44.96%
|  |  |  | Stop Machine Installation |  | 21.8%
|  |  |  | Line Cable Installation |  | 88.59%
|  |  |  | Breakdown Testing |  | 85.65%
|  |  |  | Pre-Operation Testing |  | 16.88%
114110 | E1 | HOME |  | Signal Installation |  | 32.39% | 44.79% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 15.07%
|  |  |  | Stop Machine Installation |  | 4.266%
|  |  |  | Line Cable Installation |  | 47.92%
|  |  |  | Breakdown Testing |  | 81.87%
|  |  |  | Pre-Operation Testing |  | 57.5%
114869 | E1 | HOME |  | Signal Installation |  | 2.225% | 61.72% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 70.7%
|  |  |  | Stop Machine Installation |  | 89.55%
|  |  |  | Line Cable Installation |  | 85.95%
|  |  |  | Breakdown Testing |  | 84.96%
|  |  |  | Pre-Operation Testing |  | 45.94%
119024 | E1 | APPROACH |  | Signal Installation |  | 80.61% | 38.29% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 63.43%
|  |  |  | Stop Machine Installation |  | 17.84%
|  |  |  | Line Cable Installation |  | 48.64%
|  |  |  | Breakdown Testing |  | 5.623%
|  |  |  | Pre-Operation Testing |  | 38.76%
119485 | E1 | APPROACH |  | Signal Installation |  | 87.86% | 79.66% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 15.19%
|  |  |  | Stop Machine Installation |  | 65.19%
|  |  |  | Line Cable Installation |  | 74.39%
|  |  |  | Breakdown Testing |  | 94.26%
|  |  |  | Pre-Operation Testing |  | 76.59%
| E1 | APPROACH |  | Signal Installation |  | 40.67% | 52.06% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 21.89%
|  |  |  | Stop Machine Installation |  | 60.38%
|  |  |  | Line Cable Installation |  | 19%
|  |  |  | Breakdown Testing |  | 57.61%
|  |  |  | Pre-Operation Testing |  | 82.66%
121810 | E1 | HOME |  | Signal Installation |  | 57.33% | 37.55% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 61.66%
|  |  |  | Stop Machine Installation |  | 33.73%
|  |  |  | Line Cable Installation |  | 32.94%
|  |  |  | Breakdown Testing |  | 34.05%
|  |  |  | Pre-Operation Testing |  | 29.71%
122198 | E1 | HOME |  | Signal Installation |  | 46.7% | 54.56% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 18.38%
|  |  |  | Stop Machine Installation |  | 93.12%
|  |  |  | Line Cable Installation |  | 37.35%
|  |  |  | Breakdown Testing |  | 93.82%
|  |  |  | Pre-Operation Testing |  | 1.839%
122570 | E1 | HOME |  | Signal Installation |  | 64.67% | 33.25% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 16.77%
|  |  |  | Stop Machine Installation |  | 78.69%
|  |  |  | Line Cable Installation |  | 16.65%
|  |  |  | Breakdown Testing |  | 0.8955%
|  |  |  | Pre-Operation Testing |  | 5.341%
122987 | E1 | HOME |  | Signal Installation |  | 97.34% | 47.25% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 92.79%
|  |  |  | Stop Machine Installation |  | 50.4%
|  |  |  | Line Cable Installation |  | 6.484%
|  |  |  | Breakdown Testing |  | 36%
|  |  |  | Pre-Operation Testing |  | 46.04%
123669 | D1 | HOME |  | Signal Installation |  | 63.11% | 40.34% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 60.43%
|  |  |  | Stop Machine Installation |  | 1.501%
|  |  |  | Line Cable Installation |  | 34.41%
|  |  |  | Breakdown Testing |  | 90.01%
|  |  |  | Pre-Operation Testing |  | 12.69%
73318 | E2 | APPROACH |  | Signal Installation |  | 80.6% | 68.08% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 6.187%
|  |  |  | Stop Machine Installation |  | 19.46%
|  |  |  | Line Cable Installation |  | 88.11%
|  |  |  | Breakdown Testing |  | 92.23%
|  |  |  | Pre-Operation Testing |  | 60.01%
98565 | E2 | HOME |  | Signal Installation |  | 62.34% | 49.15% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 48.83%
|  |  |  | Stop Machine Installation |  | 36.11%
|  |  |  | Line Cable Installation |  | 8.635%
|  |  |  | Breakdown Testing |  | 87.03%
|  |  |  | Pre-Operation Testing |  | 51.63%
99593 | E2 | HOME |  | Signal Installation |  | 95.66% | 52.2% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 74.13%
|  |  |  | Stop Machine Installation |  | 21.59%
|  |  |  | Line Cable Installation |  | 0.7986%
|  |  |  | Breakdown Testing |  | 50.71%
|  |  |  | Pre-Operation Testing |  | 92.25%
99970 | E2 | HOME |  | Signal Installation |  | 55.38% | 52.05% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 39.19%
|  |  |  | Stop Machine Installation |  | 83.38%
|  |  |  | Line Cable Installation |  | 27%
|  |  |  | Breakdown Testing |  | 18.85%
|  |  |  | Pre-Operation Testing |  | 75.64%
106749 | E2 | APPROACH |  | Signal Installation |  | 46.51% | 53.32% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 4.347%
|  |  |  | Stop Machine Installation |  | 41.23%
|  |  |  | Line Cable Installation |  | 82.91%
|  |  |  | Breakdown Testing |  | 23.05%
|  |  |  | Pre-Operation Testing |  | 72.92%
112529 | E2 | HOME |  | Signal Installation |  | 80.01% | 62.4% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 75.65%
|  |  |  | Stop Machine Installation |  | 81.71%
|  |  |  | Line Cable Installation |  | 42.97%
|  |  |  | Breakdown Testing |  | 44.47%
|  |  |  | Pre-Operation Testing |  | 62.86%
113850 | E2 | HOME |  | Signal Installation |  | 42.12% | 39.66% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 88.95%
|  |  |  | Stop Machine Installation |  | 33.64%
|  |  |  | Line Cable Installation |  | 13.54%
|  |  |  | Breakdown Testing |  | 14.41%
|  |  |  | Pre-Operation Testing |  | 94.58%
118065 | E2 | APPROACH |  | Signal Installation |  | 69.65% | 78.74% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 56.88%
|  |  |  | Stop Machine Installation |  | 83.05%
|  |  |  | Line Cable Installation |  | 62.86%
|  |  |  | Breakdown Testing |  | 87.81%
|  |  |  | Pre-Operation Testing |  | 90.32%
119215 | E2 | APPROACH |  | Signal Installation |  | 65.31% | 57.52% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 76.75%
|  |  |  | Stop Machine Installation |  | 84%
|  |  |  | Line Cable Installation |  | 58.22%
|  |  |  | Breakdown Testing |  | 51.36%
|  |  |  | Pre-Operation Testing |  | 28.69%
123687 | D2 | HOME |  | Signal Installation |  | 79.12% | 56.54% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 54.8%
|  |  |  | Stop Machine Installation |  | 53.47%
|  |  |  | Line Cable Installation |  | 48.55%
|  |  |  | Breakdown Testing |  | 72.1%
|  |  |  | Pre-Operation Testing |  | 29.47%
124043 | D2 | HOME |  | Signal Installation |  | 44.59% | 38.53% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 47.33%
|  |  |  | Stop Machine Installation |  | 11.88%
|  |  |  | Line Cable Installation |  | 37.71%
|  |  |  | Breakdown Testing |  | 96.71%
|  |  |  | Pre-Operation Testing |  | 1.762%
99806 | E3 | HOME |  | Signal Installation |  | 57.96% | 53.92% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 51.46%
|  |  |  | Stop Machine Installation |  | 33.87%
|  |  |  | Line Cable Installation |  | 61.45%
|  |  |  | Breakdown Testing |  | 52.1%
|  |  |  | Pre-Operation Testing |  | 64.21%
100019 | E3 | HOME |  | Signal Installation |  | 96.42% | 63.38% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 91.48%
|  |  |  | Stop Machine Installation |  | 59.72%
|  |  |  | Line Cable Installation |  | 75.91%
|  |  |  | Breakdown Testing |  | 30.89%
|  |  |  | Pre-Operation Testing |  | 53.96%
99592 | E4 | HOME |  | Signal Installation |  | 0.6689% | 41.58% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 20.53%
|  |  |  | Stop Machine Installation |  | 58.02%
|  |  |  | Line Cable Installation |  | 75.6%
|  |  |  | Breakdown Testing |  | 40.07%
|  |  |  | Pre-Operation Testing |  | 33.52%
122071 | E5 | HOME |  | Signal Installation |  | 50.68% | 71.84% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 50.41%
|  |  |  | Stop Machine Installation |  | 84.67%
|  |  |  | Line Cable Installation |  | 64.48%
|  |  |  | Breakdown Testing |  | 80.25%
|  |  |  | Pre-Operation Testing |  | 79.11%
122687 | E5 | HOME |  | Signal Installation |  | 83.25% | 58.18% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 17.31%
|  |  |  | Stop Machine Installation |  | 57.99%
|  |  |  | Line Cable Installation |  | 65.31%
|  |  |  | Breakdown Testing |  | 1.346%
|  |  |  | Pre-Operation Testing |  | 83.03%

## SWITCH
Name | Stationing | Track No | Location | Activity | Date | Progress | General Progress | Notes
B331 | 76395 | B1 |  | Switch Machine Installation |  | 47.36% | 63.84%
|  |  |  | Switch JB Installation |  | 74.41%
|  |  |  | Switch Cable Installation |  | 48.97%
|  |  |  | Line Cable Installation |  | 67.24%
|  |  |  | Breakdown Testing |  | 84.13%
|  |  |  | Pre-Operation Testing |  | 71.51%
B325 | 76395 | E2 |  | Switch Machine Installation |  | 15.47% | 48.75%
|  |  |  | Switch JB Installation |  | 84.29%
|  |  |  | Switch Cable Installation |  | 68.62%
|  |  |  | Line Cable Installation |  | 60.87%
|  |  |  | Breakdown Testing |  | 21.34%
|  |  |  | Pre-Operation Testing |  | 77.44%
633A | 99999 | E1 |  | Switch Machine Installation |  | 14.07% | 48.66%
|  |  |  | Switch JB Installation |  | 38.65%
|  |  |  | Switch Cable Installation |  | 95.29%
|  |  |  | Line Cable Installation |  | 81.44%
|  |  |  | Breakdown Testing |  | 39.99%
|  |  |  | Pre-Operation Testing |  | 12.53%
633B | 98900 | E3-4 |  | Switch Machine Installation |  | 83.14% | 43.61%
|  |  |  | Switch JB Installation |  | 17.04%
|  |  |  | Switch Cable Installation |  | 30.57%
|  |  |  | Line Cable Installation |  | 17.95%
|  |  |  | Breakdown Testing |  | 24.46%
|  |  |  | Pre-Operation Testing |  | 61.91%
625A | 98808 | E3-4 |  | Switch Machine Installation |  | 61.97% | 58.67%
|  |  |  | Switch JB Installation |  | 19%
|  |  |  | Switch Cable Installation |  | 45.46%
|  |  |  | Line Cable Installation |  | 62.86%
|  |  |  | Breakdown Testing |  | 50.74%
|  |  |  | Pre-Operation Testing |  | 72.33%
625B | 99949 | E2 |  | Switch Machine Installation |  | 8.266% | 23.91%
|  |  |  | Switch JB Installation |  | 93.77%
|  |  |  | Switch Cable Installation |  | 8.706%
|  |  |  | Line Cable Installation |  | 20.98%
|  |  |  | Breakdown Testing |  | 22.41%
|  |  |  | Pre-Operation Testing |  | 59.19%
663 | 99628 | E3-4 |  | Switch Machine Installation |  | 38.57% | 45.45%
|  |  |  | Switch JB Installation |  | 92.43%
|  |  |  | Switch Cable Installation |  | 2.828%
|  |  |  | Line Cable Installation |  | 55.89%
|  |  |  | Breakdown Testing |  | 52.73%
|  |  |  | Pre-Operation Testing |  | 77.22%
673A | 99999 | E1 |  | Switch Machine Installation |  | 12.37% | 41.19%
|  |  |  | Switch JB Installation |  | 80.62%
|  |  |  | Switch Cable Installation |  | 64.05%
|  |  |  | Line Cable Installation |  | 37.34%
|  |  |  | Breakdown Testing |  | 86.62%
|  |  |  | Pre-Operation Testing |  | 5.574%
673B | 99826 | E3 |  | Switch Machine Installation |  | 7.14% | 46.58%
|  |  |  | Switch JB Installation |  | 43.5%
|  |  |  | Switch Cable Installation |  | 94.83%
|  |  |  | Line Cable Installation |  | 79.39%
|  |  |  | Breakdown Testing |  | 48.93%
|  |  |  | Pre-Operation Testing |  | 2.62%
651A | 99761 | E4 |  | Switch Machine Installation |  | 82.96% | 57.29%
|  |  |  | Switch JB Installation |  | 83.77%
|  |  |  | Switch Cable Installation |  | 89.7%
|  |  |  | Line Cable Installation |  | 50.21%
|  |  |  | Breakdown Testing |  | 7.176%
|  |  |  | Pre-Operation Testing |  | 56.42%
651B | 99949 | E2 |  | Switch Machine Installation |  | 71.9% | 43.49%
|  |  |  | Switch JB Installation |  | 65.72%
|  |  |  | Switch Cable Installation |  | 34.18%
|  |  |  | Line Cable Installation |  | 52.16%
|  |  |  | Breakdown Testing |  | 41.72%
|  |  |  | Pre-Operation Testing |  | 17.47%
757A | 113880 | E1 |  | Switch Machine Installation |  | 8.384% | 46.46%
|  |  |  | Switch JB Installation |  | 86.78%
|  |  |  | Switch Cable Installation |  | 40.82%
|  |  |  | Line Cable Installation |  | 9.212%
|  |  |  | Breakdown Testing |  | 81.07%
|  |  |  | Pre-Operation Testing |  | 92.83%
757B | 114010 | E2 |  | Switch Machine Installation |  | 90.08% | 61.52%
|  |  |  | Switch JB Installation |  | 97.08%
|  |  |  | Switch Cable Installation |  | 59.07%
|  |  |  | Line Cable Installation |  | 59.68%
|  |  |  | Breakdown Testing |  | 6.865%
|  |  |  | Pre-Operation Testing |  | 91.89%
753A | 114010 | E1 |  | Switch Machine Installation |  | 24.43% | 50.91%
|  |  |  | Switch JB Installation |  | 74.09%
|  |  |  | Switch Cable Installation |  | 75.97%
|  |  |  | Line Cable Installation |  | 86.55%
|  |  |  | Breakdown Testing |  | 46.51%
|  |  |  | Pre-Operation Testing |  | 21.07%
753B | 113880 | E2 |  | Switch Machine Installation |  | 67.13% | 67.1%
|  |  |  | Switch JB Installation |  | 38.66%
|  |  |  | Switch Cable Installation |  | 78.05%
|  |  |  | Line Cable Installation |  | 85.93%
|  |  |  | Breakdown Testing |  | 43.83%
|  |  |  | Pre-Operation Testing |  | 60.55%
825 |  | E1 |  | Switch Machine Installation |  | 30.09% | 48.17% | Stationing missing
|  |  |  | Switch JB Installation |  | 81.09%
|  |  |  | Switch Cable Installation |  | 38.57%
|  |  |  | Line Cable Installation |  | 43.17%
|  |  |  | Breakdown Testing |  | 81.39%
|  |  |  | Pre-Operation Testing |  | 47.63%
815A | 121995 | E5 |  | Switch Machine Installation |  | 4.253% | 40.67%
|  |  |  | Switch JB Installation |  | 63.92%
|  |  |  | Switch Cable Installation |  | 34.57%
|  |  |  | Line Cable Installation |  | 28.64%
|  |  |  | Breakdown Testing |  | 65.33%
|  |  |  | Pre-Operation Testing |  | 70.57%
815B | 121831 | E2 |  | Switch Machine Installation |  | 30.66% | 56.22%
|  |  |  | Switch JB Installation |  | 13.09%
|  |  |  | Switch Cable Installation |  | 86.45%
|  |  |  | Line Cable Installation |  | 79.34%
|  |  |  | Breakdown Testing |  | 16.5%
|  |  |  | Pre-Operation Testing |  | 68.15%
851B | 122757 | E5 |  | Switch Machine Installation |  | 61.01% | 55.02%
|  |  |  | Switch JB Installation |  | 0.2887%
|  |  |  | Switch Cable Installation |  | 36.53%
|  |  |  | Line Cable Installation |  | 68.29%
|  |  |  | Breakdown Testing |  | 93.36%
|  |  |  | Pre-Operation Testing |  | 15.91%
851A | 122923 | E1 |  | Switch Machine Installation |  | 56.47% | 55.74%
|  |  |  | Switch JB Installation |  | 82.5%
|  |  |  | Switch Cable Installation |  | 61.58%
|  |  |  | Line Cable Installation |  | 13.5%
|  |  |  | Breakdown Testing |  | 93.56%
|  |  |  | Pre-Operation Testing |  | 53.61%
841 | 122923 | E2 |  | Switch Machine Installation |  | 52.14% | 61.98%
|  |  |  | Switch JB Installation |  | 70.97%
|  |  |  | Switch Cable Installation |  | 99.32%
|  |  |  | Line Cable Installation |  | 96.65%
|  |  |  | Breakdown Testing |  | 34.75%
|  |  |  | Pre-Operation Testing |  | 27.04%
753B | 113880 | E2 |  | Switch Machine Installation |  | 55.62% | 61.27%
|  |  |  | Switch JB Installation |  | 55.91%
|  |  |  | Switch Cable Installation |  | 78.06%
|  |  |  | Line Cable Installation |  | 59.07%
|  |  |  | Breakdown Testing |  | 46.56%
|  |  |  | Pre-Operation Testing |  | 67.06%

## WRU
Stationing | Track No | Location | Activity | Date | Progress | General Progress | Notes
54000 | B1 |  | Radio Unit Installation |  | 86% | 48.5% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 12.21%
|  |  | Fiber Box Installation |  | 54.16%
|  |  | Antenna Installation |  | 39.86%
|  |  | Antenna Cable Installation |  | 74.88%
|  |  | Splitter Installation |  | 31.63%
|  |  | Fiber Cable Splicing |  | 28.17%
|  |  | Fiber Testing |  | 33.63%
|  |  | Power Testing |  | 75.93%
54000 | B3 |  | Radio Unit Installation |  | 37.63% | 51.11% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 27.04%
|  |  | Fiber Box Installation |  | 85.9%
|  |  | Antenna Installation |  | 87.67%
|  |  | Antenna Cable Installation |  | 23.1%
|  |  | Splitter Installation |  | 51.8%
|  |  | Fiber Cable Splicing |  | 69.88%
|  |  | Fiber Testing |  | 32.32%
|  |  | Power Testing |  | 44.68%
54000 | B4 |  | Radio Unit Installation |  | 47.2% | 48.36% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 17.89%
|  |  | Fiber Box Installation |  | 28.78%
|  |  | Antenna Installation |  | 72.75%
|  |  | Antenna Cable Installation |  | 50.59%
|  |  | Splitter Installation |  | 89.84%
|  |  | Fiber Cable Splicing |  | 71.11%
|  |  | Fiber Testing |  | 26.52%
|  |  | Power Testing |  | 30.58%
54000 | B2 |  | Radio Unit Installation |  | 16.92% | 56.58% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 75.75%
|  |  | Fiber Box Installation |  | 99.27%
|  |  | Antenna Installation |  | 67.34%
|  |  | Antenna Cable Installation |  | 75.21%
|  |  | Splitter Installation |  | 33.83%
|  |  | Fiber Cable Splicing |  | 3.324%
|  |  | Fiber Testing |  | 43.17%
|  |  | Power Testing |  | 94.43%
54000 | B5 |  | Radio Unit Installation |  | 69.69% | 61.6% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 62.81%
|  |  | Fiber Box Installation |  | 62.17%
|  |  | Antenna Installation |  | 46.76%
|  |  | Antenna Cable Installation |  | 46.9%
|  |  | Splitter Installation |  | 97.86%
|  |  | Fiber Cable Splicing |  | 86.54%
|  |  | Fiber Testing |  | 70.2%
|  |  | Power Testing |  | 11.48%
55500 | B2 |  | Radio Unit Installation |  | 43.3% | 72.27% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 94.36%
|  |  | Fiber Box Installation |  | 62.84%
|  |  | Antenna Installation |  | 88.11%
|  |  | Antenna Cable Installation |  | 11.24%
|  |  | Splitter Installation |  | 80.99%
|  |  | Fiber Cable Splicing |  | 89.92%
|  |  | Fiber Testing |  | 86.41%
|  |  | Power Testing |  | 93.27%
55500 | B1 |  | Radio Unit Installation |  | 77.71% | 61.09% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 19.15%
|  |  | Fiber Box Installation |  | 65.77%
|  |  | Antenna Installation |  | 48.16%
|  |  | Antenna Cable Installation |  | 52.29%
|  |  | Splitter Installation |  | 79.76%
|  |  | Fiber Cable Splicing |  | 68.99%
|  |  | Fiber Testing |  | 63.77%
|  |  | Power Testing |  | 74.26%
56300 | B1 |  | Radio Unit Installation |  | 73.75% | 56.17% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 2.408%
|  |  | Fiber Box Installation |  | 97.72%
|  |  | Antenna Installation |  | 34.46%
|  |  | Antenna Cable Installation |  | 48.14%
|  |  | Splitter Installation |  | 95.56%
|  |  | Fiber Cable Splicing |  | 23.45%
|  |  | Fiber Testing |  | 70.94%
|  |  | Power Testing |  | 59.09%
56500 | B1 |  | Radio Unit Installation |  | 50.74% | 45.26% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 38.55%
|  |  | Fiber Box Installation |  | 39.42%
|  |  | Antenna Installation |  | 2.885%
|  |  | Antenna Cable Installation |  | 48.33%
|  |  | Splitter Installation |  | 83.04%
|  |  | Fiber Cable Splicing |  | 35.75%
|  |  | Fiber Testing |  | 59.12%
|  |  | Power Testing |  | 49.5%
57200 | B1 |  | Radio Unit Installation |  | 10.63% | 41.1% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 37.66%
|  |  | Fiber Box Installation |  | 63.34%
|  |  | Antenna Installation |  | 94.19%
|  |  | Antenna Cable Installation |  | 1.953%
|  |  | Splitter Installation |  | 44.05%
|  |  | Fiber Cable Splicing |  | 17.27%
|  |  | Fiber Testing |  | 43.07%
|  |  | Power Testing |  | 57.72%
57400 | B1 |  | Radio Unit Installation |  | 56.99% | 52.51% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 3.371%
|  |  | Fiber Box Installation |  | 91.12%
|  |  | Antenna Installation |  | 39.88%
|  |  | Antenna Cable Installation |  | 12.45%
|  |  | Splitter Installation |  | 58.22%
|  |  | Fiber Cable Splicing |  | 91.94%
|  |  | Fiber Testing |  | 59.21%
|  |  | Power Testing |  | 59.43%
58300 | B1 |  | Radio Unit Installation |  | 43.48% | 44.71% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 66.88%
|  |  | Fiber Box Installation |  | 82.15%
|  |  | Antenna Installation |  | 17.32%
|  |  | Antenna Cable Installation |  | 94.57%
|  |  | Splitter Installation |  | 29.28%
|  |  | Fiber Cable Splicing |  | 2.367%
|  |  | Fiber Testing |  | 5.045%
|  |  | Power Testing |  | 61.27%
58400 | B1 |  | Radio Unit Installation |  | 99.36% | 55.84% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 1.958%
|  |  | Fiber Box Installation |  | 53.14%
|  |  | Antenna Installation |  | 18.73%
|  |  | Antenna Cable Installation |  | 71.36%
|  |  | Splitter Installation |  | 43.15%
|  |  | Fiber Cable Splicing |  | 80.96%
|  |  | Fiber Testing |  | 97.82%
|  |  | Power Testing |  | 36.06%
59400 | B1 |  | Radio Unit Installation |  | 45.53% | 43.54% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 24.92%
|  |  | Fiber Box Installation |  | 26.96%
|  |  | Antenna Installation |  | 78.68%
|  |  | Antenna Cable Installation |  | 3.385%
|  |  | Splitter Installation |  | 83.95%
|  |  | Fiber Cable Splicing |  | 90.78%
|  |  | Fiber Testing |  | 24.51%
|  |  | Power Testing |  | 13.16%
59700 | B1 |  | Radio Unit Installation |  | 52.9% | 51.45% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 45.43%
|  |  | Fiber Box Installation |  | 17.89%
|  |  | Antenna Installation |  | 57.62%
|  |  | Antenna Cable Installation |  | 53.5%
|  |  | Splitter Installation |  | 94.04%
|  |  | Fiber Cable Splicing |  | 32.04%
|  |  | Fiber Testing |  | 57.51%
|  |  | Power Testing |  | 52.16%
60500 | B1 |  | Radio Unit Installation |  | 16.96% | 44.51% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 63.37%
|  |  | Fiber Box Installation |  | 32.15%
|  |  | Antenna Installation |  | 5.731%
|  |  | Antenna Cable Installation |  | 89.23%
|  |  | Splitter Installation |  | 30.95%
|  |  | Fiber Cable Splicing |  | 23.31%
|  |  | Fiber Testing |  | 40.43%
|  |  | Power Testing |  | 98.43%
60800 | B2 |  | Radio Unit Installation |  | 26.62% | 38.01% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 39.51%
|  |  | Fiber Box Installation |  | 6.944%
|  |  | Antenna Installation |  | 81.62%
|  |  | Antenna Cable Installation |  | 4.175%
|  |  | Splitter Installation |  | 58.1%
|  |  | Fiber Cable Splicing |  | 5.796%
|  |  | Fiber Testing |  | 55.26%
|  |  | Power Testing |  | 64.04%
60800 | B1 |  | Radio Unit Installation |  | 94.13% | 47.75% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 50.09%
|  |  | Fiber Box Installation |  | 35.56%
|  |  | Antenna Installation |  | 20.38%
|  |  | Antenna Cable Installation |  | 21.58%
|  |  | Splitter Installation |  | 43.79%
|  |  | Fiber Cable Splicing |  | 83.74%
|  |  | Fiber Testing |  | 37.09%
|  |  | Power Testing |  | 43.42%
61900 | B2 |  | Radio Unit Installation |  | 39.87% | 51.81% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 32.84%
|  |  | Fiber Box Installation |  | 50.84%
|  |  | Antenna Installation |  | 52.59%
|  |  | Antenna Cable Installation |  | 94.35%
|  |  | Splitter Installation |  | 94.5%
|  |  | Fiber Cable Splicing |  | 7.857%
|  |  | Fiber Testing |  | 84.41%
|  |  | Power Testing |  | 9.032%
61900 | B1 |  | Radio Unit Installation |  | 50.5% | 51.65% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 18.06%
|  |  | Fiber Box Installation |  | 37.53%
|  |  | Antenna Installation |  | 37.38%
|  |  | Antenna Cable Installation |  | 52.9%
|  |  | Splitter Installation |  | 69.82%
|  |  | Fiber Cable Splicing |  | 42.69%
|  |  | Fiber Testing |  | 64.97%
|  |  | Power Testing |  | 91.05%
62300 | B1 |  | Radio Unit Installation |  | 89.64% | 64.15% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 27.61%
|  |  | Fiber Box Installation |  | 9.913%
|  |  | Antenna Installation |  | 75.56%
|  |  | Antenna Cable Installation |  | 97.69%
|  |  | Splitter Installation |  | 8.804%
|  |  | Fiber Cable Splicing |  | 80.73%
|  |  | Fiber Testing |  | 97.51%
|  |  | Power Testing |  | 89.86%
63200 | B1 |  | Radio Unit Installation |  | 94.42% | 73.7% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0.8349%
|  |  | Fiber Box Installation |  | 76.02%
|  |  | Antenna Installation |  | 96.92%
|  |  | Antenna Cable Installation |  | 92.05%
|  |  | Splitter Installation |  | 66.7%
|  |  | Fiber Cable Splicing |  | 42.14%
|  |  | Fiber Testing |  | 99.3%
|  |  | Power Testing |  | 94.9%
63300 | B1 |  | Radio Unit Installation |  | 62.06% | 65.14% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 57.54%
|  |  | Fiber Box Installation |  | 54.68%
|  |  | Antenna Installation |  | 70.4%
|  |  | Antenna Cable Installation |  | 97.36%
|  |  | Splitter Installation |  | 66.9%
|  |  | Fiber Cable Splicing |  | 35.97%
|  |  | Fiber Testing |  | 81.75%
|  |  | Power Testing |  | 59.64%
64200 | B1 |  | Radio Unit Installation |  | 25.47% | 35.66% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0.9779%
|  |  | Fiber Box Installation |  | 4.793%
|  |  | Antenna Installation |  | 37.51%
|  |  | Antenna Cable Installation |  | 20.44%
|  |  | Splitter Installation |  | 72.33%
|  |  | Fiber Cable Splicing |  | 13.42%
|  |  | Fiber Testing |  | 88.35%
|  |  | Power Testing |  | 57.64%
64300 | B1 |  | Radio Unit Installation |  | 9.226% | 33.54% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 48.73%
|  |  | Fiber Box Installation |  | 45.65%
|  |  | Antenna Installation |  | 93.56%
|  |  | Antenna Cable Installation |  | 23.4%
|  |  | Splitter Installation |  | 24.46%
|  |  | Fiber Cable Splicing |  | 4.508%
|  |  | Fiber Testing |  | 28.83%
|  |  | Power Testing |  | 23.47%
65200 | B1 |  | Radio Unit Installation |  | 84.5% | 54.85% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 60.44%
|  |  | Fiber Box Installation |  | 3.525%
|  |  | Antenna Installation |  | 61.67%
|  |  | Antenna Cable Installation |  | 81.12%
|  |  | Splitter Installation |  | 1.512%
|  |  | Fiber Cable Splicing |  | 47.87%
|  |  | Fiber Testing |  | 75.51%
|  |  | Power Testing |  | 77.54%
65200 | B2 |  | Radio Unit Installation |  | 5.985% | 50.31% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 38.47%
|  |  | Fiber Box Installation |  | 0.2164%
|  |  | Antenna Installation |  | 99.69%
|  |  | Antenna Cable Installation |  | 74.86%
|  |  | Splitter Installation |  | 87.62%
|  |  | Fiber Cable Splicing |  | 22.23%
|  |  | Fiber Testing |  | 78.24%
|  |  | Power Testing |  | 45.44%
66300 | B1 |  | Radio Unit Installation |  | 91.76% | 56.11% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 65.65%
|  |  | Fiber Box Installation |  | 35.48%
|  |  | Antenna Installation |  | 26.26%
|  |  | Antenna Cable Installation |  | 90.07%
|  |  | Splitter Installation |  | 75.87%
|  |  | Fiber Cable Splicing |  | 26.81%
|  |  | Fiber Testing |  | 46.49%
|  |  | Power Testing |  | 46.59%
66300 | B2 |  | Radio Unit Installation |  | 87.55% | 49.27% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 42.84%
|  |  | Fiber Box Installation |  | 24.32%
|  |  | Antenna Installation |  | 66%
|  |  | Antenna Cable Installation |  | 70.75%
|  |  | Splitter Installation |  | 51.03%
|  |  | Fiber Cable Splicing |  | 37.05%
|  |  | Fiber Testing |  | 38.87%
|  |  | Power Testing |  | 25.02%
67500 | B1 |  | Radio Unit Installation |  | 6.285% | 44.35% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 62.16%
|  |  | Fiber Box Installation |  | 79.7%
|  |  | Antenna Installation |  | 44.06%
|  |  | Antenna Cable Installation |  | 17.01%
|  |  | Splitter Installation |  | 31.59%
|  |  | Fiber Cable Splicing |  | 32.16%
|  |  | Fiber Testing |  | 49.51%
|  |  | Power Testing |  | 76.63%
67500 | B2 |  | Radio Unit Installation |  | 94.5% | 37.86% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 12.73%
|  |  | Fiber Box Installation |  | 13.69%
|  |  | Antenna Installation |  | 5.213%
|  |  | Antenna Cable Installation |  | 56.83%
|  |  | Splitter Installation |  | 7.599%
|  |  | Fiber Cable Splicing |  | 12.22%
|  |  | Fiber Testing |  | 93.93%
|  |  | Power Testing |  | 44.01%
68300 | B1 |  | Radio Unit Installation |  | 88.94% | 50.96% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 36.28%
|  |  | Fiber Box Installation |  | 24.44%
|  |  | Antenna Installation |  | 90.98%
|  |  | Antenna Cable Installation |  | 48.74%
|  |  | Splitter Installation |  | 11.2%
|  |  | Fiber Cable Splicing |  | 51.39%
|  |  | Fiber Testing |  | 87.8%
|  |  | Power Testing |  | 18.86%
68300 | B2 |  | Radio Unit Installation |  | 37.83% | 64.86% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 64.48%
|  |  | Fiber Box Installation |  | 48.45%
|  |  | Antenna Installation |  | 56.14%
|  |  | Antenna Cable Installation |  | 58.95%
|  |  | Splitter Installation |  | 87.88%
|  |  | Fiber Cable Splicing |  | 63.8%
|  |  | Fiber Testing |  | 69.53%
|  |  | Power Testing |  | 96.65%
69900 | B1 |  | Radio Unit Installation |  | 99.23% | 61.18% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 58.16%
|  |  | Fiber Box Installation |  | 42.48%
|  |  | Antenna Installation |  | 11.26%
|  |  | Antenna Cable Installation |  | 12.58%
|  |  | Splitter Installation |  | 50.7%
|  |  | Fiber Cable Splicing |  | 98.87%
|  |  | Fiber Testing |  | 85.72%
|  |  | Power Testing |  | 91.57%
71400 | B1 |  | Radio Unit Installation |  | 59.07% | 36.53% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 39.25%
|  |  | Fiber Box Installation |  | 12.9%
|  |  | Antenna Installation |  | 33.92%
|  |  | Antenna Cable Installation |  | 69.07%
|  |  | Splitter Installation |  | 28.53%
|  |  | Fiber Cable Splicing |  | 35.39%
|  |  | Fiber Testing |  | 14.54%
|  |  | Power Testing |  | 36.05%
73000 | B1 |  | Radio Unit Installation |  | 19.77% | 33.62% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 7.226%
|  |  | Fiber Box Installation |  | 10.59%
|  |  | Antenna Installation |  | 63.89%
|  |  | Antenna Cable Installation |  | 59.09%
|  |  | Splitter Installation |  | 2.613%
|  |  | Fiber Cable Splicing |  | 48.26%
|  |  | Fiber Testing |  | 54.44%
|  |  | Power Testing |  | 36.7%
73000 | B2 |  | Radio Unit Installation |  | 58.21% | 51.33% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 34.04%
|  |  | Fiber Box Installation |  | 48.9%
|  |  | Antenna Installation |  | 91.9%
|  |  | Antenna Cable Installation |  | 84.99%
|  |  | Splitter Installation |  | 20.97%
|  |  | Fiber Cable Splicing |  | 48.9%
|  |  | Fiber Testing |  | 23.27%
|  |  | Power Testing |  | 50.77%
74100 | B1 |  | Radio Unit Installation |  | 8.141% | 39.63% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0.7028%
|  |  | Fiber Box Installation |  | 69.09%
|  |  | Antenna Installation |  | 57.79%
|  |  | Antenna Cable Installation |  | 65.48%
|  |  | Splitter Installation |  | 23.59%
|  |  | Fiber Cable Splicing |  | 45.3%
|  |  | Fiber Testing |  | 37.41%
|  |  | Power Testing |  | 49.2%
75300 | B1 |  | Radio Unit Installation |  | 12.05% | 40.89% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 14.36%
|  |  | Fiber Box Installation |  | 19.75%
|  |  | Antenna Installation |  | 68.92%
|  |  | Antenna Cable Installation |  | 68.36%
|  |  | Splitter Installation |  | 12.35%
|  |  | Fiber Cable Splicing |  | 90.95%
|  |  | Fiber Testing |  | 7.583%
|  |  | Power Testing |  | 73.63%
75300 | B2 |  | Radio Unit Installation |  | 12.18% | 36.69% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 35.65%
|  |  | Fiber Box Installation |  | 15.14%
|  |  | Antenna Installation |  | 97.42%
|  |  | Antenna Cable Installation |  | 41.12%
|  |  | Splitter Installation |  | 1.08%
|  |  | Fiber Cable Splicing |  | 53.03%
|  |  | Fiber Testing |  | 28.74%
|  |  | Power Testing |  | 45.88%
88300 | E1 |  | Radio Unit Installation |  | 9.173% | 42.66% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 68.22%
|  |  | Fiber Box Installation |  | 1.297%
|  |  | Antenna Installation |  | 73.18%
|  |  | Antenna Cable Installation |  | 14.23%
|  |  | Splitter Installation |  | 33.34%
|  |  | Fiber Cable Splicing |  | 94.94%
|  |  | Fiber Testing |  | 24.09%
|  |  | Power Testing |  | 65.43%
88600 | E1 |  | Radio Unit Installation |  | 12.19% | 39.55% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 28.57%
|  |  | Fiber Box Installation |  | 41.96%
|  |  | Antenna Installation |  | 28.44%
|  |  | Antenna Cable Installation |  | 83.66%
|  |  | Splitter Installation |  | 42.82%
|  |  | Fiber Cable Splicing |  | 28.35%
|  |  | Fiber Testing |  | 15.3%
|  |  | Power Testing |  | 74.66%
90800 | E1 |  | Radio Unit Installation |  | 39.72% | 51.43% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 90.43%
|  |  | Fiber Box Installation |  | 94.39%
|  |  | Antenna Installation |  | 78.7%
|  |  | Antenna Cable Installation |  | 15.08%
|  |  | Splitter Installation |  | 74.23%
|  |  | Fiber Cable Splicing |  | 24.51%
|  |  | Fiber Testing |  | 37.11%
|  |  | Power Testing |  | 8.732%
92400 | E1 |  | Radio Unit Installation |  | 91.83% | 55.3% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 36.39%
|  |  | Fiber Box Installation |  | 98.02%
|  |  | Antenna Installation |  | 81.17%
|  |  | Antenna Cable Installation |  | 1.355%
|  |  | Splitter Installation |  | 49.18%
|  |  | Fiber Cable Splicing |  | 9.148%
|  |  | Fiber Testing |  | 69.51%
|  |  | Power Testing |  | 61.1%
93600 | E1 |  | Radio Unit Installation |  | 44.28% | 52.17% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0.1666%
|  |  | Fiber Box Installation |  | 68.59%
|  |  | Antenna Installation |  | 88.04%
|  |  | Antenna Cable Installation |  | 14.07%
|  |  | Splitter Installation |  | 48.44%
|  |  | Fiber Cable Splicing |  | 78.35%
|  |  | Fiber Testing |  | 28.88%
|  |  | Power Testing |  | 98.71%
95000 | E1 |  | Radio Unit Installation |  | 78.64% | 61.65% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 7.596%
|  |  | Fiber Box Installation |  | 85.8%
|  |  | Antenna Installation |  | 86.94%
|  |  | Antenna Cable Installation |  | 6.141%
|  |  | Splitter Installation |  | 67.49%
|  |  | Fiber Cable Splicing |  | 32.2%
|  |  | Fiber Testing |  | 91.82%
|  |  | Power Testing |  | 98.25%
96500 | E1 |  | Radio Unit Installation |  | 91.82% | 54.58% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 77.94%
|  |  | Fiber Box Installation |  | 52.4%
|  |  | Antenna Installation |  | 84.28%
|  |  | Antenna Cable Installation |  | 40.32%
|  |  | Splitter Installation |  | 38.35%
|  |  | Fiber Cable Splicing |  | 26.4%
|  |  | Fiber Testing |  | 6.704%
|  |  | Power Testing |  | 73.05%
98200 | E1 |  | Radio Unit Installation |  | 98.22% | 49.34% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 24.89%
|  |  | Fiber Box Installation |  | 2.649%
|  |  | Antenna Installation |  | 55.45%
|  |  | Antenna Cable Installation |  | 44.85%
|  |  | Splitter Installation |  | 53.02%
|  |  | Fiber Cable Splicing |  | 10.2%
|  |  | Fiber Testing |  | 68.94%
|  |  | Power Testing |  | 85.83%
99700 | E1 |  | Radio Unit Installation |  | 30.97% | 59.87% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 45.13%
|  |  | Fiber Box Installation |  | 86.75%
|  |  | Antenna Installation |  | 82.56%
|  |  | Antenna Cable Installation |  | 40.6%
|  |  | Splitter Installation |  | 96.66%
|  |  | Fiber Cable Splicing |  | 73.62%
|  |  | Fiber Testing |  | 40.37%
|  |  | Power Testing |  | 42.17%
99700 | E2 |  | Radio Unit Installation |  | 2.669% | 46.82% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 41.39%
|  |  | Fiber Box Installation |  | 18.97%
|  |  | Antenna Installation |  | 27.43%
|  |  | Antenna Cable Installation |  | 16.72%
|  |  | Splitter Installation |  | 93.05%
|  |  | Fiber Cable Splicing |  | 32.07%
|  |  | Fiber Testing |  | 97.66%
|  |  | Power Testing |  | 91.42%
100400 | E1 |  | Radio Unit Installation |  | 51.96% | 47.96% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 7.667%
|  |  | Fiber Box Installation |  | 48.17%
|  |  | Antenna Installation |  | 2.376%
|  |  | Antenna Cable Installation |  | 77.66%
|  |  | Splitter Installation |  | 90.84%
|  |  | Fiber Cable Splicing |  | 98.85%
|  |  | Fiber Testing |  | 40.18%
|  |  | Power Testing |  | 13.91%
100600 | E1 |  | Radio Unit Installation |  | 71.88% | 39.31% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 97.77%
|  |  | Fiber Box Installation |  | 63.82%
|  |  | Antenna Installation |  | 11.96%
|  |  | Antenna Cable Installation |  | 19.47%
|  |  | Splitter Installation |  | 10.7%
|  |  | Fiber Cable Splicing |  | 17.33%
|  |  | Fiber Testing |  | 58%
|  |  | Power Testing |  | 2.866%
101500 | E1 |  | Radio Unit Installation |  | 95.01% | 50.34% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 70.26%
|  |  | Fiber Box Installation |  | 29.73%
|  |  | Antenna Installation |  | 61.01%
|  |  | Antenna Cable Installation |  | 73.51%
|  |  | Splitter Installation |  | 17.27%
|  |  | Fiber Cable Splicing |  | 80.26%
|  |  | Fiber Testing |  | 4.81%
|  |  | Power Testing |  | 21.18%
102600 | E1 |  | Radio Unit Installation |  | 71.66% | 55.22% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 42.37%
|  |  | Fiber Box Installation |  | 24.97%
|  |  | Antenna Installation |  | 72.95%
|  |  | Antenna Cable Installation |  | 76.63%
|  |  | Splitter Installation |  | 47.9%
|  |  | Fiber Cable Splicing |  | 69.42%
|  |  | Fiber Testing |  | 20.53%
|  |  | Power Testing |  | 70.52%
103800 | E1 |  | Radio Unit Installation |  | 98.64% | 73.85% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 82.36%
|  |  | Fiber Box Installation |  | 54.8%
|  |  | Antenna Installation |  | 95.6%
|  |  | Antenna Cable Installation |  | 62.83%
|  |  | Splitter Installation |  | 70.96%
|  |  | Fiber Cable Splicing |  | 60.65%
|  |  | Fiber Testing |  | 47.78%
|  |  | Power Testing |  | 90.99%
104700 | E1 |  | Radio Unit Installation |  | 89.8% | 49.99% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 24.24%
|  |  | Fiber Box Installation |  | 74.66%
|  |  | Antenna Installation |  | 4.164%
|  |  | Antenna Cable Installation |  | 65.57%
|  |  | Splitter Installation |  | 65.79%
|  |  | Fiber Cable Splicing |  | 49.71%
|  |  | Fiber Testing |  | 33.97%
|  |  | Power Testing |  | 42.01%
105900 | E1 |  | Radio Unit Installation |  | 88.28% | 58.28% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 15.98%
|  |  | Fiber Box Installation |  | 72.91%
|  |  | Antenna Installation |  | 81.12%
|  |  | Antenna Cable Installation |  | 70.61%
|  |  | Splitter Installation |  | 27.23%
|  |  | Fiber Cable Splicing |  | 71.78%
|  |  | Fiber Testing |  | 64.15%
|  |  | Power Testing |  | 32.47%
106900 | E1 |  | Radio Unit Installation |  | 11.46% | 51.11% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 86.94%
|  |  | Fiber Box Installation |  | 51.24%
|  |  | Antenna Installation |  | 49.97%
|  |  | Antenna Cable Installation |  | 13.62%
|  |  | Splitter Installation |  | 97.97%
|  |  | Fiber Cable Splicing |  | 81.73%
|  |  | Fiber Testing |  | 15.16%
|  |  | Power Testing |  | 51.9%
108300 | E1 |  | Radio Unit Installation |  | 25.36% | 52.28% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 1.969%
|  |  | Fiber Box Installation |  | 66.76%
|  |  | Antenna Installation |  | 49.85%
|  |  | Antenna Cable Installation |  | 99.44%
|  |  | Splitter Installation |  | 98.45%
|  |  | Fiber Cable Splicing |  | 0.1249%
|  |  | Fiber Testing |  | 66.94%
|  |  | Power Testing |  | 61.58%
109900 | E1 |  | Radio Unit Installation |  | 59.75% | 44.8% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 89.79%
|  |  | Fiber Box Installation |  | 0.2967%
|  |  | Antenna Installation |  | 72.51%
|  |  | Antenna Cable Installation |  | 47.47%
|  |  | Splitter Installation |  | 64.76%
|  |  | Fiber Cable Splicing |  | 29.76%
|  |  | Fiber Testing |  | 2.907%
|  |  | Power Testing |  | 35.94%
111100 | E1 |  | Radio Unit Installation |  | 58.61% | 56.95% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 77.67%
|  |  | Fiber Box Installation |  | 10.64%
|  |  | Antenna Installation |  | 49.21%
|  |  | Antenna Cable Installation |  | 11.39%
|  |  | Splitter Installation |  | 77.31%
|  |  | Fiber Cable Splicing |  | 92.39%
|  |  | Fiber Testing |  | 70.95%
|  |  | Power Testing |  | 64.42%
112200 | E1 |  | Radio Unit Installation |  | 33.59% | 52.21% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 5.359%
|  |  | Fiber Box Installation |  | 54.49%
|  |  | Antenna Installation |  | 38.87%
|  |  | Antenna Cable Installation |  | 46.5%
|  |  | Splitter Installation |  | 79.23%
|  |  | Fiber Cable Splicing |  | 73.25%
|  |  | Fiber Testing |  | 40.77%
|  |  | Power Testing |  | 97.83%
113000 | E1 |  | Radio Unit Installation |  | 14.11% | 57.14% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 76.73%
|  |  | Fiber Box Installation |  | 89.86%
|  |  | Antenna Installation |  | 86.75%
|  |  | Antenna Cable Installation |  | 73.85%
|  |  | Splitter Installation |  | 56.38%
|  |  | Fiber Cable Splicing |  | 4.28%
|  |  | Fiber Testing |  | 39.95%
|  |  | Power Testing |  | 72.35%
114300 | E1 |  | Radio Unit Installation |  | 28.13% | 63.24% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 66.98%
|  |  | Fiber Box Installation |  | 48.77%
|  |  | Antenna Installation |  | 79.49%
|  |  | Antenna Cable Installation |  | 82.62%
|  |  | Splitter Installation |  | 56.18%
|  |  | Fiber Cable Splicing |  | 62.93%
|  |  | Fiber Testing |  | 89.68%
|  |  | Power Testing |  | 54.41%
115500 | E1 |  | Radio Unit Installation |  | 56.62% | 61.19% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 83.44%
|  |  | Fiber Box Installation |  | 82.35%
|  |  | Antenna Installation |  | 63.7%
|  |  | Antenna Cable Installation |  | 32.61%
|  |  | Splitter Installation |  | 46.83%
|  |  | Fiber Cable Splicing |  | 78.09%
|  |  | Fiber Testing |  | 39.71%
|  |  | Power Testing |  | 67.36%
116900 | E1 |  | Radio Unit Installation |  | 36.54% | 33.67% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 46.77%
|  |  | Fiber Box Installation |  | 33.76%
|  |  | Antenna Installation |  | 34.2%
|  |  | Antenna Cable Installation |  | 23.24%
|  |  | Splitter Installation |  | 54.48%
|  |  | Fiber Cable Splicing |  | 3.508%
|  |  | Fiber Testing |  | 5.829%
|  |  | Power Testing |  | 64.72%
118300 | E1 |  | Radio Unit Installation |  | 5.607% | 49.3% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 82.7%
|  |  | Fiber Box Installation |  | 86.47%
|  |  | Antenna Installation |  | 32%
|  |  | Antenna Cable Installation |  | 67.99%
|  |  | Splitter Installation |  | 86.67%
|  |  | Fiber Cable Splicing |  | 25.83%
|  |  | Fiber Testing |  | 22%
|  |  | Power Testing |  | 34.44%
118300 | E2 |  | Radio Unit Installation |  | 17.5% | 38.35% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 56.19%
|  |  | Fiber Box Installation |  | 95.57%
|  |  | Antenna Installation |  | 9.225%
|  |  | Antenna Cable Installation |  | 19.87%
|  |  | Splitter Installation |  | 14.65%
|  |  | Fiber Cable Splicing |  | 57.71%
|  |  | Fiber Testing |  | 40.43%
|  |  | Power Testing |  | 34.04%
119500 | E1 |  | Radio Unit Installation |  | 91.81% | 68.4% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 31.24%
|  |  | Fiber Box Installation |  | 42.15%
|  |  | Antenna Installation |  | 75.89%
|  |  | Antenna Cable Installation |  | 89.94%
|  |  | Splitter Installation |  | 63.86%
|  |  | Fiber Cable Splicing |  | 89.64%
|  |  | Fiber Testing |  | 61.82%
|  |  | Power Testing |  | 69.24%
119500 | E2 |  | Radio Unit Installation |  | 71.87% | 45.76% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 32.21%
|  |  | Fiber Box Installation |  | 63.29%
|  |  | Antenna Installation |  | 31.61%
|  |  | Antenna Cable Installation |  | 55.74%
|  |  | Splitter Installation |  | 71.93%
|  |  | Fiber Cable Splicing |  | 2.896%
|  |  | Fiber Testing |  | 4.308%
|  |  | Power Testing |  | 77.95%
120800 | E1 |  | Radio Unit Installation |  | 69.46% | 52.35% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 36.84%
|  |  | Fiber Box Installation |  | 12.48%
|  |  | Antenna Installation |  | 94.23%
|  |  | Antenna Cable Installation |  | 56.31%
|  |  | Splitter Installation |  | 12.69%
|  |  | Fiber Cable Splicing |  | 51.74%
|  |  | Fiber Testing |  | 69.9%
|  |  | Power Testing |  | 67.53%
120800 | E2 |  | Radio Unit Installation |  | 79.33% | 59.33% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 79.14%
|  |  | Fiber Box Installation |  | 70.27%
|  |  | Antenna Installation |  | 9.912%
|  |  | Antenna Cable Installation |  | 88.62%
|  |  | Splitter Installation |  | 68.92%
|  |  | Fiber Cable Splicing |  | 98.84%
|  |  | Fiber Testing |  | 22.31%
|  |  | Power Testing |  | 16.59%
121900 | E1 |  | Radio Unit Installation |  | 8.561% | 40% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 46.2%
|  |  | Fiber Box Installation |  | 6.335%
|  |  | Antenna Installation |  | 62.2%
|  |  | Antenna Cable Installation |  | 3.78%
|  |  | Splitter Installation |  | 82.18%
|  |  | Fiber Cable Splicing |  | 69.66%
|  |  | Fiber Testing |  | 62.88%
|  |  | Power Testing |  | 18.2%
122800 | E1 |  | Radio Unit Installation |  | 43.09% | 64.76% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 87.17%
|  |  | Fiber Box Installation |  | 67.78%
|  |  | Antenna Installation |  | 84.5%
|  |  | Antenna Cable Installation |  | 74.47%
|  |  | Splitter Installation |  | 83.12%
|  |  | Fiber Cable Splicing |  | 21.07%
|  |  | Fiber Testing |  | 50.99%
|  |  | Power Testing |  | 70.67%
123900 | D1 |  | Radio Unit Installation |  | 38.1% | 54.33% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 80.8%
|  |  | Fiber Box Installation |  | 35.08%
|  |  | Antenna Installation |  | 12.37%
|  |  | Antenna Cable Installation |  | 86.9%
|  |  | Splitter Installation |  | 48.61%
|  |  | Fiber Cable Splicing |  | 76.16%
|  |  | Fiber Testing |  | 88.69%
|  |  | Power Testing |  | 22.26%
124900 | D1 |  | Radio Unit Installation |  | 1.075% | 38.03% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 33.55%
|  |  | Fiber Box Installation |  | 69.98%
|  |  | Antenna Installation |  | 11.66%
|  |  | Antenna Cable Installation |  | 87.44%
|  |  | Splitter Installation |  | 7.695%
|  |  | Fiber Cable Splicing |  | 75.45%
|  |  | Fiber Testing |  | 14.1%
|  |  | Power Testing |  | 41.31%
125900 | D1 |  | Radio Unit Installation |  | 75.96% | 40.16% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 12.75%
|  |  | Fiber Box Installation |  | 39.52%
|  |  | Antenna Installation |  | 7.046%
|  |  | Antenna Cable Installation |  | 16.38%
|  |  | Splitter Installation |  | 96.17%
|  |  | Fiber Cable Splicing |  | 49.42%
|  |  | Fiber Testing |  | 30.41%
|  |  | Power Testing |  | 33.81%
123900 | D2 |  | Radio Unit Installation |  | 93.33% | 35.5% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 32.39%
|  |  | Fiber Box Installation |  | 6.577%
|  |  | Antenna Installation |  | 0.3712%
|  |  | Antenna Cable Installation |  | 59.52%
|  |  | Splitter Installation |  | 21.81%
|  |  | Fiber Cable Splicing |  | 65.16%
|  |  | Fiber Testing |  | 20.83%
|  |  | Power Testing |  | 19.53%
124900 | D2 |  | Radio Unit Installation |  | 93.97% | 26.87% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 1.092%
|  |  | Fiber Box Installation |  | 16.81%
|  |  | Antenna Installation |  | 30.77%
|  |  | Antenna Cable Installation |  | 6.198%
|  |  | Splitter Installation |  | 32.77%
|  |  | Fiber Cable Splicing |  | 7.797%
|  |  | Fiber Testing |  | 28.82%
|  |  | Power Testing |  | 23.62%
125900 | D2 |  | Radio Unit Installation |  | 82.19% | 42.64% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 69.3%
|  |  | Fiber Box Installation |  | 40.51%
|  |  | Antenna Installation |  | 12%
|  |  | Antenna Cable Installation |  | 21.9%
|  |  | Splitter Installation |  | 12.42%
|  |  | Fiber Cable Splicing |  | 76.66%
|  |  | Fiber Testing |  | 49.97%
|  |  | Power Testing |  | 18.78%

## Z-CASE
Stationing | Track No | Location | Activity | Date | Progress | General Progress | Notes
|  |  | CASE Install |  | 77.33% |  | Z-CASE IS BY E1-986 (Z)
|  |  | Cable Connection/Termination |  | 90.41%
|  |  | Pre-Op testing |  | 60.45%
|  |  | CASE Install |  | 58.42% |  | Z-CASE IS BY E1-1006 (Z)
|  |  | Cable Connection/Termination |  | 55.14%
|  |  | Pre-Op testing |  | 83.28%
|  |  | CASE Install |  | 38.67% |  | Z-CASE IS BY E1-1030 (Z)
|  |  | Cable Connection/Termination |  | 23.31%
|  |  | Pre-Op testing |  | 77.4%
|  |  | CASE Install |  | 91.74% |  | Z-CASE IS BY E1-1068 (Z)
|  |  | Cable Connection/Termination |  | 44.82%
|  |  | Pre-Op testing |  | 50.49%
115725 | E1 |  | CASE Install |  | 50.1% |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
|  |  | Cable Connection/Termination |  | 63.02%
|  |  | Pre-Op testing |  | 94.34%
121810 | E1 | 21S-COU | CASE Install |  | 47.81% |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
|  |  | Cable Connection/Termination |  | 80.03%
|  |  | Pre-Op testing |  | 46.12%
| E1 |  | CASE Install |  | 94.7% |  | Z-CASE IS BY E1-1229 (Z)
|  |  | Cable Connection/Termination |  | 70.25%
|  |  | Pre-Op testing |  | 37.69%
| E1 |  | CASE Install |  | 14.03% |  | Z-CASE IS BY E1-1230 (Z)
|  |  | Cable Connection/Termination |  | 80.03%
|  |  | Pre-Op testing |  | 36.97%
98565 | E2 |  | CASE Install |  | 89.95% |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
|  |  | Cable Connection/Termination |  | 23.28%
|  |  | Pre-Op testing |  | 32.54%
114869 | E2 |  | CASE Install |  | 14.87% |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
|  |  | Cable Connection/Termination |  | 82.69%
|  |  | Pre-Op testing |  | 31.67%
| E2 |  | CASE Install |  | 32.54% |  | Z-CASE IS BY E2-1230(Z)
|  |  | Cable Connection/Termination |  | 19.03%
|  |  | Pre-Op testing |  | 38.01%
122071 | E5 |  | CASE Install |  | 40.86% |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
|  |  | Cable Connection/Termination |  | 26.95%
|  |  | Pre-Op testing |  | 9.22%
122687 | E5 |  | CASE Install |  | 45.7% |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
|  |  | Cable Connection/Termination |  | 96.86%
|  |  | Pre-Op testing |  | 92.08%

## TOPB
Stationing | Track No | Location | Activity | Date | Progress | General Progress | Notes
121810 | E1 |  | TOPB Install |  | 0.4921% |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
|  |  | Cable Connection/Termination |  | 69.9%
|  |  | Pre-Op testing |  | 66.22%
122987 | E1 |  | TOPB Install |  | 62.52% |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
|  |  | Cable Connection/Termination |  | 10.17%
|  |  | Pre-Op testing |  | 53.19%
|  |  | TOPB Install |  | 82.94% |  | TOPB @ ~D1-1239
|  |  | Cable Connection/Termination |  | 9.068%
|  |  | Pre-Op testing |  | 5.454%
121809 | E2 |  | TOPB Install |  | 11.31% |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
|  |  | Cable Connection/Termination |  | 7.842%
|  |  | Pre-Op testing |  | 0.436%
122970 | E2 |  | TOPB Install |  | 77.26% |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
|  |  | Cable Connection/Termination |  | 76.11%
|  |  | Pre-Op testing |  | 91.91%
124043 | D2 |  | TOPB Install |  | 91.83% |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
|  |  | Cable Connection/Termination |  | 62.08%
|  |  | Pre-Op testing |  | 46.38%

## Report Screenshot
Tasks | Total Quantity | Installed/Tested Quantity
Acceptance Test (Ea) | 29 | 3
Antenna Cable (ft) | 61885 | 58432
Brackets (Ea) | 12147 | 11856
Coax Cable (Ea) | 59 | 59
Insertion Loss (Segment) (ft) | 47445 | 43615
Removals (ft) | 30946 | 2380
Coupler Plates | 27 | 27
DC Resistance (Segment) | 47410 | 43580
Megger (Segment) | 47445 | 43615
VSWR (Segment) | 47445 | 43615
End-To-End | 47445 | 33565
Heat Map Test | 47445 | 29175
Coverage Test/Survey | 47445 | 3160
Megger Coax Cable (Reel) | 4000 | 4000
Megger Antenna Cable (Reel) | 80000 | 80000
Megger 1/2in Cable (Reel) | 100 | 100
DC Resistance Coax Cable (Reel) | 4000 | 4000
DC Resistance Antenna Cable (Reel) | 80000 | 80000
DC Resistance 1/2in Cable (Reel) | 100 | 100

## Dashboard
RADIO INSTALLATION DASHBOARD
OVERALL TASK COMPLETION (ALL TRACKS)
TASK PERCENT COMPLETION (PER TRACK)
OVERALL INSTALLATION PROGRESS PER TRACK SECTION
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.