## Reference
Track No. | Column Side | Activities | Bracket Type | Station | Track Stationing | Tunnel | Description | Track Stationing | Notes
B1 | W | Steel Messenger Supports | 1 | Church Avenue | 556+96 to 563+56 | CHU-FOR | Church Ave to Fort Hamilton | 563+56 to 584+88
B2 | E | Messenger Clamps | 2 | Fort Hamilton Parkway | 584+88 to 591+90 | FOR-15S | Fort Hamilton to 15th Street | 591+90 to 625+70
B3 | W | Messenger Wire Pull | 3 | 15th Street Prospect Park | 625+70 to 632+30 | 15S-7AV | 15th Street to 7th Avenue | 632+30 to 653+96
B4 | E | Messenger Wire Tension | 4 | 7th Avenue | 653+96 to 660+56 | 7AV-4TH | 7th Avenue to 4th & 9th Street | 660+56-683+83
E1 | W | Cable Pull | 4A | 4th & 9th Street | 683+83 to 690+91 | 4TH-SMI | 4th & 9th Street to Smith & 9th Street | 690+91 to 705+11
E2 | E | Messenger Straps | 5 | Smith & 9th Street | 705+11 to 712+32 | SMI-CAR | Smith & 9th Street to Carroll Street | 712+32 to 732+89
E3 |  | 15inch CMRS |  | Carroll Street | 732+39 to 738+99 | CAR-BER | Carroll Street to Bergen Street | 738+99 to 756+82
E4 |  | 24inch CMRS |  | Bergen Street | 756+82 to 763+42 | BER-HOY | Bergen Street to Hoyt Schermerhorn | 763+42 to 761+84 | track goes from 768+XX to 693+95
E5 |  | Column mount CMRS |  | Hoyt Schermerhorn | 761+84 to 768+87 | HOY-FUL | Hoyt Schermerhorn to Fulton | 768+87 to 740+30
|  | Station Brackets |  | Fulton Street | 740+30 to 733+70 | FUL-CLI | Fulton to Clinton Washington | 733+70 to 951+82 | track goes from 733+15 to 934+96
Location |  | Grounding |  | Clinton Washington Avenue | 951+82 to 958+42 | CLI-CLA | Clinton Washington to Classon | 958+42 to 970+82
Church Avenue |  | Obstruction Brackets |  | Classon Avenue | 970+82 to 977+42 | CLA-BED | Classon to Bedford Nostand | 977+42 to 989+22
CHU-FOR |  | Cable Pull |  | Bedford Nostrand Avenue | 989+22 to 995+82 | BED-MYR | Bedford Nostrand to Myrtle Willoughby | 995+82 to 1017+47
Fort Hamilton Parkway |  | Cable Tray Brackets |  | Myrtle Willoughby Ave | 1017+47 to 1024+52 | MYR-FLU | Myrtle Willoughby to Flushing Avenue | 1024+52 to 1039+42
FOR-15S |  | Installing Tray |  | Flushing Avenue Station | 1039+42 to 1046+20 | FLU-BRO | Flushing Avenue to Broadway | 1046+20 to 1060+52
15th Street Prospect Park |  | Core Drilling |  | Broadway | 1060+52 to 1067+12 | BRO-MET | Broadway to Metropolitan | 1067+12 to 1132+45
15S-7AV |  | Cable Pull |  | Metropolitan Avenue | 1132+45 to 1139+50 | MET-NAS | Metropolitan to Nassau | 1139+50 to 1131+52
7th Avenue |  | Arch Bar Installation |  | Nassau Avenue | 1131+52 to 1138+32 | NAS-GRE | Nassau to Greenpoint | 1138+32 to 1157+00
7AV-4TH |  |  |  | Greenpoint Avenue | 1157+00 to 1164+32 | GRE-21S | Greenpoint to 21 St | 1164+32 to 1211+33
4th & 9th Street |  |  |  | 21 St Station | 1211+33 to 1217+92 | 21S-COU | 21 St to Court Square | 1217+92 to 1229+23
4TH-SMI |  |  |  | Court Square | 1229+23 to 1236+66 | COU-QUE | Court Square to Queens Plaza | 1236+66 to 1250+65
Smith & 9th Street |  |  |  | Queens Plaza | 1250+65 to 1257+27
SMI-CAR
Carroll Street |  |  |  | Signal Types
CAR-BER |  |  |  | HOME
Bergen Street* |  |  |  | APPROACH
BER-HOY |  |  |  | BUMPER
Hoyt Schermerhorn |  |  |  | REV. HOME
HOY-FUL |  |  |  | REV. APPROACH
Fulton Street
FUL-CLI
Clinton Washington Avenue
CLI-CLA
Classon Avenue
CLA-BED
Bedford Nostrand Avenue
BED-MYR
Myrtle Willoughby Ave
MYR-FLU
Flushing Avenue Station
FLU-BRO
Broadway
BRO-MET
Metropolitan Avenue
MET-NAS
Nassau Avenue
NAS-GRE
Greenpoint Avenue
GRE-21S
21 St Station
21S-COU
Court Square
COU-QUE
Queens Plaza

## Work Sheet (hidden)
OVERALL INSTALLATION PER AREA
Status | Count
Not Started | #REF!
In Progress | #REF!
Completed | #REF!
Remaining | #REF!
Total Tasks | #REF!
Completed Sections | #REF!
Remaining Sections | #REF!

## Ref Activity Bar (hidden)
RADIO INSTALLATION DASHBOARD
TRACK | C3/C4
TASK | COMPLETION PROGRESS
Removals | 12.5%
Grand Total | 12.5%

## Ref Progress per Activity (hidden)
TASK | Acceptance Test
|  | Not Started | 0 | Completed Sections | 13.04%
TRACK | Average of PROGRESS | In Progress | 0 | Remaining Sections | 86.96%
C1 | 16.67% | Completed | 0
C2 | 16.67%
C3 | 0%
C3/C4 | 14.29%
C4 | 0%
C5 | 0%
C6 | 0%
Grand Total | 13.04%

## CMRS
Start | Finish | Track No | Location | Activity | Total Quantity | QTY Installed | Date | Progress | General Progress | Notes | Notes
124510 | 124500 | D1 | COU-QUE | Steel Mess Supports | 442 | 249 |  | 0.56335 | 0.60267
|  |  |  | Messenger Clamps | 951 | 804 |  | 0.84543
|  |  |  | Messenger Wire Pull | 114 | 40 |  | 0.35088
|  |  |  | Messenger Wire Tension | 318 | 82 |  | 0.25786
|  |  |  | # Cables Pulled | 122 | 101 |  | 0.82787
|  |  |  | Messenger Straps | 218 | 168 |  | 0.77064
124500 | 124320 | D1 | COU-QUE | Steel Mess Supports | 32 | 25 |  | 0.78125 | 0.45727
|  |  |  | Messenger Clamps | 459 | 185 |  | 0.40305
|  |  |  | Messenger Wire Pull | 860 | 121 |  | 0.1407
|  |  |  | Messenger Wire Tension | 621 | 203 |  | 0.32689
|  |  |  | # Cables Pulled | 525 | 109 |  | 0.20762
|  |  |  | Messenger Straps | 371 | 328 |  | 0.8841
124320 | 124100 | D1 | COU-QUE | Steel Mess Supports | 423 | 260 |  | 0.61466 | 0.48608
|  |  |  | Messenger Clamps | 882 | 695 |  | 0.78798
|  |  |  | Messenger Wire Pull | 52 | 24 |  | 0.46154
|  |  |  | Messenger Wire Tension | 825 | 6 |  | 0.0072727
|  |  |  | # Cables Pulled | 512 | 146 |  | 0.28516
|  |  |  | Messenger Straps | 608 | 462 |  | 0.75987
124100 | 123970 | D1 | COU-QUE | Steel Mess Supports | 589 | 148 |  | 0.25127 | 0.47862
|  |  |  | Messenger Clamps | 39 | 11 |  | 0.28205
|  |  |  | Messenger Wire Pull | 229 | 206 |  | 0.89956
|  |  |  | Messenger Wire Tension | 337 | 80 |  | 0.23739
|  |  |  | # Cables Pulled | 835 | 433 |  | 0.51856
|  |  |  | Messenger Straps | 946 | 646 |  | 0.68288
123970 | 123930 | D1 | COU-QUE | 15" CMRS Install | 378 | 6 |  | 0.015873 | 0.39672
|  |  |  | Column Clamp | 699 | 118 |  | 0.16881
|  |  |  | Station Brackets | 164 | 162 |  | 0.9878
|  |  |  | Grounding | 236 | 158 |  | 0.66949
|  |  |  | Obstruction Brackets | 64 | 4 |  | 0.0625
|  |  |  | # Cables Pulled | 269 | 128 |  | 0.47584
123930 | 123715 | D1 | COU-QUE | 15" CMRS Install | 765 | 484 |  | 0.63268 | 0.41555
|  |  |  | Column Clamp | 833 | 289 |  | 0.34694
|  |  |  | Station Brackets | 818 | 5 |  | 0.0061125
|  |  |  | Grounding | 434 | 21 |  | 0.048387
|  |  |  | Obstruction Brackets | 944 | 883 |  | 0.93538
|  |  |  | # Cables Pulled | 105 | 55 |  | 0.52381
|  | D1 | COU-QUE | Crossover (Arch Bar Installation) | 102 | 70 |  | 0.68627
122975 | 122827 | E1 | 21S-COU | Steel Mess Supports | 727 | 710 |  | 0.97662 | 0.5126
|  |  |  | Messenger Clamps | 428 | 25 |  | 0.058411
|  |  |  | Messenger Wire Pull | 305 | 210 |  | 0.68852
|  |  |  | Messenger Wire Tension | 748 | 270 |  | 0.36096
|  |  |  | # Cables Pulled | 208 | 117 |  | 0.5625
|  |  |  | Messenger Straps | 462 | 198 |  | 0.42857
122827 | 122250 | E1 | 21S-COU | 24" CMRS Install | 148 | 27 |  | 0.18243 | 0.3933
|  |  |  | Column Clamp | 950 | 933 |  | 0.98211
|  |  |  | Station Brackets | 992 | 94 |  | 0.094758
|  |  |  | Grounding | 642 | 154 |  | 0.23988
|  |  |  | Obstruction Brackets | 513 | 76 |  | 0.14815
|  |  |  | # Cables Pulled | 393 | 280 |  | 0.71247
122250 | 121833 | E1 | 21S-COU | Steel Mess Supports | 31 | 31 |  | 1 | 0.77785
|  |  |  | Messenger Clamps | 614 | 426 |  | 0.69381
|  |  |  | Messenger Wire Pull | 219 | 195 |  | 0.89041
|  |  |  | Messenger Wire Tension | 658 | 480 |  | 0.72948
|  |  |  | # Cables Pulled | 386 | 313 |  | 0.81088
|  |  |  | Messenger Straps | 400 | 217 |  | 0.5425
121833 | 121030 | E1 | 21 STREET | Steel Mess Supports | 147 | 89 |  | 0.60544 | 0.66167
|  |  |  | Messenger Clamps | 93 | 53 |  | 0.56989
|  |  |  | Messenger Wire Pull | 82 | 80 |  | 0.97561
|  |  |  | Messenger Wire Tension | 624 | 485 |  | 0.77724
|  |  |  | # Cables Pulled | 486 | 206 |  | 0.42387
|  |  |  | Messenger Straps | 712 | 440 |  | 0.61798
121030 | 117010 | E1 | GRE-21S | 15" CMRS Install | 220 | 74 |  | 0.33636 | 0.57314
|  |  |  | Column Clamp | 215 | 57 |  | 0.26512
|  |  |  | Station Brackets | 561 | 211 |  | 0.37611
|  |  |  | Grounding | 549 | 518 |  | 0.94353
|  |  |  | Obstruction Brackets | 505 | 430 |  | 0.85149
|  |  |  | # Cables Pulled | 803 | 535 |  | 0.66625
117010 | 116810 | E1 | GRE-21S | 15" CMRS Install | 880 | 248 |  | 0.28182 | 0.46531
|  |  |  | Column Clamp | 745 | 725 |  | 0.97315
|  |  |  | Station Brackets | 156 | 58 |  | 0.37179
|  |  |  | Grounding | 610 | 149 |  | 0.24426
|  |  |  | Obstruction Brackets | 438 | 111 |  | 0.25342
|  |  |  | # Cables Pulled | 896 | 598 |  | 0.66741
116810 | 116471 | E1 | GRE-21S | 15" CMRS Install | 423 | 80 |  | 0.18913 | 0.43688
|  |  |  | Column Clamp | 795 | 686 |  | 0.86289
|  |  |  | Station Brackets | 846 | 287 |  | 0.33924
|  |  |  | Grounding | 827 | 35 |  | 0.042322
|  |  |  | Obstruction Brackets | 874 | 517 |  | 0.59153
|  |  |  | # Cables Pulled | 156 | 93 |  | 0.59615
116471 | 115694 | E1 | GREENPOINT | 24" CMRS Install | 671 | 581 |  | 0.86587 | 0.50629
|  |  |  | Column Clamp | 302 | 260 |  | 0.86093
|  |  |  | Station Brackets | 595 | 181 |  | 0.3042
|  |  |  | Grounding | 710 | 637 |  | 0.89718
|  |  |  | Obstruction Brackets | 942 | 7 |  | 0.007431
|  |  |  | # Cables Pulled | 617 | 63 |  | 0.10211
115694 | 115628 | E1 | NAS-GRE | 24" CMRS Install | 926 | 813 |  | 0.87797 | 0.63405
|  |  |  | Column Clamp | 621 | 532 |  | 0.85668
|  |  |  | Station Brackets | 802 | 289 |  | 0.36035
|  |  |  | Grounding | 478 | 163 |  | 0.341
|  |  |  | Obstruction Brackets | 226 | 190 |  | 0.84071
|  |  |  | # Cables Pulled | 671 | 354 |  | 0.52757
115628 | 114897 | E1 | NAS-GRE | 24" CMRS Install | 950 | 783 |  | 0.82421 | 0.73145
|  |  |  | Column Clamp | 482 | 390 |  | 0.80913
|  |  |  | Station Brackets | 471 | 164 |  | 0.3482
|  |  |  | Grounding | 201 | 185 |  | 0.9204
|  |  |  | Obstruction Brackets | 544 | 428 |  | 0.78676
|  |  |  | # Cables Pulled | 130 | 91 |  | 0.7
114897 | 114719 | E1 | NAS-GRE | Steel Mess Supports | 893 | 128 |  | 0.14334 | 0.70635
|  |  |  | Messenger Clamps | 985 | 359 |  | 0.36447
|  |  |  | Messenger Wire Pull | 841 | 768 |  | 0.9132
|  |  |  | Messenger Wire Tension | 750 | 714 |  | 0.952
|  |  |  | # Cables Pulled | 376 | 326 |  | 0.86702
|  |  |  | Messenger Straps | 516 | 515 |  | 0.99806
114719 | 114040 | E1 | NAS-GRE | 24" CMRS Install | 499 | 487 |  | 0.97595 | 0.77083
|  |  |  | Column Clamp | 369 | 280 |  | 0.75881
|  |  |  | Station Brackets | 721 | 279 |  | 0.38696
|  |  |  | Grounding | 307 | 234 |  | 0.76221
|  |  |  | Obstruction Brackets | 701 | 646 |  | 0.92154
|  |  |  | # Cables Pulled | 770 | 631 |  | 0.81948
114040 | 113815 | E1 | NAS-GRE | Steel Mess Supports | 219 | 67 |  | 0.30594 | 0.6501
|  |  |  | Messenger Clamps | 564 | 512 |  | 0.9078
|  |  |  | Messenger Wire Pull | 772 | 150 |  | 0.1943
|  |  |  | Messenger Wire Tension | 321 | 298 |  | 0.92835
|  |  |  | # Cables Pulled | 538 | 524 |  | 0.97398
|  |  |  | Messenger Straps | 776 | 458 |  | 0.59021
113815 | 113019 | E1 | NASSAU | 24" CMRS Install | 277 | 109 |  | 0.3935 | 0.29894 |  | weight: 6.7 lb/ft
|  |  |  | Column Clamp | 125 | 50 |  | 0.4
|  |  |  | Station Brackets | 301 | 50 |  | 0.16611
|  |  |  | Grounding | 898 | 248 |  | 0.27617
|  |  |  | Obstruction Brackets | 534 | 78 |  | 0.14607
|  |  |  | # Cables Pulled | 17 | 7 |  | 0.41176
|  | E1 | NASSAU | 24" CMRS Install | 491 | 3 |  | 0.00611 | 0.35717
|  |  |  | Column Clamp | 53 | 10 |  | 0.18868
|  |  |  | Station Brackets | 803 | 386 |  | 0.4807
|  |  |  | Grounding | 149 | 63 |  | 0.42282
|  |  |  | Obstruction Brackets | 705 | 82 |  | 0.11631
|  |  |  | # Cables Pulled | 419 | 389 |  | 0.9284
113019 | 112700 | E1 | MET-NAS | 24" CMRS Install | 611 | 140 |  | 0.22913 | 0.6241
|  |  |  | Column Clamp | 339 | 272 |  | 0.80236
|  |  |  | Station Brackets | 492 | 450 |  | 0.91463
|  |  |  | Grounding | 403 | 354 |  | 0.87841
|  |  |  | Obstruction Brackets | 732 | 582 |  | 0.79508
|  |  |  | # Cables Pulled | 472 | 59 |  | 0.125
112700 | 110878 | E1 | MET-NAS | 15" CMRS Install | 417 | 76 |  | 0.18225 | 0.46388
|  |  |  | Column Clamp | 483 | 121 |  | 0.25052
|  |  |  | Station Brackets | 404 | 249 |  | 0.61634
|  |  |  | Grounding | 370 | 256 |  | 0.69189
|  |  |  | Obstruction Brackets | 188 | 182 |  | 0.96809
|  |  |  | # Cables Pulled | 997 | 74 |  | 0.074223
110878 | 110793 | E1 | MET-NAS | 15" CMRS Install | 352 | 55 |  | 0.15625 | 0.32777
|  |  |  | Column Clamp | 659 | 587 |  | 0.89074
|  |  |  | Station Brackets | 239 | 81 |  | 0.33891
|  |  |  | Grounding | 354 | 4 |  | 0.011299
|  |  |  | Obstruction Brackets | 760 | 83 |  | 0.10921
|  |  |  | # Cables Pulled | 804 | 370 |  | 0.4602
110793 | 109251 | E1 | MET-NAS | 15" CMRS Install | 654 | 423 |  | 0.64679 | 0.60467
|  |  |  | Column Clamp | 662 | 243 |  | 0.36707
|  |  |  | Station Brackets | 208 | 60 |  | 0.28846
|  |  |  | Grounding | 255 | 211 |  | 0.82745
|  |  |  | Obstruction Brackets | 632 | 513 |  | 0.81171
|  |  |  | # Cables Pulled | 638 | 438 |  | 0.68652
109251 | 109133 | E1 | MET-NAS | 15" CMRS Install | 220 | 166 |  | 0.75455 | 0.54332
|  |  |  | Column Clamp | 873 | 702 |  | 0.80412
|  |  |  | Station Brackets | 676 | 89 |  | 0.13166
|  |  |  | Grounding | 84 | 68 |  | 0.80952
|  |  |  | Obstruction Brackets | 658 | 119 |  | 0.18085
|  |  |  | # Cables Pulled | 808 | 468 |  | 0.57921
109133 | 108356 | E1 | METROPOLITAN | 15" CMRS Install | 332 | 74 |  | 0.22289 | 0.47779
|  |  |  | Column Clamp | 511 | 488 |  | 0.95499
|  |  |  | Station Brackets | 127 | 86 |  | 0.67717
|  |  |  | Grounding | 178 | 43 |  | 0.24157
|  |  |  | Obstruction Brackets | 757 | 519 |  | 0.6856
|  |  |  | # Cables Pulled | 71 | 6 |  | 0.084507
108356 | 107651 | E1 | BRO-MET | 15" CMRS Install | 471 | 272 |  | 0.57749 | 0.64901
|  |  |  | Column Clamp | 217 | 173 |  | 0.79724
|  |  |  | Station Brackets | 863 | 311 |  | 0.36037
|  |  |  | Grounding | 674 | 592 |  | 0.87834
|  |  |  | Obstruction Brackets | 466 | 296 |  | 0.63519
|  |  |  | # Cables Pulled | 110 | 71 |  | 0.64545
107651 | 107611 | E1 | BRO-MET | 15" CMRS Install | 16 | 13 |  | 0.8125 | 0.67515 |  | Check endings for specific stationings (DWG 48012-17N-006.0) where cable switches from 1 to 2
|  |  |  | Column Clamp | 743 | 490 |  | 0.65949
|  |  |  | Station Brackets | 214 | 177 |  | 0.8271
|  |  |  | Grounding | 589 | 259 |  | 0.43973
|  |  |  | Obstruction Brackets | 217 | 84 |  | 0.3871
|  |  |  | # Cables Pulled | 40 | 37 |  | 0.925
107611 | 106768 | E1 | BRO-MET | 15" CMRS Install | 131 | 60 |  | 0.45802 | 0.58495
|  |  |  | Column Clamp | 931 | 613 |  | 0.65843
|  |  |  | Station Brackets | 567 | 372 |  | 0.65608
|  |  |  | Grounding | 729 | 628 |  | 0.86145
|  |  |  | Obstruction Brackets | 540 | 425 |  | 0.78704
|  |  |  | # Cables Pulled | 688 | 61 |  | 0.088663
106768 | 106702 | E1 | BRO-MET | 15" CMRS Install | 198 | 72 |  | 0.36364 | 0.46889
|  |  |  | Column Clamp | 935 | 72 |  | 0.077005
|  |  |  | Station Brackets | 249 | 109 |  | 0.43775
|  |  |  | Grounding | 96 | 3 |  | 0.03125
|  |  |  | Obstruction Brackets | 404 | 386 |  | 0.95545
|  |  |  | # Cables Pulled | 116 | 110 |  | 0.94828
106702 | 106011 | E1 | BROADWAY | 15" CMRS Install | 131 | 45 |  | 0.34351 | 0.44319
|  |  |  | Column Clamp | 593 | 505 |  | 0.8516
|  |  |  | Station Brackets | 808 | 299 |  | 0.37005
|  |  |  | Grounding | 713 | 345 |  | 0.48387
|  |  |  | Obstruction Brackets | 621 | 6 |  | 0.0096618
|  |  |  | # Cables Pulled | 926 | 556 |  | 0.60043
|  | E1 | BROADWAY | 15" CMRS Install | 321 | 218 |  | 0.67913 | 0.41181
|  |  |  | Column Clamp | 818 | 330 |  | 0.40342
|  |  |  | Station Brackets | 804 | 235 |  | 0.29229
|  |  |  | Grounding | 691 | 304 |  | 0.43994
|  |  |  | Obstruction Brackets | 749 | 164 |  | 0.21896
|  |  |  | # Cables Pulled | 684 | 299 |  | 0.43713
|  | E1 | BROADWAY | 15" CMRS Install | 125 | 115 |  | 0.92 | 0.79181
|  |  |  | Column Clamp | 338 | 258 |  | 0.76331
|  |  |  | Station Brackets | 409 | 345 |  | 0.84352
|  |  |  | Grounding | 933 | 623 |  | 0.66774
|  |  |  | Obstruction Brackets | 405 | 379 |  | 0.9358
|  |  |  | # Cables Pulled | 938 | 582 |  | 0.62047
106011 | 105293 | E1 | FLU-BRO | 15" CMRS Install | 22 | 14 |  | 0.63636 | 0.49427
|  |  |  | Column Clamp | 561 | 14 |  | 0.024955
|  |  |  | Station Brackets | 980 | 402 |  | 0.4102
|  |  |  | Grounding | 222 | 155 |  | 0.6982
|  |  |  | Obstruction Brackets | 307 | 250 |  | 0.81433
|  |  |  | # Cables Pulled | 650 | 248 |  | 0.38154
105293 | 104667 | E1 | FLU-BRO | 15" CMRS Install | 37 | 8 |  | 0.21622 | 0.4898
|  |  |  | Column Clamp | 910 | 660 |  | 0.72527
|  |  |  | Station Brackets | 281 | 93 |  | 0.33096
|  |  |  | Grounding | 725 | 551 |  | 0.76
|  |  |  | Obstruction Brackets | 166 | 95 |  | 0.57229
|  |  |  | # Cables Pulled | 895 | 299 |  | 0.33408
104667 | 103784 | E1 | FLUSHING | 15" CMRS Install | 682 | 22 |  | 0.032258 | 0.48251
|  |  |  | Column Clamp | 92 | 88 |  | 0.95652
|  |  |  | Station Brackets | 849 | 208 |  | 0.24499
|  |  |  | Grounding | 826 | 652 |  | 0.78935
|  |  |  | Obstruction Brackets | 744 | 218 |  | 0.29301
|  |  |  | # Cables Pulled | 19 | 11 |  | 0.57895
103784 | 103231 | E1 | MYR-FLU | 15" CMRS Install | 549 | 6 |  | 0.010929 | 0.37644
|  |  |  | Column Clamp | 31 | 3 |  | 0.096774
|  |  |  | Station Brackets | 656 | 64 |  | 0.097561
|  |  |  | Grounding | 115 | 110 |  | 0.95652
|  |  |  | Obstruction Brackets | 681 | 581 |  | 0.85316
|  |  |  | # Cables Pulled | 636 | 155 |  | 0.24371
103231 | 103165 | E1 | MYR-FLU | 15" CMRS Install | 82 | 1 |  | 0.012195 | 0.44371
|  |  |  | Column Clamp | 584 | 110 |  | 0.18836
|  |  |  | Station Brackets | 691 | 462 |  | 0.6686
|  |  |  | Grounding | 233 | 163 |  | 0.69957
|  |  |  | Obstruction Brackets | 462 | 319 |  | 0.69048
|  |  |  | # Cables Pulled | 454 | 183 |  | 0.40308
103165 | 102533 | E1 | MYR-FLU | 15" CMRS Install | 320 | 247 |  | 0.77187 | 0.64116
|  |  |  | Column Clamp | 875 | 549 |  | 0.62743
|  |  |  | Station Brackets | 240 | 175 |  | 0.72917
|  |  |  | Grounding | 408 | 112 |  | 0.27451
|  |  |  | Obstruction Brackets | 260 | 202 |  | 0.77692
|  |  |  | # Cables Pulled | 925 | 617 |  | 0.66703
102533 | 101595 | E1 | MYRTLE | 24" CMRS Install | 65 | 19 |  | 0.29231 | 0.48633
|  |  |  | Column Clamp | 620 | 320 |  | 0.51613
|  |  |  | Station Brackets | 55 | 36 |  | 0.65455
|  |  |  | Grounding | 326 | 115 |  | 0.35276
|  |  |  | Obstruction Brackets | 534 | 74 |  | 0.13858
|  |  |  | # Cables Pulled | 880 | 848 |  | 0.96364
101595 | 101558 | E1 | BED-MYR | 24" CMRS Install | 808 | 670 |  | 0.82921 | 0.45931
|  |  |  | Column Clamp | 332 | 51 |  | 0.15361
|  |  |  | Station Brackets | 956 | 107 |  | 0.11192
|  |  |  | Grounding | 536 | 501 |  | 0.9347
|  |  |  | Obstruction Brackets | 351 | 212 |  | 0.60399
|  |  |  | # Cables Pulled | 196 | 24 |  | 0.12245
101558 | 101050 | E1 | BED-MYR | 24" CMRS Install | 989 | 769 |  | 0.77755 | 0.57357
|  |  |  | Column Clamp | 708 | 220 |  | 0.31073
|  |  |  | Station Brackets | 477 | 397 |  | 0.83229
|  |  |  | Grounding | 606 | 344 |  | 0.56766
|  |  |  | Obstruction Brackets | 258 | 238 |  | 0.92248
|  |  |  | # Cables Pulled | 228 | 7 |  | 0.030702
101050 | 101015 | E1 | BED-MYR | 24" CMRS Install | 847 | 815 |  | 0.96222 | 0.58437
|  |  |  | Column Clamp | 355 | 230 |  | 0.64789
|  |  |  | Station Brackets | 688 | 192 |  | 0.27907
|  |  |  | Grounding | 532 | 157 |  | 0.29511
|  |  |  | Obstruction Brackets | 676 | 249 |  | 0.36834
|  |  |  | # Cables Pulled | 733 | 699 |  | 0.95362
101015 | 100530 | E1 | BED-MYR | 24" CMRS Install | 350 | 177 |  | 0.50571 | 0.50409
|  |  |  | Column Clamp | 478 | 164 |  | 0.3431
|  |  |  | Station Brackets | 39 | 10 |  | 0.25641
|  |  |  | Grounding | 120 | 80 |  | 0.66667
|  |  |  | Obstruction Brackets | 190 | 48 |  | 0.25263
|  |  |  | # Cables Pulled | 36 | 36 |  | 1
100530 | 100383 | E1 | BED-MYR | Steel Mess Supports | 543 | 297 |  | 0.54696 | 0.46995
|  |  |  | Messenger Clamps | 620 | 173 |  | 0.27903
|  |  |  | Messenger Wire Pull | 390 | 166 |  | 0.42564
|  |  |  | Messenger Wire Tension | 44 | 10 |  | 0.22727
|  |  |  | # Cables Pulled | 131 | 55 |  | 0.41985
|  |  |  | Messenger Straps | 506 | 466 |  | 0.92095
|  | E1 | BED-MYR | Crossover (Arch Bar Installation) | 182 | 151 |  | 0.82967
100383 | 100282 | E1 | BED-MYR | Steel Mess Supports | 213 | 28 |  | 0.13146 | 0.3363
|  |  |  | Messenger Clamps | 584 | 434 |  | 0.74315
|  |  |  | Messenger Wire Pull | 522 | 55 |  | 0.10536
|  |  |  | Messenger Wire Tension | 395 | 114 |  | 0.28861
|  |  |  | # Cables Pulled | 868 | 396 |  | 0.45622
|  |  |  | Messenger Straps | 157 | 46 |  | 0.29299
100282 | 100036 | E1 | BED-MYR | Steel Mess Supports | 697 | 270 |  | 0.38737 | 0.49558
|  |  |  | Messenger Clamps | 989 | 699 |  | 0.70677
|  |  |  | Messenger Wire Pull | 253 | 97 |  | 0.3834
|  |  |  | Messenger Wire Tension | 364 | 199 |  | 0.5467
|  |  |  | # Cables Pulled | 731 | 653 |  | 0.8933
|  |  |  | Messenger Straps | 143 | 8 |  | 0.055944
100036 | 99560 | E1 | BED-MYR | Steel Mess Supports | 855 | 143 |  | 0.16725 | 0.47465
|  |  |  | Messenger Clamps | 187 | 185 |  | 0.9893
|  |  |  | Messenger Wire Pull | 379 | 166 |  | 0.43799
|  |  |  | Messenger Wire Tension | 699 | 181 |  | 0.25894
|  |  |  | # Cables Pulled | 744 | 503 |  | 0.67608
|  |  |  | Messenger Straps | 267 | 85 |  | 0.31835
98845 | 98555 | E1 | CLA-BED | 24" CMRS Install | 732 | 198 |  | 0.27049 | 0.4437
|  |  |  | Column Clamp | 953 | 304 |  | 0.31899
|  |  |  | Station Brackets | 186 | 16 |  | 0.086022
|  |  |  | Grounding | 507 | 367 |  | 0.72387
|  |  |  | Obstruction Brackets | 382 | 248 |  | 0.64921
|  |  |  | # Cables Pulled | 132 | 81 |  | 0.61364
|  | E1 | CLA-BED | Crossover (Arch Bar Installation) | 663 | 96 |  | 0.1448
98555 | 98220 | E1 | CLA-BED | 24" CMRS Install | 710 | 546 |  | 0.76901 | 0.36415
|  |  |  | Column Clamp | 112 | 1 |  | 0.0089286
|  |  |  | Station Brackets | 264 | 0 |  | 0
|  |  |  | Grounding | 641 | 137 |  | 0.21373
|  |  |  | Obstruction Brackets | 750 | 606 |  | 0.808
|  |  |  | # Cables Pulled | 771 | 297 |  | 0.38521
98220 | 98140 | E1 | CLA-BED | 24" CMRS Install | 196 | 105 |  | 0.53571 | 0.17841
|  |  |  | Column Clamp | 750 | 292 |  | 0.38933
|  |  |  | Station Brackets | 298 | 7 |  | 0.02349
|  |  |  | Grounding | 14 | 0 |  | 0
|  |  |  | Obstruction Brackets | 903 | 85 |  | 0.094131
|  |  |  | # Cables Pulled | 432 | 12 |  | 0.027778
98140 | 97920 | E1 | CLA-BED | 24" CMRS Install | 327 | 89 |  | 0.27217 | 0.36735
|  |  |  | Column Clamp | 59 | 7 |  | 0.11864
|  |  |  | Station Brackets | 773 | 136 |  | 0.17594
|  |  |  | Grounding | 128 | 103 |  | 0.80469
|  |  |  | Obstruction Brackets | 717 | 557 |  | 0.77685
|  |  |  | # Cables Pulled | 197 | 11 |  | 0.055838
97920 | 97670 | E1 | CLA-BED | Steel Mess Supports | 759 | 743 |  | 0.97892 | 0.54629
|  |  |  | Messenger Clamps | 418 | 5 |  | 0.011962
|  |  |  | Messenger Wire Pull | 239 | 215 |  | 0.89958
|  |  |  | Messenger Wire Tension | 299 | 122 |  | 0.40803
|  |  |  | # Cables Pulled | 377 | 69 |  | 0.18302
|  |  |  | Messenger Straps | 319 | 254 |  | 0.79624
97670 | 97580 | E1 | CLASSON | 24" CMRS Install | 945 | 435 |  | 0.46032 | 0.54847
|  |  |  | Column Clamp | 233 | 22 |  | 0.094421
|  |  |  | Station Brackets | 567 | 486 |  | 0.85714
|  |  |  | Grounding | 628 | 490 |  | 0.78025
|  |  |  | Obstruction Brackets | 523 | 107 |  | 0.20459
|  |  |  | # Cables Pulled | 510 | 456 |  | 0.89412
97580 | 97230 | E1 | CLASSON | 24" CMRS Install | 474 | 37 |  | 0.078059 | 0.49345
|  |  |  | Column Clamp | 288 | 156 |  | 0.54167
|  |  |  | Station Brackets | 663 | 499 |  | 0.75264
|  |  |  | Grounding | 887 | 453 |  | 0.51071
|  |  |  | Obstruction Brackets | 636 | 411 |  | 0.64623
|  |  |  | # Cables Pulled | 153 | 66 |  | 0.43137
97230 | 96920 | E1 | CLASSON | 24" CMRS Install | 35 | 29 |  | 0.82857 | 0.43566
|  |  |  | Column Clamp | 392 | 7 |  | 0.017857
|  |  |  | Station Brackets | 724 | 138 |  | 0.19061
|  |  |  | Grounding | 586 | 484 |  | 0.82594
|  |  |  | Obstruction Brackets | 130 | 88 |  | 0.67692
|  |  |  | # Cables Pulled | 189 | 14 |  | 0.074074
96920 | 96685 | E1 | CLI-CLA | Steel Mess Supports | 993 | 213 |  | 0.2145 | 0.59544
|  |  |  | Messenger Clamps | 144 | 70 |  | 0.48611
|  |  |  | Messenger Wire Pull | 978 | 861 |  | 0.88037
|  |  |  | Messenger Wire Tension | 518 | 224 |  | 0.43243
|  |  |  | # Cables Pulled | 449 | 317 |  | 0.70601
|  |  |  | Messenger Straps | 436 | 372 |  | 0.85321
96685 | 96460 | E1 | CLI-CLA | 24" CMRS Install | 987 | 804 |  | 0.81459 | 0.54275
|  |  |  | Column Clamp | 889 | 593 |  | 0.66704
|  |  |  | Station Brackets | 578 | 107 |  | 0.18512
|  |  |  | Grounding | 892 | 498 |  | 0.5583
|  |  |  | Obstruction Brackets | 888 | 181 |  | 0.20383
|  |  |  | # Cables Pulled | 557 | 461 |  | 0.82765
96460 | 96387 | E1 | CLI-CLA | 24" CMRS Install | 878 | 94 |  | 0.10706 | 0.44107
|  |  |  | Column Clamp | 533 | 478 |  | 0.89681
|  |  |  | Station Brackets | 169 | 50 |  | 0.29586
|  |  |  | Grounding | 468 | 103 |  | 0.22009
|  |  |  | Obstruction Brackets | 951 | 429 |  | 0.4511
|  |  |  | # Cables Pulled | 903 | 610 |  | 0.67553
96387 | 96051 | E1 | CLI-CLA | 24" CMRS Install | 607 | 348 |  | 0.57331 | 0.31747
|  |  |  | Column Clamp | 410 | 165 |  | 0.40244
|  |  |  | Station Brackets | 22 | 2 |  | 0.090909
|  |  |  | Grounding | 971 | 208 |  | 0.21421
|  |  |  | Obstruction Brackets | 464 | 143 |  | 0.30819
|  |  |  | # Cables Pulled | 871 | 275 |  | 0.31573
96038 | 95998 | E1 | CLI-CLA | 24" CMRS Install | 932 | 85 |  | 0.091202 | 0.5398
|  |  |  | Column Clamp | 602 | 556 |  | 0.92359
|  |  |  | Station Brackets | 455 | 155 |  | 0.34066
|  |  |  | Grounding | 520 | 406 |  | 0.78077
|  |  |  | Obstruction Brackets | 132 | 28 |  | 0.21212
|  |  |  | # Cables Pulled | 858 | 764 |  | 0.89044
95998 | 95873 | E1 | CLI-CLA | 24" CMRS Install | 722 | 657 |  | 0.90997 | 0.5341
|  |  |  | Column Clamp | 48 | 7 |  | 0.14583
|  |  |  | Station Brackets | 951 | 912 |  | 0.95899
|  |  |  | Grounding | 93 | 57 |  | 0.6129
|  |  |  | Obstruction Brackets | 298 | 35 |  | 0.11745
|  |  |  | # Cables Pulled | 74 | 34 |  | 0.45946
95873 | 95781 | E1 | CLINTON-WASHINGTON | 24" CMRS Install | 219 | 202 |  | 0.92237 | 0.49327
|  |  |  | Column Clamp | 892 | 726 |  | 0.8139
|  |  |  | Station Brackets | 583 | 93 |  | 0.15952
|  |  |  | Grounding | 616 | 33 |  | 0.053571
|  |  |  | Obstruction Brackets | 726 | 100 |  | 0.13774
|  |  |  | # Cables Pulled | 847 | 739 |  | 0.87249
95781 | 95695 | E1 | CLINTON-WASHINGTON | 24" CMRS Install | 669 | 446 |  | 0.66667 | 0.70915
|  |  |  | Column Clamp | 979 | 859 |  | 0.87743
|  |  |  | Station Brackets | 201 | 120 |  | 0.59701
|  |  |  | Grounding | 466 | 157 |  | 0.33691
|  |  |  | Obstruction Brackets | 400 | 359 |  | 0.8975
|  |  |  | # Cables Pulled | 912 | 802 |  | 0.87939
95695 | 95544 | E1 | CLINTON-WASHINGTON | 24" CMRS Install | 392 | 80 |  | 0.20408 | 0.70819
|  |  |  | Column Clamp | 328 | 327 |  | 0.99695
|  |  |  | Station Brackets | 673 | 238 |  | 0.35364
|  |  |  | Grounding | 294 | 262 |  | 0.89116
|  |  |  | Obstruction Brackets | 755 | 717 |  | 0.94967
|  |  |  | # Cables Pulled | 205 | 175 |  | 0.85366
95544 | 95155 | E1 | CLINTON-WASHINGTON | 24" CMRS Install | 136 | 118 |  | 0.86765 | 0.61008
|  |  |  | Column Clamp | 221 | 146 |  | 0.66063
|  |  |  | Station Brackets | 546 | 338 |  | 0.61905
|  |  |  | Grounding | 905 | 447 |  | 0.49392
|  |  |  | Obstruction Brackets | 604 | 374 |  | 0.61921
|  |  |  | # Cables Pulled | 10 | 4 |  | 0.4
95155 | 95004 | E1 | CLINTON-WASHINGTON | 24" CMRS Install | 748 | 32 |  | 0.042781 | 0.39118
|  |  |  | Column Clamp | 212 | 109 |  | 0.51415
|  |  |  | Station Brackets | 740 | 387 |  | 0.52297
|  |  |  | Grounding | 577 | 325 |  | 0.56326
|  |  |  | Obstruction Brackets | 46 | 14 |  | 0.30435
|  |  |  | # Cables Pulled | 916 | 366 |  | 0.39956
95004 | 94266 | E1 | FUL-CLI | 24" CMRS Install | 790 | 622 |  | 0.78734 | 0.76737
|  |  |  | Column Clamp | 777 | 523 |  | 0.6731
|  |  |  | Station Brackets | 51 | 37 |  | 0.72549
|  |  |  | Grounding | 411 | 352 |  | 0.85645
|  |  |  | Obstruction Brackets | 576 | 479 |  | 0.8316
|  |  |  | # Cables Pulled | 708 | 517 |  | 0.73023
94266 | 94207 | E1 | FUL-CLI | 24" CMRS Install | 292 | 108 |  | 0.36986 | 0.57495
|  |  |  | Column Clamp | 706 | 130 |  | 0.18414
|  |  |  | Station Brackets | 556 | 275 |  | 0.4946
|  |  |  | Grounding | 483 | 482 |  | 0.99793
|  |  |  | Obstruction Brackets | 740 | 360 |  | 0.48649
|  |  |  | # Cables Pulled | 48 | 44 |  | 0.91667
94207 | 93350 | E1 | FUL-CLI | 24" CMRS Install | 735 | 52 |  | 0.070748 | 0.32745
|  |  |  | Column Clamp | 137 | 65 |  | 0.47445
|  |  |  | Station Brackets | 545 | 295 |  | 0.54128
|  |  |  | Grounding | 42 | 12 |  | 0.28571
|  |  |  | Obstruction Brackets | 264 | 53 |  | 0.20076
|  |  |  | # Cables Pulled | 97 | 38 |  | 0.39175
73350 | 73690 | E1 | FULTON | 15" CMRS Install | 687 | 560 |  | 0.81514 | 0.61682
|  |  |  | Column Clamp | 573 | 92 |  | 0.16056
|  |  |  | Station Brackets | 121 | 101 |  | 0.83471
|  |  |  | Grounding | 873 | 402 |  | 0.46048
|  |  |  | Obstruction Brackets | 672 | 467 |  | 0.69494
|  |  |  | # Cables Pulled | 419 | 308 |  | 0.73508
73690 | 74030 | E1 | FULTON | 15" CMRS Install | 659 | 326 |  | 0.49469 | 0.53458
|  |  |  | Column Clamp | 437 | 308 |  | 0.70481
|  |  |  | Station Brackets | 561 | 197 |  | 0.35116
|  |  |  | Grounding | 367 | 229 |  | 0.62398
|  |  |  | Obstruction Brackets | 847 | 179 |  | 0.21133
|  |  |  | # Cables Pulled | 493 | 405 |  | 0.8215
|  | E1 | FULTON | 15" CMRS Install | 529 | 326 |  | 0.61626 | 0.4839
|  |  |  | Column Clamp | 419 | 202 |  | 0.4821
|  |  |  | Station Brackets | 395 | 62 |  | 0.15696
|  |  |  | Grounding | 733 | 560 |  | 0.76398
|  |  |  | Obstruction Brackets | 42 | 30 |  | 0.71429
|  |  |  | # Cables Pulled | 695 | 118 |  | 0.16978
74030 | 76085 | E1 | HOY-FUL | 24" CMRS Install | 53 | 32 |  | 0.60377 | 0.6477
|  |  |  | Column Clamp | 622 | 423 |  | 0.68006
|  |  |  | Station Brackets | 658 | 499 |  | 0.75836
|  |  |  | Grounding | 832 | 657 |  | 0.78966
|  |  |  | Obstruction Brackets | 538 | 534 |  | 0.99257
|  |  |  | # Cables Pulled | 615 | 38 |  | 0.061789
76085 | 76110 | E1 | HOY-FUL | 15" CMRS Install | 769 | 267 |  | 0.3472 | 0.43866
|  |  |  | Column Clamp | 839 | 425 |  | 0.50656
|  |  |  | Station Brackets | 516 | 277 |  | 0.53682
|  |  |  | Grounding | 688 | 412 |  | 0.59884
|  |  |  | Obstruction Brackets | 696 | 377 |  | 0.54167
|  |  |  | # Cables Pulled | 575 | 58 |  | 0.10087
76110 | 76165 | E1 | HOY-FUL | 15" CMRS Install | 409 | 64 |  | 0.15648 | 0.26341
|  |  |  | Column Clamp | 611 | 3 |  | 0.00491
|  |  |  | Station Brackets | 880 | 241 |  | 0.27386
|  |  |  | Grounding | 51 | 2 |  | 0.039216
|  |  |  | Obstruction Brackets | 487 | 190 |  | 0.39014
|  |  |  | # Cables Pulled | 549 | 393 |  | 0.71585
76165 | 77470 | E1 | HOYT SCHERMERHORN | 15" CMRS Install | 752 | 431 |  | 0.57314 | 0.39348
|  |  |  | Column Clamp | 30 | 9 |  | 0.3
|  |  |  | Station Brackets | 236 | 217 |  | 0.91949
|  |  |  | Grounding | 616 | 40 |  | 0.064935
|  |  |  | Obstruction Brackets | 589 | 160 |  | 0.27165
|  |  |  | # Cables Pulled | 505 | 117 |  | 0.23168
77470 | 77595 | E1 | BER-HOY | 15" CMRS Install | 211 | 103 |  | 0.48815 | 0.41928
|  |  |  | Column Clamp | 296 | 38 |  | 0.12838
|  |  |  | Station Brackets | 608 | 335 |  | 0.55099
|  |  |  | Grounding | 347 | 91 |  | 0.26225
|  |  |  | Obstruction Brackets | 927 | 106 |  | 0.11435
|  |  |  | # Cables Pulled | 950 | 923 |  | 0.97158
77595 | 78230 | E1 | BER-HOY | 24" CMRS Install | 134 | 10 |  | 0.074627 | 0.49845
|  |  |  | Column Clamp | 776 | 274 |  | 0.35309
|  |  |  | Station Brackets | 661 | 529 |  | 0.8003
|  |  |  | Grounding | 873 | 757 |  | 0.86712
|  |  |  | Obstruction Brackets | 419 | 29 |  | 0.069212
|  |  |  | # Cables Pulled | 167 | 138 |  | 0.82635
78230 | 78515 | E1 | BER-HOY | 24" CMRS Install | 568 | 519 |  | 0.91373 | 0.64031
|  |  |  | Column Clamp | 194 | 67 |  | 0.34536
|  |  |  | Station Brackets | 660 | 230 |  | 0.34848
|  |  |  | Grounding | 306 | 245 |  | 0.80065
|  |  |  | Obstruction Brackets | 393 | 332 |  | 0.84478
|  |  |  | # Cables Pulled | 951 | 560 |  | 0.58885
|  | E2 | BERGEN | Cable Tray Brackets | 308 | 144 |  | 0.46753 | 0.44964
|  |  |  | Installing Tray | 443 | 300 |  | 0.6772
|  |  |  | Core Drilling | 254 | 27 |  | 0.1063
|  |  |  | Cable Pull | 831 | 455 |  | 0.54753
78515 | 78315 | E2 | BER-HOY | Steel Mess Supports | 542 | 79 |  | 0.14576 | 0.54189
|  |  |  | Messenger Clamps | 727 | 387 |  | 0.53232
|  |  |  | Messenger Wire Pull | 313 | 308 |  | 0.98403
|  |  |  | Messenger Wire Tension | 575 | 414 |  | 0.72
|  |  |  | # Cables Pulled | 726 | 355 |  | 0.48898
|  |  |  | Messenger Straps | 263 | 100 |  | 0.38023
78315 | 77655 | E2 | BER-HOY | 24" CMRS Install | 27 | 8 |  | 0.2963 | 0.26896
|  |  |  | Column Clamp | 595 | 136 |  | 0.22857
|  |  |  | Station Brackets | 833 | 363 |  | 0.43577
|  |  |  | Grounding | 223 | 72 |  | 0.32287
|  |  |  | Obstruction Brackets | 824 | 176 |  | 0.21359
|  |  |  | # Cables Pulled | 977 | 114 |  | 0.11668
77655 | 77585 | E2 | BER-HOY | 24" CMRS Install | 820 | 615 |  | 0.75 | 0.50343
|  |  |  | Column Clamp | 507 | 395 |  | 0.77909
|  |  |  | Station Brackets | 73 | 36 |  | 0.49315
|  |  |  | Grounding | 814 | 314 |  | 0.38575
|  |  |  | Obstruction Brackets | 760 | 398 |  | 0.52368
|  |  |  | # Cables Pulled | 810 | 72 |  | 0.088889
77585 | 76845 | E2 | BER-HOY | 24" CMRS Install | 415 | 290 |  | 0.6988 | 0.59664
|  |  |  | Column Clamp | 933 | 583 |  | 0.62487
|  |  |  | Station Brackets | 265 | 173 |  | 0.65283
|  |  |  | Grounding | 718 | 389 |  | 0.54178
|  |  |  | Obstruction Brackets | 687 | 279 |  | 0.40611
|  |  |  | # Cables Pulled | 595 | 390 |  | 0.65546
76845 | 76150 | E2 | HOYT SCHERMERHORN | 24" CMRS Install | 337 | 25 |  | 0.074184 | 0.39457
|  |  |  | Column Clamp | 858 | 121 |  | 0.14103
|  |  |  | Station Brackets | 598 | 177 |  | 0.29599
|  |  |  | Grounding | 847 | 655 |  | 0.77332
|  |  |  | Obstruction Brackets | 310 | 148 |  | 0.47742
|  |  |  | # Cables Pulled | 474 | 287 |  | 0.60549
76150 | 76090 | E2 | HOY-FUL | 24" CMRS Install | 700 | 148 |  | 0.21143 | 0.60625
|  |  |  | Column Clamp | 534 | 463 |  | 0.86704
|  |  |  | Station Brackets | 390 | 320 |  | 0.82051
|  |  |  | Grounding | 481 | 177 |  | 0.36798
|  |  |  | Obstruction Brackets | 366 | 208 |  | 0.56831
|  |  |  | # Cables Pulled | 718 | 576 |  | 0.80223
76090 | 75950 | E2 | HOY-FUL | 24" CMRS Install | 325 | 197 |  | 0.60615 | 0.53877
|  |  |  | Column Clamp | 984 | 590 |  | 0.59959
|  |  |  | Station Brackets | 180 | 79 |  | 0.43889
|  |  |  | Grounding | 431 | 151 |  | 0.35035
|  |  |  | Obstruction Brackets | 497 | 300 |  | 0.60362
|  |  |  | # Cables Pulled | 153 | 97 |  | 0.63399
75950 | 75900 | E2 | HOY-FUL | Steel Mess Supports | 902 | 92 |  | 0.102 | 0.36104
|  |  |  | Messenger Clamps | 452 | 147 |  | 0.32522
|  |  |  | Messenger Wire Pull | 581 | 169 |  | 0.29088
|  |  |  | Messenger Wire Tension | 195 | 132 |  | 0.67692
|  |  |  | # Cables Pulled | 441 | 276 |  | 0.62585
|  |  |  | Messenger Straps | 399 | 58 |  | 0.14536
75900 | 74590 | E2 | HOY-FUL | 24" CMRS Install | 82 | 17 |  | 0.20732 | 0.29258
|  |  |  | Column Clamp | 174 | 105 |  | 0.60345
|  |  |  | Station Brackets | 382 | 206 |  | 0.53927
|  |  |  | Grounding | 820 | 162 |  | 0.19756
|  |  |  | Obstruction Brackets | 863 | 86 |  | 0.099652
|  |  |  | # Cables Pulled | 351 | 38 |  | 0.10826
74590 | 74450 | E2 | HOY-FUL | Steel Mess Supports | 781 | 676 |  | 0.86556 | 0.58815
|  |  |  | Messenger Clamps | 874 | 654 |  | 0.74828
|  |  |  | Messenger Wire Pull | 822 | 596 |  | 0.72506
|  |  |  | Messenger Wire Tension | 629 | 293 |  | 0.46582
|  |  |  | # Cables Pulled | 926 | 483 |  | 0.5216
|  |  |  | Messenger Straps | 311 | 63 |  | 0.20257
74450 | 74070 | E2 | HOY-FUL | 24" CMRS Install | 664 | 90 |  | 0.13554 | 0.38699
|  |  |  | Column Clamp | 122 | 97 |  | 0.79508
|  |  |  | Station Brackets | 796 | 61 |  | 0.076633
|  |  |  | Grounding | 571 | 175 |  | 0.30648
|  |  |  | Obstruction Brackets | 811 | 387 |  | 0.47719
|  |  |  | # Cables Pulled | 855 | 454 |  | 0.53099
74070 | 74030 | E2 | HOY-FUL | 24" CMRS Install | 331 | 168 |  | 0.50755 | 0.44405
|  |  |  | Column Clamp | 582 | 41 |  | 0.070447
|  |  |  | Station Brackets | 688 | 382 |  | 0.55523
|  |  |  | Grounding | 135 | 31 |  | 0.22963
|  |  |  | Obstruction Brackets | 918 | 629 |  | 0.68519
|  |  |  | # Cables Pulled | 912 | 562 |  | 0.61623
74030 | 73690 | E2 | FULTON | 15" CMRS Install | 915 | 118 |  | 0.12896 | 0.44929
|  |  |  | Column Clamp | 140 | 5 |  | 0.035714
|  |  |  | Station Brackets | 621 | 515 |  | 0.82931
|  |  |  | Grounding | 907 | 584 |  | 0.64388
|  |  |  | Obstruction Brackets | 389 | 255 |  | 0.65553
|  |  |  | # Cables Pulled | 169 | 68 |  | 0.40237
73690 | 73250 | E2 | FULTON | 15" CMRS Install | 295 | 237 |  | 0.80339 | 0.46242 | Cable Management Takeoffs Cell F110* - 147LF instead of 440LF | Cable Management Takeoffs Cell F110* - 147LF instead of 440LF
|  |  |  | Column Clamp | 644 | 501 |  | 0.77795
|  |  |  | Station Brackets | 513 | 47 |  | 0.091618
|  |  |  | Grounding | 161 | 146 |  | 0.90683
|  |  |  | Obstruction Brackets | 178 | 20 |  | 0.11236
|  |  |  | # Cables Pulled | 935 | 77 |  | 0.082353
|  | E2 | FULTON | 15" CMRS Install | 167 | 63 |  | 0.37725 | 0.52881
|  |  |  | Column Clamp | 205 | 165 |  | 0.80488
|  |  |  | Station Brackets | 130 | 65 |  | 0.5
|  |  |  | Grounding | 510 | 274 |  | 0.53725
|  |  |  | Obstruction Brackets | 297 | 93 |  | 0.31313
|  |  |  | # Cables Pulled | 798 | 511 |  | 0.64035
73250 | 72315 | E2 | FUL-CLI | 24" CMRS Install | 545 | 135 |  | 0.24771 | 0.61311
|  |  |  | Column Clamp | 634 | 466 |  | 0.73502
|  |  |  | Station Brackets | 454 | 250 |  | 0.55066
|  |  |  | Grounding | 787 | 741 |  | 0.94155
|  |  |  | Obstruction Brackets | 996 | 781 |  | 0.78414
|  |  |  | # Cables Pulled | 143 | 60 |  | 0.41958
94400 | 94989 | E2 | FUL-CLI | 24" CMRS Install | 128 | 68 |  | 0.53125 | 0.4772
|  |  |  | Column Clamp | 563 | 266 |  | 0.47247
|  |  |  | Station Brackets | 62 | 57 |  | 0.91935
|  |  |  | Grounding | 744 | 526 |  | 0.70699
|  |  |  | Obstruction Brackets | 161 | 7 |  | 0.043478
|  |  |  | # Cables Pulled | 833 | 158 |  | 0.18968
94989 | 95114 | E2 | FUL-CLI | 24" CMRS Install | 890 | 168 |  | 0.18876 | 0.30258
|  |  |  | Column Clamp | 572 | 253 |  | 0.44231
|  |  |  | Station Brackets | 742 | 286 |  | 0.38544
|  |  |  | Grounding | 618 | 89 |  | 0.14401
|  |  |  | Obstruction Brackets | 314 | 72 |  | 0.2293
|  |  |  | # Cables Pulled | 491 | 209 |  | 0.42566
94989 | 95114 | E2 | CLINTON-WASHINGTON | 24" CMRS Install | 401 | 175 |  | 0.43641 | 0.58605
|  |  |  | Column Clamp | 26 | 20 |  | 0.76923
|  |  |  | Station Brackets | 412 | 118 |  | 0.28641
|  |  |  | Grounding | 799 | 680 |  | 0.85106
|  |  |  | Obstruction Brackets | 212 | 118 |  | 0.5566
|  |  |  | # Cables Pulled | 772 | 476 |  | 0.61658
95503 | 95701 | E2 | CLINTON-WASHINGTON | 24" CMRS Install | 37 | 23 |  | 0.62162 | 0.2998
|  |  |  | Column Clamp | 205 | 63 |  | 0.30732
|  |  |  | Station Brackets | 900 | 342 |  | 0.38
|  |  |  | Grounding | 222 | 5 |  | 0.022523
|  |  |  | Obstruction Brackets | 844 | 373 |  | 0.44194
|  |  |  | # Cables Pulled | 551 | 14 |  | 0.025408
95767 | 95852 | E2 | CLINTON-WASHINGTON | 24" CMRS Install | 947 | 679 |  | 0.717 | 0.54447
|  |  |  | Column Clamp | 665 | 130 |  | 0.19549
|  |  |  | Station Brackets | 444 | 277 |  | 0.62387
|  |  |  | Grounding | 42 | 29 |  | 0.69048
|  |  |  | Obstruction Brackets | 581 | 140 |  | 0.24096
|  |  |  | # Cables Pulled | 607 | 485 |  | 0.79901
95852 | 96366 | E2 | CLINTON-WASHINGTON | 24" CMRS Install | 177 | 147 |  | 0.83051 | 0.38997
|  |  |  | Column Clamp | 755 | 228 |  | 0.30199
|  |  |  | Station Brackets | 346 | 86 |  | 0.24855
|  |  |  | Grounding | 420 | 97 |  | 0.23095
|  |  |  | Obstruction Brackets | 240 | 2 |  | 0.0083333
|  |  |  | # Cables Pulled | 82 | 59 |  | 0.71951
96366 | 96432 | E2 | CLINTON-WASHINGTON | 24" CMRS Install | 640 | 367 |  | 0.57344 | 0.72159
|  |  |  | Column Clamp | 987 | 949 |  | 0.9615
|  |  |  | Station Brackets | 546 | 496 |  | 0.90842
|  |  |  | Grounding | 172 | 125 |  | 0.72674
|  |  |  | Obstruction Brackets | 927 | 813 |  | 0.87702
|  |  |  | # Cables Pulled | 602 | 170 |  | 0.28239
96432 | 96649 | E2 | CLINTON-WASHINGTON | 24" CMRS Install | 348 | 66 |  | 0.18966 | 0.25296
|  |  |  | Column Clamp | 426 | 69 |  | 0.16197
|  |  |  | Station Brackets | 776 | 68 |  | 0.087629
|  |  |  | Grounding | 453 | 108 |  | 0.23841
|  |  |  | Obstruction Brackets | 273 | 152 |  | 0.55678
|  |  |  | # Cables Pulled | 780 | 221 |  | 0.28333
95767 | 95852 | E2 | CLINTON-WASHINGTON | 24" CMRS Install | 845 | 822 |  | 0.97278 | 0.48044
|  |  |  | Column Clamp | 831 | 178 |  | 0.2142
|  |  |  | Station Brackets | 879 | 397 |  | 0.45165
|  |  |  | Grounding | 390 | 195 |  | 0.5
|  |  |  | Obstruction Brackets | 842 | 343 |  | 0.40736
|  |  |  | # Cables Pulled | 300 | 101 |  | 0.33667
95852 | 96366 | E2 | CLI-CLA | 24" CMRS Install | 778 | 472 |  | 0.60668 | 0.72096
|  |  |  | Column Clamp | 674 | 661 |  | 0.98071
|  |  |  | Station Brackets | 64 | 17 |  | 0.26562
|  |  |  | Grounding | 294 | 204 |  | 0.69388
|  |  |  | Obstruction Brackets | 469 | 428 |  | 0.91258
|  |  |  | # Cables Pulled | 486 | 421 |  | 0.86626
96366 | 96432 | E2 | CLI-CLA | 24" CMRS Install | 541 | 535 |  | 0.98891 | 0.79411
|  |  |  | Column Clamp | 137 | 103 |  | 0.75182
|  |  |  | Station Brackets | 296 | 201 |  | 0.67905
|  |  |  | Grounding | 127 | 106 |  | 0.83465
|  |  |  | Obstruction Brackets | 851 | 652 |  | 0.76616
|  |  |  | # Cables Pulled | 168 | 125 |  | 0.74405
96432 | 96649 | E2 | CLI-CLA | 24" CMRS Install | 802 | 21 |  | 0.026185 | 0.43237
|  |  |  | Column Clamp | 251 | 249 |  | 0.99203
|  |  |  | Station Brackets | 395 | 67 |  | 0.16962
|  |  |  | Grounding | 101 | 3 |  | 0.029703
|  |  |  | Obstruction Brackets | 754 | 603 |  | 0.79973
|  |  |  | # Cables Pulled | 26 | 15 |  | 0.57692
96649 | 96770 | E2 | CLI-CLA | 24" CMRS Install | 274 | 272 |  | 0.9927 | 0.61116
|  |  |  | Column Clamp | 813 | 584 |  | 0.71833
|  |  |  | Station Brackets | 11 | 0 |  | 0
|  |  |  | Grounding | 427 | 308 |  | 0.72131
|  |  |  | Obstruction Brackets | 313 | 297 |  | 0.94888
|  |  |  | # Cables Pulled | 49 | 14 |  | 0.28571
96770 | 96990 | E2 | CLI-CLA | Steel Mess Supports | 208 | 42 |  | 0.20192 | 0.44037
|  |  |  | Messenger Clamps | 185 | 0 |  | 0
|  |  |  | Messenger Wire Pull | 867 | 634 |  | 0.73126
|  |  |  | Messenger Wire Tension | 763 | 763 |  | 1
|  |  |  | # Cables Pulled | 255 | 88 |  | 0.3451
|  |  |  | Messenger Straps | 588 | 214 |  | 0.36395
96990 | 97230 | E2 | CLASSON | 24" CMRS Install | 733 | 131 |  | 0.17872 | 0.27377
|  |  |  | Column Clamp | 540 | 5 |  | 0.0092593
|  |  |  | Station Brackets | 81 | 49 |  | 0.60494
|  |  |  | Grounding | 404 | 213 |  | 0.52723
|  |  |  | Obstruction Brackets | 890 | 157 |  | 0.1764
|  |  |  | # Cables Pulled | 445 | 65 |  | 0.14607
97230 | 97538 | E2 | CLASSON | 24" CMRS Install | 467 | 251 |  | 0.53747 | 0.57174
|  |  |  | Column Clamp | 828 | 246 |  | 0.2971
|  |  |  | Station Brackets | 173 | 173 |  | 1
|  |  |  | Grounding | 650 | 289 |  | 0.44462
|  |  |  | Obstruction Brackets | 191 | 160 |  | 0.8377
|  |  |  | # Cables Pulled | 421 | 132 |  | 0.31354
97538 | 97670 | E2 | CLASSON | 24" CMRS Install | 319 | 164 |  | 0.51411 | 0.28966
|  |  |  | Column Clamp | 65 | 2 |  | 0.030769
|  |  |  | Station Brackets | 324 | 119 |  | 0.36728
|  |  |  | Grounding | 744 | 130 |  | 0.17473
|  |  |  | Obstruction Brackets | 295 | 171 |  | 0.57966
|  |  |  | # Cables Pulled | 140 | 10 |  | 0.071429
97670 | 98015 | E2 | CLA-BED | Steel Mess Supports | 1000 | 224 |  | 0.224 | 0.23552
|  |  |  | Messenger Clamps | 577 | 110 |  | 0.19064
|  |  |  | Messenger Wire Pull | 235 | 4 |  | 0.017021
|  |  |  | Messenger Wire Tension | 21 | 16 |  | 0.7619
|  |  |  | # Cables Pulled | 195 | 36 |  | 0.18462
|  |  |  | Messenger Straps | 429 | 15 |  | 0.034965
98015 | 98125 | E2 | CLA-BED | 24" CMRS Install | 59 | 38 |  | 0.64407 | 0.52234
|  |  |  | Column Clamp | 895 | 442 |  | 0.49385
|  |  |  | Station Brackets | 745 | 80 |  | 0.10738
|  |  |  | Grounding | 512 | 451 |  | 0.88086
|  |  |  | Obstruction Brackets | 349 | 342 |  | 0.97994
|  |  |  | # Cables Pulled | 967 | 27 |  | 0.027921
98125 | 98185 | E2 | CLA-BED | 24" CMRS Install | 170 | 117 |  | 0.68824 | 0.52044
|  |  |  | Column Clamp | 983 | 677 |  | 0.68871
|  |  |  | Station Brackets | 51 | 24 |  | 0.47059
|  |  |  | Grounding | 158 | 100 |  | 0.63291
|  |  |  | Obstruction Brackets | 262 | 10 |  | 0.038168
|  |  |  | # Cables Pulled | 841 | 508 |  | 0.60404
98185 | 98440 | E2 | CLA-BED | 24" CMRS Install | 43 | 5 |  | 0.11628 | 0.58339
|  |  |  | Column Clamp | 796 | 242 |  | 0.30402
|  |  |  | Station Brackets | 207 | 127 |  | 0.61353
|  |  |  | Grounding | 242 | 231 |  | 0.95455
|  |  |  | Obstruction Brackets | 157 | 93 |  | 0.59236
|  |  |  | # Cables Pulled | 535 | 492 |  | 0.91963
|  | E2 | CLA-BED | Crossover (Arch Bar Installation) | 408 | 6 |  | 0.014706
98440 | 98586 | E2 | CLA-BED | 24" CMRS Install | 501 | 263 |  | 0.52495 | 0.5717
|  |  |  | Column Clamp | 742 | 632 |  | 0.85175
|  |  |  | Station Brackets | 382 | 156 |  | 0.40838
|  |  |  | Grounding | 729 | 361 |  | 0.4952
|  |  |  | Obstruction Brackets | 389 | 306 |  | 0.78663
|  |  |  | # Cables Pulled | 256 | 93 |  | 0.36328
98586 | 98836 | E2 | CLA-BED | Steel Mess Supports | 97 | 89 |  | 0.91753 | 0.62729
|  |  |  | Messenger Clamps | 633 | 328 |  | 0.51817
|  |  |  | Messenger Wire Pull | 334 | 215 |  | 0.64371
|  |  |  | Messenger Wire Tension | 240 | 117 |  | 0.4875
|  |  |  | # Cables Pulled | 791 | 193 |  | 0.24399
|  |  |  | Messenger Straps | 106 | 101 |  | 0.95283
98836 | 99505 | E2 | BEDFORD NOSTRAND | Cable Tray Brackets | 43 | 36 |  | 0.83721 | 0.44019
|  |  |  | Installing Tray | 883 | 114 |  | 0.12911
|  |  |  | Core Drilling | 672 | 286 |  | 0.4256
|  |  |  | Cable Pull | 770 | 284 |  | 0.36883
99505 | 99950 | E2 | BED-MYR | Steel Mess Supports | 883 | 433 |  | 0.49037 | 0.31641
|  |  |  | Messenger Clamps | 573 | 273 |  | 0.47644
|  |  |  | Messenger Wire Pull | 284 | 133 |  | 0.46831
|  |  |  | Messenger Wire Tension | 648 | 94 |  | 0.14506
|  |  |  | # Cables Pulled | 544 | 39 |  | 0.071691
|  |  |  | Messenger Straps | 953 | 235 |  | 0.24659
|  | E2 | CLA-BED | Crossover (Arch Bar Installation) | 475 | 315 |  | 0.66316
99950 | 100290 | E2 | BED-MYR | 24" CMRS Install | 469 | 137 |  | 0.29211 | 0.43208
|  |  |  | Column Clamp | 990 | 21 |  | 0.021212
|  |  |  | Station Brackets | 819 | 541 |  | 0.66056
|  |  |  | Grounding | 418 | 154 |  | 0.36842
|  |  |  | Obstruction Brackets | 470 | 259 |  | 0.55106
|  |  |  | # Cables Pulled | 924 | 646 |  | 0.69913
100290 | 100740 | E2 | BED-MYR | 24" CMRS Install | 885 | 516 |  | 0.58305 | 0.49042
|  |  |  | Column Clamp | 708 | 186 |  | 0.26271
|  |  |  | Station Brackets | 447 | 342 |  | 0.7651
|  |  |  | Grounding | 420 | 12 |  | 0.028571
|  |  |  | Obstruction Brackets | 804 | 467 |  | 0.58085
|  |  |  | # Cables Pulled | 18 | 13 |  | 0.72222
100740 | 100792 | E2 | BED-MYR | 24" CMRS Install | 73 | 41 |  | 0.56164 | 0.57769
|  |  |  | Column Clamp | 732 | 274 |  | 0.37432
|  |  |  | Station Brackets | 866 | 628 |  | 0.72517
|  |  |  | Grounding | 554 | 372 |  | 0.67148
|  |  |  | Obstruction Brackets | 848 | 794 |  | 0.93632
|  |  |  | # Cables Pulled | 284 | 56 |  | 0.19718
100792 | 101595 | E2 | BED-MYR | 24" CMRS Install | 576 | 79 |  | 0.13715 | 0.58997
|  |  |  | Column Clamp | 176 | 141 |  | 0.80114
|  |  |  | Station Brackets | 642 | 618 |  | 0.96262
|  |  |  | Grounding | 118 | 99 |  | 0.83898
|  |  |  | Obstruction Brackets | 888 | 675 |  | 0.76014
|  |  |  | # Cables Pulled | 452 | 18 |  | 0.039823
101595 | 101688 | E2 | BED-MYR | 24" CMRS Install | 769 | 737 |  | 0.95839 | 0.6568
|  |  |  | Column Clamp | 486 | 191 |  | 0.393
|  |  |  | Station Brackets | 664 | 444 |  | 0.66867
|  |  |  | Grounding | 603 | 136 |  | 0.22554
|  |  |  | Obstruction Brackets | 52 | 42 |  | 0.80769
|  |  |  | # Cables Pulled | 160 | 142 |  | 0.8875
101688 | 102400 | E2 | MYRTLE AVE | 15" CMRS Install | 966 | 361 |  | 0.37371 | 0.56902
|  |  |  | Column Clamp | 886 | 751 |  | 0.84763
|  |  |  | Station Brackets | 258 | 184 |  | 0.71318
|  |  |  | Grounding | 279 | 95 |  | 0.3405
|  |  |  | Obstruction Brackets | 102 | 41 |  | 0.40196
|  |  |  | # Cables Pulled | 757 | 558 |  | 0.73712
102400 | 102550 | E2 | MYR-FLU | Steel Mess Supports | 296 | 158 |  | 0.53378 | 0.58435
|  |  |  | Messenger Clamps | 114 | 114 |  | 1
|  |  |  | Messenger Wire Pull | 488 | 240 |  | 0.4918
|  |  |  | Messenger Wire Tension | 702 | 10 |  | 0.014245
|  |  |  | # Cables Pulled | 224 | 178 |  | 0.79464
|  |  |  | Messenger Straps | 67 | 45 |  | 0.67164
102550 | 103165 | E2 | MYR-FLU | 15" CMRS Install | 669 | 430 |  | 0.64275 | 0.37745
|  |  |  | Column Clamp | 704 | 19 |  | 0.026989
|  |  |  | Station Brackets | 308 | 112 |  | 0.36364
|  |  |  | Grounding | 843 | 411 |  | 0.48754
|  |  |  | Obstruction Brackets | 862 | 445 |  | 0.51624
|  |  |  | # Cables Pulled | 167 | 38 |  | 0.22754
103165 | 103230 | E2 | MYR-FLU | 15" CMRS Install | 248 | 197 |  | 0.79435 | 0.3404
|  |  |  | Column Clamp | 863 | 289 |  | 0.33488
|  |  |  | Station Brackets | 42 | 11 |  | 0.2619
|  |  |  | Grounding | 411 | 12 |  | 0.029197
|  |  |  | Obstruction Brackets | 114 | 46 |  | 0.40351
|  |  |  | # Cables Pulled | 668 | 146 |  | 0.21856
103230 | 103809 | E2 | MYR-FLU | 15" CMRS Install | 344 | 112 |  | 0.32558 | 0.52069
|  |  |  | Column Clamp | 176 | 115 |  | 0.65341
|  |  |  | Station Brackets | 289 | 275 |  | 0.95156
|  |  |  | Grounding | 902 | 441 |  | 0.48891
|  |  |  | Obstruction Brackets | 606 | 351 |  | 0.57921
|  |  |  | # Cables Pulled | 550 | 69 |  | 0.12545
103809 | 103902 | E2 | MYR-FLU | 15" CMRS Install | 75 | 35 |  | 0.46667 | 0.47816
|  |  |  | Column Clamp | 936 | 770 |  | 0.82265
|  |  |  | Station Brackets | 24 | 3 |  | 0.125
|  |  |  | Grounding | 230 | 34 |  | 0.14783
|  |  |  | Obstruction Brackets | 614 | 446 |  | 0.72638
|  |  |  | # Cables Pulled | 286 | 166 |  | 0.58042
103902 | 104595 | E2 | FLUSHING | 15" CMRS Install | 751 | 142 |  | 0.18908 | 0.44356
|  |  |  | Column Clamp | 977 | 462 |  | 0.47288
|  |  |  | Station Brackets | 928 | 874 |  | 0.94181
|  |  |  | Grounding | 92 | 21 |  | 0.22826
|  |  |  | Obstruction Brackets | 65 | 14 |  | 0.21538
|  |  |  | # Cables Pulled | 961 | 590 |  | 0.61394
104595 | 104750 | E2 | FLU-BRO | Steel Mess Supports | 288 | 217 |  | 0.75347 | 0.62134
|  |  |  | Messenger Clamps | 179 | 85 |  | 0.47486
|  |  |  | Messenger Wire Pull | 650 | 502 |  | 0.77231
|  |  |  | Messenger Wire Tension | 840 | 173 |  | 0.20595
|  |  |  | # Cables Pulled | 986 | 837 |  | 0.84888
|  |  |  | Messenger Straps | 284 | 191 |  | 0.67254
104750 | 105270 | E2 | FLU-BRO | 15" CMRS Install | 150 | 12 |  | 0.08 | 0.39962
|  |  |  | Column Clamp | 859 | 541 |  | 0.6298
|  |  |  | Station Brackets | 900 | 234 |  | 0.26
|  |  |  | Grounding | 710 | 185 |  | 0.26056
|  |  |  | Obstruction Brackets | 282 | 197 |  | 0.69858
|  |  |  | # Cables Pulled | 128 | 60 |  | 0.46875
105270 | 105930 | E2 | FLU-BRO | 15" CMRS Install | 921 | 921 |  | 1 | 0.64282
|  |  |  | Column Clamp | 580 | 201 |  | 0.34655
|  |  |  | Station Brackets | 123 | 76 |  | 0.61789
|  |  |  | Grounding | 668 | 506 |  | 0.75749
|  |  |  | Obstruction Brackets | 825 | 445 |  | 0.53939
|  |  |  | # Cables Pulled | 366 | 218 |  | 0.59563
105930 | 106003 | E2 | FLU-BRO | 15" CMRS Install | 621 | 50 |  | 0.080515 | 0.44311
|  |  |  | Column Clamp | 305 | 0 |  | 0
|  |  |  | Station Brackets | 491 | 445 |  | 0.90631
|  |  |  | Grounding | 766 | 173 |  | 0.22585
|  |  |  | Obstruction Brackets | 180 | 174 |  | 0.96667
|  |  |  | # Cables Pulled | 484 | 232 |  | 0.47934
106003 | 106648 | E2 | BROADWAY | 15" CMRS Install | 941 | 694 |  | 0.73751 | 0.45964
|  |  |  | Column Clamp | 513 | 63 |  | 0.12281
|  |  |  | Station Brackets | 626 | 6 |  | 0.0095847
|  |  |  | Grounding | 183 | 41 |  | 0.22404
|  |  |  | Obstruction Brackets | 132 | 88 |  | 0.66667
|  |  |  | # Cables Pulled | 715 | 713 |  | 0.9972
|  | E2 | BROADWAY | 15" CMRS Install | 249 | 41 |  | 0.16466 | 0.38576
|  |  |  | Column Clamp | 752 | 129 |  | 0.17154
|  |  |  | Station Brackets | 97 | 21 |  | 0.21649
|  |  |  | Grounding | 822 | 505 |  | 0.61436
|  |  |  | Obstruction Brackets | 119 | 116 |  | 0.97479
|  |  |  | # Cables Pulled | 220 | 38 |  | 0.17273
|  | E2 | BROADWAY | 15" CMRS Install | 958 | 567 |  | 0.59186 | 0.65275
|  |  |  | Column Clamp | 882 | 722 |  | 0.81859
|  |  |  | Station Brackets | 1000 | 902 |  | 0.902
|  |  |  | Grounding | 619 | 344 |  | 0.55574
|  |  |  | Obstruction Brackets | 473 | 393 |  | 0.83087
|  |  |  | # Cables Pulled | 561 | 122 |  | 0.21747
106650 | 106920 | E2 | BRO-MET | Steel Mess Supports | 967 | 298 |  | 0.30817 | 0.53804
|  |  |  | Messenger Clamps | 315 | 230 |  | 0.73016
|  |  |  | Messenger Wire Pull | 887 | 453 |  | 0.51071
|  |  |  | Messenger Wire Tension | 673 | 459 |  | 0.68202
|  |  |  | # Cables Pulled | 171 | 131 |  | 0.76608
|  |  |  | Messenger Straps | 502 | 116 |  | 0.23108
106918 | 107620 | E2 | BRO-MET | 15" CMRS Install | 469 | 322 |  | 0.68657 | 0.49645
|  |  |  | Column Clamp | 281 | 12 |  | 0.042705
|  |  |  | Station Brackets | 947 | 406 |  | 0.42872
|  |  |  | Grounding | 889 | 344 |  | 0.38695
|  |  |  | Obstruction Brackets | 833 | 455 |  | 0.54622
|  |  |  | # Cables Pulled | 249 | 221 |  | 0.88755
107620 | 107683 | E2 | BRO-MET | 15" CMRS Install | 551 | 177 |  | 0.32123 | 0.32499
|  |  |  | Column Clamp | 550 | 278 |  | 0.50545
|  |  |  | Station Brackets | 665 | 282 |  | 0.42406
|  |  |  | Grounding | 537 | 196 |  | 0.36499
|  |  |  | Obstruction Brackets | 834 | 61 |  | 0.073141
|  |  |  | # Cables Pulled | 226 | 59 |  | 0.26106
107683 | 108360 | E2 | BRO-MET | 15" CMRS Install | 864 | 847 |  | 0.98032 | 0.62801
|  |  |  | Column Clamp | 326 | 287 |  | 0.88037
|  |  |  | Station Brackets | 318 | 10 |  | 0.031447
|  |  |  | Grounding | 10 | 7 |  | 0.7
|  |  |  | Obstruction Brackets | 24 | 20 |  | 0.83333
|  |  |  | # Cables Pulled | 867 | 297 |  | 0.34256
108360 | 109235 | E2 | METROPOLITAN | 15" CMRS Install | 513 | 210 |  | 0.40936 | 0.46612
|  |  |  | Column Clamp | 219 | 48 |  | 0.21918
|  |  |  | Station Brackets | 10 | 4 |  | 0.4
|  |  |  | Grounding | 210 | 9 |  | 0.042857
|  |  |  | Obstruction Brackets | 211 | 192 |  | 0.90995
|  |  |  | # Cables Pulled | 65 | 53 |  | 0.81538
109235 | 110795 | E2 | MET-NAS | 24" CMRS Install | 915 | 477 |  | 0.52131 | 0.45569
|  |  |  | Column Clamp | 937 | 279 |  | 0.29776
|  |  |  | Station Brackets | 765 | 258 |  | 0.33725
|  |  |  | Grounding | 741 | 616 |  | 0.83131
|  |  |  | Obstruction Brackets | 603 | 196 |  | 0.32504
|  |  |  | # Cables Pulled | 541 | 228 |  | 0.42144
110795 | 110865 | E2 | MET-NAS | 24" CMRS Install | 380 | 295 |  | 0.77632 | 0.48975
|  |  |  | Column Clamp | 321 | 110 |  | 0.34268
|  |  |  | Station Brackets | 155 | 116 |  | 0.74839
|  |  |  | Grounding | 724 | 22 |  | 0.030387
|  |  |  | Obstruction Brackets | 404 | 254 |  | 0.62871
|  |  |  | # Cables Pulled | 250 | 103 |  | 0.412
110865 | 113020 | E2 | MET-NAS | 24" CMRS Install | 954 | 743 |  | 0.77883 | 0.48199
|  |  |  | Column Clamp | 792 | 626 |  | 0.7904
|  |  |  | Station Brackets | 808 | 5 |  | 0.0061881
|  |  |  | Grounding | 606 | 72 |  | 0.11881
|  |  |  | Obstruction Brackets | 922 | 708 |  | 0.7679
|  |  |  | # Cables Pulled | 819 | 352 |  | 0.42979
113020 | 113155 | E2 | MET-NAS | 24" CMRS Install | 409 | 390 |  | 0.95355 | 0.60659
|  |  |  | Column Clamp | 874 | 328 |  | 0.37529
|  |  |  | Station Brackets | 738 | 246 |  | 0.33333
|  |  |  | Grounding | 730 | 560 |  | 0.76712
|  |  |  | Obstruction Brackets | 670 | 424 |  | 0.63284
|  |  |  | # Cables Pulled | 407 | 235 |  | 0.5774
113155 | 113815 | E2 | NASSAU | 24" CMRS Install | 156 | 20 |  | 0.12821 | 0.46828
|  |  |  | Column Clamp | 999 | 119 |  | 0.11912
|  |  |  | Station Brackets | 147 | 142 |  | 0.96599
|  |  |  | Grounding | 308 | 60 |  | 0.19481
|  |  |  | Obstruction Brackets | 534 | 518 |  | 0.97004
|  |  |  | # Cables Pulled | 913 | 394 |  | 0.43154
113815 | 114105 | E2 | NAS-GRE | Steel Mess Supports | 105 | 79 |  | 0.75238 | 0.45478
|  |  |  | Messenger Clamps | 353 | 333 |  | 0.94334
|  |  |  | Messenger Wire Pull | 722 | 241 |  | 0.3338
|  |  |  | Messenger Wire Tension | 536 | 134 |  | 0.25
|  |  |  | # Cables Pulled | 673 | 110 |  | 0.16345
|  |  |  | Messenger Straps | 63 | 18 |  | 0.28571
114105 | 114730 | E2 | NAS-GRE | 24" CMRS Install | 437 | 419 |  | 0.95881 | 0.50249
|  |  |  | Column Clamp | 648 | 90 |  | 0.13889
|  |  |  | Station Brackets | 418 | 103 |  | 0.24641
|  |  |  | Grounding | 178 | 152 |  | 0.85393
|  |  |  | Obstruction Brackets | 230 | 182 |  | 0.7913
|  |  |  | # Cables Pulled | 430 | 11 |  | 0.025581
114730 | 114910 | E2 | NAS-GRE | Steel Mess Supports | 933 | 346 |  | 0.37085 | 0.52823
|  |  |  | Messenger Clamps | 120 | 24 |  | 0.2
|  |  |  | Messenger Wire Pull | 46 | 44 |  | 0.95652
|  |  |  | Messenger Wire Tension | 896 | 104 |  | 0.11607
|  |  |  | # Cables Pulled | 61 | 39 |  | 0.63934
|  |  |  | Messenger Straps | 970 | 860 |  | 0.8866
114910 | 115625 | E2 | NAS-GRE | 24" CMRS Install | 585 | 2 |  | 0.0034188 | 0.3286
|  |  |  | Column Clamp | 718 | 170 |  | 0.23677
|  |  |  | Station Brackets | 125 | 71 |  | 0.568
|  |  |  | Grounding | 131 | 120 |  | 0.91603
|  |  |  | Obstruction Brackets | 463 | 74 |  | 0.15983
|  |  |  | # Cables Pulled | 674 | 59 |  | 0.087537
115625 | 116435 | E2 | GREENPOINT | 24" CMRS Install | 229 | 167 |  | 0.72926 | 0.46187
|  |  |  | Column Clamp | 289 | 165 |  | 0.57093
|  |  |  | Station Brackets | 428 | 106 |  | 0.24766
|  |  |  | Grounding | 118 | 19 |  | 0.16102
|  |  |  | Obstruction Brackets | 52 | 27 |  | 0.51923
|  |  |  | # Cables Pulled | 626 | 340 |  | 0.54313
116435 | 117130 | E2 | GRE-21S | 24" CMRS Install | 91 | 32 |  | 0.35165 | 0.57348
|  |  |  | Column Clamp | 880 | 646 |  | 0.73409
|  |  |  | Station Brackets | 575 | 206 |  | 0.35826
|  |  |  | Grounding | 576 | 570 |  | 0.98958
|  |  |  | Obstruction Brackets | 328 | 251 |  | 0.76524
|  |  |  | # Cables Pulled | 252 | 61 |  | 0.24206
|  | E2 | GRE-21S | Crossover (Arch Bar Installation) | 21 | 5 |  | 0.2381
117130 | 121035 | E2 | GRE-21S | 24" CMRS Install | 475 | 67 |  | 0.14105 | 0.30367
|  |  |  | Column Clamp | 617 | 32 |  | 0.051864
|  |  |  | Station Brackets | 402 | 43 |  | 0.10697
|  |  |  | Grounding | 220 | 212 |  | 0.96364
|  |  |  | Obstruction Brackets | 607 | 278 |  | 0.45799
|  |  |  | # Cables Pulled | 796 | 80 |  | 0.1005
121035 | 122030 | E2 | 21ST STATION | Steel Mess Supports | 443 | 155 |  | 0.34989 | 0.47918
|  |  |  | Messenger Clamps | 92 | 32 |  | 0.34783
|  |  |  | Messenger Wire Pull | 503 | 399 |  | 0.79324
|  |  |  | Messenger Wire Tension | 738 | 614 |  | 0.83198
|  |  |  | # Cables Pulled | 358 | 114 |  | 0.31844
|  |  |  | Messenger Straps | 937 | 219 |  | 0.23372
122030 | 122430 | E2 | 21S-COU | 24" CMRS Install | 138 | 85 |  | 0.61594 | 0.51914
|  |  |  | Column Clamp | 989 | 564 |  | 0.57027
|  |  |  | Station Brackets | 640 | 136 |  | 0.2125
|  |  |  | Grounding | 924 | 535 |  | 0.579
|  |  |  | Obstruction Brackets | 751 | 611 |  | 0.81358
|  |  |  | # Cables Pulled | 989 | 320 |  | 0.32356
122430 | 122660 | E2 | 21S-COU | Steel Mess Supports | 78 | 37 |  | 0.47436 | 0.45909
|  |  |  | Messenger Clamps | 373 | 148 |  | 0.39678
|  |  |  | Messenger Wire Pull | 322 | 40 |  | 0.12422
|  |  |  | Messenger Wire Tension | 531 | 433 |  | 0.81544
|  |  |  | # Cables Pulled | 805 | 655 |  | 0.81366
|  |  |  | Messenger Straps | 446 | 58 |  | 0.13004
122660 | 122827 | E2 | 21S-COU | 24" CMRS Install | 836 | 359 |  | 0.42943 | 0.50146
|  |  |  | Column Clamp | 700 | 303 |  | 0.43286
|  |  |  | Station Brackets | 440 | 7 |  | 0.015909
|  |  |  | Grounding | 615 | 263 |  | 0.42764
|  |  |  | Obstruction Brackets | 38 | 35 |  | 0.92105
|  |  |  | # Cables Pulled | 596 | 466 |  | 0.78188
122827 | 123085 | E2 | 21S-COU | Steel Mess Supports | 270 | 177 |  | 0.65556 | 0.43836
|  |  |  | Messenger Clamps | 673 | 515 |  | 0.76523
|  |  |  | Messenger Wire Pull | 521 | 322 |  | 0.61804
|  |  |  | Messenger Wire Tension | 48 | 4 |  | 0.083333
|  |  |  | # Cables Pulled | 150 | 57 |  | 0.38
|  |  |  | Messenger Straps | 125 | 16 |  | 0.128
123085 | 123690 | E2 | COURT SQ | Cable Tray Brackets | 271 | 11 |  | 0.04059 | 0.29437
|  |  |  | Installing Tray | 201 | 64 |  | 0.31841
|  |  |  | Core Drilling | 74 | 10 |  | 0.13514
|  |  |  | Cable Pull | 180 | 123 |  | 0.68333
123690 | 123750 | E2 | COU-QUE | Steel Mess Supports | 47 | 39 |  | 0.82979 | 0.46799
|  |  |  | Messenger Clamps | 898 | 444 |  | 0.49443
|  |  |  | Messenger Wire Pull | 705 | 405 |  | 0.57447
|  |  |  | Messenger Wire Tension | 437 | 106 |  | 0.24256
|  |  |  | # Cables Pulled | 311 | 92 |  | 0.29582
|  |  |  | Messenger Straps | 302 | 112 |  | 0.37086
123750 | 123950 | E2 | COU-QUE | Steel Mess Supports | 46 | 10 |  | 0.21739 | 0.40625
|  |  |  | Messenger Clamps | 154 | 55 |  | 0.35714
|  |  |  | Messenger Wire Pull | 170 | 24 |  | 0.14118
|  |  |  | Messenger Wire Tension | 982 | 477 |  | 0.48574
|  |  |  | # Cables Pulled | 794 | 259 |  | 0.3262
|  |  |  | Messenger Straps | 965 | 878 |  | 0.90984
123950 | 124050 | E2 | COU-QUE | Steel Mess Supports | 355 | 111 |  | 0.31268 | 0.23047
|  |  |  | Messenger Clamps | 406 | 27 |  | 0.066502
|  |  |  | Messenger Wire Pull | 969 | 255 |  | 0.26316
|  |  |  | Messenger Wire Tension | 310 | 127 |  | 0.40968
|  |  |  | # Cables Pulled | 90 | 29 |  | 0.32222
|  |  |  | Messenger Straps | 350 | 3 |  | 0.0085714
124050 | 124190 | E2 | COU-QUE | Steel Mess Supports | 621 | 163 |  | 0.26248 | 0.40597
|  |  |  | Messenger Clamps | 269 | 13 |  | 0.048327
|  |  |  | Messenger Wire Pull | 780 | 580 |  | 0.74359
|  |  |  | Messenger Wire Tension | 466 | 370 |  | 0.79399
|  |  |  | # Cables Pulled | 79 | 26 |  | 0.32911
|  |  |  | Messenger Straps | 120 | 31 |  | 0.25833
124190 | 124490 | E2 | COU-QUE | Steel Mess Supports | 963 | 414 |  | 0.42991 | 0.33164
|  |  |  | Messenger Clamps | 556 | 289 |  | 0.51978
|  |  |  | Messenger Wire Pull | 417 | 38 |  | 0.091127
|  |  |  | Messenger Wire Tension | 263 | 17 |  | 0.064639
|  |  |  | # Cables Pulled | 116 | 87 |  | 0.75
|  |  |  | Messenger Straps | 186 | 25 |  | 0.13441
124490 | 124700 | E2 | COU-QUE | Steel Mess Supports | 132 | 74 |  | 0.56061 | 0.35546
|  |  |  | Messenger Clamps | 204 | 5 |  | 0.02451
|  |  |  | Messenger Wire Pull | 847 | 27 |  | 0.031877
|  |  |  | Messenger Wire Tension | 102 | 70 |  | 0.68627
|  |  |  | # Cables Pulled | 12 | 3 |  | 0.25
|  |  |  | Messenger Straps | 283 | 164 |  | 0.57951
124700 | 125010 | E2 | COU-QUE | Steel Mess Supports | 429 | 398 |  | 0.92774 | 0.82235
|  |  |  | Messenger Clamps | 916 | 903 |  | 0.98581
|  |  |  | Messenger Wire Pull | 283 | 123 |  | 0.43463
|  |  |  | Messenger Wire Tension | 135 | 96 |  | 0.71111
|  |  |  | # Cables Pulled | 750 | 737 |  | 0.98267
|  |  |  | Messenger Straps | 612 | 546 |  | 0.89216
|  | E2 | COU-QUE | Crossover (Arch Bar Installation) | 694 | 32 |  | 0.04611
75650 | 78244 | B3 | BERGEN ST | Steel Mess Supports | 104 | 17 |  | 0.16346 | 0.46873
|  |  |  | Messenger Clamps | 541 | 458 |  | 0.84658
|  |  |  | Messenger Wire Pull | 366 | 48 |  | 0.13115
|  |  |  | Messenger Wire Tension | 713 | 151 |  | 0.21178
|  |  |  | # Cables Pulled | 849 | 498 |  | 0.58657
|  |  |  | Messenger Straps | 936 | 817 |  | 0.87286
|  | B3 | BER-JAY | Steel Mess Supports | 789 | 689 |  | 0.87326 | 0.48943
|  |  |  | Messenger Clamps | 866 | 456 |  | 0.52656
|  |  |  | Messenger Wire Pull | 909 | 257 |  | 0.28273
|  |  |  | Messenger Wire Tension | 106 | 81 |  | 0.76415
|  |  |  | # Cables Pulled | 365 | 5 |  | 0.013699
|  |  |  | Messenger Straps | 168 | 80 |  | 0.47619
|  | B4 | BER-JAY | Steel Mess Supports | 482 | 127 |  | 0.26349 | 0.30548
|  |  |  | Messenger Clamps | 378 | 56 |  | 0.14815
|  |  |  | Messenger Wire Pull | 659 | 127 |  | 0.19272
|  |  |  | Messenger Wire Tension | 400 | 139 |  | 0.3475
|  |  |  | # Cables Pulled | 205 | 151 |  | 0.73659
|  |  |  | Messenger Straps | 457 | 66 |  | 0.14442
|  | E3/E4 | COURT SQ | Steel Mess Supports | 194 | 128 |  | 0.65979 | 0.39975
|  |  |  | Messenger Clamps | 939 | 181 |  | 0.19276
|  |  |  | Messenger Wire Pull | 979 | 599 |  | 0.61185
|  |  |  | Messenger Wire Tension | 997 | 264 |  | 0.26479
|  |  |  | # Cables Pulled | 647 | 269 |  | 0.41577
|  |  |  | Messenger Straps | 284 | 72 |  | 0.25352
75640 | 75300 | B1 | BER-CAR | Steel Mess Supports | 566 | 331 |  | 0.58481 | 0.55393
|  |  |  | Messenger Clamps | 263 | 182 |  | 0.69202
|  |  |  | Messenger Wire Pull | 577 | 207 |  | 0.35875
|  |  |  | Messenger Wire Tension | 78 | 41 |  | 0.52564
|  |  |  | # Cables Pulled | 47 | 25 |  | 0.53191
|  |  |  | Messenger Straps | 184 | 116 |  | 0.63043
68570 | 68330 | B3 | 4TH AVE | Steel Mess Supports | 140 | 133 |  | 0.95 | 0.69445
|  |  |  | Messenger Clamps | 616 | 440 |  | 0.71429
|  |  |  | Messenger Wire Pull | 511 | 470 |  | 0.91977
|  |  |  | Messenger Wire Tension | 263 | 213 |  | 0.80989
|  |  |  | # Cables Pulled | 245 | 119 |  | 0.48571
|  |  |  | Messenger Straps | 547 | 157 |  | 0.28702
68330 | 68030 | B3 | 4AV-7AV | Steel Mess Supports | 529 | 308 |  | 0.58223 | 0.5408
|  |  |  | Messenger Clamps | 275 | 199 |  | 0.72364
|  |  |  | Messenger Wire Pull | 938 | 820 |  | 0.8742
|  |  |  | Messenger Wire Tension | 980 | 275 |  | 0.28061
|  |  |  | # Cables Pulled | 121 | 22 |  | 0.18182
|  |  |  | Messenger Straps | 948 | 571 |  | 0.60232
66070 | 66000 | B3 | 4AV-7AV | Steel Mess Supports | 117 | 99 |  | 0.84615 | 0.55174
|  |  |  | Messenger Clamps | 725 | 722 |  | 0.99586
|  |  |  | Messenger Wire Pull | 495 | 15 |  | 0.030303
|  |  |  | Messenger Wire Tension | 131 | 109 |  | 0.83206
|  |  |  | # Cables Pulled | 321 | 154 |  | 0.47975
|  |  |  | Messenger Straps | 578 | 73 |  | 0.1263
60350 | 60000 | B1 | 15S-FOR | Steel Mess Supports | 826 | 93 |  | 0.11259 | 0.66102
|  |  |  | Messenger Clamps | 434 | 429 |  | 0.98848
|  |  |  | Messenger Wire Pull | 17 | 16 |  | 0.94118
|  |  |  | Messenger Wire Tension | 199 | 162 |  | 0.81407
|  |  |  | # Cables Pulled | 40 | 14 |  | 0.35
|  |  |  | Messenger Straps | 941 | 715 |  | 0.75983
56440 | 56350 | B1 | FOR-CHU | Steel Mess Supports | 131 | 91 |  | 0.69466 | 0.38826
|  |  |  | Messenger Clamps | 282 | 152 |  | 0.53901
|  |  |  | Messenger Wire Pull | 963 | 119 |  | 0.12357
|  |  |  | Messenger Wire Tension | 496 | 428 |  | 0.8629
|  |  |  | # Cables Pulled | 543 | 13 |  | 0.023941
|  |  |  | Messenger Straps | 433 | 37 |  | 0.08545
55580 | 54500 | B2 | CHU-DIT | Steel Mess Supports | 445 | 354 |  | 0.79551 | 0.48035
|  |  |  | Messenger Clamps | 356 | 199 |  | 0.55899
|  |  |  | Messenger Wire Pull | 273 | 32 |  | 0.11722
|  |  |  | Messenger Wire Tension | 574 | 232 |  | 0.40418
|  |  |  | # Cables Pulled | 267 | 163 |  | 0.61049
|  |  |  | Messenger Straps | 470 | 186 |  | 0.39574
54730 | 55000 | B2 | CHU-DIT | Steel Mess Supports | 363 | 197 |  | 0.5427 | 0.53414
|  |  |  | Messenger Clamps | 514 | 264 |  | 0.51362
|  |  |  | Messenger Wire Pull | 983 | 430 |  | 0.43744
|  |  |  | Messenger Wire Tension | 627 | 385 |  | 0.61404
|  |  |  | # Cables Pulled | 394 | 64 |  | 0.16244
|  |  |  | Messenger Straps | 627 | 586 |  | 0.93461
55485 | 55725 | B2 | CHU-DIT | Steel Mess Supports | 185 | 84 |  | 0.45405 | 0.41927
|  |  |  | Messenger Clamps | 910 | 378 |  | 0.41538
|  |  |  | Messenger Wire Pull | 185 | 33 |  | 0.17838
|  |  |  | Messenger Wire Tension | 107 | 3 |  | 0.028037
|  |  |  | # Cables Pulled | 855 | 376 |  | 0.43977
|  |  |  | Messenger Straps | 618 | 618 |  | 1
55725 | 56635 | B2 | CHURCH AVE | Steel Mess Supports | 993 | 355 |  | 0.3575 | 0.45289
|  |  |  | Messenger Clamps | 815 | 458 |  | 0.56196
|  |  |  | Messenger Wire Pull | 587 | 244 |  | 0.41567
|  |  |  | Messenger Wire Tension | 889 | 275 |  | 0.30934
|  |  |  | # Cables Pulled | 686 | 473 |  | 0.6895
|  |  |  | Messenger Straps | 999 | 383 |  | 0.38338
57320 | 57445 | B2 | CHU-FOR | Steel Mess Supports | 28 | 10 |  | 0.35714 | 0.34331
|  |  |  | Messenger Clamps | 628 | 276 |  | 0.43949
|  |  |  | Messenger Wire Pull | 81 | 33 |  | 0.40741
|  |  |  | Messenger Wire Tension | 860 | 385 |  | 0.44767
|  |  |  | # Cables Pulled | 868 | 134 |  | 0.15438
|  |  |  | Messenger Straps | 331 | 84 |  | 0.25378
60165 | 60620 | B2 | 15S-FOR | Steel Mess Supports | 396 | 64 |  | 0.16162 | 0.34646
|  |  |  | Messenger Clamps | 625 | 323 |  | 0.5168
|  |  |  | Messenger Wire Pull | 76 | 8 |  | 0.10526
|  |  |  | Messenger Wire Tension | 300 | 111 |  | 0.37
|  |  |  | # Cables Pulled | 571 | 118 |  | 0.20665
|  |  |  | Messenger Straps | 618 | 444 |  | 0.71845
62560 | 63425 | B2 | 15TH STREET PROSPECT PARK | Steel Mess Supports | 294 | 172 |  | 0.58503 | 0.59921
|  |  |  | Messenger Clamps | 395 | 347 |  | 0.87848
|  |  |  | Messenger Wire Pull | 577 | 309 |  | 0.53553
|  |  |  | Messenger Wire Tension | 134 | 123 |  | 0.91791
|  |  |  | # Cables Pulled | 959 | 404 |  | 0.42127
|  |  |  | Messenger Straps | 922 | 237 |  | 0.25705
67950 | 68330 | B4/B2 | 4AV-7AV | Steel Mess Supports | 48 | 46 |  | 0.95833 | 0.74831
|  |  |  | Messenger Clamps | 604 | 383 |  | 0.63411
|  |  |  | Messenger Wire Pull | 472 | 347 |  | 0.73517
|  |  |  | Messenger Wire Tension | 375 | 281 |  | 0.74933
|  |  |  | # Cables Pulled | 63 | 27 |  | 0.42857
|  |  |  | Messenger Straps | 766 | 754 |  | 0.98433
74740 | 74840 | B2 | CAR-BER | Steel Mess Supports | 898 | 658 |  | 0.73274 | 0.77502
|  |  |  | Messenger Clamps | 711 | 610 |  | 0.85795
|  |  |  | Messenger Wire Pull | 74 | 68 |  | 0.91892
|  |  |  | Messenger Wire Tension | 919 | 418 |  | 0.45484
|  |  |  | # Cables Pulled | 444 | 402 |  | 0.90541
|  |  |  | Messenger Straps | 892 | 696 |  | 0.78027
75395 | 75650 | B2 | CAR-BER | Steel Mess Supports | 484 | 260 |  | 0.53719 | 0.71198
|  |  |  | Messenger Clamps | 398 | 352 |  | 0.88442
|  |  |  | Messenger Wire Pull | 482 | 376 |  | 0.78008
|  |  |  | Messenger Wire Tension | 407 | 136 |  | 0.33415
|  |  |  | # Cables Pulled | 274 | 248 |  | 0.90511
|  |  |  | Messenger Straps | 479 | 398 |  | 0.8309
78905 | 75950 | B3 | JAY-BER | Steel Mess Supports | 890 | 159 |  | 0.17865 | 0.49946
|  |  |  | Messenger Clamps | 823 | 741 |  | 0.90036
|  |  |  | Messenger Wire Pull | 149 | 30 |  | 0.20134
|  |  |  | Messenger Wire Tension | 366 | 35 |  | 0.095628
|  |  |  | # Cables Pulled | 83 | 65 |  | 0.78313
|  |  |  | Messenger Straps | 542 | 454 |  | 0.83764
75950 | 75650 | B3 | BERGEN ST | Steel Mess Supports | 938 | 207 |  | 0.22068 | 0.34271
|  |  |  | Messenger Clamps | 636 | 274 |  | 0.43082
|  |  |  | Messenger Wire Pull | 956 | 331 |  | 0.34623
|  |  |  | Messenger Wire Tension | 159 | 35 |  | 0.22013
|  |  |  | # Cables Pulled | 943 | 126 |  | 0.13362
|  |  |  | Messenger Straps | 105 | 74 |  | 0.70476
75650 | 75420 | B3 | BER-CAR | Steel Mess Supports | 268 | 103 |  | 0.38433 | 0.54847
|  |  |  | Messenger Clamps | 853 | 756 |  | 0.88628
|  |  |  | Messenger Wire Pull | 736 | 607 |  | 0.82473
|  |  |  | Messenger Wire Tension | 285 | 284 |  | 0.99649
|  |  |  | # Cables Pulled | 968 | 81 |  | 0.083678
|  |  |  | Messenger Straps | 815 | 94 |  | 0.11534
73285 | 72960 | B3 | BER-CAR | Steel Mess Supports | 844 | 582 |  | 0.68957 | 0.61391
|  |  |  | Messenger Clamps | 381 | 59 |  | 0.15486
|  |  |  | Messenger Wire Pull | 204 | 72 |  | 0.35294
|  |  |  | Messenger Wire Tension | 360 | 338 |  | 0.93889
|  |  |  | # Cables Pulled | 829 | 519 |  | 0.62606
|  |  |  | Messenger Straps | 520 | 479 |  | 0.92115
72960 | 72035 | B3/B4 | CAR-4TH | Steel Mess Supports | 228 | 161 |  | 0.70614 | 0.37847
|  |  |  | Messenger Clamps | 291 | 236 |  | 0.811
|  |  |  | Messenger Wire Pull | 672 | 31 |  | 0.046131
|  |  |  | Messenger Wire Tension | 592 | 266 |  | 0.44932
|  |  |  | # Cables Pulled | 99 | 9 |  | 0.090909
|  |  |  | Messenger Straps | 747 | 125 |  | 0.16734
71150 | 70965 | B3/B4 | CAR-4TH | Steel Mess Supports | 126 | 121 |  | 0.96032 | 0.61579
|  |  |  | Messenger Clamps | 824 | 747 |  | 0.90655
|  |  |  | Messenger Wire Pull | 352 | 98 |  | 0.27841
|  |  |  | Messenger Wire Tension | 579 | 333 |  | 0.57513
|  |  |  | # Cables Pulled | 525 | 32 |  | 0.060952
|  |  |  | Messenger Straps | 866 | 791 |  | 0.91339
70965 | 70445 | B3/B6 | CAR-4TH | Steel Mess Supports | 985 | 251 |  | 0.25482 | 0.4179
|  |  |  | Messenger Clamps | 806 | 104 |  | 0.12903
|  |  |  | Messenger Wire Pull | 238 | 209 |  | 0.87815
|  |  |  | Messenger Wire Tension | 887 | 201 |  | 0.22661
|  |  |  | # Cables Pulled | 832 | 183 |  | 0.21995
|  |  |  | Messenger Straps | 527 | 421 |  | 0.79886
70445 | 70045 | B3/B7 | CAR-4TH | Steel Mess Supports | 196 | 140 |  | 0.71429 | 0.64773
|  |  |  | Messenger Clamps | 141 | 114 |  | 0.80851
|  |  |  | Messenger Wire Pull | 35 | 20 |  | 0.57143
|  |  |  | Messenger Wire Tension | 201 | 166 |  | 0.82587
|  |  |  | # Cables Pulled | 694 | 344 |  | 0.49568
|  |  |  | Messenger Straps | 17 | 8 |  | 0.47059
68625 | 68400 | B3/B8 | CAR-4TH | Steel Mess Supports | 366 | 143 |  | 0.39071 | 0.57764
|  |  |  | Messenger Clamps | 991 | 734 |  | 0.74067
|  |  |  | Messenger Wire Pull | 876 | 850 |  | 0.97032
|  |  |  | Messenger Wire Tension | 909 | 231 |  | 0.25413
|  |  |  | # Cables Pulled | 907 | 567 |  | 0.62514
|  |  |  | Messenger Straps | 596 | 289 |  | 0.4849
68400 | 68330 | B3/B9 | CAR-4TH | Steel Mess Supports | 122 | 65 |  | 0.53279 | 0.55494
|  |  |  | Messenger Clamps | 801 | 606 |  | 0.75655
|  |  |  | Messenger Wire Pull | 593 | 394 |  | 0.66442
|  |  |  | Messenger Wire Tension | 484 | 192 |  | 0.39669
|  |  |  | # Cables Pulled | 99 | 53 |  | 0.53535
|  |  |  | Messenger Straps | 534 | 237 |  | 0.44382

## AXLE COUNTER
Stationing | Track No | Location | Activity | Date | Progress | General Progress | Notes | DWG REF.
54600 | B1 | DIT-CHU | Axle Counter Installation |  | 0.588 | 60.08% | STATIONING SHOWN IS THAT OF THE NEAREST IJ, AXC STATIONING DOES NOT EXIST | B1-546
|  |  | JB Installation |  | 74.47%
|  |  | Line Cable Installation |  | 91.12%
|  |  | Express Cable Installation |  | 4.428%
|  |  | Pre-Operation Testing |  | 71.56%
| B1 |  | Axle Counter Installation |  | 97.32% | 63.58% | NO INFO | B1-547
|  |  | JB Installation |  | 29.13%
|  |  | Line Cable Installation |  | 25.01%
|  |  | Express Cable Installation |  | 95.6%
|  |  | Pre-Operation Testing |  | 70.83%
59297 | B1 | FOR-15S | Axle Counter Installation |  | 82.72% | 58.31% |  | B1-553
|  |  | JB Installation |  | 20.69%
|  |  | Line Cable Installation |  | 86.82%
|  |  | Express Cable Installation |  | 62.92%
|  |  | Pre-Operation Testing |  | 38.39%
| B1 |  | Axle Counter Installation |  | 17.33% | 35.5% | NO INFO | B1-554
|  |  | JB Installation |  | 29.97%
|  |  | Line Cable Installation |  | 34.61%
|  |  | Express Cable Installation |  | 90.38%
|  |  | Pre-Operation Testing |  | 5.191%
55687 | B1 | DIT-CHU | Axle Counter Installation |  | 95.13% | 64.37% |  | B1-557
|  |  | JB Installation |  | 74.59%
|  |  | Line Cable Installation |  | 25.25%
|  |  | Express Cable Installation |  | 89.69%
|  |  | Pre-Operation Testing |  | 37.19%
56367 | B1 | CHU-FOR | Axle Counter Installation |  | 20.76% | 28.88% |  | B1-564
|  |  | JB Installation |  | 17.24%
|  |  | Line Cable Installation |  | 6.988%
|  |  | Express Cable Installation |  | 25.82%
|  |  | Pre-Operation Testing |  | 73.59%
58524.6 | B1 | FORT HAMILTON PARKWAY | Axle Counter Installation |  | 62.96% | 50.1% |  | B1-585
|  |  | JB Installation |  | 38.22%
|  |  | Line Cable Installation |  | 95.99%
|  |  | Express Cable Installation |  | 26.4%
|  |  | Pre-Operation Testing |  | 26.91%
59210.25 | B1 | FOR-15S | Axle Counter Installation |  | 35.72% | 68.88% |  | B1-592
|  |  | JB Installation |  | 92.51%
|  |  | Line Cable Installation |  | 44.39%
|  |  | Express Cable Installation |  | 73.06%
|  |  | Pre-Operation Testing |  | 98.72%
62572.5 | B1 | FOR-15S | Axle Counter Installation |  | 93.82% | 75.84% |  | B1-626
|  |  | JB Installation |  | 93.85%
|  |  | Line Cable Installation |  | 40.44%
|  |  | Express Cable Installation |  | 61.86%
|  |  | Pre-Operation Testing |  | 89.23%
63251.4 | B1 | 15S-7AV | Axle Counter Installation |  | 80.48% | 56.4% |  | B1-632
|  |  | JB Installation |  | 16.22%
|  |  | Line Cable Installation |  | 21.15%
|  |  | Express Cable Installation |  | 97.8%
|  |  | Pre-Operation Testing |  | 66.37%
65387.3 | B1 | 15S-7AV | Axle Counter Installation |  | 47.99% | 61.24% |  | B1-654
|  |  | JB Installation |  | 91.87%
|  |  | Line Cable Installation |  | 95.53%
|  |  | Express Cable Installation |  | 39.02%
|  |  | Pre-Operation Testing |  | 31.77%
66076 | B1 | 7AV-4TH | Axle Counter Installation |  | 15.69% | 43.83% |  | B1-661
|  |  | JB Installation |  | 32.99%
|  |  | Line Cable Installation |  | 33.83%
|  |  | Express Cable Installation |  | 68.41%
|  |  | Pre-Operation Testing |  | 68.23%
73206.7 | B1 | SMI-CAR | Axle Counter Installation |  | 60.66% | 43.15% |  | B1-732
|  |  | JB Installation |  | 6.736%
|  |  | Line Cable Installation |  | 42.23%
|  |  | Express Cable Installation |  | 66.9%
|  |  | Pre-Operation Testing |  | 39.2%
73932 | B1 | CAR-BER | Axle Counter Installation |  | 66.59% | 58.19% |  | B1-739
|  |  | JB Installation |  | 27.74%
|  |  | Line Cable Installation |  | 86.42%
|  |  | Express Cable Installation |  | 42.4%
|  |  | Pre-Operation Testing |  | 67.82%
75408 | B1 | CAR-BER | Axle Counter Installation |  | 31.46% | 58.38% |  | B1-755
|  |  | JB Installation |  | 85.93%
|  |  | Line Cable Installation |  | 59.21%
|  |  | Express Cable Installation |  | 90.95%
|  |  | Pre-Operation Testing |  | 24.36%
75669 | B1 | CAR-BER | Axle Counter Installation |  | 44.23% | 50.32% |  | B1-756
|  |  | JB Installation |  | 54.16%
|  |  | Line Cable Installation |  | 25.13%
|  |  | Express Cable Installation |  | 69.79%
|  |  | Pre-Operation Testing |  | 58.3%
76352 | B1 | BER-HOY | Axle Counter Installation |  | 96.59% | 52.97% |  | B1-763, B1-764
|  |  | JB Installation |  | 89.83%
|  |  | Line Cable Installation |  | 45.95%
|  |  | Express Cable Installation |  | 25.2%
|  |  | Pre-Operation Testing |  | 7.285%
76589 | B1 | HOYT-SCHERMERHORN | Axle Counter Installation |  | 44.56% | 82.51% |  | B1-766
|  |  | JB Installation |  | 99.25%
|  |  | Line Cable Installation |  | 83.96%
|  |  | Express Cable Installation |  | 90.77%
|  |  | Pre-Operation Testing |  | 94%
76901.5 | B1 | HOY-FUL | Axle Counter Installation |  | 94.07% | 64.58% |  | B1-770
|  |  | JB Installation |  | 99.09%
|  |  | Line Cable Installation |  | 94.96%
|  |  | Express Cable Installation |  | 33.92%
|  |  | Pre-Operation Testing |  | 0.8488%
77088 | B1 | FUL-CLI | Axle Counter Installation |  | 50.69% | 49.58% |  | B1-771
|  |  | JB Installation |  | 51.03%
|  |  | Line Cable Installation |  | 50.45%
|  |  | Express Cable Installation |  | 59.05%
|  |  | Pre-Operation Testing |  | 36.67%
54737 | B2 | DIT-CHU | Axle Counter Installation |  | 15.65% | 61.44% |  | B2-546
|  |  | JB Installation |  | 87.82%
|  |  | Line Cable Installation |  | 33.58%
|  |  | Express Cable Installation |  | 70.86%
|  |  | Pre-Operation Testing |  | 99.27%
54731 | B2 |  | Axle Counter Installation |  | 4.778% | 38.31% |  | B2-547
|  |  | JB Installation |  | 38.02%
|  |  | Line Cable Installation |  | 77.46%
|  |  | Express Cable Installation |  | 42.8%
|  |  | Pre-Operation Testing |  | 28.49%
55000 | B2 | DIT-CHU | Axle Counter Installation |  | 5.747% | 46.07% |  | B2-549
|  |  | JB Installation |  | 60.42%
|  |  | Line Cable Installation |  | 59.04%
|  |  | Express Cable Installation |  | 99.17%
|  |  | Pre-Operation Testing |  | 5.939%
55498 | B2 | DIT-CHU | Axle Counter Installation |  | 43.03% | 48.65% |  | B2-554
|  |  | JB Installation |  | 97.23%
|  |  | Line Cable Installation |  | 38.14%
|  |  | Express Cable Installation |  | 18.19%
|  |  | Pre-Operation Testing |  | 46.67%
| B2 |  | Axle Counter Installation |  | 18.39% | 59.18% | NO REF DWG EXISTS | B2-555
|  |  | JB Installation |  | 85.73%
|  |  | Line Cable Installation |  | 87.14%
|  |  | Express Cable Installation |  | 97.69%
|  |  | Pre-Operation Testing |  | 6.963%
| B2 |  | Axle Counter Installation |  | 61.14% | 50.35% | NO REF DWG EXISTS | B2-556
|  |  | JB Installation |  | 72.65%
|  |  | Line Cable Installation |  | 79.64%
|  |  | Express Cable Installation |  | 0.7603%
|  |  | Pre-Operation Testing |  | 37.56%
55857 | B2 | CHURCH AVE | Axle Counter Installation |  | 60.84% | 60.19% |  | B2-558
|  |  | JB Installation |  | 1.839%
|  |  | Line Cable Installation |  | 72.59%
|  |  | Express Cable Installation |  | 88.39%
|  |  | Pre-Operation Testing |  | 77.31%
58500 | B2 | FORT HAMILTON PARKWAY | Axle Counter Installation |  | 69.03% | 66.04% |  | B2-585
|  |  | JB Installation |  | 79.4%
|  |  | Line Cable Installation |  | 61.37%
|  |  | Express Cable Installation |  | 39.12%
|  |  | Pre-Operation Testing |  | 81.27%
59203.8 | B2 | FOR-15S | Axle Counter Installation |  | 70.01% | 59.52% |  | B2-592
|  |  | JB Installation |  | 38.07%
|  |  | Line Cable Installation |  | 53.19%
|  |  | Express Cable Installation |  | 41.01%
|  |  | Pre-Operation Testing |  | 95.35%
62550.6 | B2 |  | Axle Counter Installation |  | 60.94% | 66.63% |  | B2-625
|  |  | JB Installation |  | 34.92%
|  |  | Line Cable Installation |  | 96.96%
|  |  | Express Cable Installation |  | 65.49%
|  |  | Pre-Operation Testing |  | 74.86%
65375.3 | B2 | 15S-7AV | Axle Counter Installation |  | 29.72% | 45.58% |  | B2-654
|  |  | JB Installation |  | 19.49%
|  |  | Line Cable Installation |  | 18.73%
|  |  | Express Cable Installation |  | 72.08%
|  |  | Pre-Operation Testing |  | 87.87%
66062.3 | B2 | 7AV-4TH | Axle Counter Installation |  | 98.91% | 73.85% |  | B2-661
|  |  | JB Installation |  | 95.38%
|  |  | Line Cable Installation |  | 93.01%
|  |  | Express Cable Installation |  | 68.31%
|  |  | Pre-Operation Testing |  | 13.62%
| B2 |  | Axle Counter Installation |  | 15.93% | 23.33% | NO REF DWG EXISTS | B2-665
|  |  | JB Installation |  | 5.011%
|  |  | Line Cable Installation |  | 18.57%
|  |  | Express Cable Installation |  | 4.291%
|  |  | Pre-Operation Testing |  | 72.85%
| B2 |  | Axle Counter Installation |  | 35.29% | 34.41% | NO REF DWG EXISTS | B2-684
|  |  | JB Installation |  | 78.75%
|  |  | Line Cable Installation |  | 12.05%
|  |  | Express Cable Installation |  | 22.13%
|  |  | Pre-Operation Testing |  | 23.84%
| B2 |  | Axle Counter Installation |  | 75.21% | 54.83% | NO REF DWG EXISTS | B2-691
|  |  | JB Installation |  | 25.88%
|  |  | Line Cable Installation |  | 95.08%
|  |  | Express Cable Installation |  | 18.15%
|  |  | Pre-Operation Testing |  | 59.82%
| B2 |  | Axle Counter Installation |  | 2.219% | 36.51% | NO REF DWG EXISTS | B2-692
|  |  | JB Installation |  | 19.31%
|  |  | Line Cable Installation |  | 22.4%
|  |  | Express Cable Installation |  | 58.13%
|  |  | Pre-Operation Testing |  | 80.52%
| B2 |  | Axle Counter Installation |  | 57.47% | 36.43% | NO REF DWG EXISTS | B2-692A
|  |  | JB Installation |  | 20.22%
|  |  | Line Cable Installation |  | 51.83%
|  |  | Express Cable Installation |  | 18.91%
|  |  | Pre-Operation Testing |  | 33.72%
| B2 |  | Axle Counter Installation |  | 7.168% | 34.94% | NO REF DWG EXISTS | B2-693
|  |  | JB Installation |  | 97.03%
|  |  | Line Cable Installation |  | 25.34%
|  |  | Express Cable Installation |  | 22.22%
|  |  | Pre-Operation Testing |  | 22.96%
| B2 |  | Axle Counter Installation |  | 64.02% | 40.34% | NO REF DWG EXISTS | B2-705
|  |  | JB Installation |  | 19.87%
|  |  | Line Cable Installation |  | 48.02%
|  |  | Express Cable Installation |  | 60.44%
|  |  | Pre-Operation Testing |  | 9.349%
| B2 |  | Axle Counter Installation |  | 64.95% | 41.11% | NO REF DWG EXISTS | B2-712
|  |  | JB Installation |  | 32.66%
|  |  | Line Cable Installation |  | 24.19%
|  |  | Express Cable Installation |  | 30.63%
|  |  | Pre-Operation Testing |  | 53.1%
| B2 |  | Axle Counter Installation |  | 82.09% | 75% | DWG EXISTS, BUT EMPTY | B2-732
|  |  | JB Installation |  | 79.31%
|  |  | Line Cable Installation |  | 64.56%
|  |  | Express Cable Installation |  | 94.76%
|  |  | Pre-Operation Testing |  | 54.29%
73926.3 | B2 | CARROLL STREET | Axle Counter Installation |  | 60% | 43.28% |  | B2-739
|  |  | JB Installation |  | 69.32%
|  |  | Line Cable Installation |  | 10.36%
|  |  | Express Cable Installation |  | 52.26%
|  |  | Pre-Operation Testing |  | 24.46%
75267 | B2 | CAR-BER | Axle Counter Installation |  | 49.74% | 29.18% |  | B2-753
|  |  | JB Installation |  | 5.469%
|  |  | Line Cable Installation |  | 0.6676%
|  |  | Express Cable Installation |  | 81.94%
|  |  | Pre-Operation Testing |  | 8.101%
| B2 |  | Axle Counter Installation |  | 55.72% | 71.34% | NO REF DWG EXISTS | B2-755
|  |  | JB Installation |  | 61.74%
|  |  | Line Cable Installation |  | 93.07%
|  |  | Express Cable Installation |  | 76.12%
|  |  | Pre-Operation Testing |  | 70.04%
75646 | B2 | CAR-BER | Axle Counter Installation |  | 10.27% | 28.05% |  | B2-756
|  |  | JB Installation |  | 4.931%
|  |  | Line Cable Installation |  | 61.32%
|  |  | Express Cable Installation |  | 5.713%
|  |  | Pre-Operation Testing |  | 57.99%
76352 | B2 |  | Axle Counter Installation |  | 79.43% | 53.05% |  | B2-763, B2-764
|  |  | JB Installation |  | 89.3%
|  |  | Line Cable Installation |  | 3.506%
|  |  | Express Cable Installation |  | 64.98%
|  |  | Pre-Operation Testing |  | 28.05%
76536 | B2 |  | Axle Counter Installation |  | 85.28% | 57.54% |  | B2-765
|  |  | JB Installation |  | 53.68%
|  |  | Line Cable Installation |  | 31.53%
|  |  | Express Cable Installation |  | 35.43%
|  |  | Pre-Operation Testing |  | 81.78%
76797 | B2 |  | Axle Counter Installation |  | 91.91% | 68.94% |  | B2-768
|  |  | JB Installation |  | 90.29%
|  |  | Line Cable Installation |  | 77.77%
|  |  | Express Cable Installation |  | 17.62%
|  |  | Pre-Operation Testing |  | 67.13%
77116 | B2 |  | Axle Counter Installation |  | 44.17% | 51.52% |  | B2-770
|  |  | JB Installation |  | 23.88%
|  |  | Line Cable Installation |  | 80.9%
|  |  | Express Cable Installation |  | 25.35%
|  |  | Pre-Operation Testing |  | 83.32%
| B3 |  | Axle Counter Installation |  | 7.309% | 28% | REF DWG EXISTS, NO STATIONINGS SHOWN | B3-546
|  |  | JB Installation |  | 8.018%
|  |  | Line Cable Installation |  | 13.51%
|  |  | Express Cable Installation |  | 24.67%
|  |  | Pre-Operation Testing |  | 86.49%
| B3 |  | Axle Counter Installation |  | 76% | 60.58% | REF DWG EXISTS, NO STATIONINGS SHOWN | B3-548
|  |  | JB Installation |  | 81.76%
|  |  | Line Cable Installation |  | 84.01%
|  |  | Express Cable Installation |  | 36.2%
|  |  | Pre-Operation Testing |  | 24.92%
53361 | B3 |  | Axle Counter Installation |  | 10.14% | 49.79% |  | B3-554
|  |  | JB Installation |  | 94.39%
|  |  | Line Cable Installation |  | 70.42%
|  |  | Express Cable Installation |  | 27.56%
|  |  | Pre-Operation Testing |  | 46.41%
55626 | B3 |  | Axle Counter Installation |  | 3.099% | 19.13% |  | B3-555
|  |  | JB Installation |  | 49.16%
|  |  | Line Cable Installation |  | 38.59%
|  |  | Express Cable Installation |  | 1.257%
|  |  | Pre-Operation Testing |  | 3.543%
| B3 |  | Axle Counter Installation |  | 22.79% | 54.8% | REF DWG EXISTS, NO STATIONINGS SHOWN | B3-556
|  |  | JB Installation |  | 69.89%
|  |  | Line Cable Installation |  | 93.62%
|  |  | Express Cable Installation |  | 66.13%
|  |  | Pre-Operation Testing |  | 21.6%
| B3 |  | Axle Counter Installation |  | 20.56% | 39.05% | REF DWG EXISTS, NO STATIONINGS SHOWN | B3-557
|  |  | JB Installation |  | 69.57%
|  |  | Line Cable Installation |  | 20.17%
|  |  | Express Cable Installation |  | 44.06%
|  |  | Pre-Operation Testing |  | 40.89%
| B3 |  | Axle Counter Installation |  | 13.7% | 31.02% | NO REF DWG EXISTS | B3-565
|  |  | JB Installation |  | 5.152%
|  |  | Line Cable Installation |  | 41.24%
|  |  | Express Cable Installation |  | 4.527%
|  |  | Pre-Operation Testing |  | 90.46%
65384.6 | B3 |  | Axle Counter Installation |  | 23.89% | 45.89% |  | B3-654
|  |  | JB Installation |  | 73.32%
|  |  | Line Cable Installation |  | 31.36%
|  |  | Express Cable Installation |  | 10.54%
|  |  | Pre-Operation Testing |  | 90.35%
66073.4 | B3 |  | Axle Counter Installation |  | 13.59% | 45.23% |  | B3-661
|  |  | JB Installation |  | 54.33%
|  |  | Line Cable Installation |  | 64.57%
|  |  | Express Cable Installation |  | 31.38%
|  |  | Pre-Operation Testing |  | 62.26%
| B3 |  | Axle Counter Installation |  | 88.46% | 43.04% | NO REF DWG EXISTS | B3-689
|  |  | JB Installation |  | 61%
|  |  | Line Cable Installation |  | 28.95%
|  |  | Express Cable Installation |  | 30.66%
|  |  | Pre-Operation Testing |  | 6.129%
| B3 |  | Axle Counter Installation |  | 52.02% | 38.28% | NO REF DWG EXISTS | B3-690
|  |  | JB Installation |  | 43.73%
|  |  | Line Cable Installation |  | 20.5%
|  |  | Express Cable Installation |  | 51.56%
|  |  | Pre-Operation Testing |  | 23.59%
| B3 |  | Axle Counter Installation |  | 38.23% | 38.63% | NO REF DWG EXISTS | B3-691
|  |  | JB Installation |  | 2.66%
|  |  | Line Cable Installation |  | 73.04%
|  |  | Express Cable Installation |  | 19.62%
|  |  | Pre-Operation Testing |  | 59.59%
| B3 |  | Axle Counter Installation |  | 61.62% | 39.71% | NO REF DWG EXISTS | B3-692
|  |  | JB Installation |  | 66.31%
|  |  | Line Cable Installation |  | 41.02%
|  |  | Express Cable Installation |  | 16.07%
|  |  | Pre-Operation Testing |  | 13.53%
| B3 |  | Axle Counter Installation |  | 59.12% | 55.73% | NO REF DWG EXISTS | B3-693
|  |  | JB Installation |  | 78.2%
|  |  | Line Cable Installation |  | 22.5%
|  |  | Express Cable Installation |  | 90.97%
|  |  | Pre-Operation Testing |  | 27.87%
| B3 |  | Axle Counter Installation |  | 56.08% | 41.74% | NO REF DWG EXISTS | B3-694
|  |  | JB Installation |  | 40.22%
|  |  | Line Cable Installation |  | 79.21%
|  |  | Express Cable Installation |  | 17.41%
|  |  | Pre-Operation Testing |  | 15.78%
| B3 |  | Axle Counter Installation |  | 85.5% | 49.67% | NO REF DWG EXISTS | B3-695
|  |  | JB Installation |  | 84.42%
|  |  | Line Cable Installation |  | 32.45%
|  |  | Express Cable Installation |  | 1.263%
|  |  | Pre-Operation Testing |  | 44.73%
| B3 |  | Axle Counter Installation |  | 25.32% | 52.2% | NO REF DWG EXISTS | B3-696
|  |  | JB Installation |  | 7.274%
|  |  | Line Cable Installation |  | 86.89%
|  |  | Express Cable Installation |  | 51.04%
|  |  | Pre-Operation Testing |  | 90.48%
75405 | B3 |  | Axle Counter Installation |  | 13.3% | 29.48% |  | B3-754
|  |  | JB Installation |  | 41%
|  |  | Line Cable Installation |  | 33.36%
|  |  | Express Cable Installation |  | 40.28%
|  |  | Pre-Operation Testing |  | 19.48%
| B3 |  | Axle Counter Installation |  | 60.7% | 66.87% | NO REF DWG EXISTS | B3-755
|  |  | JB Installation |  | 98.94%
|  |  | Line Cable Installation |  | 4.638%
|  |  | Express Cable Installation |  | 75.22%
|  |  | Pre-Operation Testing |  | 94.86%
75405 | B3 |  | Axle Counter Installation |  | 91.44% | 45.8% |  | B3-756
|  |  | JB Installation |  | 2.438%
|  |  | Line Cable Installation |  | 15.51%
|  |  | Express Cable Installation |  | 25.52%
|  |  | Pre-Operation Testing |  | 94.09%
76383 | B3 |  | Axle Counter Installation |  | 87.05% | 39.07% |  | B3-764
|  |  | JB Installation |  | 41.96%
|  |  | Line Cable Installation |  | 6.493%
|  |  | Express Cable Installation |  | 18.03%
|  |  | Pre-Operation Testing |  | 41.83%
76920 | B3 |  | Axle Counter Installation |  | 11.86% | 41.32% |  | B3-769
|  |  | JB Installation |  | 32.47%
|  |  | Line Cable Installation |  | 39.57%
|  |  | Express Cable Installation |  | 90.69%
|  |  | Pre-Operation Testing |  | 32%
| B4 |  | Axle Counter Installation |  | 74.44% | 41.29% | REF DWG EXISTS, NO STATIONINGS SHOWN | B4-547
|  |  | JB Installation |  | 19.51%
|  |  | Line Cable Installation |  | 28.27%
|  |  | Express Cable Installation |  | 65.1%
|  |  | Pre-Operation Testing |  | 19.14%
| B4 |  | Axle Counter Installation |  | 47.92% | 59.76% | REF DWG EXISTS, NO STATIONINGS SHOWN | B4-551
|  |  | JB Installation |  | 90.64%
|  |  | Line Cable Installation |  | 68%
|  |  | Express Cable Installation |  | 32.35%
|  |  | Pre-Operation Testing |  | 59.9%
| B4 |  | Axle Counter Installation |  | 35.12% | 47.05% | NO REF DWG EXISTS, AWAITING RESPONSE FROM THALES ON WHETHER THIS AXC WILL BE INSTALLED | B4-554A, B4-554B
|  |  | JB Installation |  | 11.68%
|  |  | Line Cable Installation |  | 4.924%
|  |  | Express Cable Installation |  | 87.43%
|  |  | Pre-Operation Testing |  | 96.1%
55533 | B4 |  | Axle Counter Installation |  | 30.79% | 55.38% |  | B4-555
|  |  | JB Installation |  | 90.68%
|  |  | Line Cable Installation |  | 53.9%
|  |  | Express Cable Installation |  | 63.07%
|  |  | Pre-Operation Testing |  | 38.44%
55685 | B4 |  | Axle Counter Installation |  | 2.205% | 51.5% |  | B4-556
|  |  | JB Installation |  | 65.87%
|  |  | Line Cable Installation |  | 89.49%
|  |  | Express Cable Installation |  | 90.02%
|  |  | Pre-Operation Testing |  | 9.898%
56396.5 | B4 |  | Axle Counter Installation |  | 21.64% | 45.21% |  | B4-564
|  |  | JB Installation |  | 88.49%
|  |  | Line Cable Installation |  | 37.19%
|  |  | Express Cable Installation |  | 59.88%
|  |  | Pre-Operation Testing |  | 18.83%

## SIGNALS
Stationing | Track No | Signal Type | Location | Activity | Date | Progress | General Progress | Notes
74076 | E1 | APPROACH |  | Signal Installation |  | 58.9% | 29.61% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 46.93%
|  |  |  | Stop Machine Installation |  | 47.27%
|  |  |  | Line Cable Installation |  | 4.356%
|  |  |  | Breakdown Testing |  | 21.29%
|  |  |  | Pre-Operation Testing |  | 16.22%
98643 | E1 | HOME |  | Signal Installation |  | 8.049% | 43.95% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 84.28%
|  |  |  | Stop Machine Installation |  | 9.542%
|  |  |  | Line Cable Installation |  | 57.24%
|  |  |  | Breakdown Testing |  | 49.02%
|  |  |  | Pre-Operation Testing |  | 95.91%
98903 | E1 | HOME |  | Signal Installation |  | 61.06% | 52.29% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 82.58%
|  |  |  | Stop Machine Installation |  | 76.21%
|  |  |  | Line Cable Installation |  | 26.17%
|  |  |  | Breakdown Testing |  | 78.02%
|  |  |  | Pre-Operation Testing |  | 19.98%
100068 | E1 | HOME |  | Signal Installation |  | 56.53% | 56.89% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 42.44%
|  |  |  | Stop Machine Installation |  | 75.53%
|  |  |  | Line Cable Installation |  | 44.32%
|  |  |  | Breakdown Testing |  | 78.2%
|  |  |  | Pre-Operation Testing |  | 29.86%
106031 | E1 | APPROACH |  | Signal Installation |  | 3.777% | 42.27% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 0.4216%
|  |  |  | Stop Machine Installation |  | 68.39%
|  |  |  | Line Cable Installation |  | 0.3964%
|  |  |  | Breakdown Testing |  | 90.28%
|  |  |  | Pre-Operation Testing |  | 48.53%
113852 | E1 | HOME |  | Signal Installation |  | 6.404% | 72.85% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 39.36%
|  |  |  | Stop Machine Installation |  | 95.34%
|  |  |  | Line Cable Installation |  | 80.78%
|  |  |  | Breakdown Testing |  | 90.38%
|  |  |  | Pre-Operation Testing |  | 91.34%
114110 | E1 | HOME |  | Signal Installation |  | 92.56% | 72.93% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 18.75%
|  |  |  | Stop Machine Installation |  | 98.27%
|  |  |  | Line Cable Installation |  | 54.86%
|  |  |  | Breakdown Testing |  | 59.5%
|  |  |  | Pre-Operation Testing |  | 59.48%
114869 | E1 | HOME |  | Signal Installation |  | 63.9% | 71.66% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 59.95%
|  |  |  | Stop Machine Installation |  | 99.92%
|  |  |  | Line Cable Installation |  | 97.54%
|  |  |  | Breakdown Testing |  | 13.84%
|  |  |  | Pre-Operation Testing |  | 83.11%
119024 | E1 | APPROACH |  | Signal Installation |  | 28.75% | 56.74% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 89.97%
|  |  |  | Stop Machine Installation |  | 82.84%
|  |  |  | Line Cable Installation |  | 69.54%
|  |  |  | Breakdown Testing |  | 31.77%
|  |  |  | Pre-Operation Testing |  | 70.78%
119485 | E1 | APPROACH |  | Signal Installation |  | 47.97% | 40.67% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 97.65%
|  |  |  | Stop Machine Installation |  | 29.7%
|  |  |  | Line Cable Installation |  | 35.99%
|  |  |  | Breakdown Testing |  | 38.95%
|  |  |  | Pre-Operation Testing |  | 50.75%
| E1 | APPROACH |  | Signal Installation |  | 40.65% | 38.16% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 50.17%
|  |  |  | Stop Machine Installation |  | 34.33%
|  |  |  | Line Cable Installation |  | 13.81%
|  |  |  | Breakdown Testing |  | 91.13%
|  |  |  | Pre-Operation Testing |  | 10.86%
121810 | E1 | HOME |  | Signal Installation |  | 89.41% | 71.15% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 13.18%
|  |  |  | Stop Machine Installation |  | 93.22%
|  |  |  | Line Cable Installation |  | 53.82%
|  |  |  | Breakdown Testing |  | 27.59%
|  |  |  | Pre-Operation Testing |  | 91.7%
122198 | E1 | HOME |  | Signal Installation |  | 98.26% | 74.55% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 83.03%
|  |  |  | Stop Machine Installation |  | 88.42%
|  |  |  | Line Cable Installation |  | 91.46%
|  |  |  | Breakdown Testing |  | 43.03%
|  |  |  | Pre-Operation Testing |  | 51.58%
122570 | E1 | HOME |  | Signal Installation |  | 68.82% | 53.56% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 34.54%
|  |  |  | Stop Machine Installation |  | 35.63%
|  |  |  | Line Cable Installation |  | 94.9%
|  |  |  | Breakdown Testing |  | 29.33%
|  |  |  | Pre-Operation Testing |  | 39.14%
122987 | E1 | HOME |  | Signal Installation |  | 13.49% | 37.05% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 32.65%
|  |  |  | Stop Machine Installation |  | 22.13%
|  |  |  | Line Cable Installation |  | 76.15%
|  |  |  | Breakdown Testing |  | 44.88%
|  |  |  | Pre-Operation Testing |  | 28.59%
123669 | D1 | HOME |  | Signal Installation |  | 74.86% | 66.43% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 7.41%
|  |  |  | Stop Machine Installation |  | 97.07%
|  |  |  | Line Cable Installation |  | 47.55%
|  |  |  | Breakdown Testing |  | 74.91%
|  |  |  | Pre-Operation Testing |  | 37.73%
73318 | E2 | APPROACH |  | Signal Installation |  | 10.24% | 40.69% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 30.36%
|  |  |  | Stop Machine Installation |  | 42.68%
|  |  |  | Line Cable Installation |  | 25.1%
|  |  |  | Breakdown Testing |  | 81.07%
|  |  |  | Pre-Operation Testing |  | 44.36%
98565 | E2 | HOME |  | Signal Installation |  | 44.54% | 45.77% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 99.91%
|  |  |  | Stop Machine Installation |  | 57.43%
|  |  |  | Line Cable Installation |  | 1.289%
|  |  |  | Breakdown Testing |  | 55.8%
|  |  |  | Pre-Operation Testing |  | 69.78%
99593 | E2 | HOME |  | Signal Installation |  | 80.28% | 78.28% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 87.47%
|  |  |  | Stop Machine Installation |  | 94.46%
|  |  |  | Line Cable Installation |  | 71.36%
|  |  |  | Breakdown Testing |  | 64.83%
|  |  |  | Pre-Operation Testing |  | 80.46%
99970 | E2 | HOME |  | Signal Installation |  | 71.05% | 68.73% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 69.01%
|  |  |  | Stop Machine Installation |  | 95.82%
|  |  |  | Line Cable Installation |  | 81.73%
|  |  |  | Breakdown Testing |  | 62.46%
|  |  |  | Pre-Operation Testing |  | 32.57%
106749 | E2 | APPROACH |  | Signal Installation |  | 49.62% | 64.44% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 65.92%
|  |  |  | Stop Machine Installation |  | 65.02%
|  |  |  | Line Cable Installation |  | 78.93%
|  |  |  | Breakdown Testing |  | 93.29%
|  |  |  | Pre-Operation Testing |  | 35.34%
112529 | E2 | HOME |  | Signal Installation |  | 24.49% | 39.98% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 42.93%
|  |  |  | Stop Machine Installation |  | 88.15%
|  |  |  | Line Cable Installation |  | 5.104%
|  |  |  | Breakdown Testing |  | 48.12%
|  |  |  | Pre-Operation Testing |  | 34.03%
113850 | E2 | HOME |  | Signal Installation |  | 52.96% | 75.71% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 86.28%
|  |  |  | Stop Machine Installation |  | 82.72%
|  |  |  | Line Cable Installation |  | 93.19%
|  |  |  | Breakdown Testing |  | 99.4%
|  |  |  | Pre-Operation Testing |  | 50.26%
118065 | E2 | APPROACH |  | Signal Installation |  | 71.36% | 51.88% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 53.51%
|  |  |  | Stop Machine Installation |  | 43.56%
|  |  |  | Line Cable Installation |  | 89.4%
|  |  |  | Breakdown Testing |  | 31.47%
|  |  |  | Pre-Operation Testing |  | 23.62%
119215 | E2 | APPROACH |  | Signal Installation |  | 17.07% | 30.84% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 90.8%
|  |  |  | Stop Machine Installation |  | 38.34%
|  |  |  | Line Cable Installation |  | 6.373%
|  |  |  | Breakdown Testing |  | 80.33%
|  |  |  | Pre-Operation Testing |  | 12.1%
123687 | D2 | HOME |  | Signal Installation |  | 55.39% | 62.17% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 97.53%
|  |  |  | Stop Machine Installation |  | 74.89%
|  |  |  | Line Cable Installation |  | 85.19%
|  |  |  | Breakdown Testing |  | 30.86%
|  |  |  | Pre-Operation Testing |  | 64.54%
124043 | D2 | HOME |  | Signal Installation |  | 82.48% | 39.57% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 8.422%
|  |  |  | Stop Machine Installation |  | 33.07%
|  |  |  | Line Cable Installation |  | 24.59%
|  |  |  | Breakdown Testing |  | 5.812%
|  |  |  | Pre-Operation Testing |  | 51.89%
99806 | E3 | HOME |  | Signal Installation |  | 93.61% | 44.18% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 42.26%
|  |  |  | Stop Machine Installation |  | 1.808%
|  |  |  | Line Cable Installation |  | 22.65%
|  |  |  | Breakdown Testing |  | 14.86%
|  |  |  | Pre-Operation Testing |  | 87.96%
100019 | E3 | HOME |  | Signal Installation |  | 56.42% | 40.15% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 48.75%
|  |  |  | Stop Machine Installation |  | 45.27%
|  |  |  | Line Cable Installation |  | 24.07%
|  |  |  | Breakdown Testing |  | 3.308%
|  |  |  | Pre-Operation Testing |  | 71.7%
99592 | E4 | HOME |  | Signal Installation |  | 18.71% | 45.12% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 37.19%
|  |  |  | Stop Machine Installation |  | 35.52%
|  |  |  | Line Cable Installation |  | 44.05%
|  |  |  | Breakdown Testing |  | 59.83%
|  |  |  | Pre-Operation Testing |  | 67.49%
122071 | E5 | HOME |  | Signal Installation |  | 72.92% | 56.32% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 64.03%
|  |  |  | Stop Machine Installation |  | 26.68%
|  |  |  | Line Cable Installation |  | 78.84%
|  |  |  | Breakdown Testing |  | 60.31%
|  |  |  | Pre-Operation Testing |  | 42.88%
122687 | E5 | HOME |  | Signal Installation |  | 79.87% | 48.59% | STATIONINGS SHOWN ARE THAT OF NEAREST IJ
|  |  |  | Signal JB Installation |  | 38.04%
|  |  |  | Stop Machine Installation |  | 8.206%
|  |  |  | Line Cable Installation |  | 20.22%
|  |  |  | Breakdown Testing |  | 72.48%
|  |  |  | Pre-Operation Testing |  | 62.15%

## SWITCH
Name | Stationing | Track No | Location | Activity | Date | Progress | General Progress | Notes
B331 | 76395 | B1 |  | Switch Machine Installation |  | 58.07% | 79.41%
|  |  |  | Switch JB Installation |  | 82.37%
|  |  |  | Switch Cable Installation |  | 84.89%
|  |  |  | Line Cable Installation |  | 65.25%
|  |  |  | Breakdown Testing |  | 94.42%
|  |  |  | Pre-Operation Testing |  | 94.41%
B325 | 76395 | E2 |  | Switch Machine Installation |  | 96.78% | 59.45%
|  |  |  | Switch JB Installation |  | 60.21%
|  |  |  | Switch Cable Installation |  | 16.81%
|  |  |  | Line Cable Installation |  | 59.68%
|  |  |  | Breakdown Testing |  | 48.32%
|  |  |  | Pre-Operation Testing |  | 75.67%
633A | 99999 | E1 |  | Switch Machine Installation |  | 4.901% | 16.04%
|  |  |  | Switch JB Installation |  | 73.01%
|  |  |  | Switch Cable Installation |  | 17.7%
|  |  |  | Line Cable Installation |  | 3.812%
|  |  |  | Breakdown Testing |  | 39.94%
|  |  |  | Pre-Operation Testing |  | 13.84%
633B | 98900 | E3-4 |  | Switch Machine Installation |  | 34.38% | 38.11%
|  |  |  | Switch JB Installation |  | 30.2%
|  |  |  | Switch Cable Installation |  | 34.9%
|  |  |  | Line Cable Installation |  | 55.25%
|  |  |  | Breakdown Testing |  | 3.578%
|  |  |  | Pre-Operation Testing |  | 62.44%
625A | 98808 | E3-4 |  | Switch Machine Installation |  | 28.36% | 52.21%
|  |  |  | Switch JB Installation |  | 49.95%
|  |  |  | Switch Cable Installation |  | 31.56%
|  |  |  | Line Cable Installation |  | 84.41%
|  |  |  | Breakdown Testing |  | 22.81%
|  |  |  | Pre-Operation Testing |  | 93.9%
625B | 99949 | E2 |  | Switch Machine Installation |  | 13.57% | 51.88%
|  |  |  | Switch JB Installation |  | 93.84%
|  |  |  | Switch Cable Installation |  | 76.08%
|  |  |  | Line Cable Installation |  | 38.87%
|  |  |  | Breakdown Testing |  | 69.46%
|  |  |  | Pre-Operation Testing |  | 61.45%
663 | 99628 | E3-4 |  | Switch Machine Installation |  | 42.34% | 45.33%
|  |  |  | Switch JB Installation |  | 35.48%
|  |  |  | Switch Cable Installation |  | 59.95%
|  |  |  | Line Cable Installation |  | 52.17%
|  |  |  | Breakdown Testing |  | 26.47%
|  |  |  | Pre-Operation Testing |  | 45.74%
673A | 99999 | E1 |  | Switch Machine Installation |  | 68.72% | 63.18%
|  |  |  | Switch JB Installation |  | 16.76%
|  |  |  | Switch Cable Installation |  | 53.91%
|  |  |  | Line Cable Installation |  | 70.32%
|  |  |  | Breakdown Testing |  | 32.17%
|  |  |  | Pre-Operation Testing |  | 90.75%
673B | 99826 | E3 |  | Switch Machine Installation |  | 50.21% | 56.41%
|  |  |  | Switch JB Installation |  | 86.31%
|  |  |  | Switch Cable Installation |  | 70.85%
|  |  |  | Line Cable Installation |  | 52.57%
|  |  |  | Breakdown Testing |  | 41.58%
|  |  |  | Pre-Operation Testing |  | 66.83%
651A | 99761 | E4 |  | Switch Machine Installation |  | 99.61% | 65.2%
|  |  |  | Switch JB Installation |  | 46.05%
|  |  |  | Switch Cable Installation |  | 85.94%
|  |  |  | Line Cable Installation |  | 43.08%
|  |  |  | Breakdown Testing |  | 93.36%
|  |  |  | Pre-Operation Testing |  | 3.995%
651B | 99949 | E2 |  | Switch Machine Installation |  | 60.18% | 49.49%
|  |  |  | Switch JB Installation |  | 86.42%
|  |  |  | Switch Cable Installation |  | 47.81%
|  |  |  | Line Cable Installation |  | 70.99%
|  |  |  | Breakdown Testing |  | 33.13%
|  |  |  | Pre-Operation Testing |  | 35.34%
757A | 113880 | E1 |  | Switch Machine Installation |  | 34.01% | 64.94%
|  |  |  | Switch JB Installation |  | 64.64%
|  |  |  | Switch Cable Installation |  | 82.03%
|  |  |  | Line Cable Installation |  | 91.62%
|  |  |  | Breakdown Testing |  | 90.52%
|  |  |  | Pre-Operation Testing |  | 26.53%
757B | 114010 | E2 |  | Switch Machine Installation |  | 86.84% | 48.87%
|  |  |  | Switch JB Installation |  | 95.4%
|  |  |  | Switch Cable Installation |  | 17.17%
|  |  |  | Line Cable Installation |  | 44.34%
|  |  |  | Breakdown Testing |  | 49.95%
|  |  |  | Pre-Operation Testing |  | 46.07%
753A | 114010 | E1 |  | Switch Machine Installation |  | 41.8% | 23.55%
|  |  |  | Switch JB Installation |  | 19.75%
|  |  |  | Switch Cable Installation |  | 6.774%
|  |  |  | Line Cable Installation |  | 18.35%
|  |  |  | Breakdown Testing |  | 14.14%
|  |  |  | Pre-Operation Testing |  | 36.69%
753B | 113880 | E2 |  | Switch Machine Installation |  | 11.49% | 38.94%
|  |  |  | Switch JB Installation |  | 30.2%
|  |  |  | Switch Cable Installation |  | 93.71%
|  |  |  | Line Cable Installation |  | 24.92%
|  |  |  | Breakdown Testing |  | 41.18%
|  |  |  | Pre-Operation Testing |  | 23.39%
825 |  | E1 |  | Switch Machine Installation |  | 55.41% | 52.93% | Stationing missing
|  |  |  | Switch JB Installation |  | 27.45%
|  |  |  | Switch Cable Installation |  | 58.72%
|  |  |  | Line Cable Installation |  | 34.9%
|  |  |  | Breakdown Testing |  | 73.03%
|  |  |  | Pre-Operation Testing |  | 42.58%
815A | 121995 | E5 |  | Switch Machine Installation |  | 81.71% | 58.2%
|  |  |  | Switch JB Installation |  | 16.21%
|  |  |  | Switch Cable Installation |  | 71.61%
|  |  |  | Line Cable Installation |  | 21.19%
|  |  |  | Breakdown Testing |  | 50.6%
|  |  |  | Pre-Operation Testing |  | 65.9%
815B | 121831 | E2 |  | Switch Machine Installation |  | 89.54% | 52.48%
|  |  |  | Switch JB Installation |  | 53.04%
|  |  |  | Switch Cable Installation |  | 31.28%
|  |  |  | Line Cable Installation |  | 32.24%
|  |  |  | Breakdown Testing |  | 58.36%
|  |  |  | Pre-Operation Testing |  | 50.98%
851B | 122757 | E5 |  | Switch Machine Installation |  | 68.3% | 58.97%
|  |  |  | Switch JB Installation |  | 89.31%
|  |  |  | Switch Cable Installation |  | 60.3%
|  |  |  | Line Cable Installation |  | 34.23%
|  |  |  | Breakdown Testing |  | 52.29%
|  |  |  | Pre-Operation Testing |  | 79.74%
851A | 122923 | E1 |  | Switch Machine Installation |  | 86.22% | 78.73%
|  |  |  | Switch JB Installation |  | 5%
|  |  |  | Switch Cable Installation |  | 68.54%
|  |  |  | Line Cable Installation |  | 71.03%
|  |  |  | Breakdown Testing |  | 99.06%
|  |  |  | Pre-Operation Testing |  | 68.77%
841 | 122923 | E2 |  | Switch Machine Installation |  | 98.34% | 62.91%
|  |  |  | Switch JB Installation |  | 10.4%
|  |  |  | Switch Cable Installation |  | 79.82%
|  |  |  | Line Cable Installation |  | 86.83%
|  |  |  | Breakdown Testing |  | 20.35%
|  |  |  | Pre-Operation Testing |  | 29.23%
753B | 113880 | E2 |  | Switch Machine Installation |  | 86.82% | 81.42%
|  |  |  | Switch JB Installation |  | 93.55%
|  |  |  | Switch Cable Installation |  | 77.31%
|  |  |  | Line Cable Installation |  | 56.59%
|  |  |  | Breakdown Testing |  | 90.32%
|  |  |  | Pre-Operation Testing |  | 96.07%

## WRU
Stationing | Track No | Location | Activity | Date | Progress | General Progress | Notes
54000 | B1 |  | Radio Unit Installation |  | 5.051% | 50.96% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 68.58%
|  |  | Fiber Box Installation |  | 48.35%
|  |  | Antenna Installation |  | 15.81%
|  |  | Antenna Cable Installation |  | 64.27%
|  |  | Splitter Installation |  | 77.6%
|  |  | Fiber Cable Splicing |  | 55.78%
|  |  | Fiber Testing |  | 33.26%
|  |  | Power Testing |  | 89.94%
54000 | B3 |  | Radio Unit Installation |  | 53.13% | 57.58% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 89.81%
|  |  | Fiber Box Installation |  | 68.72%
|  |  | Antenna Installation |  | 4.81%
|  |  | Antenna Cable Installation |  | 8.745%
|  |  | Splitter Installation |  | 62.14%
|  |  | Fiber Cable Splicing |  | 78.32%
|  |  | Fiber Testing |  | 58.16%
|  |  | Power Testing |  | 94.44%
54000 | B4 |  | Radio Unit Installation |  | 80.03% | 50.75% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 65.47%
|  |  | Fiber Box Installation |  | 36.25%
|  |  | Antenna Installation |  | 2.05%
|  |  | Antenna Cable Installation |  | 99.54%
|  |  | Splitter Installation |  | 27.87%
|  |  | Fiber Cable Splicing |  | 2.793%
|  |  | Fiber Testing |  | 81.53%
|  |  | Power Testing |  | 61.22%
54000 | B2 |  | Radio Unit Installation |  | 65.21% | 40.28% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 27.75%
|  |  | Fiber Box Installation |  | 0.2693%
|  |  | Antenna Installation |  | 91.13%
|  |  | Antenna Cable Installation |  | 42.84%
|  |  | Splitter Installation |  | 73.3%
|  |  | Fiber Cable Splicing |  | 24.62%
|  |  | Fiber Testing |  | 23.91%
|  |  | Power Testing |  | 13.49%
54000 | B5 |  | Radio Unit Installation |  | 25.12% | 42.36% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 72.53%
|  |  | Fiber Box Installation |  | 54.07%
|  |  | Antenna Installation |  | 39.14%
|  |  | Antenna Cable Installation |  | 19.24%
|  |  | Splitter Installation |  | 32.52%
|  |  | Fiber Cable Splicing |  | 29.5%
|  |  | Fiber Testing |  | 69.62%
|  |  | Power Testing |  | 39.48%
55500 | B2 |  | Radio Unit Installation |  | 91.74% | 42.02% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 40.13%
|  |  | Fiber Box Installation |  | 14.11%
|  |  | Antenna Installation |  | 5.861%
|  |  | Antenna Cable Installation |  | 46.58%
|  |  | Splitter Installation |  | 61.82%
|  |  | Fiber Cable Splicing |  | 4.649%
|  |  | Fiber Testing |  | 90.83%
|  |  | Power Testing |  | 22.47%
55500 | B1 |  | Radio Unit Installation |  | 71.45% | 46.69% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 39.35%
|  |  | Fiber Box Installation |  | 54.14%
|  |  | Antenna Installation |  | 11.26%
|  |  | Antenna Cable Installation |  | 35.6%
|  |  | Splitter Installation |  | 17.01%
|  |  | Fiber Cable Splicing |  | 35.43%
|  |  | Fiber Testing |  | 92.78%
|  |  | Power Testing |  | 63.2%
56300 | B1 |  | Radio Unit Installation |  | 96.34% | 47.86% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 53.89%
|  |  | Fiber Box Installation |  | 21.25%
|  |  | Antenna Installation |  | 34.16%
|  |  | Antenna Cable Installation |  | 70.1%
|  |  | Splitter Installation |  | 35.01%
|  |  | Fiber Cable Splicing |  | 34.11%
|  |  | Fiber Testing |  | 41.1%
|  |  | Power Testing |  | 44.81%
56500 | B1 |  | Radio Unit Installation |  | 90.71% | 53.77% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 98.06%
|  |  | Fiber Box Installation |  | 65.93%
|  |  | Antenna Installation |  | 96.56%
|  |  | Antenna Cable Installation |  | 12.55%
|  |  | Splitter Installation |  | 24.75%
|  |  | Fiber Cable Splicing |  | 1.996%
|  |  | Fiber Testing |  | 23.22%
|  |  | Power Testing |  | 70.17%
57200 | B1 |  | Radio Unit Installation |  | 45.91% | 49.66% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 3.334%
|  |  | Fiber Box Installation |  | 36.91%
|  |  | Antenna Installation |  | 60.29%
|  |  | Antenna Cable Installation |  | 36.63%
|  |  | Splitter Installation |  | 93.1%
|  |  | Fiber Cable Splicing |  | 7.23%
|  |  | Fiber Testing |  | 94.68%
|  |  | Power Testing |  | 68.84%
57400 | B1 |  | Radio Unit Installation |  | 33% | 75.37% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 92.69%
|  |  | Fiber Box Installation |  | 24.13%
|  |  | Antenna Installation |  | 96.63%
|  |  | Antenna Cable Installation |  | 87.22%
|  |  | Splitter Installation |  | 81.43%
|  |  | Fiber Cable Splicing |  | 95.96%
|  |  | Fiber Testing |  | 86.29%
|  |  | Power Testing |  | 81.03%
58300 | B1 |  | Radio Unit Installation |  | 76.86% | 63.3% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 97.3%
|  |  | Fiber Box Installation |  | 15.26%
|  |  | Antenna Installation |  | 52.02%
|  |  | Antenna Cable Installation |  | 30.55%
|  |  | Splitter Installation |  | 46.47%
|  |  | Fiber Cable Splicing |  | 80%
|  |  | Fiber Testing |  | 81.25%
|  |  | Power Testing |  | 90.02%
58400 | B1 |  | Radio Unit Installation |  | 59.06% | 52.56% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 77.31%
|  |  | Fiber Box Installation |  | 64.92%
|  |  | Antenna Installation |  | 82.28%
|  |  | Antenna Cable Installation |  | 63.72%
|  |  | Splitter Installation |  | 20.4%
|  |  | Fiber Cable Splicing |  | 12.24%
|  |  | Fiber Testing |  | 71.66%
|  |  | Power Testing |  | 21.46%
59400 | B1 |  | Radio Unit Installation |  | 62.29% | 44.77% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 40.91%
|  |  | Fiber Box Installation |  | 5.355%
|  |  | Antenna Installation |  | 39.63%
|  |  | Antenna Cable Installation |  | 69.52%
|  |  | Splitter Installation |  | 31.73%
|  |  | Fiber Cable Splicing |  | 31.85%
|  |  | Fiber Testing |  | 78.18%
|  |  | Power Testing |  | 43.51%
59700 | B1 |  | Radio Unit Installation |  | 26.05% | 41.16% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 28.07%
|  |  | Fiber Box Installation |  | 9.174%
|  |  | Antenna Installation |  | 42.93%
|  |  | Antenna Cable Installation |  | 84.51%
|  |  | Splitter Installation |  | 63.06%
|  |  | Fiber Cable Splicing |  | 22.81%
|  |  | Fiber Testing |  | 40.37%
|  |  | Power Testing |  | 53.5%
60500 | B1 |  | Radio Unit Installation |  | 52.65% | 56.24% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 12.14%
|  |  | Fiber Box Installation |  | 34.33%
|  |  | Antenna Installation |  | 67.54%
|  |  | Antenna Cable Installation |  | 87.73%
|  |  | Splitter Installation |  | 58.96%
|  |  | Fiber Cable Splicing |  | 61.39%
|  |  | Fiber Testing |  | 35.24%
|  |  | Power Testing |  | 96.15%
60800 | B2 |  | Radio Unit Installation |  | 34.61% | 33.38% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 41.32%
|  |  | Fiber Box Installation |  | 2.194%
|  |  | Antenna Installation |  | 12.89%
|  |  | Antenna Cable Installation |  | 17.47%
|  |  | Splitter Installation |  | 39.47%
|  |  | Fiber Cable Splicing |  | 58.66%
|  |  | Fiber Testing |  | 34.02%
|  |  | Power Testing |  | 59.83%
60800 | B1 |  | Radio Unit Installation |  | 79.38% | 39.43% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 29.55%
|  |  | Fiber Box Installation |  | 54.65%
|  |  | Antenna Installation |  | 33.5%
|  |  | Antenna Cable Installation |  | 18.62%
|  |  | Splitter Installation |  | 71.64%
|  |  | Fiber Cable Splicing |  | 27.57%
|  |  | Fiber Testing |  | 18.64%
|  |  | Power Testing |  | 21.37%
61900 | B2 |  | Radio Unit Installation |  | 29.58% | 40.25% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 59.7%
|  |  | Fiber Box Installation |  | 2.719%
|  |  | Antenna Installation |  | 28.81%
|  |  | Antenna Cable Installation |  | 25.34%
|  |  | Splitter Installation |  | 99.75%
|  |  | Fiber Cable Splicing |  | 17.65%
|  |  | Fiber Testing |  | 60.95%
|  |  | Power Testing |  | 37.8%
61900 | B1 |  | Radio Unit Installation |  | 4.237% | 12.51% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 4.219%
|  |  | Fiber Box Installation |  | 12.44%
|  |  | Antenna Installation |  | 26.02%
|  |  | Antenna Cable Installation |  | 4.968%
|  |  | Splitter Installation |  | 3.599%
|  |  | Fiber Cable Splicing |  | 0.6788%
|  |  | Fiber Testing |  | 7.823%
|  |  | Power Testing |  | 48.6%
62300 | B1 |  | Radio Unit Installation |  | 9.616% | 40.53% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 80.86%
|  |  | Fiber Box Installation |  | 25.23%
|  |  | Antenna Installation |  | 46.19%
|  |  | Antenna Cable Installation |  | 8.83%
|  |  | Splitter Installation |  | 18.36%
|  |  | Fiber Cable Splicing |  | 70.61%
|  |  | Fiber Testing |  | 60.3%
|  |  | Power Testing |  | 44.77%
63200 | B1 |  | Radio Unit Installation |  | 92.08% | 75.35% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 62.02%
|  |  | Fiber Box Installation |  | 24.77%
|  |  | Antenna Installation |  | 95.35%
|  |  | Antenna Cable Installation |  | 96.47%
|  |  | Splitter Installation |  | 81.29%
|  |  | Fiber Cable Splicing |  | 79%
|  |  | Fiber Testing |  | 52.96%
|  |  | Power Testing |  | 94.19%
63300 | B1 |  | Radio Unit Installation |  | 41.79% | 64.5% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 96%
|  |  | Fiber Box Installation |  | 68.97%
|  |  | Antenna Installation |  | 69.24%
|  |  | Antenna Cable Installation |  | 70.62%
|  |  | Splitter Installation |  | 51.96%
|  |  | Fiber Cable Splicing |  | 97.62%
|  |  | Fiber Testing |  | 25%
|  |  | Power Testing |  | 59.3%
64200 | B1 |  | Radio Unit Installation |  | 13.05% | 36.19% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 78.17%
|  |  | Fiber Box Installation |  | 48.97%
|  |  | Antenna Installation |  | 13.03%
|  |  | Antenna Cable Installation |  | 46.75%
|  |  | Splitter Installation |  | 24.26%
|  |  | Fiber Cable Splicing |  | 31.71%
|  |  | Fiber Testing |  | 68.66%
|  |  | Power Testing |  | 1.114%
64300 | B1 |  | Radio Unit Installation |  | 94.25% | 46.12% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 19.23%
|  |  | Fiber Box Installation |  | 54.37%
|  |  | Antenna Installation |  | 25.26%
|  |  | Antenna Cable Installation |  | 47.47%
|  |  | Splitter Installation |  | 55.55%
|  |  | Fiber Cable Splicing |  | 67.45%
|  |  | Fiber Testing |  | 16.25%
|  |  | Power Testing |  | 35.22%
65200 | B1 |  | Radio Unit Installation |  | 65.14% | 45.03% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 36.83%
|  |  | Fiber Box Installation |  | 68.54%
|  |  | Antenna Installation |  | 22.9%
|  |  | Antenna Cable Installation |  | 71.84%
|  |  | Splitter Installation |  | 17.01%
|  |  | Fiber Cable Splicing |  | 63.76%
|  |  | Fiber Testing |  | 22.38%
|  |  | Power Testing |  | 36.86%
65200 | B2 |  | Radio Unit Installation |  | 19.65% | 41.99% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 55.58%
|  |  | Fiber Box Installation |  | 73.81%
|  |  | Antenna Installation |  | 43.11%
|  |  | Antenna Cable Installation |  | 10.93%
|  |  | Splitter Installation |  | 37.53%
|  |  | Fiber Cable Splicing |  | 54.06%
|  |  | Fiber Testing |  | 33.39%
|  |  | Power Testing |  | 49.81%
66300 | B1 |  | Radio Unit Installation |  | 20.91% | 37.53% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 82.05%
|  |  | Fiber Box Installation |  | 72.31%
|  |  | Antenna Installation |  | 33.44%
|  |  | Antenna Cable Installation |  | 12.66%
|  |  | Splitter Installation |  | 20.96%
|  |  | Fiber Cable Splicing |  | 37.98%
|  |  | Fiber Testing |  | 19.06%
|  |  | Power Testing |  | 38.44%
66300 | B2 |  | Radio Unit Installation |  | 30.21% | 41.69% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 14.41%
|  |  | Fiber Box Installation |  | 62.05%
|  |  | Antenna Installation |  | 75.01%
|  |  | Antenna Cable Installation |  | 18.74%
|  |  | Splitter Installation |  | 47.62%
|  |  | Fiber Cable Splicing |  | 99.28%
|  |  | Fiber Testing |  | 18.14%
|  |  | Power Testing |  | 9.788%
67500 | B1 |  | Radio Unit Installation |  | 20.28% | 41.48% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 0.5307%
|  |  | Fiber Box Installation |  | 38.94%
|  |  | Antenna Installation |  | 71.98%
|  |  | Antenna Cable Installation |  | 38.52%
|  |  | Splitter Installation |  | 76.37%
|  |  | Fiber Cable Splicing |  | 23.65%
|  |  | Fiber Testing |  | 22.8%
|  |  | Power Testing |  | 80.28%
67500 | B2 |  | Radio Unit Installation |  | 20.77% | 38.12% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 14.06%
|  |  | Fiber Box Installation |  | 34.28%
|  |  | Antenna Installation |  | 74.1%
|  |  | Antenna Cable Installation |  | 37.17%
|  |  | Splitter Installation |  | 66.24%
|  |  | Fiber Cable Splicing |  | 35%
|  |  | Fiber Testing |  | 46.46%
|  |  | Power Testing |  | 14.97%
68300 | B1 |  | Radio Unit Installation |  | 3.643% | 60.99% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 72.35%
|  |  | Fiber Box Installation |  | 92.18%
|  |  | Antenna Installation |  | 71.11%
|  |  | Antenna Cable Installation |  | 86.96%
|  |  | Splitter Installation |  | 27.6%
|  |  | Fiber Cable Splicing |  | 60.91%
|  |  | Fiber Testing |  | 79.24%
|  |  | Power Testing |  | 54.92%
68300 | B2 |  | Radio Unit Installation |  | 49.46% | 38.87% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 47.78%
|  |  | Fiber Box Installation |  | 32.69%
|  |  | Antenna Installation |  | 38.78%
|  |  | Antenna Cable Installation |  | 5.488%
|  |  | Splitter Installation |  | 2.254%
|  |  | Fiber Cable Splicing |  | 61.7%
|  |  | Fiber Testing |  | 63.13%
|  |  | Power Testing |  | 48.54%
69900 | B1 |  | Radio Unit Installation |  | 28.47% | 62.55% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 81.7%
|  |  | Fiber Box Installation |  | 94.47%
|  |  | Antenna Installation |  | 37.75%
|  |  | Antenna Cable Installation |  | 9.201%
|  |  | Splitter Installation |  | 76.88%
|  |  | Fiber Cable Splicing |  | 96.29%
|  |  | Fiber Testing |  | 38.98%
|  |  | Power Testing |  | 99.25%
71400 | B1 |  | Radio Unit Installation |  | 62.37% | 58.83% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 61.47%
|  |  | Fiber Box Installation |  | 74.54%
|  |  | Antenna Installation |  | 79.95%
|  |  | Antenna Cable Installation |  | 42.72%
|  |  | Splitter Installation |  | 22.76%
|  |  | Fiber Cable Splicing |  | 46.67%
|  |  | Fiber Testing |  | 91.51%
|  |  | Power Testing |  | 47.46%
73000 | B1 |  | Radio Unit Installation |  | 67.54% | 48.65% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 38.21%
|  |  | Fiber Box Installation |  | 78.42%
|  |  | Antenna Installation |  | 58.49%
|  |  | Antenna Cable Installation |  | 22.98%
|  |  | Splitter Installation |  | 38.32%
|  |  | Fiber Cable Splicing |  | 39.91%
|  |  | Fiber Testing |  | 49.14%
|  |  | Power Testing |  | 44.81%
73000 | B2 |  | Radio Unit Installation |  | 37.7% | 44.35% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 5.648%
|  |  | Fiber Box Installation |  | 1.314%
|  |  | Antenna Installation |  | 98.05%
|  |  | Antenna Cable Installation |  | 13.84%
|  |  | Splitter Installation |  | 95.74%
|  |  | Fiber Cable Splicing |  | 16.57%
|  |  | Fiber Testing |  | 34.03%
|  |  | Power Testing |  | 96.28%
74100 | B1 |  | Radio Unit Installation |  | 29.71% | 49.85% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 43.27%
|  |  | Fiber Box Installation |  | 63.95%
|  |  | Antenna Installation |  | 35.24%
|  |  | Antenna Cable Installation |  | 46.28%
|  |  | Splitter Installation |  | 30.01%
|  |  | Fiber Cable Splicing |  | 67.05%
|  |  | Fiber Testing |  | 44.88%
|  |  | Power Testing |  | 88.28%
75300 | B1 |  | Radio Unit Installation |  | 21.87% | 50.81% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 42.34%
|  |  | Fiber Box Installation |  | 18.32%
|  |  | Antenna Installation |  | 50.47%
|  |  | Antenna Cable Installation |  | 39.64%
|  |  | Splitter Installation |  | 71.87%
|  |  | Fiber Cable Splicing |  | 69.06%
|  |  | Fiber Testing |  | 52.82%
|  |  | Power Testing |  | 90.93%
75300 | B2 |  | Radio Unit Installation |  | 70.23% | 43.53% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 47.8%
|  |  | Fiber Box Installation |  | 8.025%
|  |  | Antenna Installation |  | 20.79%
|  |  | Antenna Cable Installation |  | 70.27%
|  |  | Splitter Installation |  | 36.33%
|  |  | Fiber Cable Splicing |  | 35.63%
|  |  | Fiber Testing |  | 29.84%
|  |  | Power Testing |  | 72.85%
88300 | E1 |  | Radio Unit Installation |  | 80.73% | 69.09% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 67.08%
|  |  | Fiber Box Installation |  | 60.27%
|  |  | Antenna Installation |  | 81.95%
|  |  | Antenna Cable Installation |  | 57.86%
|  |  | Splitter Installation |  | 68.42%
|  |  | Fiber Cable Splicing |  | 62.32%
|  |  | Fiber Testing |  | 51.38%
|  |  | Power Testing |  | 91.84%
88600 | E1 |  | Radio Unit Installation |  | 48% | 35.05% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 39.01%
|  |  | Fiber Box Installation |  | 37.55%
|  |  | Antenna Installation |  | 13.96%
|  |  | Antenna Cable Installation |  | 69.32%
|  |  | Splitter Installation |  | 38.64%
|  |  | Fiber Cable Splicing |  | 40.87%
|  |  | Fiber Testing |  | 4.093%
|  |  | Power Testing |  | 23.98%
90800 | E1 |  | Radio Unit Installation |  | 93.31% | 40.34% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 69.93%
|  |  | Fiber Box Installation |  | 87.26%
|  |  | Antenna Installation |  | 20.83%
|  |  | Antenna Cable Installation |  | 9.707%
|  |  | Splitter Installation |  | 4.354%
|  |  | Fiber Cable Splicing |  | 24.95%
|  |  | Fiber Testing |  | 39.1%
|  |  | Power Testing |  | 13.6%
92400 | E1 |  | Radio Unit Installation |  | 60.4% | 49.71% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 44.88%
|  |  | Fiber Box Installation |  | 92.25%
|  |  | Antenna Installation |  | 33.01%
|  |  | Antenna Cable Installation |  | 56.36%
|  |  | Splitter Installation |  | 1.515%
|  |  | Fiber Cable Splicing |  | 60.06%
|  |  | Fiber Testing |  | 17.58%
|  |  | Power Testing |  | 81.36%
93600 | E1 |  | Radio Unit Installation |  | 77.91% | 50.37% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 86.66%
|  |  | Fiber Box Installation |  | 3.489%
|  |  | Antenna Installation |  | 27.02%
|  |  | Antenna Cable Installation |  | 97.97%
|  |  | Splitter Installation |  | 66.77%
|  |  | Fiber Cable Splicing |  | 2.382%
|  |  | Fiber Testing |  | 86.16%
|  |  | Power Testing |  | 5.017%
95000 | E1 |  | Radio Unit Installation |  | 53.28% | 54.79% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 48.18%
|  |  | Fiber Box Installation |  | 1.012%
|  |  | Antenna Installation |  | 16.39%
|  |  | Antenna Cable Installation |  | 87.67%
|  |  | Splitter Installation |  | 78.36%
|  |  | Fiber Cable Splicing |  | 86.05%
|  |  | Fiber Testing |  | 46.34%
|  |  | Power Testing |  | 75.86%
96500 | E1 |  | Radio Unit Installation |  | 94.92% | 67.72% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 98.05%
|  |  | Fiber Box Installation |  | 38.19%
|  |  | Antenna Installation |  | 50.17%
|  |  | Antenna Cable Installation |  | 98.13%
|  |  | Splitter Installation |  | 90.29%
|  |  | Fiber Cable Splicing |  | 74.38%
|  |  | Fiber Testing |  | 14.95%
|  |  | Power Testing |  | 50.36%
98200 | E1 |  | Radio Unit Installation |  | 47.74% | 62.92% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 64.18%
|  |  | Fiber Box Installation |  | 94.37%
|  |  | Antenna Installation |  | 73.61%
|  |  | Antenna Cable Installation |  | 92.91%
|  |  | Splitter Installation |  | 77.01%
|  |  | Fiber Cable Splicing |  | 78.32%
|  |  | Fiber Testing |  | 19.36%
|  |  | Power Testing |  | 18.76%
99700 | E1 |  | Radio Unit Installation |  | 90.2% | 47.77% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 83.64%
|  |  | Fiber Box Installation |  | 30.57%
|  |  | Antenna Installation |  | 55.1%
|  |  | Antenna Cable Installation |  | 3.758%
|  |  | Splitter Installation |  | 80.35%
|  |  | Fiber Cable Splicing |  | 27.34%
|  |  | Fiber Testing |  | 57.27%
|  |  | Power Testing |  | 1.734%
99700 | E2 |  | Radio Unit Installation |  | 88.01% | 54.48% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 37.5%
|  |  | Fiber Box Installation |  | 44.56%
|  |  | Antenna Installation |  | 43.15%
|  |  | Antenna Cable Installation |  | 65.45%
|  |  | Splitter Installation |  | 5.387%
|  |  | Fiber Cable Splicing |  | 76.9%
|  |  | Fiber Testing |  | 72.91%
|  |  | Power Testing |  | 56.43%
100400 | E1 |  | Radio Unit Installation |  | 7.922% | 46.01% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 81.44%
|  |  | Fiber Box Installation |  | 21.83%
|  |  | Antenna Installation |  | 46.11%
|  |  | Antenna Cable Installation |  | 28.85%
|  |  | Splitter Installation |  | 68.57%
|  |  | Fiber Cable Splicing |  | 47.66%
|  |  | Fiber Testing |  | 64.22%
|  |  | Power Testing |  | 47.46%
100600 | E1 |  | Radio Unit Installation |  | 37.66% | 45.41% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 8.092%
|  |  | Fiber Box Installation |  | 91.5%
|  |  | Antenna Installation |  | 72.84%
|  |  | Antenna Cable Installation |  | 5.843%
|  |  | Splitter Installation |  | 25.38%
|  |  | Fiber Cable Splicing |  | 60.01%
|  |  | Fiber Testing |  | 67.11%
|  |  | Power Testing |  | 40.22%
101500 | E1 |  | Radio Unit Installation |  | 36.58% | 47.27% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 8.126%
|  |  | Fiber Box Installation |  | 32.21%
|  |  | Antenna Installation |  | 68.25%
|  |  | Antenna Cable Installation |  | 32.77%
|  |  | Splitter Installation |  | 60.4%
|  |  | Fiber Cable Splicing |  | 75.76%
|  |  | Fiber Testing |  | 59.44%
|  |  | Power Testing |  | 51.92%
102600 | E1 |  | Radio Unit Installation |  | 31.66% | 33.84% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 60.54%
|  |  | Fiber Box Installation |  | 20.59%
|  |  | Antenna Installation |  | 6.708%
|  |  | Antenna Cable Installation |  | 37.63%
|  |  | Splitter Installation |  | 19.01%
|  |  | Fiber Cable Splicing |  | 67.46%
|  |  | Fiber Testing |  | 13.95%
|  |  | Power Testing |  | 46.97%
103800 | E1 |  | Radio Unit Installation |  | 53.02% | 54.62% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 82.97%
|  |  | Fiber Box Installation |  | 94.14%
|  |  | Antenna Installation |  | 15.03%
|  |  | Antenna Cable Installation |  | 72.76%
|  |  | Splitter Installation |  | 12.23%
|  |  | Fiber Cable Splicing |  | 16.27%
|  |  | Fiber Testing |  | 62.5%
|  |  | Power Testing |  | 82.62%
104700 | E1 |  | Radio Unit Installation |  | 26.07% | 45.65% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 69.06%
|  |  | Fiber Box Installation |  | 44.54%
|  |  | Antenna Installation |  | 48.01%
|  |  | Antenna Cable Installation |  | 74.39%
|  |  | Splitter Installation |  | 16.6%
|  |  | Fiber Cable Splicing |  | 20.85%
|  |  | Fiber Testing |  | 41.99%
|  |  | Power Testing |  | 69.35%
105900 | E1 |  | Radio Unit Installation |  | 61.23% | 50.78% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 66.19%
|  |  | Fiber Box Installation |  | 99.48%
|  |  | Antenna Installation |  | 49.12%
|  |  | Antenna Cable Installation |  | 87.5%
|  |  | Splitter Installation |  | 7.555%
|  |  | Fiber Cable Splicing |  | 60.11%
|  |  | Fiber Testing |  | 13.28%
|  |  | Power Testing |  | 12.54%
106900 | E1 |  | Radio Unit Installation |  | 40.3% | 48.33% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 78.8%
|  |  | Fiber Box Installation |  | 37.13%
|  |  | Antenna Installation |  | 64.35%
|  |  | Antenna Cable Installation |  | 18.29%
|  |  | Splitter Installation |  | 47.24%
|  |  | Fiber Cable Splicing |  | 69.34%
|  |  | Fiber Testing |  | 22.78%
|  |  | Power Testing |  | 56.71%
108300 | E1 |  | Radio Unit Installation |  | 36.95% | 47.55% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 41.51%
|  |  | Fiber Box Installation |  | 60.21%
|  |  | Antenna Installation |  | 66.25%
|  |  | Antenna Cable Installation |  | 36.27%
|  |  | Splitter Installation |  | 85.94%
|  |  | Fiber Cable Splicing |  | 2.966%
|  |  | Fiber Testing |  | 95.67%
|  |  | Power Testing |  | 2.174%
109900 | E1 |  | Radio Unit Installation |  | 98.24% | 53.1% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 53.48%
|  |  | Fiber Box Installation |  | 92.31%
|  |  | Antenna Installation |  | 10.3%
|  |  | Antenna Cable Installation |  | 89.84%
|  |  | Splitter Installation |  | 9.11%
|  |  | Fiber Cable Splicing |  | 90.74%
|  |  | Fiber Testing |  | 18.32%
|  |  | Power Testing |  | 15.53%
111100 | E1 |  | Radio Unit Installation |  | 42.98% | 61.23% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 93.06%
|  |  | Fiber Box Installation |  | 78.94%
|  |  | Antenna Installation |  | 58.19%
|  |  | Antenna Cable Installation |  | 45.11%
|  |  | Splitter Installation |  | 2.635%
|  |  | Fiber Cable Splicing |  | 95.26%
|  |  | Fiber Testing |  | 75.96%
|  |  | Power Testing |  | 58.97%
112200 | E1 |  | Radio Unit Installation |  | 0.9155% | 59.91% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 35.32%
|  |  | Fiber Box Installation |  | 51.35%
|  |  | Antenna Installation |  | 87.84%
|  |  | Antenna Cable Installation |  | 20.64%
|  |  | Splitter Installation |  | 97.99%
|  |  | Fiber Cable Splicing |  | 90.49%
|  |  | Fiber Testing |  | 84.3%
|  |  | Power Testing |  | 70.39%
113000 | E1 |  | Radio Unit Installation |  | 75.35% | 56.18% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 6.276%
|  |  | Fiber Box Installation |  | 95.37%
|  |  | Antenna Installation |  | 89.18%
|  |  | Antenna Cable Installation |  | 37%
|  |  | Splitter Installation |  | 12.62%
|  |  | Fiber Cable Splicing |  | 49.26%
|  |  | Fiber Testing |  | 48.8%
|  |  | Power Testing |  | 91.75%
114300 | E1 |  | Radio Unit Installation |  | 1.467% | 48.72% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 16.63%
|  |  | Fiber Box Installation |  | 55.7%
|  |  | Antenna Installation |  | 78.24%
|  |  | Antenna Cable Installation |  | 58.7%
|  |  | Splitter Installation |  | 67.72%
|  |  | Fiber Cable Splicing |  | 29.25%
|  |  | Fiber Testing |  | 98.5%
|  |  | Power Testing |  | 32.29%
115500 | E1 |  | Radio Unit Installation |  | 15.05% | 51.66% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 14.95%
|  |  | Fiber Box Installation |  | 79.81%
|  |  | Antenna Installation |  | 55.23%
|  |  | Antenna Cable Installation |  | 82.19%
|  |  | Splitter Installation |  | 84.31%
|  |  | Fiber Cable Splicing |  | 68.12%
|  |  | Fiber Testing |  | 62.81%
|  |  | Power Testing |  | 2.474%
116900 | E1 |  | Radio Unit Installation |  | 30.58% | 52.46% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 35.07%
|  |  | Fiber Box Installation |  | 36.55%
|  |  | Antenna Installation |  | 98.15%
|  |  | Antenna Cable Installation |  | 11.49%
|  |  | Splitter Installation |  | 93.28%
|  |  | Fiber Cable Splicing |  | 86.98%
|  |  | Fiber Testing |  | 34.77%
|  |  | Power Testing |  | 45.3%
118300 | E1 |  | Radio Unit Installation |  | 23.39% | 35.46% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 11.3%
|  |  | Fiber Box Installation |  | 23.06%
|  |  | Antenna Installation |  | 6.945%
|  |  | Antenna Cable Installation |  | 85.39%
|  |  | Splitter Installation |  | 42.21%
|  |  | Fiber Cable Splicing |  | 73.45%
|  |  | Fiber Testing |  | 7.282%
|  |  | Power Testing |  | 46.06%
118300 | E2 |  | Radio Unit Installation |  | 94.9% | 56.88% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 84.99%
|  |  | Fiber Box Installation |  | 96.75%
|  |  | Antenna Installation |  | 12.5%
|  |  | Antenna Cable Installation |  | 25.5%
|  |  | Splitter Installation |  | 60.15%
|  |  | Fiber Cable Splicing |  | 47.08%
|  |  | Fiber Testing |  | 86.8%
|  |  | Power Testing |  | 3.225%
119500 | E1 |  | Radio Unit Installation |  | 0.843% | 54.37% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 1.229%
|  |  | Fiber Box Installation |  | 89.16%
|  |  | Antenna Installation |  | 71.81%
|  |  | Antenna Cable Installation |  | 39.12%
|  |  | Splitter Installation |  | 95.66%
|  |  | Fiber Cable Splicing |  | 71.44%
|  |  | Fiber Testing |  | 53.83%
|  |  | Power Testing |  | 66.25%
119500 | E2 |  | Radio Unit Installation |  | 34.49% | 53.45% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 76.3%
|  |  | Fiber Box Installation |  | 52.68%
|  |  | Antenna Installation |  | 83.28%
|  |  | Antenna Cable Installation |  | 59.61%
|  |  | Splitter Installation |  | 93.82%
|  |  | Fiber Cable Splicing |  | 3.692%
|  |  | Fiber Testing |  | 76.21%
|  |  | Power Testing |  | 0.9354%
120800 | E1 |  | Radio Unit Installation |  | 19.45% | 42.98% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 64.64%
|  |  | Fiber Box Installation |  | 35.1%
|  |  | Antenna Installation |  | 4.904%
|  |  | Antenna Cable Installation |  | 14.45%
|  |  | Splitter Installation |  | 83.37%
|  |  | Fiber Cable Splicing |  | 69.7%
|  |  | Fiber Testing |  | 80.92%
|  |  | Power Testing |  | 14.28%
120800 | E2 |  | Radio Unit Installation |  | 72.59% | 40.2% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 55.43%
|  |  | Fiber Box Installation |  | 68.4%
|  |  | Antenna Installation |  | 23.83%
|  |  | Antenna Cable Installation |  | 63.61%
|  |  | Splitter Installation |  | 13.42%
|  |  | Fiber Cable Splicing |  | 15.16%
|  |  | Fiber Testing |  | 12.69%
|  |  | Power Testing |  | 36.63%
121900 | E1 |  | Radio Unit Installation |  | 67.59% | 47.6% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 32.33%
|  |  | Fiber Box Installation |  | 44.02%
|  |  | Antenna Installation |  | 55.43%
|  |  | Antenna Cable Installation |  | 12.55%
|  |  | Splitter Installation |  | 90.24%
|  |  | Fiber Cable Splicing |  | 94.63%
|  |  | Fiber Testing |  | 21.93%
|  |  | Power Testing |  | 9.718%
122800 | E1 |  | Radio Unit Installation |  | 62.47% | 46.25% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 5.422%
|  |  | Fiber Box Installation |  | 92.41%
|  |  | Antenna Installation |  | 52.47%
|  |  | Antenna Cable Installation |  | 15.15%
|  |  | Splitter Installation |  | 66.73%
|  |  | Fiber Cable Splicing |  | 11.46%
|  |  | Fiber Testing |  | 14.11%
|  |  | Power Testing |  | 96.06%
123900 | D1 |  | Radio Unit Installation |  | 62.1% | 64.93% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 23.44%
|  |  | Fiber Box Installation |  | 54.95%
|  |  | Antenna Installation |  | 87.8%
|  |  | Antenna Cable Installation |  | 96.07%
|  |  | Splitter Installation |  | 21.22%
|  |  | Fiber Cable Splicing |  | 88.15%
|  |  | Fiber Testing |  | 81.09%
|  |  | Power Testing |  | 69.53%
124900 | D1 |  | Radio Unit Installation |  | 56.42% | 66.72% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 95.57%
|  |  | Fiber Box Installation |  | 90.58%
|  |  | Antenna Installation |  | 84.74%
|  |  | Antenna Cable Installation |  | 39.54%
|  |  | Splitter Installation |  | 42.55%
|  |  | Fiber Cable Splicing |  | 85.29%
|  |  | Fiber Testing |  | 39.17%
|  |  | Power Testing |  | 66.62%
125900 | D1 |  | Radio Unit Installation |  | 14.66% | 48.87% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 63.06%
|  |  | Fiber Box Installation |  | 49.4%
|  |  | Antenna Installation |  | 9.545%
|  |  | Antenna Cable Installation |  | 24.06%
|  |  | Splitter Installation |  | 86.73%
|  |  | Fiber Cable Splicing |  | 49.16%
|  |  | Fiber Testing |  | 54.53%
|  |  | Power Testing |  | 88.65%
123900 | D2 |  | Radio Unit Installation |  | 74.48% | 54.13% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 34%
|  |  | Fiber Box Installation |  | 5.571%
|  |  | Antenna Installation |  | 87.08%
|  |  | Antenna Cable Installation |  | 27.13%
|  |  | Splitter Installation |  | 22.64%
|  |  | Fiber Cable Splicing |  | 94.06%
|  |  | Fiber Testing |  | 90.02%
|  |  | Power Testing |  | 52.15%
124900 | D2 |  | Radio Unit Installation |  | 63.49% | 66.15% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 76.76%
|  |  | Fiber Box Installation |  | 69.74%
|  |  | Antenna Installation |  | 16.98%
|  |  | Antenna Cable Installation |  | 81.37%
|  |  | Splitter Installation |  | 54.63%
|  |  | Fiber Cable Splicing |  | 42.09%
|  |  | Fiber Testing |  | 99.01%
|  |  | Power Testing |  | 91.25%
125900 | D2 |  | Radio Unit Installation |  | 1.306% | 41.04% | STATIONINGS ARE NOT EXACT, WITHIN 100FT
|  |  | Power JB Installation |  | 23.84%
|  |  | Fiber Box Installation |  | 14.62%
|  |  | Antenna Installation |  | 74.47%
|  |  | Antenna Cable Installation |  | 39.08%
|  |  | Splitter Installation |  | 60.5%
|  |  | Fiber Cable Splicing |  | 8.527%
|  |  | Fiber Testing |  | 66.29%
|  |  | Power Testing |  | 80.7%

## Z-CASE
Stationing | Track No | Location | Activity | Date | Progress | General Progress | Notes
|  |  | CASE Install |  | 64.98% |  | Z-CASE IS BY E1-986 (Z)
|  |  | Cable Connection/Termination |  | 85.9%
|  |  | Pre-Op testing |  | 94.72%
|  |  | CASE Install |  | 3.76% |  | Z-CASE IS BY E1-1006 (Z)
|  |  | Cable Connection/Termination |  | 15.48%
|  |  | Pre-Op testing |  | 86.03%
|  |  | CASE Install |  | 36.94% |  | Z-CASE IS BY E1-1030 (Z)
|  |  | Cable Connection/Termination |  | 41.74%
|  |  | Pre-Op testing |  | 44.75%
|  |  | CASE Install |  | 23.61% |  | Z-CASE IS BY E1-1068 (Z)
|  |  | Cable Connection/Termination |  | 6.628%
|  |  | Pre-Op testing |  | 88.68%
115725 | E1 |  | CASE Install |  | 82.11% |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
|  |  | Cable Connection/Termination |  | 89.99%
|  |  | Pre-Op testing |  | 66.28%
121810 | E1 |  | CASE Install |  | 57.73% |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
|  |  | Cable Connection/Termination |  | 22.73%
|  |  | Pre-Op testing |  | 8.993%
| E1 |  | CASE Install |  | 21.67% |  | Z-CASE IS BY E1-1229 (Z)
|  |  | Cable Connection/Termination |  | 33.11%
|  |  | Pre-Op testing |  | 91.5%
| E1 |  | CASE Install |  | 35.48% |  | Z-CASE IS BY E1-1230 (Z)
|  |  | Cable Connection/Termination |  | 29.31%
|  |  | Pre-Op testing |  | 45.26%
98565 | E2 |  | CASE Install |  | 86.47% |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
|  |  | Cable Connection/Termination |  | 70.74%
|  |  | Pre-Op testing |  | 61.12%
114869 | E2 |  | CASE Install |  | 17.55% |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
|  |  | Cable Connection/Termination |  | 99.59%
|  |  | Pre-Op testing |  | 16.22%
| E2 |  | CASE Install |  | 62.9% |  | Z-CASE IS BY E2-1230(Z)
|  |  | Cable Connection/Termination |  | 15.56%
|  |  | Pre-Op testing |  | 60.94%
122071 | E5 |  | CASE Install |  | 8.335% |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
|  |  | Cable Connection/Termination |  | 41.24%
|  |  | Pre-Op testing |  | 52.78%
122687 | E5 |  | CASE Install |  | 43.29% |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
|  |  | Cable Connection/Termination |  | 52.84%
|  |  | Pre-Op testing |  | 9.374%

## TOPB
Stationing | Track No | Location | Activity | Date | Progress | General Progress | Notes
121810 | E1 |  | TOPB Install |  | 80.27% |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
|  |  | Cable Connection/Termination |  | 46.33%
|  |  | Pre-Op testing |  | 20.37%
122987 | E1 |  | TOPB Install |  | 98.94% |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
|  |  | Cable Connection/Termination |  | 12.5%
|  |  | Pre-Op testing |  | 54.57%
|  |  | TOPB Install |  | 91.83% |  | TOPB @ ~D1-1239
|  |  | Cable Connection/Termination |  | 21.72%
|  |  | Pre-Op testing |  | 47.39%
121809 | E2 |  | TOPB Install |  | 92.29% |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
|  |  | Cable Connection/Termination |  | 98.69%
|  |  | Pre-Op testing |  | 40.56%
122970 | E2 |  | TOPB Install |  | 85.25% |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
|  |  | Cable Connection/Termination |  | 90.16%
|  |  | Pre-Op testing |  | 61.08%
124043 | D2 |  | TOPB Install |  | 58.04% |  | STATIONINGS SHOWN ARE THAT OF NEAREST I.J.
|  |  | Cable Connection/Termination |  | 62.6%
|  |  | Pre-Op testing |  | 46.05%

## Report Screenshot
Tasks | Total Quantity | Installed/Tested Quantity
Acceptance Test (Ea) | 29 | 3
Antenna Cable (ft) | 61885 | 58432
Brackets (Ea) | 12147 | 11856
Coax Cable (Ea) | 59 | 59
Insertion Loss (Segment) (ft) | 47445 | 43615
Removals (ft) | 30946 | 2380
Coupler Plates | 27 | 27
DC Resistance (Segment) | 47410 | 43580
Megger (Segment) | 47445 | 43615
VSWR (Segment) | 47445 | 43615
End-To-End | 47445 | 33565
Heat Map Test | 47445 | 29175
Coverage Test/Survey | 47445 | 3160
Megger Coax Cable (Reel) | 4000 | 4000
Megger Antenna Cable (Reel) | 80000 | 80000
Megger 1/2in Cable (Reel) | 100 | 100
DC Resistance Coax Cable (Reel) | 4000 | 4000
DC Resistance Antenna Cable (Reel) | 80000 | 80000
DC Resistance 1/2in Cable (Reel) | 100 | 100

## Dashboard
RADIO INSTALLATION DASHBOARD
OVERALL TASK COMPLETION (ALL TRACKS)
TASK PERCENT COMPLETION (PER TRACK)
OVERALL INSTALLATION PROGRESS PER TRACK SECTION
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.